##### K/W-4

KARNATAKA NEERAVARI NIGAM LIMITED

(A Government of Karnataka Enterprise)

## DRAFT   TENDER  DOCUMENT

| Name of the Work: Amount put to tender | RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292) Rs.473.53Lakhs(including GST) |
| --- | --- |
| Name of the Division: | Office of the Executive Engineer, Karnataka Neeravari Nigam Limited, No.5 Bhadra canal Division, Davanagere. |

Executive Engineer, KNNL,No.5Bhadara canal Division, Davanagere -577002,Davanagere District

E-Mail eebcddvg@yahoo.co.in

.

TENDERS FOR THE WORK:RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292)

TENDER REFERENCE                   :KNNL/2024-25/IW/WORK_INDENT

LAST DATE AND TIME FOR

RECEIPT OF TENDERS						:

TIME AND DATE OF OPENING OF

COVER ONE OF TENDERS					:

PLACE OF OPENING OF COVER ONE OF TENDERS	: Office of the Executive Engineer, KNNL, No.5Bhadra canalDivision,Davanagere

TIME AND DATE OF OPENING OF

COVER TWO OF TENDERS					:

PLACE OF OPENING OF COVER TWO OF TENDERS	: Office of the Executive Engineer, KNNL, No.5 Bhadra canalDivision,Davanagere

ADDRESS FOR COMMUNICATION	: Office of the Executive Engineer, KNNL, No.5 Bhadra canalDivision,Davanagere

Contents

Section 					Description						Page

No.

1		Invitation for Tenders (IFT)						3

2		Instructions to Tenderers (ITT)					4

3.		qualification information						14

4.		FORM OF TENDER, LETTER OF ACCEPTANCE, notice to	17

PROCEED WITH THE WORK AND agreement form

5.		Conditions of Contract (CC)						20

6.		CONTRACT DATA									34

7		Specifications									40

8		Drawings										41

9.		Bill of Quantities								42

SECTION 1: INVITATION FOR TENDERS (IFT)

(E-procurement only) (TWO TENDER DOCUMENT SYSTEM)

Tender Notification No: EE/ KNNL/ BCD-5/DVG/PB-4/4701/1040/ 2024-25Dated:10.09.2024.

1. Office of the Executive Engineer, KNNL, No.5 BhadracanalDivision,Davanagereon behalf of the Managing Director, Karnataka Neeravari Nigam Limited, 4th Floor, Coffee Board Building, No.1, Dr. B.R.AmbedkarVeedhi, Bangalore-01,invites percentage tenders from eligible tenderers, for the construction of works detailed in the Table below.  The tenderers may submit tenders for any or all of the works given in the Table in Two Tender Document System i.e., 1st Electronic document, i.e., Technical Bid & 2nd Electronic documenti.e Financial bid, procedure as per Rule28 of the KTPP Act shall be followed. The Tenders are required to submit two separate electronic document 1st Electronic document containing the Earnest money deposit and the details of their capability to undertake the tender (as detailed in ITT Clause 3and 6), which will be opened first and the second Electronic document  containing the price tender (Financial Bid) which will be opened only if the Tenderer is found to be qualified to execute the tendered works. The Tenderers are advised to note the minimum qualification criteria specified in Clause 3 of the Instructions to Tenderers to qualify for award of the contract.

2. Tender documents may be downloaded from Government of Karnataka kppp portal website https://kppp.karnataka.gov.in/#/portal/portal-homeunder login for Contractors:

After login to Contractors, Please scroll down to the right side bottom to see List of Tenders, Please click there to find the details of NIT and download copy of the tender.   The tender can be downloaded in the portal as per prescribed date and time published in the portal. Only Interested   Contractors   who wish to participate should remit online transaction fee for tender after registering in the portal. The transaction fee is non-refundable if you wish to participate.

3.Tenders must be accompanied by earnest money deposit which will paid online through kppp portal as mentioned.

4. Tenders must be electronically submitted (on-line through internet) with in the date and time published in kppp portal. First Electronic Tenderdocument will be opened at prescribed time and date in the kpppportal, in the presence of the Tenderers who wish to attend at theOffice of the Executive Engineer, KNNL, No.5 Bhadra canal Division,Davanagere

5.A Pre-tender meeting will be held at the Office of the Executive Engineer, KNNL, No.5 Bhadra canal Division,Davanagereto clarify the issues if any, and to answer questions on any matter that may be raised at that stage as stated in Clause 8.2 of ‘Instructions to Tenderers’ of the tender document.

6.	Other details can be seen in the tender documents.

# TABLE

| Sl. No | Name of work | work Portion | GST | EMD in RS | Transaction fee (only for the tenderers who wish to participate) | Stipulated period for completion (Including mansoon) | Category of contractors eligible. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 |  | 4 | 5 | 6 | 7 |
| 1 | RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292) | 402.35 | 72.42 | 6,04,000/- | As perkppp-portal | 06 Months | KPWDClass-II& above. |

Each tenderer must pay specified full E.M.D. in the KPPP portal platform through any of the payment modes as:- a) Credit card b) Direct Debit c)National Electronic fund transfer (NEFT)  d)Over the counter (OTC).  Tenders without valid E.M.D. shall be rejected.

Calendar of Events:

| SL.No. | Details | E-Procurement Portal |
| --- | --- | --- |
| i | Contractors can have access to e-tender documents from dtd:13.09.2024onwards | XX.XX.XXXX Upto 5.00PM |
| ii | Pre-Bid meeting dtd:20.09.2024at office of the Executive Engineer, KNNL, No.5Bhadra canalDivision, Davanagere. | XX.XX.XXXX @ 11.00 a.m |
| iii | Last date for Submission of e-tender documents uptodtd:23.09.2024 | XX.XX.XXXX Upto5.00p.m |
| iv | Opening of Cover I (Technical Bid) as on: 24.09.2024 | XX.XX.XXXX @ 5.15p.m |
| V | Cover-II (Financial Bid) will be opened after obtaining approval of technical bid from competent authority the financial bid will be opened. |  |

If any of the dates mentioned above happens to be general holiday, the next working day will holds good.

The contractor can down load e-tender documents from the website https://kppp.karnataka.gov.in/#/portal/portal-homelink on payment (non-refundable) as per KPPP portalusing payment modes on or before above mentioned date.

General Conditions

- All the documents must be attested, scanned and uploaded.

- The contractor should neither make any alteration in the conditions of contract or not stipulate any conditions of his own.

- The Electronic document i.e., Financial bid of all the participated bidder will be opened after approval of the technical bidqualification among eligible bidders the lowest bidder will be identified. If the lowest bidder fails to produce the original documents for entering into an agreement or the original documents submitted does not match with the uploaded documents or found false, then his bid is treated as non-responsive bid as per clause-26(4) of the KTPP rules & his name would be recommended for the removal from the select list of KPWD enrolment and barred from participation in any of the tenders invited by the KNNL apart from forfeiting the EMD paid through e-cash.

- Evaluation will be done based on the information provided by the contractor as per the document uploaded through KPPP portalthe correctness of the uploaded document will be verified if necessary.

- Any bidders who is otherwise technically qualified withdraws from the bidding process at any stage before a final decisions taken on the tender, the EMD of such bidder shall be forfeited, the name of such bidder shall be recommended for removal from the KPWD contractors at least for a minimum period of one year in KNNL, besides making such bidders liable for black listing.

- Any of the bidder who withdraws from the bidding process after completion of tender submission date at any stage before a final decision taken on the tender, the EMD of such bidder shall be forfeited and the name of such bidder shall be removed from the select list of KPWD registration and barred from participation in any of the tenders invited by KNNL thereafter

- GST Agency has to quote the rates exclusive of GST. GST will be added at prevailing rates at the time of Agreement.As per Govt. order  FD:447:Exependiture:12/2022 Bangalore dt. 30-7-2022  G.S.T will be paid at 18%  or  applicable rates at the time of payment of RA Bills, subject to verificationGST will be added at prevailing rates at the time of Agreement.

- The bidders shall ensure credit of Tender Processing Fee and EMD into the respective receiving bank accounts of KPPP portal on or before the last date of bid submission (Through Electronic Media)

- The tenderer is required to ensure browser compatibility of the computer well in advance to the last date and time for receipt of tenders. The department shall not be responsible for non-accessibility of KPPP portaldue to internet connectivity issues and technical glitches.

- Even though the agency/firm meets the qualifying criteria, they are subjected to disqualification if they have made misleading or false representations in the forms, statements and attachments submitted in proof of the qualification requirements and incomplete filling of details in the prequalification document.

- The evaluation of pre-qualification will be done based on the information provided by the contractor as per the documents uploaded through KPPP portal. The correctness of the uploaded documents will be verified if necessary.

- Conditional tenders will be rejected. The officer competent to accept the tender shall have the right to reject any or all the tender without assigning any reason whatsoever.

- Taxes will be deducted at the prevailing rates.

- The intending bidders are advised to visit the site of work before attending and also submitting their tenders.

- Karnataka Neeravari Nigam Ltd., Reserves the right to verify the correctness of the statements and documents furnished and inspect the jobs executed by the agency/firm, if found necessary.

- The Tenders are invited as per Standard tender Bid Document of KW-4.

- All relevant documents as per the KNNL need to be uploaded while submitting bid in general documents provision in KPPP portal.

- Contractors should follow strictly prevailing rules of labour act.

- Bidders should not be under any declaration of ineligibility for corrupt and Fraudulent practices issued by Government of Karnataka.

- Scanned Signature of the Bidder/Authorized Representative incase of firm/company to be attached while uploading bid documents along with valid power of attorney.

- The officer competent to accept the tenders shall have the right to reject any or all the tenders without assigning any reason and whatsoever.

- The Contractor should adhere to the accepted execution plan submitted by his under any circumstances without linking to the pending payment of the work & also land acquisition problem if any.

- Considering the availability of funds, the bill of the Agency will be paid.

- Tenders from Joint ventures are not acceptable.

- Relevant documents must be uploaded wherever necessary.

- If any of the dates mentioned in the Calendar of events happened to be declared holiday, the next working day holds good for event.

- Bidder should having Annual Turnover of more than Rs.100.00crores shall submit GST E-Invoice, while claiming the Bills under the above work.

- The uploaded drawings are for Tender purpose only.

- ¤zÉÃð±ÀPÀgÀPÀbÉÃj, UÀtÂ ªÀÄvÀÄÛ ¨sÀÆ«eÁÕ£À E¯ÁSÉ, £ÀA.49, R¤d ¨sÀªÀ£À, ¨ÉAUÀ¼ÀÆgÀÄ-01 gÀªÀgÀ ¸ÀÄvÉÆÛÃ¯É ¢£ÁAPÀ: 07.11.2023gÀ C£ÀéAiÀÄ ¸ÀPÁðj PÁªÀÄUÁjUÀ¼À°è §¼ÀPÉ ªÀiÁqÀÄªÀ G¥ÀR¤dUÀ½UÉ UÀtÂ ªÀÄvÀÄÛ ¨sÀÆ«eÁÕ£ÀE¯ÁSÉ¬ÄAzÀUÀtÂUÀÄwÛUÉUÉ ªÀÄAdÆgÀÄ ªÀiÁqÀ¯ÁzÀG¥ÀR¤dUÀtÂUÀÄwÛUÉzÁgÀjAzÀR¤dgÀªÁ£É ¥ÀgÀªÁ¤UÉ (MDP) UÀ¼À ¥ÀæwUÀ¼À£ÀÄß PÁªÀÄUÁjAiÀÄ ©°è£ÉÆA¢UÉ ®UÀwÛ¹ ¸À°è¸ÀvÀPÀÌzÀÄÝ.vÀ¦àzÀÝ°èRoyaltyAiÀÄ 5 ¥ÀlÄÖzÀAqÀªÀ£ÀÄß ©°è£À°è PÀrvÀUÉÆ½¸À¯ÁUÀÄªÀÅzÀÄ.

- Further information about tendering can be had from https://kppp.karnataka.gov.in/#/portal/portal-home	 and office of the undersigned during office hours. (08192-264669).

- Further corrigendum/modifications/corrections/addendum if any can be had from https://kppp.karnataka.gov.in/#/portal/portal-home.

Sd/-

Executive Engineer, 
                                                                      Karnataka Neeravari Nigam Limited,

No.5 Bhadra canal Division, Davanagere

- Copy submitted to the Personal Secretary to Hon’able Irrigation Minister, Water Resources Department, VidhanaSoudha, Bangalore for kind information.

- Copy submitted to the Managing Director, KNNL, 4th Floor, Coffee Board building, No.1, Dr. B.R. AmbedkarVeedhi, Bangalore – 01 for kind information.

- Copy submitted to Chief Engineer, KNNL, UpperTunga Project Zone. Shivamoga, for kind information.

- Copy submitted to Superintending Engineer, KNNL, Bhadra Project Circle, B.R.P for kind information.

- Copy submitted to Chief Administrative Office/Chief accounts Officers, Karnataka Neeravari Nigam Limited, Central Office, Srinagara Circle, Vijaya Complex, Haliyala Road, Dharwad for kind information.

- Copy forwarded to the Assistant Executive Engineer, No-1,2, 3 & 4Bhadra canal Sub-Division, Davanagere, Thyavangi and Harihara for information and necessary action.

- Copy to Division Account Branch.

- Notice Board.

Executive Engineer

Karnataka Neeravari Nigam Limited

No.5 Bhadra canal Division

Davanagere

# SECTION – 2

INSTRUCTIONS TO THE TENDERERS (ITT)

Section 2:  Instructions to Tenderers (ITT)

Table of Clauses

A.	General

1.	Scope of Tender

2.	Eligible Tenderers

3.	Qualification of the Tenderer

B.	Tender Documents

- Content of Tender documents

5.	Amendment of Tender documents

C.	Preparation of Tenders

6.	Documents comprising the Tender

7.	Tender prices

8.	Tender validity

9.	Earnest money deposit

10.	Format and signing of Tender

D.	Submission of Tenders

11.	Sealing and marking of Tenders

12.	Deadline for submission of Tenders

- Late Tenders

14.	Modification and Withdrawal of Tenders

E.	Tender opening and evaluation

15.     Opening of First electronic document  of all Tenders and evaluation to determine

qualified Tenderers

16.	Opening of Second electronic document  Tenders of qualified Tenders and evaluation

17.	Process to be confidential

18.	Clarification of Tenders

19.	Examination of Tenders and determination of responsiveness

20.	Correction of errors

21.	Evaluation and comparison of Tenders

F.	Award of contract

22.	Award criteria

23.	Employer’s right to accept any Tender and to reject any or all Tenders

24.	Notification of award and signing of Agreement

25.	Security deposit

26.	Corrupt or Fraudulent Practices

A. General

1.	Scope of Tender

1.1	The Executive Engineer,KNNl, No.5 Bhadra canal Division, Davanagere(Referred to as Employer in these documents) invites tenders following Two  tender document System  procedure, from eligible Tenderers, for the workRe construction of RCC Aquaduct @ ch.58.80Km, Re construction of Road Bridge @ ch.58.80Km, Re construction of CTC cum Super passage at 7th Zone distry @ ch. 60.00km d/s wall(as defined in these documents and referred to as "the works") detailed in the Table given in the Invitation for Tenders (IFT). The Tenderers may submit tenders for any or all of the works detailed in the table given in IFT.

2.	Eligible Tenderers

2.1	Tenderers shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued by the Government of Karnataka

2.2	Tenders from Joint ventures are not acceptable.

3.	Qualification of the Tenderer:

3.1	All Tenderers shall provide the requested information accurately and in sufficient detail in Section 3:  Qualification information.

INSTRUCTIONS TO TENDERERS

PRE-QUALIFICATION STIPULATIONS

  - First Electronic document (on line Technical bid) shall contain the following documents.

- A Copy of Valid Registation certificate under KPWD class II and above

- A copy of the valid Employees Provident Fund (EPF) registration Certificate.

iii)   Each tenderer must pay specified full E.M.D. in the KPPP Portal platform through any of the payment modes as:- a) Credit card b) Direct Debit c)National Electronic fund transfer (NEFT)  d)Over the counter (OTC).  Tenders without valid E.M.D. shall be rejected.

iv)  The valid copy of GST Registration Certificate

- The annual turnover of intending bidder shall not be less than the two times the amount put to tender i.e., Rs949.50Lakhs in any two financial years during the last 5 years i.e, from 2021-22 to 2025-26 (in all Classes of Civil Engineering Construction works only). The audit Profit and Loss account certified by a practicing Chartered Accountant duly showing with UDINi.e (Unique Document Identification Number) along with income tax return should be uploaded. The turnover of previous years will be updated to the present value of the year 2026-27giving weightage of 10% for each previous year turnover value.

- The intending bidder should have in last five years i.e., from 2021-22 to 2025-26satisfactorily completed (at least 90% of the contract value) as a prime contractor at least one similar nature of work such as Aquaduct/Bridge/Bridge cum Barrage/Box culvert of value not less than 50% of the estimate value of amount put to tender ie, Rs. 237.40Lakhs. The Work done certificates obtained from the officer not below rank of Executive Engineer should be uploaded. The work done value of the previous year shall be updated to present price level of 2026-27at 10% per annum.

- The intending bidder should have executed following minimum quantity of items in any one financial year in previous 5 financial years (i.e., from 2021-22 to 2025-26) for which the necessary certificates issued by officers not below the rank of Executive Engineer, shall be uploaded.

  - Earth work/Embankment –4260  Cum

  - M-15  & above grade Cement Concrete – 3038 Cum

  - Steel reinforcement– 50.50Tonne

(ix) 	Liquid assets and or availability of credit facilities of not less than Rs.142.50lakhs (Credit Lines/Letters of Credit/Certificates from Nationalized Banks) for meeting the fund requirement etc., The Contractor should upload necessary documents issued by the Nationalized banks as per prescribed formats enclosed as annexure-I to the Notification.

- Each Tenderer should further demonstrate:

(a) Availability by owning the following key and critical equipment for this work:

The intending bidder / firm / company should furnish details of ownership of Machineries/Equipments etc., to an extent of more than 50% of the requirement and also should furnish copies of lease agreement of hiring of Machineries/Equipments etc., to be deployed for this work.

| Sl.no | Machineries/Equipments | Total | Own | Own/Lease |
| --- | --- | --- | --- | --- |
| 1 | Excavator of not less than 0.90 cum capacity | 2 No.s | 1 No. | 1 No. |
| 2 | Vibratory roller/ soil compactor | 2 No.s | 1 No. | 1 No. |
| 3 | Tippers | 6 No.s | 3No.s | 3 No.s |
| 4 | Water Tanker 2000 ltrs | 2 No.s | 1 No. | 1 No. |
| 5 | Machine concrete mixer with hopper | 2 No.s | 1 No. | 1No. |

3.4 To qualify for a package of contracts made up of this and other contracts for which tenders are invited in this IFT, the Tenderer must demonstrate having experience and resources to meet the aggregate of the qualifying criteria for the individual contracts.

3.5 Sub-contractor’s experience and resources shall not be taken into account in determining the Tenderer’s compliance with the qualifying criteria except to the extent stated in 3.2 (d) and (e) above. -Deleted

3.6 Tenderers who meet the above specified minimum qualifying criteria, will only be qualified, if their available tender capacity is more than the total tender value. The available tender capacity will be calculated as under:

# Assessed available tender capacity = ( A*N*1.5 - B )

where

A = Maximum value of civil engineering works executed in any one year during the  last five years (updated to 2026-27price level) taking into account  the completed as well as works in progress.

N = Number of years prescribed for completion of the works for which tenders are invited.

B =	 Value, at 2026-27 price level, of existing commitments and on-going works to be completed during the next 6/12year(period of completion of the works for which Tender are invited)form the probable date of Award of this contract.

Note:	The statements showing the value of existing commitments and on-going works  as well as the stipulated period of completion remaining for each of the works listed should be countersigned by the Employer in charge, not below the rank of an Executive Engineer or equivalent.

3.7	Even though the Tenderers meet the above criteria, they are subject to be disqualified if they have:

-	made misleading or false representations in the forms, statements and attachments submitted in proof of the qualification requirements; and/or

-	record of poor performance such as abandoning the works, not properly completing the contract, inordinate delays in completion, litigation history, or financial failures etc.; and/or

-	participated in the previous Tender for the same work and had quoted unreasonably high tender prices and could not furnish rational justification.

# One Tender per Tenderer:

  - deleted

5.	Cost of Tendering:

5.1	The tenderer shall bear all costs associated with the preparation and submission of his tender, and the Employer will in no case be responsible and liable for those costs.

# 6.	Site visit:

# The Tenderer at his own responsibility and risk is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the Tender and entering into a contract for construction of the Works. The cost of visiting the Site shall be at the Tenderer’s own expense.

# B.  Tender documents

7.	Content of Tender documents

7.1	The set of tender documents shall have all the Sections given in Page 2:

7.2	Both the sets should be completed and returned with the tender.

8.	Clarification of Tender Documents

8.1	A prospective tenderer requiring any clarification of the tender documents may notify the Employer in writing or e-mail (hereinafter “cable” includes telex and facsimile) at the Employer’s address indicated in the invitation to tender. The Employer will respond to any request for clarification which he receives earlier than 15 days prior to the deadline for submission of tenders. Copies of the Employer’s response will be forwarded to all purchasers of the tender documents, including a description of the enquiry but without identifying its source.

8.2	Pre-tender meeting:

8.2.1	The tenderer or his authorized representative is invited to attend a pre-tender meeting which will take place at Office of the Executive Engineer,   KNNL, No.5 Bhadra canal division, Davanagere District – 577002

8.2.2	The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage

8.2.3	The tenderer is requested to submit any questions in writing or by cable to reach the Employer not later than one week before the meeting.

8.2.4	Minutes of the meeting, including the text of the questions raised (without identifying the source of enquiry) and the responses given will be transmitted without delay to all purchasers of the tender documents. Any modification of the tender documents listed in Sub-Clause 7.1 which may become necessary as a result of the pre-tender meeting shall be made by the Employer exclusively through the issue of an Addendum pursuant to Clause 9 and not through the minutes of the pre-tender meeting.

8.2.5	Non-attendance at the pre-tender meeting will not be a cause for disqualification of a tenderer.

9.	Amendment of Tender documents

9.1	Before the deadline for submission of tenders, the Employer may modify the tender documents by issuing addenda.

9.2	Any addendum thus issued shall be part of the tender documents and shall be communicated in kppp portal platformto all the purchasers of the tender documents.

9.3	To give prospective Tenderers reasonable time in which to take an addendum into account in preparing their tenders, the Employer shall extend as necessary the deadline for submission of tenders, in accordance with Sub-Clause 16.2 below.

# C.  Preparation of Tenders

10.	Documents comprising the Tender

10.1	The tender submitted by the Tenderer shall tender document and shall contain the documents as follows:

10.1.1	First Electronic Document :(Only online)

(a)	Earnest Money Deposit; on line payment through kppp portal platform.

- Qualification Information as per formats given in Section 3 and to comply the task created in the kppp Portal under General terms Conditions and Technical parameters and Documents required from Tenderer.

    - SecondElectronic Document :(Only online)

- The Tender (in the format indicated in Section 4)

- Priced Bill of Quantities (Section 9); online through kppp portal, no hardcopy of commercials should be attached or disclosed.

and any other materials required to be completed and submitted by Tenderers in accordance with these instructions. The documents listed under Sections 3, 4, 6 and 9 shall be filled in without exception.

10.2	Tenderers submitting tenders together with other contracts stated in the IFT to form a package will so indicate in the tender together with any discounts offered for the award of more than one contract.

11.	Tender prices

11.1	The contract shall be for the whole works as described in Sub-Clause 1.1, based on the priced Bill of Quantities submitted by the Tenderer.

11.2	Not applicable (Since % tender adopted)

11.3	All duties, taxes, and other levies payable by the contractor under the contract, or for any other cause, shall be included in the rates, prices and total Tender Price submitted by the Tenderer.As per Govt. order  FD:447:Exependiture:12/2022 Bangalore dt. 30-7-2022 & Karnataka Neeravari Nigam Limited circular No:KNNL/FD/GST/2022-23/3144 dt:18.08.2022 GST 18% will be added to the contract amount separately.

11.4	The rates and prices quoted by the Tenderer shall be subject to adjustment during the performance of the Contract in accordance with the provisions of Clause of the Conditions of Contract.

12.	Tender validity

12.1	Tenders shall remain valid for a period not less than One Eighty daysafter the deadline date for tender submission specified in Clause 16.  A tender valid for a shorter period shall be rejected by the Employer as non-responsive.

12.2	In exceptional circumstances, prior to expiry of the original time limit, the Employer may request that the Tenderers may extend the period of validity for a specified additional period.  The request and the Tenderers' responses shall be made in writing or by cable.  A Tenderer may refuse the request without forfeiting his earnest money deposit.  A Tenderer agreeing to the request will not be required or permitted to modify his tender, but will be required to extend the validity of his earnest money deposit for a period of the extension, and in compliance with Clause 13 in all respects.

13.	Earnest money deposit

13.1	Earnest Money Deposit/ Bid security(as per e-procurement portal)

| A | UptoRs. 20 lakh | 2.5% |
| --- | --- | --- |
| B | Rs. 20 lakhs and above upto Rs.1 Crore | 2% subject to minimum of Rs.50,000/- |
| C | Rs.1 Crore and above upto Rs.10 Crore | 1.5% subject to a min. of Rs. 2,00,000/- |
| D | Rs. 10 crore and above | 1% subject to minimum of Rs. 15,00,000/- |

The supplier/contractor can pay the Earnest Money Deposit (EMD) in the e-Procurement portal using any of the following payment modes:

- Credit Card

- Direct Debit

- National Electronic Fund Transfer (NEFT)

- Over the Counter (OTC)

OTC payment procedure

If a contractor/supplier chooses to make payment of EMD/tender processing fees Over The Counter (OTC) in any of the designated Axis Bank branches listed in the kppp portal web-site (https://kppp.karnataka.gov.in/#/portal/portal-home), the contractor/supplier will need to log into kppp portal system, access the tender for which bid is being created and then select the OTC option under the payment section and print the Challan shown in that section. The printed challan will have the unique bid reference number and the amount to be remitted. Along with the challan, contractor can choose to make the payment either in the form of cash or in the form of Demand Draft. Cheque payments will not be accepted. The contractor is requested to specifically inform the bank officer to input the unique bid reference number printed in the challan in the banking software. Upon successful receipt of the payment, the bank will provide a 16-digit reference number acknowledging the receipt of payment. This 16-digit reference number has to be inputted by contractor in the payment section of its bid as payment confirmation before the bid is submitted (i.e.) as a pre-requisite for bid submission.

NEFT payment procedure

If a contractor/supplier chooses to make payment of EMD/tender processing fees using Reserve Bank of India's (RBI) National Electronic Fund Transfer (NEFT) system, the contractor/supplier will need to log into kppp portal system, access the tender for which bid is being created and then select the NEFT option under the payment section and print the Challan shown in that section. The printed challan will have the unique bid reference number, account details of Government of Karnataka and the amount to be remitted. The contractor has to submit the printed challan to its bank-branch (NEFT-enabled) and request for an account-to-account transfer, wherein the money will get transferred from the contractors' bank account to GoK's bank account. The contractor should ensure that NEFT transfer instructions are executed and the funds are wired to the Government of Karnataka's principal account before the last date for bid submission and preferably 24 hours before the last date for bid submission. If the contractor's bank transfers/wires the money after the last date for bid submission, the contractor's bid will be liable for rejection. Upon executing the transfer, the contractor's bank will provide a reference number generated by NEFT software as confirmation of transfer, which has to be inputted by contractor in the payment section of its bid as payment confirmation before the bid is submitted (i.e.) as a pre-requisite for bid submission. Also, the account number from which the funds were transferred have to be inputted in the e-Procurement system as part of its bid.

The supplier/contractor’s bid will be evaluated only on confirmation of receipt of the payment (EMD) in the Government of Karnataka central pooling a/c held at Axis Bank

EMD amount will have to be submitted by the supplier/contractor taking into account the following conditions:

a. EMD will be accepted only in the form of electronic cash (and not through Demand Draft or Bank Guarantee) and will be maintained in the Govt.’s central pooling account at Axis Bank until the contract is closed.

b. The entire EMD amount for a particular tender has to be paid in a single transaction

For details on e-Payment services refer to kppp portal for more details on the process.

13.2	Instruments having fixed validity issued as earnest money deposit for the tender shall be valid for 45 days beyond the validity of the tender.

13.3	Any tender not accompanied by an acceptable earnest money deposit and not secured as indicated in Sub-Clauses 13.1 and 13.2 above shall be rejected by the Employer as non-responsive.

13.4	The earnest money deposit of unsuccessful Tenderers will be returned within 30 days of the end of the tender validity period specified in Sub-Clause 12.1.

13.5	The earnest money deposit of the successful Tenderer will be discharged when the Tenderer has signed the Agreement and furnished the required Performance Security.

13.6	The earnest money deposit may be forfeited:

(a)	if the Tenderer withdraws the Tender after tender opening during the period of tender validity;

(b)	if the Tenderer does not accept the correction of the Tender Price, pursuant to Clause 24; or

(c)	in the case of a successful Tenderer, if the Tenderer fails within the specified time limit to

(i)	sign the Agreement; or

(ii)	furnish the required  Security deposit

14.	Format and signing of Tender

Tenderer shall submit the Bid electronically before the submission date and time published in KPPP portal.

D.  Submission of Tenders

15.	Sealing and marking of tenders

Tenderer shall submit the Bid electronically before the submission date and time published.

16.	Deadline for submission of the Tenders

  - Tenders must be submitted on line in the e-Procurement portal to the Employer on or before  the submission date and time published as per kppp portal.

16.2    The Employer may extend the deadline for submission of tenders by issuing an

amendment in accordance with Clause 9, in which case all rights and obligations of the

Employer and the Tenderers previously subject to the original deadline will then be

subject to the new deadline.

17.	Late Tenders

17.1	In online e-procurement system, you shall not be able to submit the bid after the bid submission time and date as the icon or the task in the e-procurement portal will not be available.

18.	Modification and Withdrawal of Tenders

# 18.1	  Tender has all the time to modify and correct or upload any relevant document in the portal till Bid submission date and time, as published in the e-procurement portal.

18.2	Each Tenderer's modification separately for each Cover or withdrawal notice shall be prepared, sealed, marked, and delivered in accordance with Clause 14 & 15, with the outer and inner envelopes additionally marked "MODIFICATION FOR FIRST/SECOND COVER" or "WITHDRAWAL", as appropriate.

18.3	No Tender may be modified after the deadline for submission of Tenders.

18.4	Withdrawal or modification of a Tender between the deadline for submission of Tenders and the expiration of the original period of Tender validity specified in Clause 12.1 above or as extended pursuant to Clause 12.2 may result in the forfeiture of the earnest money deposit pursuant to Clause 13.

1 8.5	Tenderers may only offer discounts to, or otherwise modify the prices of their Tenders by submitting Tender modifications in accordance with this clause, or included in the original Tender submission.

# E.  Tender opening and evaluation

19.	Opening of First  Electronic Document  of all Tenders and evaluation to determine qualified Tenderers:

19.1	The Employer will open the First Covers of all the Tenders received (except those received late or withdrawn), including modifications for First Cover made pursuant to Clause 18, in the presence of the Tenderers or their representatives who choose to attend at 17.15 hours on the date and the place specified in Clause 16. In the event of the specified date of Tender opening being declared a holiday for the Employer, the Tenders will be opened at the appointed time and location on the next working day.

  - In kppp Portal, Contractor has the option of withdrawing the Bid by digitally signing to withdraw / cancel the bid, before the bid submission time /Date.

  - The Tenderers names, the presence or absence of earnest money deposit (amount, format and validity), the submission of qualification information and such other information as the Employer may consider appropriate will be announced by the Employer at the opening. Late and withdrawn Tenders will be returned unopened to tenders.

  - The Employer shall prepare minutes of the Tender opening, including the information disclosed to those present in accordance with Sub-Clause 19.3.

  - The Second Cover of all the Tenderers including modifications for Second Cover shall be placed in a large cover and securely sealed in the presence of the tenderers or their representatives, who are present and also get the same signed by all those tenderers or their representatives. The large cover shall be kept in safe custody by the Employer.

  - The Employer will evaluate and determine whether each tender (a) meets the eligibility criteria defined in ITT Clause 2; (b) is accompanied by the required earnest money deposit as per stipulations in ITT Clause and (c) meets the minimum qualification criteria stipulated in ITT Clause 3. The Employer will draw out a list of qualified Tenderers.

- Opening of Second Electronic Document  of qualified Tenderers and evaluation:

  - The Employer will inform all the Qualified Tenderers the time, date and venue fixed for the opening of the Second Cover containing the priced Tenders. The Employer will open the Second Covers of Qualified Tenderers at the appointed time and date in the presence of the Tenders or their representatives who choose to attend. In the event of the specified date of Second Cover opening being declared a holiday for the Employer, the Second Covers will be opened at the appointed time and location on the next working day.

  - Envelopes marked “MODIFICATION FOR SECOND COVER” shall be opened and the submissions therein read out in appropriate detail.

20.3	The Tenderers' names, the Tender prices, the total amount of each Tender, any discounts, Tender modifications and withdrawals, and such other details as the Employer may consider appropriate, will be announced by the Employer at the opening.  No Tender shall be rejected at Tender opening.

20.4	The Employer shall prepare minutes of the Second Electronic document Tender opening, including the information disclosed to those present in accordance with Sub-Clause 20.3.

21.	Process to be confidential

21.1	Information relating to the examination, clarification, evaluation, and comparison of Tenders and recommendations for the award of a contract shall not be disclosed to Tenderers or any other persons not officially concerned with such process until the award to the successful Tenderer has been announced. Any effort by a Tenderer to influence the Employer's processing of Tenders or award decisions may result in the rejection of his Tender.

22	Clarification of Tenders

22.1	To assist in the examination, evaluation, and comparison of Tenders, the Employer may, at his discretion, ask any Tenderer for clarification of his Tender, including breakdowns of unit rates. The request for clarification and the response shall be in writing or by cable, but no change in the price or substance of the Tender shall be sought, offered, or permitted except as required to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Tenders in accordance with Clause 24.

22.2	Subject to sub-clause 22.1, no Tenderer shall contact the Employer on any matter relating to its Tender from the time of the Tender opening to the time the contract is awarded.  If the Tenderer wishes to bring additional information to the notice of the Employer, it should do so in writing. Tenderer also can submit on line clarification through kppp portal through query option.

If they have any query or need clarification related to kpppportalcontactkppp portal Help desk from 9 AM to 9 PM. (Monday to Saturday) Ph. No.   – 080 – 22485867

22.3	Any effort by the Tenderer to influence the Employer in the Employer’s Tender evaluation, Tender comparison or contract award decisions may result in the rejection of the Tenderers’ Tender.

23.	Examination of Tenders and determination of responsiveness

23.1	Prior to the detailed evaluation of Tenders, the Employer will determine whether each Tender; (a) has been properly signed; and; (b) is substantially responsive to the requirements of the Tender documents.

23.2	A substantially responsive Tender is one which conforms to all the terms, conditions, and specifications of the Tender documents, without material deviation or reservation. A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of the Works; (b) which limits in any substantial way, inconsistent with the Tender documents, the Employer's rights or the Tenderer's obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other Tenderers presenting substantially responsive Tenders.

23.3	If a Tender is not substantially responsive, it will be rejected by the Employer, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation.

24.	Correction of errors

24.1	Tenders determined to be substantially responsive will be checked by the Employer for any arithmetic errors. Errors will be corrected by the Employer as follows:

(a)	Where there is a discrepancy between the rates in figures and in words, the lower of the two will govern; and

(b)	where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by the quantity, the unit rate as quoted will govern.

24.2	The amount stated in the Tender will be adjusted by the Employer in accordance with the above procedure for the correction of errors and, with the concurrence of the Tenderer, shall be considered as binding upon the Tenderer. If the Tenderer does not accept the corrected amount the Tender will be rejected, and the earnest money deposit may be forfeited in accordance with Sub-Clause 13.6 (b).

25.	Evaluation and comparison of Tenders

25.1	The Employer will evaluate and compare only the Tenders determined to be substantially responsive in accordance with Cause 23.

25.2	In evaluating the Tenders, the Employer will determine for each Tender the evaluated Tender Price by adjusting the Tender Price as follows:

(a)	making any correction for errors pursuant to Clause 24;  and

(b)	making appropriate adjustments to reflect discounts or other price modifications offered in accordance with Sub Clause 18.5.

25.3	The Employer reserves the right to accept or reject any variation, deviation, or alternative offer. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the Tender documents or otherwise result in unsolicited benefits for the Employer shall not be taken into account in Tender evaluation.

25.4	The estimated effect of the price adjustment conditions under Clause 41 of the Conditions of Contract, during the implementation of the Contract, will not be taken into account in tender Evaluation

# 25.5	If the tender of the successful tenderer is seriously unbalanced in relation to the Employer’s estimate of the cost of the work to be performed under the contract, the Employer may require the Tenderer to produce detailed price analyses for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, the Employer may require that the amount of the  performance security set forth in Clause 29 be increased at the expense of the successful Tenderer to a level sufficient to protect the Employer against financial loss in the event of default of the successful under the contract.

Kw-4The Employer will evaluate and compare only the Tenders determined to be substantially responsive in accordance with Clause 19.

21.3	The Employer reserves the right to accept or reject any variation, deviation, or alternative offer. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the Tender documents or otherwise result in unsolicited benefits for the Employer shall not be taken into account in Tender evaluation.

# F.  Award of Contract

26.	Awardcriteria

26.1	Subject to Clause 27, the Employer will award the Contract to the Tenderer whose Tender has been determined to be substantially responsive to the Tender documents and who has offered the lowest evaluated Tender Price, provided that such Tenderer has been determined to be (a) eligible in accordance with the provisions of Clause 2, and (b) qualified in accordance with the provisions of Clause 3.

27.	Employer's right to accept any Tender and to reject any or all Tenders

27.1	Notwithstanding Clause 26, the Employer reserves the right to accept or reject any Tender, and to cancel the Tender process and reject all Tenders, at any time prior to the award of Contract, without thereby incurring any liability to the affected Tenderer or Tenderers or any obligation to inform the affected Tenderer or Tenderers of the grounds for the Employer's action.

28.	Notification of award and signing of Agreement

28.1	The Tenderer whose Tender has been accepted will be notified of the award by the Employer prior to expiration of the Tender validity period by cable, telex, e-mail or facsimile confirmed by registered letter. This letter (hereinafter and in the Conditions ofContract called the "Letter of Acceptance") will state  the sum that the Employer will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the "Contract Price").

28.2	The notification of award will constitute the formation of the Contract, subject only to the furnishing of Security deposit in accordance with the provisions of Clause 29.

28.3	The Agreement will incorporate all agreements between the Employer and the successful Tenderer. It will be kept ready for signature of the successful Tenderer in the office of Employer within 30 days following the notification of award along with the Letter of Acceptance. Within 20 days of receipt, the successful Tenderer will sign the Agreement and deliver it to the Employer.

28.4	Upon the furnishing by the successful Tenderer of the Performance Security, the Employer will promptly notify the other Tenderers that their Tenders have been unsuccessful.

29.	Security deposit

29.1	Within 20 days of receipt of the Letter of Acceptance, the successful Tenderer shall deliver to the Employer a Security deposit in any of the forms given below for an amount equivalent to 5% of the Contract price plus additional security for unbalanced tenders (Difference between amount put to tender as per current CSR and quoted amount) shall be adopted as per  Government of Karnataka Order:DE: 456:ªÉZÀÑ: 12/ 2022/ ¨ÉAUÀ¼ÀÆgÀÄ ¢£ÁAPÀ; 10.08.2022 as specified below: -

Banker’s cheque/Demand draft,/Pay Order in favour of  theExecutive

Engineer, KNNL, No.5Bhadra canal  Division, Davanagere.

  - . Payable at. Davanagere.or

Irreovacble bank guarantee, including e-bank Guarantee, insurance surety Bonds issued by Insurance company authorized by insurance Regulatory and Development Authorised of India  in the form given in Section 10; orSpecified Small Savings Instruments pledged to Executive Engineer, KNNL, No.5 Bhadra canal Division, Davanagere.

29.2	If the security deposit is provided by the successful Tenderer in the form of a Bank Guarantee, it shall be issued either by a Nationalized/Scheduled bank.

29.3	The security deposit if furnished in cash or demand draft can, if requested, be converted to interest bearing securities at the cost of the contractor.

29.4	Failure of the successful Tenderer to comply with the requirements of Sub-Clause 29.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Earnest money deposit.

30	Advance Payment and Security:

  - Not applicable.

31.	Corrupt or Fraudulent practices

31.1	The GOK requires that the Tenderers/Suppliers/Contractors, observe the highest standard of ethics during the procurement and execution of such contracts.  In pursuance of this policy, GOK :

(a)	will reject a proposal for award if it determines that the Tenderer recommended for award has engaged in corrupt or fraudulent practices in competing for the contract in question;

(b)	will declare a firm ineligible, either indefinitely or for a stated period of time, to be awarded a GOK contract if it at any time determines that the firm has engaged in corrupt or fraudulent practices in competing for, or in executing, a GOK contract.

31.2	Furthermore, Tenderers shall be aware of the provision stated in sub-clause 50.2 of the Conditions of Contract.

SECTION :3

QUALIFICATION INFORMATION

SECTION 3: QUALIFICATION INFORMATION

The information to be filled in by the Tenderer hereunder will be used for purposes of computing Tender capacity as provided for in Clause 3 of the Instructions to Tenderers. This information will not be incorporated in the Contract.

1.1	Constitution or legal status of Tenderer				[Attach copy]

Place of Registration		_______________________________

(Attach Copy)

Principal place of business:	 _______________________________

1.2	Total value of works executed and payments received in the last five years

2021-22______________

2022-23______________

2023-24	______________

(in Rs. Lakhs)	2024-25

______________2025-26______________

1.3	Work performed as Prime Contractor (in the same name) on works of similar nature over during the five years specified in 1.2 above.

| Project Name | Name of Employer | Description of Work | Contract Number | Value of contract Rs Lakhs | Date of issue of Work | Specified period of complet- ion | Actual date of complet- ion | Remarks explaining reasons for delay in completion of work |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |

1.4	Quantities of work executed as prime contractor (in the same name) during the last five years specified in 1.2 above:

| Year | Name of Work | Name of Employer | Quantity of work performed [As per Clause 3.2 (c)] |  |  |  |  | Remarks (Indicate contract reference) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2021-22 |  |  |  |  |  |  |  |  |
| 2022-23 |  |  |  |  |  |  |  |  |
| 2023-24 |  |  |  |  |  |  |  |  |
| 2024-25 |  |  |  |  |  |  |  |  |
| 2025-26 |  |  |  |  |  |  |  |  |

1.5	Information on works for which Tenders have been submitted and works which are yet to be completed as on the date of this Tender.

(A)	Existing commitments and on-going works:

| Description of Work | Place & State | Contract No. & Date | Name and Address of Employer | Value of Contract (Rs. Lakhs) | Stipulated period of completion | Value of works remaining to be completed (Rs. Lakhs) | Anticipated date of completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |

(B)	Works for which Tenders already submitted:

| Description of Work | Place and State | Name and Address of Employer | Estimated value of works (Rs. Lakhs) | Stipulated period of completion | Date when decision is expected | Remarks if any |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |

  - The following items of equipment are considered essential for successfully carrying out the works. The tenderer should furnish all the information listed below.

| Item of Equipment | Requirement No. Capacity | Owned | Owned and available |  | Remarks |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Number/ Capacity | Age/ Condition |  |
| (as specified in clause 3.3) |  |  |  |  |  |

1.7	Reports on the financial standing of the tenderer, such as profit and loss statements and auditor’s reports for the last five years;

1.8	Qualification and experience of the key technical and management personnel in permanent employment with the tenderer and those that are proposed to be deployed  on this contract, if awarded.

1.9.	Name, address, and telephone, telex, and fax numbers of the Tenderers' bankers who may provide references if contacted by the Employer.

1.10	Evidence of access to financial resources to meet the qualification requirement specified in ITT Clause3.3 (b): Cash in hand, Letter of Credit etc. List them below and attach certificate from the Banker in the suggested format as under:

ON BANKS LETTER HEAD

FORMAT OF BANKER’S CERTIFICATE/LINE OF CREDIT LETTER

[To be issue in the Letter Head of The Bank Branch)

BANKER’S CERTIFICATE

To:	Executive Engineer,

KNNL, No.5 Bhadra Canal Division,

Davanagere.

This is to certify that Mr./M/s.__________________________________(name of the customer) having his/their registered/administrative office at ________________________________ is a customer of our Bank and is are engaged in ______________________________________ (nature of activity) . If the said customer is allotted/ awarded with 	“RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292)“ (brief details of wirks), we may extend credit facilities uptoRs. 142.50Lakhs  to meet his/ their working capital requirement towards the execution of the said work order as per the loan policy of the Bank.

This certificate is valid upto 6 months from date of issue, that is up to dd/mm/yyyy

Sd/-

Name of the Bank, Senior Bank Manger

Address:……………………………….

  - Proposals for subcontracting components of works amounting to more than 20% of the contract price.

| Item of Work | Value of Sub-Contract | Identified Sub-Contractor (Name and address) | Experience of similar work |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |
| ----------------- | ------DELETED------ | ------------------ | ----------------- |

1.12	Information on litigations in which the Tenderer is involved:

| Other Party (ies) | Employer | Details of dispute | Amount involved | Remarks showing present status |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |

1.13	The proposed methodology and program of construction, backed with equipment planning and deployment, duly supported with broad calculations and quality control procedures proposed to be adopted, justifying their capability of execution and completion of the work as per technical specifications within the stipulated period of completion as per milestones.

SECTION:4

FORMS OF TENDER, LETTER OF ACCEPTANCE,

NOTICE TO PROCEED WITH THE WORK

AND AGREEMENT FORM

SECTION 4 : FORMS OF TENDER, LETTER OF ACEPTANCE, NOTICE TO

PROCEED WITH THE WORK AND AGREEMENT FORM

# Form of Tender

Description of the Work:-RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292)

To		:   Executive Engineer, KNNLNo.5 Bhadra canal, Division, Davanagere

Address	:

# GENTLEMEN,

We offer to execute the Works described above in accordance with the Conditions of Contract accompanying this Tender for the Contract Price of _________  [in figures] (________________________________________________) [in letters].

This Tender and your written acceptance of it shall constitute a binding contract between us. We understand that you are not bound to accept the lowest or any Tender you receive.

The advance payment required is Rs…………………………….

We undertake that, in competing for (and, if the award is made to us, in executing) the above contract, we will strictly observe the laws against fraud and corruption in force in India namely “Prevention of Corruption Act 1988”.

We hereby confirm that this Tender complies with the Tender validity and Earnest money deposit required by the Tender documents.

# We attach herewith our current income-tax clearance certificate.

# Yours faithfully,

Authorized Signature:

# Name & Title of Signatory:  ______________________________________________

Name of Tenderer     ______________________________________________

Address:		__________________________________________

________________________________________

# Letter of Acceptance

(letterhead paper of the Employer)

________________________[date]

To:	_________________________________________________________________________[name and address of the Contractor]

# Dear Sirs,

This is to notify you that your Tender dated ____________ for execution of the workRe-RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292)

for the Contract Price of Rupees _________________________________________________________ (_____________) [amount in words and figures], as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted by our Agency.

You are hereby requested to furnish Security deposit plus additional security for unbalanced tenders in terms of  Clause 25.5 of ITT, in the form detailed in Clause  29.1 of ITT for an amount of  Rs.————— within 20 days of the receipt of this letter of acceptance valid up to 30 days from the date of expiry of Defects Liability Period i.e. up to ............ and sign the contract, failing which action as stated in Para 29.4 of ITT will be taken.

# Yours faithfully,

# Authorized Signature

# Name and Title of Signatory

# Name of Agency

-------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------

# ----------------------------------------------------------------------------------

# Issue of Notice to proceed with the work

(letterhead of the Employer)

————— (date)

To

—————————————— (name and address of the Contractor)

——————————————

——————————————

Dear Sirs:

Pursuant to your furnishing the requisite security deposit as stipulated in ITT Clause 29.1 and signing of the contract agreement for the Work of RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292)

a Tender Price of Rs.——————, you are hereby instructed to proceed with the execution of the said works in accordance with the contract documents.

# Yours faithfully,

(Signature, name and title of signatory authorized to sign on behalf of Employer)

# Agreement Form

# Agreement

This agreement, made the ___________________day of ______________20_______, between___________________________________________________________________________________________________________________________[name and address of Employer]

(hereinafter called “the Employer”) of the one part and _____________________________________________ ________________________________________________________________________________________________________________________________________________[name and address of contractor] (hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor execute RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292)

[name and identification number of Contract] (hereinafter called “the Works”) and the Employer has accepted the Tender by the Contractor for the execution and completion of such Works and the remedying of any defects therein  at a contract price of Rupees...............................

NOW THIS AGREEMENT WITNESSETH as follows:

1.	In this Agreement, words and expression shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

2.	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all aspects with the provisions of the Contract.

3.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying the defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

4.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

i)	Letter of Acceptance;

ii)	Notice to proceed with the works;

iii)	Contractor’s Tender;

iv)	Contract Data;

v)	Conditions of contract (including Special Conditions of Contract);

vi)	Specifications;

vii)	Drawings;

viii)	Bill of Quantities;  and

ix)	Any other document listed in the Contract Data as forming part of the contract.

In witness whereof the parties thereto have caused this Agreement to be executed the day and year first before written.

The Common Seal of 	__________________________________________________

was hereunto affixed in the presence of:

# Signed, Sealed and Delivered by the said  ____________________________________________________________________________________________________________________________________

in the presence of:

Binding Signature of Employer	_______________________________________________________

Binding Signature of Contractor	_____________________________________________________

-33-

SECTION :5

CONDITIONS OF CONTRACT

SECTION 5:Conditions of Contract

Table of Contents

| A. General |  |  | C. Quality Control |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Page no. |  |  | Page No. |
| 1 | Definitions |  | 29 | Identifying Defects |  |
| 2 | Interpretation |  | 30 | Tests |  |
| 3 | Law governing contract |  | 31 | Correction of Defects |  |
| 4 | Employers decisions |  | 32 | Uncorrected Defects |  |
| 5 | Delegation |  |  |  |  |
| 6 | Communications |  |  |  |  |
| 7 | Subcontracting |  | D. Cost Control |  |  |
| 8 | Other Contractors |  | 33 | Bill of Quantities |  |
| 9 | Personnel |  | 34 | Variations |  |
| 10 | Employer’s & Contractor’s Risks |  | 35 | Payments for Variations |  |
| 11 | Employer’s Risks |  | 36 | Submission of bills for payment |  |
| 12 | Contractor’s Risks |  | 37 | Payments |  |
| 13 | Insurance |  | 38 | Compensation events |  |
| 14 | Site Investigation Reports |  | 39 | Tax |  |
| 15 | Queries about the Contract |  | 40 | Price Adjustment |  |
|  | Data |  | 41 | Liquidated Damages |  |
| 16 | Contractor to Construct the |  | 42 | Advance Payments |  |
|  | Works |  | 43 | Securities |  |
| 17 | The Works to be completed by |  | 44 | Cost of Repairs |  |
|  | the intended completion date |  |  |  |  |
| 18 | Approvals by the Employer |  | E | Finalising the Contract |  |
| 19 | Safety |  | 45 | Completion |  |
| 20 | Discoveries |  | 46 | Taking Over |  |
| 21 | Possession of the Site |  | 47 | Final Account |  |
| 22 | Access to site |  | 48 | As build drawings / Operating and Maintenance Manuals |  |
| 23 | Instructions |  | 49 | Termination |  |
| 24 | Procedure for resolution of disputes |  | 50 | Payment upon Termination |  |
|  |  |  | 51 | Property |  |
|  |  |  | 52 | Release from performance |  |
| B. Time Control |  |  | F | Special conditions of contract |  |
| 25 | Program |  |  |  |  |
| 26 | Extension of the Intended Completion date |  |  |  |  |
| 27 | Delays Ordered by the Employer |  |  |  |  |
| 28 | Management meetings |  |  |  |  |

Conditions of Contract

A.  General

# 1.	Definitions

1.1	Terms which are defined in the Contract Data are not also defined in the Conditions of Contract but keep their defined meanings. Bold letters are used to identify defined terms.

Bill of Quantities means the priced and completed Bill of Quantities forming part of the Tender.

Compensation events are those defined in Clause 38 hereunder.

The Completion Date is the date of completion of the Works as certified by the Employer in accordance with Sub Clause 46.1.

The Contract is the contract between the Employer and the Contractor to execute, complete and maintain the Works. It consists of the documents listed in Clause 2.2 below.

The Contract Data defines the documents and other information which comprise the Contract.

The Contractor is a person or corporate body whose Tender to carry out the Works has been accepted by the Employer.

The Contractor's Tender is the completed Tender document submitted by the Contractor to the Employer.

The Contract price is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract.

Days are calendar days; months are calendar months.

A Defect is any part of the Works not completed in accordance with the Contract.

The Defects liability period is the period named in the Contract Data and calculated from the Completion Date.

The Employer is the party who will employ the Contractor to carry out the Works.

Equipment is the Contractor's machinery and vehicles brought temporarily to the Site to construct the Works.

The Initial Contract price is the Contract Price listed in the Employer's Letter of Acceptance.

The Intended Completion Date is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Contract Data. The Intended Completion Date may be revised only by the Employer by issuing an extension of time.

Materials are all supplies, including consumables, used by the contractor for incorporation in the Works.

Plant is any integral part of the Works which is to have a mechanical, electrical, electronic or chemical or biological function.

The Site is the area defined as such in the Contract Data.

Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Employer.

The Start Date is given in the Contract Data. It is the date when the Contractor shall commence execution of the works. It does not necessarily coincide with any of the Site Possession Dates.

A Sub contractor - Deleted

A Variation is an instruction given by the Employer which varies the Works.

The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the Contract Data.

2.	Interpretation

2.1	In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter, and the other way around. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Employer will provide instructions clarifying queries about the Conditions of  Contract.

2.2		The documents forming the Contract shall be interpreted in the following order of priority:

(1)	Agreement

(2)	Letter of Acceptance, notice to proceed with the works

(3)	Contractor’s Tender

(4)	Contract Data

(5)	Conditions of Contract

(6)	Specifications

(7)	Drawings

(8)	Bill of quantities and

(9)	any other document listed in the Contract Data as forming part of the Contract.

# 3.	 Law governing contract

3.1	The  law governing the Contract is the Laws of India supplanted by the Karnataka Local Acts.

4.	Employer's decisions

4.1	Except where otherwise specifically stated, the Employer will decide contractual matters between the Employer and the Contractor .

# 5.	Delegation

5.1		The Employer may delegate any of his duties and responsibilities to other people after notifying the Contractor and may cancel any delegation after notifying the Contractor.

# 6.		Communications

6.1		Communications between parties which are referred to in the conditions are effective only when in writing. A notice shall be effective only when it is delivered (in terms of Indian Contract Act).

7.		Subcontracting

deleted

# 8.	Other Contractors

  - The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the Employer.

9.	Personnel

  - The Contractor shall employ the technical personnel (of number and qualifications) as may be stipulated by GOK from time to time during the execution of the work. The technical staff so employed shall be available at site as may be stipulated by the Employer.

  - If the Employer asks the Contractor to remove a person who is a member of  the Contractor’s staff or his work force stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract.

# 10. 		Employer’s and Contractor's risks

10.1		The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks.

11. 		Employer's risks

  - The Employer is responsible for the excepted risks which are:

- rebellion,  riot commotion or disorder unless solely restricted to employees of the Contractor or his Sub-Contractors arising from the conduct of the Works;  or

- a cause due solely to the design of the Works, other than the Contractor’s design; or

- any operation of the forces of nature (in so far as it occurs on the Site) which an experienced  contractor:

  - could not have reasonably foreseen; or

  - could reasonably have foreseen, but against which he could not reasonably have taken at least one of the following measures;

    - prevent loss or damage to physical property from occurring by taking appropriate measures or

    - insure against such loss or damage

12.		Contractor’s risks

12.1		All risks of loss of or damage to physical property and of personal injury and death which arise during and in consequence of the performance of the Contract other than the excepted risks are the responsibility of the Contractor.

13.	Insurance:

13.1		The Contractor shall prior to commencing the works, effect and thereafter maintain insurances , in the joint names of the Employer and the Contractor, (cover from the first working day after the Start Date to the end of Defects  Liability Period), in the amounts stated in the Contract Data :

- for loss of or damage to the Works, Plants and Materials and the Contractor’s equipment;

- for liability of both Parties for loss, damage, death and injury to third parties or their property arising out of the Contractor’s performance of the  Contract including the Contractor’s liability for damage to the Employer’s property other than the Works and

- for liability of both Parties and of any Employer’s representative for death and injury to the Contractor’s personnel except to the extent that liability arises from the negligence of the Employer, any Employer’s representative or their Employees.

  - Policies and certificates for insurance shall be delivered by the Contractor to the Employer for his approval before the Start Date. All such insurance shall provide for compensation to be payable to rectify the loss or damage incurred. All payments received from insurers relating to loss or damage shall be held jointly by the Parties and used for the repair of the loss or damage or as compensation for loss or damage that is not to be repaired.

13.3		If the Contractor fails to effect or keep in force any of the insurances referred to in the previous sub-clauses or fails to provide satisfactory evidence, policies or receipts, the Employer may without prejudice to any other right or remedy, effect insurance for the cover relevant to such default and pay the premiums due and recover the same as a deduction from any other monies due to the Contractor. If no payments is due, the payment of the premiums shall be a debt due.

13.4		Alterations to the terms of an insurance shall not be made without the approval of

the Employer.

13.5		Both Parties shall comply with any conditions of the insurance policies.

14.		Site Investigation Reports:

14.1		The Contractor, in preparing the tender, shall rely on any site investigation reports referred to in the Contract data, supplemented by any information available to the Tenderer.

15. 		Queries about the Contract Data

15.1		The Employer will clarify queries on the Contract Data.

# 16. 		Contractor to construct the Works

16.1		The Contractor shall construct the Works in accordance with the Specification and Drawings.

# 17. 		The Works to be completed by the Intended Completion Date

17.1		The Contractor may  commence execution of the Works on the Start Date  and shall carry out the Works in accordance with the program submitted by the Contractor, as updated with the approval of the Employer, and complete them by the Intended Completion Date.

# 18.		Approval by the Employer:

  - The Contractor shall submit Specification and drawings showing the proposed Temporary Works to the Employer, who is to approve them if they comply with the Specifications and Drawings.

# 18.2	The Contractor shall be responsible for the design of Temporary Works

# 18.3		The Employer’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works.

# 18.4		The Contractor shall obtain approval of third parties to the design of third parties to the design of the temporary Works where required.

# 18.5		All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Employer before their use.

# 19. 		Safety

19.1		The Contractor shall be responsible for the safety of all activities on the Site.

20. 		Discoveries

20.1		Anything of historical or other interest or of significant value unexpectedly discovered on the Site is the property of the Employer. The Contractor is to notify the Employer of such discoveries and carry out the Employer's instructions for dealing with them.

# 21. 		Possession of the Site

21.1		The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the Contract Data the Employer is deemed to have delayed the start of the relevant activities and this will be Compensation Event.

22. 		Access to the Site

22.1		The Contractor shall allow the Employer and any person authorized by the Employer access to the Site, to any place where work in connection with the Contract is being carried out or is intended to be carried out and to any place where materials or plant are being manufactured / fabricated / assembled for the works.

# 23. 		Instructions

23.1		The Contractor shall carry out all instructions of the Employer which comply with the applicable laws where the Site is located.

B.  Time Control

# 25. 		Program

25.1		Within the time stated in the Contract Data the Contractor shall submit to the Employer for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works.

25.2		The Employer's approval of the Program shall not alter the Contractor's obligations. The Contractor may revise the Program and submit it to the Employer again at any time. A revised Program is to show the effect of Variations and Compensation Events.

# 26. 		Extension of the Intended Completion Date

26.1		The Employer shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date.

26.2		The Employer shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Employer for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information.

# 27. 		Delays ordered by the Employer

27.1		The Employer may instruct the Contractor to delay the start or progress of any activity within the Works.

28.		Management meetings

28.1		The Employer may require the Contractor to attend a management meeting. The business of a management meeting shall be to review the progress achieved and the plans for remaining work.

28.2		The responsibility of the parties for actions to be taken is to be decided by the Employer either at the management meeting or after the management meeting and stated in writing to be distributed to all who attended the meeting.

# C.  Quality Control

# 29. 		Identifying defects

29.1		The Employer shall check the Contractor's work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor's responsibilities. The Employer may instruct the Contractor to search for a Defect and to uncover and test any work that the Employer considers may have a Defect

30. 		Tests

30.1		If the Employer instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect the test shall be a Compensation Event.

# 31. 		Correction of defects

31.1		The Employer shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion and is defined in the Contract Data. The Defects Liability Period shall be extended for as long as Defects remain to be corrected.

31.2		Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Employer’s notice.

# 32.		Uncorrected defects

32.1		If the Contractor has not corrected a Defect within the time specified in the Employer’s notice, the Employer will assess the cost of having the Defect corrected, and the Contractor will pay this amount.

# D    Cost Control

33. 		Bill of Quantities (BOQ)

33.1		The BOQ shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor.

33.2		The BOQ is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the BOQ for each item

# 34. 		Variations

  - The Employer shall have power to order the Contractor to do any or all of the following as considered necessary or advisable  during the progress of the work by him

- Increase or decrease of any item of work included in the Bill of Quantities (BOQ);

- Omit any item of work;

- Change the character or quality or kind of any item of work;

- Change the levels, lines, positions and dimensions of any part of the work;

- Execute additional items of work of any kind necessary for the completion of the works; and

- Change in any specified sequence, methods or timing of construction of any part of the work.

34.2		The Contractor shall be bound to carry out the work in accordance with any instructions in this connection, which may be given to him in writing by the Employer and such alteration shall not vitiate or invalidate the contract.

34.3		Variations shall not be made by the Contractor without an order in writing by the Employer, provided that no order in writing shall be required for increase or decrease in the quantity of an item appearing in the BOQ so long as the work executed conforms to the approved drawings.

34.4		The Contractor shall promptly request in writing to the Employer to confirm verbal orders and the officer issuing oral instructions shall confirm it in writing within 30 days, failing which the work shall be carried out as though there is no variation.  In case variation, is approved it shall be accompanied by BOQ , failing which the contractor shall be responsible for deviation if any.  Further, approval of Govt. has to be obtained for the variation exceeding 5% of Contract Price.

35. 		Payments for Variations

  - Payment for increase in the quantities of an item in the BOQ up to 25% of that provided in the Bill of Quantities shall be made at the rates quoted by the Contractor.

  - For quantities in excess of 125% of the tendered quantity of an item as given in the BOQ, the Contractor shall be paid at the rate entered in or derived from  in the Schedule of Rates (applicable for the area of the work and current at the time of award of contract) plus or minus the overall percentage of the original tendered rates over the current Schedule of Rates prevalent at the time of award of contract.

35.3		If there is no rate for the additional, substituted or altered item of the work in the BOQ, efforts would be made to derive the rates from those given in the BOQ or the Schedule of Rates (applicable for the area of the work and current at the time of award of contract) and if found feasible the payment would be made at the derived rate for the item plus or minus the overall percentage of the original tendered rates over the current Schedule of Rates prevalent at the time of award of contract

35.4		If the rates for additional, substituted or altered item of work cannot be determined either as at 35.1 or 35.2 or 35.3 above, the Contractor shall be requested to submit his quotation for the items supported by analysis of the rate or rates claimed, within 7 days.

  - If the Contractor's quotation is determined unreasonable, the Employer may order the Variation and make a change to the Contract Price which shall be based on Employer’s own forecast of the effects of the Variation on the Contractor's costs.

35.6		If the Employer decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event.

35.7		Under no circumstances the Contractor shall suspend the work on the plea of non-settlement of rates for items falling under this Clause.

36. 		Submission of bills for payment

36.1		The Contractor shall submit to the Employer monthly bills of the value of the work completed less the cumulative amount paid previously.

36.2		The Employer shall check the Contractor's bill and determine the value of the work executed which shall comprise of (i) value of the quantities of the items in the BOQ completed and (ii) valuation of Variations and Compensation Events.

36.3		The Employer may exclude any item paid in a previous bill or reduce the proportion of any item previously paid in the light of later information.

# 37. 		Payments

37.1		Payments shall be adjusted for deductions for advance payments, other recoveries in terms of the contract and taxes, at source, as applicable under the law.  The Employer shallAs for as possiblepay the Contractor within 60 days of submission of billas per availability of grant. The contractor shall be liable to pay liquidated damages for shortfall in progress.

For progress beyond the agreed programme payment is subject to availability of the grants.

37.2		Items of the Works for which no rate or price has been entered in will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract.

38. 		Compensation events

38.1		The following are Compensation events unless they are caused by the Contractor:

(a)	The Employer does not give access to a part of the Site by the Site Possession Date stated in the Contract Data.

(b)	The Employer orders a delay or does not issue drawings, specifications or instructions required for execution of works on time.

(c)	The Employer instructs the Contractor to uncover or to carry out additional tests upon work which is then found to have no Defects.

(d)	The Employer gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons.

(e)	The effect on the Contractor of any of the Employer’s Risks.

(f)	The Employer unreasonably delays issuing a Certificate of Completion.

(g)	Other Compensation Events listed in the Contract Data or mentioned in the Contract.

38.2		If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date is extended. The Employer shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended.

38.3		As soon as information demonstrating the effect of each Compensation event upon the Contractor's forecast cost has been provided by the Contractor, it is to be assessed by the Employer and the Contract Price shall be adjusted accordingly. If the Contractor's forecast is deemed unreasonable, the Employer shall adjust the Contract Price based on Employer’s own forecast. The Employer will assume that the Contractor will react competently and promptly to the event.

38.4		The Contractor shall not be entitled to compensation to the extent that the Employer's interests are adversely affected by the Contractor not having given early warning or not having cooperated with the Employer.

# 39. 	Tax

39.1	The rates quoted by the Contractor shall be deemed to be exclusive of the GST that the Contractor will have to pay for the performance of this Contract.  The Employer will perform such duties in regard to the deduction of such taxes at source as per applicable law.As per Govt. order  FD:447:Exependiture:12/2022 Bangalore dt. 30-7-2022  GST 18% will be added to the contract amount separately

Increase in GST shall not be paid in the extended period of contract for which the contractor

alone is responsible for delay as determined by the authority while granting the extension of

time.

40.		Price Adjustment: APPLICABALEas per the prevailing Govt order, attached separately

[“If the period of execution is more than 6 months but less than or equal to 12 months for work costing more than Rs.50.00 lakhs, star rates in respect of specified materials (cement, steel and bitumen) only shall be payable as per Government order No: FD 3 PCL 2008, Bangalore Dated:  21-11-2008” and Circular instructions vide No.PWD/159/CRM/2009 dated 30-09-2010.]

40.1 Contract price shall be adjusted for increase or decrease in rates and prices of labour, materials, fuels and lubricants in accordance with the following principles and procedures and as per formulae given in the Contract Data.

(a) The price Adjustment shall apply for the work done from the date of commencement up to the end of original period of completion or extensions granted by the Employer and shall not apply to work carried out beyond the stipulated period of completion for reasons attributable to the Contractor;

(b) Price Adjustment shall be admissible from the date of opening of tenders (original or extended)

(c) The price adjustment shall be determined during each quarter from the formulae given in Contract Data.

(d) Following expressions and meanings are assigned to the work done during the quarter:

R = Total value of work done during the quarter. It will exclude value for works executed under variations for which price adjustment (if any) will be worked out separately based on the terms mutually agreed.

40.2 To the extent that full compensation for any rise or fall in costs to the contractor is not

covered by the provisions of this or other Clauses in the Contract, the unit rates

included in the contract shall be deemed to include amounts to cover the contingency

of such other rise or fall in costs.

CLAUSE – 45 ::

Care should be taken while retrieve of PCC slab and Atleast 80 % of the quantity retrieved  should be in reasonable condition. For damage in reasonable condition . For damage in excess of the limit (ie., more than 20 % ) cost as per SR will be recovered from the contractor

41. 		Liquidated damages

41.1		The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the Contract Data for each day that the Completion Date is later than the Intended Completion Date (for the whole of the works or the milestone as stated in the Contract Data).  The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages does not affect the Contractor's liabilities.

41.2		If the Intended Completion Date is extended after liquidated damages have been paid, the Employer shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment of bill.

42. 		Advance Payments:

Deleted

43.		Securities:

  - The Security deposit (including additional security for unbalanced tenders) shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount and form and type of instrument acceptable to the Employer. The Security deposit shall be valid until a date 30 days from the date of expiry of Defects Liability Period and the additional security for unbalanced tenders shall be valid until a date 30 days from the date of issue of the certificate of completion.

44.	Cost of Repairs:

44.1	Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor's cost if the loss or damage arises from the Contractor's acts or omissions.

E.  Finishing the Contract

# 45.		Completion

45.1		The Contractor shall request the Employer to issue a Certificate of Completion of the Works and the Employer will do so upon deciding that the Work is completed.

# 46.		Taking over

46.1		The Employer shall take over the Site and the Works within seven days of  issuing a certificate of Completion.

47. 		Final account

47.1		The Contractor shall supply to the Employer a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Employer shall issue a Defect Liability Certificate and certify any final payment that is due to the Contractor within 90 days of receiving the Contractor's account if it is correct and complete. If it is not, the Employer shall issue within 90 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Employer shall decide on the amount payable to the Contractor and  make payment within 60 days of receiving the Contractor’s revised account.

# 48.		As built drawings and /or Operating and Maintenance Manuals

48.1		If “as built” Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the Contract Data.

48.2		If the Contractor does not supply the Drawings by the dates stated in the Contract Data, or they do not receive the Employer’s approval,

# 49. 		Termination

49.1		The Employer may terminate the Contract if the other party causes a fundamental breach of the Contract.

49.2		Fundamental breaches of Contract include, but shall not be limited to the following:

(a)	the Contractor stops work for 45 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Employer;

(b)	deleted

(c)	The Contractor becomes bankrupt or goes into liquidation other than for a reconstruction or amalgamation;

(d)	deleted

(e)	the Employer gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Employer;

(f)	the Contractor does not maintain a security which is required;

(g)	the Contractor has delayed the completion of works by the number of days for which the maximum amount of liquidated damages can be paid as defined in the Contract data; and

(h)	if the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulent practices in competing for or in the executing the Contract.

For the purpose of this paragraph : “corrupt practice” means the offering, giving, receiving or soliciting of any thing of value to influence the action of a public official in the procurement process or in contract execution.  “Fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of the Borrower, and includes collusive practice among Tenderers (prior to or after Tender submission) designed to establish Tender prices at artificial non-competitive levels and to deprive the Borrower of the benefits of free and open competition.”

49.3		When either party to the Contract gives notice of a breach of contract to the Employer for a cause other than those listed under Sub Clause 49.2 above, the Employer shall decide whether the breach is fundamental or not.

49.4		Notwithstanding the above, the Employer may terminate the Contract for convenience.

49.5		If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secure and leave the Site as soon as reasonably possible.

50. 		Payment upon Termination

50.1		If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Employer shall prepare bill for the value of the work done less advance payments received up to the date of the bill, less other recoveries due in terms of the contract, less taxes due to be deducted at source as per applicable law and less the percentage to apply to the work not completed as indicated in the Contract Data. Additional Liquidated Damages shall not apply.  If the total amount due to the Employer exceeds any payment due to the Contractor the difference shall be a debt payable to the Employer.

50.2		If the Contract is terminated at the Employer's convenience or because of a fundamental breach of Contract by the Employer, the Employer shall prepare bill for the value of the work done, the reasonable cost of removal of Equipment, repatriation of the Contractor's personnel employed solely on the Works, and the Contractor's costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the contract, and less taxes due to be deducted at source as per applicable law and make payment accordingly.

# 51. 		Property

51.1		All materials on the Site, Plant, Equipment, Temporary Works and Works are deemed to be the property of the Employer, if the Contract is terminated because of a Contractor’s default.

52. 		Release from performance

52.1		If the Contract is frustrated by any event entirely outside the control of either the Employer or the Contractor the Employer shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which commitment was made

General Conditions:

- 1% of the Tendered amount will be deducted towards “Labour Welfare Fund “.

- The Tenderer has to produce all the relevant Documents as indicated in the Bid Document in originals during the opening of the Technical Bid  “ Mandatorily ” . This is in addition to Uploading all the relevant Documents in the e-procurement portal. If the Originals are not submitted, the Tender will be rejected.

- All other documents which are required to be submitted are to be uploaded in the e-Procurement Portal in General Documents section, while electronically submitting the bid. If any of the Documents as desired are not submitted the Tender will be rejected.

# F.   Special Conditions of Contract

1.	Labour:

The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for the engagement of all staff and labour, local or other, and for their payment, housing, feeding and transport.

The Contractor shall, if required by the Employer, deliver to the Employer a return in detail, in such form and at such intervals as the Employer may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the Contractor on the Site and such other information as the Employer may require.

2.	Compliance with labourregulations:

During continuance of the contract, the Contractor and his sub contractors shall abide at all times by all existing labour enactments and rules made there under, regulations, notifications and bye laws of the State or Central Government or local authority and any other labour law (including rules), regulations, bye laws that may be passed or notification that may be issued under any labour law in future either by the State or the Central Government or the local authority. The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authority on account of contravention of any of the provisions of any Act or rules made there under, regulations or notifications including amendments. If the Employer is caused to pay or reimburse, such amounts as may be necessary to cause or observe, or for non-observance of the provisions stipulated in the notifications/bye laws/Acts/Rules/regulations including amendments, if any, on the part of the Contractor, Employer shall have the right to deduct any money due to the Contractor including his amount of security deposit.  The Employer shall also have right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by the Employer.

The employees of the Contractor and the Sub-Contractor in no case shall be treated as the employees of the Employer at any point of time.

3.		 Protection of Environment:

The contractor shall take all reasonable steps to protect the environment on and off the Site and to avoid damage or nuisance to persons or to property of the public or others resulting from pollution, noise or other causes arising as a consequence of his methods of operation. During continuance of the contract, the contractor and his sub-contractors shall abide at all times by all existing enactments on environmental protection and rules made there under, regulations, notifications and bye-laws of the State or Central Government, or local authorities and any other law, bye-law, regulations that may be passed or notification that may be issued in this respect in future by the State or Central Government or the local authority.

4.	Arbitration (Clause 24)  - Deleted Refer Sl. No. 4 below

  - The procedure for arbitration shall be as follows:

- In case of dispute or difference arising between the Employer and the Contractor relating to any matter arising out of or connected with this agreement it shall be settled in accordance with the Arbitration and Conciliation Act 1996. The disputes or differences shall be referred to a Sole Arbitrator. The Sole Arbitrator shall be appointed by agreement between the parties; failing such agreement, by the Appointing Authority (any one of the Organizations as per list enclosed in Annexure)- Deleted

- Arbitration proceedings shall be held at………….. , Karnataka, India - Deleted

- The cost and expenses of arbitration proceedings will be paid as determined by the Arbitrator. However the expenses incurred by each party in connection with the preparation, presentation, etc., shall be borne by each party itself.-  Deleted

- Performance under the contract shall continue during the arbitration proceedings and payments due the Contractor by the Employer shall not be withheld, unless they are the subject matter of the arbitration proceedings.- Deleted

4. SETTLEMENT OF DISPUTES- TIME LIMIT FOR DECISION

(a)  If any dispute or difference of any kind whatsoever were to arise between the Executive Engineer/Superintending Engineer and the contractor regarding the following matters namely,

(i)	The meaning of the specifications, designs, drawings and instructions herein before mentioned;

II) The quality of workmanship or materials used on the work and

III) Any other question, claim, right, matter, thing whatsoever, in any way arising out of or relating to the contract, designs, drawings, specifications, estimates, instructions, or orders, or those conditions or failure to execute the same whether arising during the progress of the work, or after the completion, termination or abandonment thereof, the dispute shall, in the first place, be referred to the Chief Engineer who has jurisdiction over the work specified in the contract. The Chief Engineer shall, within a period of sixty days from the date of being requested by the Contractor to do so, give written notice of his decision to the Contractor. If the Contractor is aggrieved by the decision of the Chief Engineer, or if the Chief Engineer fails to give written notice of his decision within the above said period of sixty days, the contractor may appeal to the Managing Director, KNNL, within 60 days from the receipt of written notice of Chief Engineer's decision or from the expiry of first named period of 60 days.

        (b) Subject to the Managing Director's decision on appeal and subject to other form of settlement hereafter provided, the Chief Engineer's decision in respect of every dispute or difference so referred shall be final and binding upon the contractor.  The said decision shall forthwith be given effect to and contractor shall proceed with the execution of the work with all due diligence.

Remedy when Managing Director's decision on appeal is not acceptable to contractor

(c) In case the decision of the Managing Director is not acceptable to the contractor, he may approach the Law Courts at Davanagere(*) for settlement of dispute after giving due written notice in this regard to the Managing Director within a period of ninety days from the date of receipt of the written notice of the decision of the Managing Director.

Time limit for notice to approach law court by contractor
        (d) If the Managing Director has given written notice to the contractor of his decision on his appeal and no written notice to approach the law court has been communicated to him by the contractor within a period of ninety days from receipt of such notice, the said decision shall be final and binding upon the contractor.

Time limit for notice to approach law court by contractor when decision is not given by Managing Director.
        (e) If the Managing Director fails to give notice of his decision within a period of ninety days from the receipt of the contractor's appeal, the Contractor may within ninety days after the expiry of the above named period of ninety days approach the Law Courts at Davanagere(*)giving due notice to the Managing Director. 

        Note: (*) In sub clauses (c) and (e) specify the place where the Court under whose jurisdiction the work is situated/is located.

        (f) Whether the claim is referred to the Chief Engineer or Managing Director or to the Law Courts, as the case may be, the contractor shall proceed to execute and complete the works with all due diligence pending settlement of the said dispute of differences.

Obligations of the Executive Engineer and contractor shall remain unaltered during considerations of dispute
	(g) The reference of any dispute or difference to the Chief Engineer or Managing Director or the Law Court may proceed not withstanding that the works shall then be or be alleged to be complete, provided always that the obligations of the Executive Engineer and the contractor shall not be altered by reason of the said dispute or difference being referred to the Chief Engineer or Managing Director or the Law Court during the progress of the works.

Aggravated Contractor to Approach Civil Court

(h) It is clearly understood and agreed upon by both the parties that no part of the above clause shall be construed to be an arbitration clause. In the event of any dispute or difference  arising between the parties to this contract, upon exhausting the remedies  under clauses 29(a) to (g). The only remedy available shall be to approach the jurisdictional Civil court by filing a suit in accordance with law.

5. 		DEATH OF THE CONTRACTOR:

In case if the death of a contractor, after executing the agreement / commencement of the work, his legal heir, is  an eligible registered contractor and is willing, can execute and complete the work, at the accepted tender rates, irrespective of the cost of the work.

Annexure:

LIST OF ORGANIZATIONS WHO ARE CONSIDERED AS APPOINTING AUTHORITY FOR APPOINTMENT OF ARBITRATORS

  - Indian Council of Arbitration, New Delhi;

  - International Centre for Alternative Disputes Resolution  (India);

  - Indian Roads Congress;

  - IndianBuilding Congress;

  - Indian Institute of Bridge Engineers;

  - Indian Institute of Public Health Engineers;

  - Institute of Water Works

6.Royalty charges shall be recovered as per the prevailing rates issued by the department of mines & geology

7.	     AS per GO No LD300 LET 2006 Bangalore dated 18-01-2007 Cess at the rate of 1% of cost of construction will be deducted from the Bill towards building and other construction workers   welfare fund.

8.	     All the works are to be carried out as per the standard specifications issued from time to time by RIS & as per the relevant I.S. Code.

9.         In the case of death of a contractor after executing / commencement of the work, his legal heir, if an eligible registered contractor and willing can executive and complete the work at the accepted tender rates irrespective of the cost of work.

10.      	The Tenderer has to produce all the relevant Documents as indicated in the Bid Document in originals during the opening of the Technical Bid “Mandatorily”

If any of the Documents as desired are not submitted the Tender will be rejected

SECTION : 6

CONTRACT DATA

# SECTION 6: CONTRACT DATA

# Items marked "N/A" do not apply in this Contract.

# The following documents are also part of the Contract:		Clause Reference

- The Schedule of Operating and Maintenance Manuals		[48]	[48]

- The Methodology and Program of Construction			[25]

- Site Investigation Reports			[14]

- The Schedule of Key and Critical Equipment to be deployed

on the work as per agreed program of construction.			[25]

The Employer is :

Name: Executive Engineer 			[1.1]

# Address: Office of the Executive Engineer, KNNL, No.5 Bhadra Canal Division, Davangere.

# Name of authorized Representative:

# The name and identification number of the Contract is

# KNNL/2024-25/IW/WORK_INDENT1549[1.1]

The Works consist of RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292)[brief summary, including relationship to other contracts under the Project].

The start date shall be the date of issue of notice to proceed with the work.	[1.1]

The Intended Completion Date for the whole

of the Works is6 months from the date of Award with the following milestones

[17, 26]

Milestone dates:Physical works to be completedPeriod from the date of issue of

Notice to proceed with the work

Milestone1i.e.,…20% of the work value for 2- month

Milestone 2 i.e.,…25% of the work value for 2- month

Milestone 3 i.e.,…25% of the work value for1- month

Milestone 4 i.e.,…30% of the work value for1- month

The Site Possession Date is  : 			[21]

The Site is located  inDavanageretaluk.		[1.1]

and is defined in drawings Index map

The Defects Liability Period is 365days			[31]

Insurance requirements are as under:			[13]

|  | Type of Cover | Minimum cover for Insurance |
| --- | --- | --- |
| (i) | Works and of Plant and materials | The sum stated in the Agreement plus 20% |
| (ii) | Loss or damage to equipment | Full replacement cost |
| (iii) | Loss or damage to property of Third Party | Full replacement cost |
| (iv) | Personal injury or death insurance (a) for Third Party |  |
|  | (b) for Contractor’s employees or labour | In accordance with the statutory requirements applicable to Karnataka |

Price Adjustment Formula :  As per the prevailing Govt order		[40]

The star rates shall be worked out as per the provisions of clause 40 (a) to 40 (d) based on the price index issued from time to time by the Ministry of  Commerce and Industry, Government of India.

The liquidated damages for the whole of the works areRs.0.1% of the Contract Prices (amount) per day  and that for the each milestones and the maximum amount of liquidated damages for the whole of the works is ten percent of final contract price

[41]

The date by which “as-built” drawings (in scale 1 : 100)  in 2 sets are required is within 30

days of issue of certificate of completion of Whole or Section of the Work as the case may -deleted

be.		  [48]

The date by which Operating and Maintenance Manuals are required is within 30 days of issue of certificate of completion of Whole or Section of the Work as the case may be.						[48]

[48]

The amount to be withheld for failing to supply “as built” drawings or supply of Operation and Maintenance Manuals by the date required is at 0.25% of contract price	-Deleted		[48]

# The following events shall also be fundamental breach of the contract :                [49.2]

1.	The contractor has contravened Sub-clause 7.1 and Clause 9 of CC.

The percentage to apply to the value of the work not completed representing the Employer's 	[50.1]

additional cost for completing the Works shall be 30 percent.

SECTION : 7

DETAILED TECHNICAL SPECIFICATIONS

DETAILED  SPECIFICATION

The detailed Specification for Items in schedule-B can had

from website kpwd.gov.inand  from the sections given below

# SECTION 8: DRAWINGS

Separately attached

# SECTION 9: BILL OF QUANTITIES

Separately attached

|  |  |  |  | Rate (Rs) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sl. No. |  | Quantity | Unit | In figures | In words | Amount (Rs) |
|  |  | Total Tender Price (in figures) |  |  |  |  |
|  |  |  | (in words) |  |  |  |

Note:

- Item for which no rate or price has been entered in will not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities (refer: ITB Clause 11.2 and CC Clause 37.2).

- Unit rates and prices shall be quoted by the Tenderer in Indian Rupees.

- Where there is a discrepancy between the rate in figures and words, the lower of the two will govern. [ITT Clause 24.1(a)]

- Where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by quantity, the unit rate quoted shall govern [ITT Clause 24.1 (b)]

# SECTION 10: FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT

To:	Executive Engineer, KNNL,No.5 Bhadra canal Division, Division

WHEREAS _________________________ [name and address of Contractor] (hereinafter called "the Contractor") has undertaken, in pursuance of Contract No. _____ dated ________________ to RE-CONSTRUCTION OF HANUMANHALLI AQUEDUCT @ CH: 58.800KM UNDER MAIN CANAL OF DBC (KNNL/2025-26/IW/WORK_INDENT4292)[name of Contract and brief description of Works] (hereinafter called "the Contract");

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

# AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of Rs.____________________ [amount of guarantee] Rupees__________________________ __________________________[in words], and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ____________________ [amount of guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

# This guarantee shall be valid until 30 days from the date of expiry of the Defects Liability Period.

# Signature and seal of the guarantor _____________________________

Name of Bank ____________________________________________

Address ____________________________________________

Date ____________________________________________

Note:

    - The royalty charges will be recovered as per the govt. Orders issued from time to time.

Attached Separately

    - The following conversion factors shall be adopted under KNNL for calculation of royalty Charges.

| sl. no. | type of materilas | weight per cum of material |
| --- | --- | --- |
| 1 | Stones |  |
| a | Basalt/Trap | 2.90 tonnes/cum |
| b | Gneiss | 2.45 tonnes/cum |
| c | Lime Stones | 2.60 tonnes/cum |
| d | Granite | 2.60 tonnes/cum |
| e | Laterite | 2.25 tonnes/cum |
| f | Quartzite | 2.64 tonnes/cum |
| g | Sand Stone | 2.30 tonnes/cum |
| h | Shale | 2.80 tonnes/cum |
| 2 | Ordinary Sand | 1.84 tonnes/cum |
| 3 | Murrum, All Kinds Of Soil | 1.80 tonnes/cum |

Annexure -D

PROCEEDINGS OF THE GOVERNMENT OF KARNATAKA

Sub : Deduction of Shrinkage of settlement in earthwork embankment.

Ref : Correspondence ending with the letter  No. BRP/EBR/TE-77/TA-4 dated 11th            November 1965 from the Chief Engineer, Irrigation Project, Bangalore.

PREMABLE :4

The  Chief Engineer, Irrigation Project has reported that there was no uniform practive of standard vouge for deduction for deduction for settlement in earth work embankment and that it was discussed in the meeting of Chief Engineers held in 1961 who have made certain recommendations. The recommendations on receipt in government were examined and Government asked Chief Engineer, Irrigation project to obtain report in the matter. Then the matter, has been referred to the Director, Karnataka Engineering Research Station, K.R. Sagar for conducting experiments on various types of the embankments and under various condition in order to take decision on the uniform procedure to be adopted in making deductions for shrinkage settlement in earthwork embankments. The Director Karnataka Engineering Research Station has made the following recommendations

Settlement in percent of height of bank

Sl. 	Type of Embankment			Before 		After		After	After		No.					Monsson	Monsoon	second	Third										Mansoon	Mansoon

1		2				   3		   4		  5	    6

1.	Dry unrolled embankment in clay	25		12.50		6.5	Nil

soil including black cotton soils.

2.	Dry unrolled embankment in all 	20		10.00		5.00	Nil

soils other than clayey soil

3. Compacted embankments without

field control of placement

a) 	Manual labour or rollers	15		7.50		3.75	Nil		 less than six tonnes.

b)	By power rollers of more	10		5.00		2.50	Nil		than six tonnes.

4.	compacted embankment with 	5		2.50		Nil	Nil          field control placement

The Matter was further refered to the Board of Chief Engineer for consideration and opinion. The board holds that the recommendations of Director are based on generalisation and are indication of general trends in different types of soils. However, soil differs from place to place and it is desirable that actual tests are carried out and averages applied in individual cases. Where it is not possible to carry out the individual experiments the general values may be adopted.