Annexure I

PÁªÉÃj ¤ÃgÁªÀj ¤UÀªÀÄ ¤AiÀÄ«ÄvÀ

CAUVERY NEERAVARI NIGAMA(N)

(PÀ£ÁðlPÀ ¸ÀPÁðgÀzÀGzÀåªÀÄ)

(A Government of Karnataka Enterprises)

PÁAiÀÄð¥Á®PÀ EAf¤AiÀÄgïgÀªÀgÀ PÀbÉÃj,  «.¹ «¨sÁUÀ, ªÀÄAqÀåf¯Éè: ªÀÄAqÀå ¦£ï PÉÆÃqï: 571401

Telephones: 08232-225046                                                       mail-id  :vcdnmndya@gmail.com

Tender for the work of Improvements to vulnerable reaches in Karssavadi G Pickup under 8th distributary of Cauvery branch canal in Mandya Taluk.(Indent No. 5017)

Notification no: 04/2026-27, dated: 22.06.2026.

Two cover System

Through e –procurement

TENDER REFERENCE : CNNL/2026-27/OW/WORK_INDENT5017

ACCESSING OF BID DOCUMENT

ON e PORTAL                                                    : Please refer KPPP

LAST DATE FOR UPLOADING

(SUBMISSION) BIDS                                         :PleasereferKPPP

TIME AND DATE OF OPENING OF BIDS     :Please refer KPPP

PLACE OF OPENING OF BIDS          :Office of the EXECUTIVE   ENGINEER

CNNL,   V C  DIVISION.

Mandya

ADDRESS FOR COMMUNICATION:Office of the EXECUTIVE   ENGINEER

CNNL,   V C  DIVISION.

Mandya

Contents

Section No. Description 		Page

1 		INVITATION FOR TENDERS (IFT)

2 		INSTRUCTIONS TO TENDERERS (ITT)

3. 		FORM OF TENDER AND QUALIFICATION INFORMATION

4. 		CONDITIONS OF CONTRACT (CC)

5 		CONTRACT DATA

6 		SPECIFICATIONS

7 		DRAWINGS

8. 		BILL OF QUANTITIES

SECTION 1: INVITATION FOR TENDERS (IFT)

Date:22.06.2026.		IFT No.:04/2026-27

CNNL/2026-27/OW/WORK_INDENT5017

1. The Executive Engineer, CNNL, V CDivision,Mandya invites itemwise tenders from eligible tenderers, registered in KPWD, forthe construction of works detailed in the Table below. The tenderers may submit tenders for any or all of theworks given in the Table.

2. 	Tender documents may be downloaded from Government of KPPP website https://kppp.karnataka.gov.in   under login for Contractors:

After login to Contractors, Please scroll down to the right side bottom to see List of Tenders, Please click there to find the details of NIT and download copy of the tender.   The tender can be downloaded in the portal as per prescribed date and time published in the portal. Only Interested   Contractors   who wish to participate should remit online transaction fee for tender after registering in the portal. The transaction fee is non-refundable if you wish to participate.

AFETRSecurity Check

Please click on search tenders there to find the details of NIT and download copy of the tender. The tender can be downloaded in the portal as per prescribed date and time published in the portal. Only Interested Contractors who wish to participate should remit online transaction fee for tender after registering in the portal. The transaction fee is non-refundable if you wish to participate..

3.     Tenders must be accompanied by earnest money deposit which will paid online through  KPPP as mentioned .  Tenders must be accompanied by the earnest money deposit specified for the work in the table below.  Earnest money deposit will have to be in any of the forms as per the instructions in the KPPP and shall have to be valid for 45 days beyond the validity of the tender.

- Tenders must be electronically submitted (on-line through internet) with in the date and time  published in KPPP. Tenders will be opened at prescribed time  and date in the KPPP.

5. 	Other details can be seen in the tender documents.

TABLE

| Sl. No. | Name of work | Approximate Value of work (in Lakhs.) | Earnest Money Deposit (Rs.) | Tender Processing Fee (Non-refundable) (Rs.) | Period of completion | Category |
| --- | --- | --- | --- | --- | --- | --- |
| 01 | Improvements to vulnerable reaches in Karssavadi G Pickup under 8th distributary of Cauvery branch canal in Mandya Taluk.(Indent No. 5017) | 16.78 | 42,000.00 | As per KPPP | 60 days | KPWD Class-IV and above. |

Executive Engineer,

CNNL, V C DIVISION, Mandya

Executive Engineer,

CNNL, KRSM &MIPDivision,

Malavally .

SECTION 2: INSTRUCTIONS TO TENDERERS (ITT)

Table of Clauses

A. 	General

1. Scope of Tender

2. Eligible Tenderers

3. Tender capacity

B. 	Tender Documents

4. Content of Tender documents

5. Amendment of Tender documents

C. Preparation of Tenders

6. Documents comprising the Tender

7. Tender prices

8. Tender validity

9. Earnest money deposit

10. Format and signing of Tender

D. 	Submission of Tenders

11 Sealing and marking of Tenders

12 Deadline for submission of Tenders

13 Late Tenders

14 Modification and Withdrawal of Tenders

E. 	Tender opening and evaluation

15. Tender opening

16. Process to be confidential

17. Clarification of Tenders

19. Correction of errors

20. Evaluation and comparison of Tenders

F. 	Award of contract

21. Award criteria

22 Employer’s right to accept any Tender and to reject any or all Tenders

23. Notification of award and signing of Agreement

24. Security deposit

25. Corrupt or Fraudulent practices

A. General

1. Scope of Tender

1.1 	The Executive Engineer, CNNL, V C Division,Mandya. invites tenders fromContractors registered in KPWDfor the construction of works (as defined in these documents and referred to as "the works") detailed in the Table given in the Invitation forTenders (IFT). The tenderers may submit tenders for any or all of the works detailed in the table givenin IFT.

2. Eligible Tenderers

2.1 	Tenderers shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued by the Government of Karnataka

2.2 	Tenders from Joint ventures are not acceptable.

3. Tender capacity:

3.1	 Eligible Tenderers will be qualified only if their available tender capacity is more than the total tender value. The available tender capacity will be calculated as under:

Assessed available tender capacity = ( A*N*2.5 - B )

Where

A = Maximum value of civil engineering works executed in any one year during the last

five years(updated to 2026-27 price level) taking into account the completed as

well as works in progress.

N = Number of years prescribed for completion of the works for which Tenders are

invited.

B = Value, at 2026-27 price level, of existing commitments and on-going works to be

completed during          years (the period for completion of work for which the tender is invited.)

Note: 	The statements showing the value of existing commitments and on-going works as well as thestipulated period of completion remaining for each of the works listed should be countersigned bythe Employer in charge, not below the rank of an Executive Engineer or equivalent.

3.2 (a)	Even though the tenderers meet the above criteria, they are subject to be disqualified if they have:

- made misleading or false representations in the forms, statements and attachments submitted inproof of the qualification requirements; and/or

- record of poor performance such as abandoning the works, not properly completing the contract,inordinate delays in completion, litigation history, or financial failures etc.; and/or

- Participated in the previous Tender for the same work and had quoted unreasonably high tenderprices and could not furnish rational justification.

- In case of the death of the contractor after executing the agreement/commencement of the work, his legal heir, if an eligible registered contractor and willing can execute and complete the work at the accepted tender rates

B. Tender documents

4. 	Content of Tender documents

4.1 	The set of tender documents shall have all the Sections given in Page 2:

  - Both the sets should be completed and returned with the tender.

5. 	Amendment of Tender documents

5.1 	Before the deadline for submission of tenders, the Employer may modify the tender documents byissuing addenda.

5.2 	Any addendum thus issued shall be part of the tender documents and shall be communicated in writingor by cable to all the purchasers of the tender documents.

5.3 	To give prospective tenderers reasonable time in which to take an addendum into account in preparingtheir tenders, the Employer shall extend as necessary the deadline for submission of tenders, inaccordance with Sub-Clause 12.2 below.

C. Preparation of Tenders

6. Documents comprising the Tender

6.1 	The tender submitted by the Tenderer shall comprise the following:

(a) 	The Tender (in the format indicated in Section 3).

(b) 	Earnest Money Deposit;

(c) 	Priced Bill of Quantities;

(d) 	Qualification Information Form and Documents;

and any other materials required to be completed and submitted by tenderers in accordance with theseinstructions. The documents listed under Sections 3, 5 and 8 shall be filled in without exception.

7. Tender prices

7.1 	The contract shall be for the whole works as described in Sub-Clause 1.1, based on the priced Bill ofQuantities submitted by the Tenderer.

7.2 	The Tenderer shall fill in rates and prices and line item total (both in figures and words) for all items ofthe Works described in the Bill of Quantities along with total tender price (both in figures and words).Items for which no rate or price is entered by the Tenderer will not be paid for by the Employer whenexecuted and shall be deemed covered by the other rates and prices in the Bill of Quantities.Corrections, if any, shall be made by crossing out, initialing, dating and rewriting.

7.3 	All duties, taxes, and other levies payable by the contractor under the contract, or for any other cause,shall be included in the rates, prices and total Tender Price submitted by the Tenderer.

7.4 	The rates and prices quoted by the Tenderer shall be fixed for the duration of the Contract and shallnot be subject to adjustment on any account.

8. Tender validity

8.1 	Tenders shall remain valid for a period not less than ninety days after the deadline date for tendersubmission specified in Clause 12. A tender valid for a shorter periodshall be rejected by theEmployer as non-responsive.

8.2 	In exceptional circumstances, prior to expiry of the original time limit, the Employer may request thatthe tenderers may extend the period of validity for a specified additional period. The request and thetenderers' responses shall be made in writing or by cable. A tenderer may refuse the request withoutforfeiting his earnest money deposit. A tenderer agreeing to the request will not be required orpermitted to modify his tender, but will be required to extend the validity of his earnest money depositfor a period of the extension, and in compliance with Clause 9 in all respects.

9. Earnest money deposit

9.1 The contractor can pay the Earnest Money Deposit (EMD) in the KPPP using

any of the following payment modes:

- Credit Card

- Debit Card

- National Electronic Fund Transfer (NEFT)

- Over the Counter (OTC)

The contractor’s bid will be evaluated only on confirmation of receipt of the payment (EMD)

in the Government of Karnataka central pooling a/c held at Bank

EMD amount will have to be submitted by the contractor taking into account the following conditions:

- EMD will be accepted only in the form of electronic cash (and not through Demand Draft or

Bank Guarantee) and will be maintained in the Govt.’s central pooling account at

Bank until the contract is closed.

- The entire EMD amount for a particular tender has to be paid in a single transaction

For details on e-Payment services refer to KPPP for more details on the process.

The tenderer shall furnish, as part of his tender, earnest money deposit in the amount as shown in the table of IFT for this particular work

9.2 	Instruments having fixed validity issued as earnest money deposit for the tender shall be valid for 45days beyond the validity of the tender.

9.3 	Any tender not accompanied by an acceptable earnest money deposit and not secured as indicated inSub-Clauses 9.1 and 9.2 above shall be rejected by the Employer as non-responsive.

9.4 	The earnest money deposit of unsuccessful tenderers will be returned within 30 days of the end of thetender validity period specified in Sub-Clause 8.1.

9.5 	The earnest money deposit of the successful Tenderer will be discharged when the Tenderer has signedthe Agreement and furnished the required Performance Security.

9.6 	The earnest money deposit may be forfeited:

(a) 	if the Tenderer withdraws the Tender after tender opening during the period of tender validity;

(b) 	if the Tenderer does not accept the correction of the Tender Price, pursuant to Clause 19; or

(c)	in the case of a successful Tenderer, if the Tenderer fails within the specified time limit to

(i) 	sign the Agreement; or

(ii)	furnish the required Security deposit

10. Format and signing of Tender

10.1 	-Not Applicable-

10.2 	-Not Applicable-

10.3 	-Not Applicable-

Tenderer shall submit the Bid electronically before the submission date and time published in

KPPP.

D. Submission of Tenders

11. Sealing and marking of tenders

11.1 	-Not Applicable-

11.2 	                                         a) -Not Applicable-

b)  -Not Applicable-

11.3 	-Not Applicable-

11.4                                                  -Not Applicable-

Tenderer shall submit the Bid electronically before the submission date and time published in KPPP portal.

12. Deadline for submission of the Tenders

12.1 	Tenders must be received by the Employer at the address specified above , on or before the time & date specified in KPPP.

12.2 	The Employer may extend the deadline for submission of tenders by issuing an amendment in

accordance with Clause 5, in which case all rights and obligations of the Employer and the Tenderrspreviously subject to the original deadline will then be subject to the new deadline.

13. Late Tenders

13.1 	Any  tenders received by the employeer after the deadline prescribed in clause 12 will be returned unopened to the tenderer.

14. Modification and Withdrawal of Tenders)

14.1 	-Not Applicable-

14.2 	-Not Applicable-

14.3 	-Not Applicable-

14.4                                                 -Not Applicable-

14.5                                                 -Not Applicable-

E. Tender opening and evaluation

15. Tender opening

15.1 	The Employer will open all the Tenders received including modifications made pursuant to Clause 14, in the presence of the Tenderers or their representatives who choose to attend at the time, date and the place as notified in KPPP(clause 12). In the event of the specified date of Tender opening being declared a holiday for the Employer, the Tenders will be opened at the appointed time and location on the next working day.

15.2                                                -Not applicable-

15.3 	The Tenderers' names, the Tender prices, the total amount of each Tender, any discounts, Tender modifications and withdrawals, the presence or absence of Tender security, and such other details as the Employer may consider appropriate, will be announced by the Employer at the opening. No Tender shall be rejected at Tender opening except for the late Tenders pursuant to Clause 13. Tenders [and modifications] sent pursuant to Clause 14 that are not opened and read out at Tender opening will not be considered for further evaluation regardless of circumstances. Late and withdrawn Tenders will be returned un-opened to Tenderers.

15.4 	The Employer shall prepare minutes of the Tender opening, including the information disclosed to those present in accordance with Sub-Clause 15.3.

.

16. Process to be confidential

16.1 	Information relating to the examination, clarification, evaluation, and comparison of Tenders andrecommendations for the award of a contract shall not be disclosed to Tenderers or any other personsnot officially concerned with such process until the award to the successful Tenderer has been

announced. Any effort by a Tenderer to influence the Employer's processing of Tenders or awarddecisions may result in the rejection of his Tender.

17. Clarification of Tenders

17.1 	To assist in the examination, evaluation, and comparison of Tenders, the Employer may, at hisdiscretion, ask any Tenderer for clarification of his Tender, including breakdowns of unit rates. Therequest for clarification and the response shall be in writing or by cable, but no change in the price orsubstance of the Tender shall be sought, offered, or permitted except as required to confirm thecorrection of arithmetic errors discovered by the Employer in the evaluation of the Tenders inaccordance with Clause 19.

17.2 	Subject to sub-clause 17.1, no Tenderer shall contact the Employer on any matter relating to its Tenderfrom the time of the Tender opening to the time the contract is awarded. If the Tenderer wishes tobring additional information to the notice of the Employer, it should do so in writing.

17.3 	Any effort by the Tenderer to influence the Employer in the Employer’s Tender evaluation, Tendercomparison or contract award decisions may result in the rejection of the Tenderers’ Tender.

18. Examination of Tenders and determination of responsiveness

18.1 	Prior to the detailed evaluation of Tenders, the Employer will determine whether each Tender (a)meets the eligibility criteria defined in Clause 2; (b) has been properly signed; (c) is accompanied bythe required earnest money deposit and; (d) is substantially responsive to the requirements of theTender documents.

18.2 	A substantially responsive Tender is one which conforms to all the terms, conditions, and

specifications of the Tender documents, without material deviation or reservation. A material deviationor reservation is one (a) which affects in any substantial way the scope, quality, or performance of theWorks; (b) which limits in any substantial way, inconsistent with the Tender documents, theEmployer's rights or the Tenderer's obligations under the Contract; or (c) whose rectification wouldaffect unfairly the competitive position of other Tenderers presenting substantially responsive Tenders.

18.3 	If a Tender is not substantially responsive, it will be rejected by the Employer, and may not

subsequently be made responsive by correction or withdrawal of the nonconforming deviation orreservation.

19. Correction of errors

19.1 	                                            -Not Applicable-

19.2 	                                             -Not Applicable-

20. Evaluation and comparison of Tenders

20.1 	The Employer will evaluate and compare only the Tenders determined to be substantially responsive inaccordance with Clause 18.

20.2 	In evaluating the Tenders, the Employer will determine for each Tender the evaluated Tender Price byadjusting the Tender Price as follows:

- - Not Applicable-

- - Not Applicable-

20.3 	The Employer reserves the right to accept or reject any variation, deviation, or alternative offer.Variations, deviations, and alternative offers and other factors which are in excess of the requirementsof the Tender documents or otherwise result in unsolicited benefits for the Employer shall not be takeninto account in Tender evaluation.

20.4If the tender of the successful tenderer is seriously unbalanced in relation to the Employer’s

estimate of the cost of the work to be performed under the contract, the Employer may require

the Tenderer to produce detailed price analyses for any or all items of the Bill of Quantities, to

demonstrate the internal consistency of those prices with the construction methods and

schedule proposed. After evaluation of the price analyses, the Employer may require that the

amount of the performance security set forth in Clause 24 be increased at the expense of the

successful Tenderer to a level sufficient to protect the Employer against financial loss in the

event of default of the successful under the contract.

F. Award of Contract

21. Award criteria

21.1 	Subject to Clause 22, the Employer will award the Contract to the Tenderer whose Tender has beenddetermined to be substantially responsive to the Tender documents and who has offered the lowestevaluated Tender Price, provided that such Tenderer has been determined to be (a) eligible inaccordance with the provisions of Clause 2, and (b) qualified in accordance with the provisions ofClause 3.

22. Employer's right to accept any Tender and to reject any or all Tenders

22.1 	Notwithstanding Clause 21, the Employer reserves the right to accept or reject any Tender, and tocancel the Tender process and reject all Tenders, at any time prior to the award of Contract, withoutthereby incurring any liability to the affected Tenderer or Tenderers or any obligation to inform theaffected Tenderer or Tenderers of the grounds for the Employer's action.

23. Notification of award and signing of Agreement

23.1 	The Tenderer whose Tender has been accepted will be notified of the award by the Employer prior toexpiration of the Tender validity period by cable, telex or facsimile confirmed by registered letter. Thisletter (hereinafter and in the Conditions of Contract called the "Letter of Acceptance") will state thesum that the Employer will pay the Contractor in consideration of the execution, completion, andmaintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in theContract called the "Contract Price").

23.2 	The notification of award will constitute the formation of the Contract, subject only to the furnishing ofa performance security in accordance with the provisions of Clause 24.

23.3 	The Agreement will incorporate all agreements between the Employer and the successful Tenderer. Itwill be kept ready for signature of the successful Tenderer in the office of Employer within 30 daysfollowing the notification of award along with the Letter of Acceptance. Within 20 days of receipt, thesuccessful Tenderer will sign the Agreement and deliver it to the Employer.

23.4 	Upon the furnishing by the successful Tenderer of the Security deposit, the Employer willpromptlynotify the other Tenderers that their Tenders have been unsuccessful.

24. Security deposit

24.1 	Within 7 days of receipt of the Letter of Acceptance, the successful Tenderer shall deliver to the Employer a Security deposit in any of the forms given below for an amount equivalent to 5% of the Contract price plus additional security for unbalanced tenders in accordance with clause 20.4 of  ITT

- Cash

- Banker’s cheque/Demand draft,/Pay Order in favourofExecutive Engineer, CNNL,  V C Division,Mandya. PayableatMandyaor- Specified Small Savings Instruments pledged toExecutive Engineer, CNNL, V C Division,Mandya.

24.2 	The Security deposit if furnished in cash or demand draft can, if requested, be converted to interestbearing securities at the cost of the contractor.

24.3 	Failure of the successful Tenderer to comply with the requirements of Sub-Clause 24.1 shall constitutesufficient grounds for cancellation of the award and forfeiture of the earnest money deposit.

25. Corrupt or Fraudulent practices

25.1 	The GOK requires that the Tenderers, observe the highest standard of ethics during the KPPPand execution of such contracts. In pursuance of this policy, GOK :

- will reject a proposal for award if it determines that the Tenderer recommended for

awardhasengaged in corrupt or fraudulent practices in competing for the contract in

question;

- will declare a firm ineligible, either indefinitely or for a stated period of time, to be awarded aGOK contract if it at any time determines that the firm has engaged in corrupt or fraudulentpractices in competing for, or in executing, a GOK contract.

25.2 	Furthermore, Tenderers shall be aware of the provision stated in sub-clause 43.2 of the Conditions ofContract.

SECTION 3: FORMS OF TENDER, AND QUALIFICATION INFORMATION

TABLE OF FORMS:

- FORM OF TENDER

- QUALIFICATION INFORMATION

- LETTER OF ACCEPTANCE

- NOTICE TO PROCEED WITH THE WORK

- AGREEMENT FORM

Form of Tender

Description of the Works:

Improvements to vulnerable reaches in Karssavadi G Pickup under 8th distributary of Cauvery branch canal in Mandya Taluk.(Indent No. 5017)

Executive Engineer.

CNNL, V C DIVISION,

MANDYA

To,

GENTLEMEN,

We offer to execute the Works described above in accordance with the Conditions of Contract accompanyingthis Tender for the Contract Price ofRs……………………….….[in figures](………………..…………………………..…………………………………………………)[in letters].

This Tender and your written acceptance of it shall constitute a binding contract between us. We understand thatyou are not bound to accept the lowest or any Tender you receive.

We undertake that, in competing for (and, if the award is made to us, in executing) the above contract, we willstrictly observe the laws against fraud and corruption in force in India namely “Prevention of Corruption Act1988”.

`	We hereby confirm that this Tender complies with the Tender validity and Earnest money deposit required bythe Tender documents.

We attach herewith our current income-tax clearance certificate.

Yours faithfully,

Authorized Signature:

Name & Title of Signatory:

Name of Tenderer ………………………………………………….

Address: ----------------------------------------------------------------------

----------------------------------------------------------------------

-----------------------------------------------------------------------

Qualification Information

The information to be filled in by the Tenderer hereunder will be used for purposes of computing Tendercapacity as provided for in Clause 3 of the Instructions to Tenderers. This information will not be incorporatedin the Contract.

1.1 	Constitution or legal status of Tenderer[Attach copy]

Agency in which Registered (with Registration No.) …………………………………..

(Attach Copy)

Principal place of business:…………………………………………..

1.2 	Total value of civil engineering construction

works executed and payments received in the last

five years (in Rs. Lakhs) ( Attached certificates from

Charted Accounted)                                                    	           2021-22 …………………

2022-23 ………………....

2023-24………………….

2024-25 …………………

2025-26………………….

1.3 	Information on works for which Tenders have been submitted and works which are yet to be completedas on the date of this Tender.(The Contractor shall enclose / attach all the necessary certificates duly attested by the employer not lower than Executive Engineer.)

(A) Existing commitments and on-going works:

_________________________________________________________________________________

Description Place Contract No. Name Value of    Stipulated      Value of works     Anticipated

of		&	& Date and 	Contract period of	remaining to bedate of

Work 	State 		Address (Rs. lakhs) completion completed completion

of Employer(Rs. lakhs)

(1)		 (2) 	(3) 		(4) 	(5) 		(6) 		(7)		 (8)

_________________________________________________________________________________

(B) Works for which Tenders already submitted:

_________________________________________________________________________________

Description 	Place 	Name and 		Estimated 	Stipulated 	Date when 	Remarks

of&Addressof        value of works       period of decision is if any

Work State Employer (Rs. lakhs) completion expected

(1) 		(2) 		(3) 		(4)		(5) 	(6) 	(7)

1.4. 	Name, address, and telephone, telex, and fax numbers of the Tenderers' bankers who may providereferences if contacted by the Employer.

Letter of Acceptance

(letterhead paper of the Employer)

Date………………….

To: …………………………………..

…………………………………..

…………………………………..

…………………………………..

[nameandaddress of the Contractor]

Dear Sirs,

This is to notify you that your Tender dated ……………..for execution of the ……………………………………………………………………………………[name of the contract and identification number, as given in the Instructions to Tenderers] for the Contract Priceof Rupees …………………………………………………………     (…………………)

[amount in words and figures], as corrected and modified in accordance with the Instructions to Tenderers ishereby accepted by our Agency.

You are hereby requested to furnish Security deposit, in the form detailed in Para 24.1 of ITT for anamount of Rs………………. within 07 days of the receipt of this letter of acceptance valid up to 45 days from thedate of expiry of Defects Liability Period i.e. up to 365 DAYS and sign the contract, failing which action as statedin Para 24.3 of ITT will be taken.

Yours faithfully,

Authorized Signature…………………………………..

Name and Title of Signatory…………..………………

Name of Agency…………………….…………………

--------------------------------------------------------------------------------------------------------------------------

Issue of Notice to proceed with the work

(letterhead of the Employer)

Date………………….

To: …………………………………..

…………………………………..

…………………………………..

…………………………………..

[name and address of the Contractor]

Dear Sirs

Pursuant to your furnishing the requisite Security deposit as stipulated in ITT Clause 24.1 and signing ofthe contract agreement for the construction of …………. a Tender Price of Rs……………, you arehereby instructed to proceed with the execution of the said works in accordance with the contract documents.

Yours faithfully,

(Signature, name and title of signatory authorized to sign on behalf of Employer)

Agreement Form

Agreement

This agreement, made the ___________________day of ______________20_______,

between__________________________________________________________________________

________________________________________[name and address of Employer](hereinafter called “the Employer”) of the one part and _____________________________________________

_________________________________________________________________________________

______________________________________________________[name and address of contractor]

(hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor execute _____________________________

_________________________________________________________________________________

_________________________________________________________________________________[name and identification number of Contract] (hereinafter called “the Works”) and the Employer has acceptedthe Tender by the Contractor for the execution and completion of such Works and the remedying of any defectstherein at a contract price of Rupees...............................

NOW THIS AGREEMENT WITNESSETH as follows:

1. 	In this Agreement, words and expression shall have the same meanings as are respectively assigned tothem in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be readand construed as part of this Agreement.

2. 	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned,the Contractor hereby covenants with the Employer to execute and complete the Works and remedy anydefects therein in conformity in all aspects with the provisions of the Contract.

3. 	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion ofthe Works and the remedying the defects wherein the Contract Price or such other sum as may becomepayable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

4. 	The following documents shall be deemed to form and be read and construed as part of this Agreement,

viz:

i) 	Letter of Acceptance;

ii) 	Notice to proceed with the works;

iii) 	Contractor’s Tender;

iv) 	Contract Data;

v) 	Conditions of contract (including Special Conditions of Contract);

vi) 	Specifications;

vii) 	Drawings;

viii) Bill of Quantities; and

ix) 	Any other document listed in the Contract Data as forming part of the contract.

In witness whereof the parties thereto have caused this Agreement to be executed the day and year first beforewritten.

The Common Seal of ___________________________________________________________

was hereunto affixed in the presence of:

Signed, Sealed and Delivered by the said ______________________________________________________________________________

in the presence of:

Binding Signature of Employer _____________________________________________________

Binding Signature of Contractor _____________________________________________________

SECTION 4: CONDITIONS OF CONTRACT

Table of Contents

A. General 								Page No.

1. Definitions								23

2. Interpretation 								23

3. Law governing contract 						24

4. Employers decisions 							24

5. Delegation 								24

6. Communications 							24

7. Subcontracting 							24

8. Other Contractors 							24

9. Personnel							              24

10. Employer’s and Contractor’s risks 					24

11. Employer’s risks 							24

12 Contractor’s risks 							25

13 Query about Contract Data 						25

14 Contractor to construct the Works 					25

15. The Works to be completed by Intended Completion Date 			25

16. Safety 								25

17. Discoveries 								25

18. Possession of the Site 							25

19. Access to the Site						              25

20. Instructions 								25

B. Time Control

21. Program 								25

22. Extension of the Intended Completion Date				26

23. Delays ordered by the Employer					 26

24. Management meetings 						26

C. Quality Control

25. Identifying defects 							26

26. Tests 								26

27. Correction of defects						 26

28 Uncorrected defects 							26

D. Cost Control

29 Bill of Quantities (BOQ) 						26

30 Variations 								27

31. Payment for Variations 						27

32. Submission of bills for payment 					27

33 Payments								 28

34. Compensation events 							28

35. Tax 									28

36. Liquidated damages							 28

37. Cost of repairs 							29

E Finishing of Contract

38. Completion 								29

39. Taking Over 								29

40. Final account 								29

41. As built drawings							 29

42. Termination 								29

43 Payment upon termination 						30

44. Property 								30

45. Release from performance 						30

F Special Conditions of Contract 							31

Conditions of Contract

A. General

1. Definitions

1.1 	Terms which are defined in the Contract Data are not also defined in the Conditions of Contract butkeep their defined meanings. Bold letters are used to identify defined terms.

Bill of Quantities means the priced and completed Bill of Quantities forming part of the Tender.

Compensation events are those defined in Clause 34 hereunder.

The Completion Date is the date of completion of the Works as certified by the Employer in

accordance with Sub Clause 38.1.

The Contract is the contract between the Employer and the Contractor to execute, complete andmaintain the Works. It consists of the documents listed in Clause 2.3 below.

The Contract Data defines the documents and other information which comprise the Contract.

The Contractor is a person or corporate body whose Tender to carry out the Works has been acceptedby the Employer.

The Contractor's Tender is the completed Tender document submitted by the Contractor to the

Employer.

The Contract price is the price stated in the Letter of Acceptance and thereafter as adjusted in

accordance with the provisions of the Contract.

Days are calendar days; months are calendar months.

A Defect is any part of the Works not completed in accordance with the Contract.

The Defects liability period is the period named in the Contract Data and calculated from the

Completion Date.

The Employer is the party who will employ the Contractor to carry out the Works.

Equipment is the Contractor's machinery and vehicles brought temporarily to the Site to construct theWorks.

The Initial Contract price is the Contract Price listed in the Employer's Letter of Acceptance.

The Intended Completion Date is the date on which it is intended that the Contractor shall completethe Works. The Intended Completion Date is specified in the Contract Data. The Intended Completion

Date may be revised only by the Employer by issuing an extension of time.

Materials are all supplies, including consumables, used by the contractor for incorporation in theWorks.

Plant is any integral part of the Works which is to have a mechanical, electrical, electronic or chemicalor biological function.

The Site is the area defined as such in the Contract Data.

Specification means the Specification of the Works included in the Contract and any modification oraddition made or approved by the Employer.

The Start Date is given in the Contract Data. It is the date when the Contractor shall commenceexecution of the works. It does not necessarily coincide with any of the Site Possession Dates.

A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out apart of the work in the Contract which includes work on the Site.

A Variation is an instruction given by the Employer which varies the Works.

The Works are what the Contract requires the Contractor to construct, install, and turn over to theEmployer, as defined in the Contract Data.

2. Interpretation

2.1 	In interpreting these Conditions of Contract, singular also means plural, male also means female orneuter, and the other way around. Headings have no significance. Words have their normal meaningunder the language of the Contract unless specifically defined. The Employer will provide instructionsclarifying queries about the Conditions of Contract.

2.2 	The documents forming the Contract shall be interpreted in the following order of priority:

(1) Agreement

(2) Letter of Acceptance, notice to proceed with the works

(3) Contractor’s Tender

(4) Contract Data

(5) Conditions of Contract

(6) Specifications

(7) Drawings

(8) Bill of quantities and

(9) any other document listed in the Contract Data as forming part of the Contract.

3. Law governing contract

3.1 	The law governing the Contract is the Laws of India supplanted by the Karnataka Local Acts.

4. Employer's decisions

4.1 	Except where otherwise specifically stated, the Employer will decide contractual matters between theEmployer and the Contractor.

5. Delegation

5.1 	The Employer may delegate any of his duties and responsibilities to other people after notifying theContractor and may cancel any delegation after notifying the Contractor.

6. Communications

6.1 	Communications between parties which are referred to in the conditions are effective only when inwriting. A notice shall be effective only when it is delivered (in terms of Indian Contract Act).

7. Subcontracting

7.1 	The Contractor may subcontract with the approval of the Employer but may not assign the Contractwithout the approval of the Employer in writing. Subcontracting does not alter the Contractor'sobligations.

8. Other Contractors

8.1	The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities,and the Employer.

9. Personnel

9.1 	The Contractor shall employ the technical personnel (of number and qualifications) as may be

stipulated by GOK from time to time during the execution of the work. The technical staff so

employed shall be available at site as may be stipulated by the Employer.

9.2 	If the Employer asks the Contractor to remove a person who is a member of the Contractor’s staff orhis work force stating the reasons, the Contractor shall ensure that the person leaves the Site withinseven days and has no further connection with the work in the Contract.

10. Employer’s and Contractor's risks

10.1 	The Employer carries the risks which this Contract states are Employer’s risks, and the Contractorcarries the risks which this Contract states are Contractor’s risks.

11. Employer's risks

11.1 	The Employer is responsible for the excepted risks which are (a) in so far as rebellion, riot

commotion or disorder or (b) a cause due solely to the design of the Works, other than the

Contractor’s design.

12. Contractor’s risks

12.1 	All risks of loss of or damage to physical property and of personal injury and death which ariseduringand in consequence of the performance of the Contract other than the excepted risks are theresponsibility of the Contractor.

13. Queries about the Contract Data

13.1 	The Employer will clarify queries on the Contract Data.

14. Contractor to construct the Works

14.1 	The Contractor shall construct the Works in accordance with the Specification and Drawings.

15. The Works to be completed by the Intended Completion Date

15.1 	The Contractor may commence execution of the Works on the Start Date and complete them by theIntended Completion Date.

16. Safety

16.1 	The Contractor shall be responsible for the safety of all activities on the Site.

17. Discoveries

17.1 	Anything of historical or other interest or of significant value unexpectedly discovered on the Site isthe property of the Employer. The Contractor is to notify the Employer of such discoveries and carryout the Employer's instructions for dealing with them.

18. Possession of the Site

18.1 	The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part isnot given by the date stated in the Contract Data the Employer is deemed to have delayed the start ofthe relevant activities and this will be Compensation Event.

19. Access to the Site

19.1 	The Contractor shall allow the Employer and any person authorized by the Employer access to theSite, to any place where work in connection with the Contract is being carried out or is intended to becarried out and to any place where materials or plant are being manufactured / fabricated / assembledfor the works.

20. Instructions

20.1 	The Contractor shall carry out all instructions of the Employer which comply with the applicable lawswhere the Site is located.

B. Time Control

21. Program

21.1 	Within the time stated in the Contract Data the Contractor shall submit to the Employer for approval aProgram showing the general methods, arrangements, order, and timing for all the activities in theWorks.

21.2 	The Employer's approval of the Program shall not alter the Contractor's obligations. The Contractormay revise the Program and submit it to the Employer again at any time. A revised Program is to showthe effect of Variations and Compensation Events.

22. Extension of the Intended Completion Date

22.1	 The Employer shall extend the Intended Completion Date if a Compensation Event occurs or aVariation is issued which makes it impossible for Completion to be achieved by the IntendedCompletion Date.

22.2 	The Employer shall decide whether and by how much to extend the Intended Completion Date within21 days of the Contractor asking the Employer for a decision upon the effect of a Compensation Eventor Variation and submitting full supporting information.

23. Delays ordered by the Employer

23.1 	The Employer may instruct the Contractor to delay the start or progress of any activity within theWorks.

24. Management meetings

24.1 	The Employer may require the Contractor to attend a management meeting. The business of a

management meeting shall be to review the progress achieved and the plans for remaining work.

24.2 	The responsibility of the parties for actions to be taken is to be decided by the Employer either at themanagement meeting or after the management meeting and stated in writing to be distributed to allwho attended the meeting.

C. Quality Control

25. Identifying defects

25.1 	The Employer shall check the Contractor's work and notify the Contractor of any Defects that arefound. Such checking shall not affect the Contractor's responsibilities. The Employer may instruct theContractor to search for a Defect and to uncover and test any work that the Employer considers mayhave a Defect

26. Tests

26.1	 If the Employer instructs the Contractor to carry out a test not specified in the Specification to checkwhether any work has a Defect and the test shows that it does, the Contractor shall pay for the test andany samples. If there is no Defect the test shall be a Compensation Event.

27. Correction of defects

27.1 	The Employer shall give notice to the Contractor of any Defects before the end of the Defects LiabilityPeriod, which begins at Completion and is defined in the Contract Data. The Defects Liability Periodshallbe extended for as long as Defects remain to be corrected.

27.2 	Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the lengthof time specified by the Employer’s notice.

28. Uncorrected defects

28.1 	If the Contractor has not corrected a Defect within the time specified in the Employer’s notice, theEmployer will assess the cost of having the Defect corrected, and the Contractor will pay this amount.

D. Cost Control

29. Bill of Quantities (BOQ)

29.1 	The BOQ shall contain items for the construction, installation, testing, and commissioning work to bedone by the Contractor.

29.2 	The BOQ is used to calculate the Contract Price. The Contractor is paid for the quantity of the workdone at the rate in the BOQ for each item

30. Variations

30.1 	The Employer shall have power to order the Contractor to do any or all of the following as considerednecessary or advisable during the progress of the work by him

(a) 	Increase or decrease of any item of work included in the Bill of Quantities (BOQ);

(b) 	Omit any item of work;

(c) 	Change the character or quality or kind of any item of work;

(d) 	Change the levels, lines, positions and dimensions of any part of the work;

(e) 	Execute additional items of work of any kind necessary for the completion of the works; and

(f) 	Change in any specified sequence, methods or timing of construction of any part of the work.

30.2 	The Contractor shall be bound to carry out the work in accordance with any instructions in thisconnection, which may be given to him in writing by the Employer and such alteration shall not vitiateor invalidate the contract.

30.3 	Variations shall not be made by the Contractor without an order in writing by the Employer, providedthat no order in writing shall be required for increase or decrease in the quantity of an item appearingin the BOQ so long as the work executed conforms to the approved drawings.

30.4	 The Contractor shall promptly request in writing the Employer to confirm verbal orders and if no suchconfirmation is received within 15 days of request, it shall be deemed to be an order in writing by theEmployer.

31. Payments for Variations

31.1 	Payment for increase in the quantities of an item in the BOQ up to 25% of that provided in the Bill ofQuantities shall be made at the rates quoted by the Contractor.

31.2 	For quantities in excess of 125% of the tendered quantity of an item as given in the BOQ, the

Contractor shall be paid at the rate entered in or derived from, in the Schedule of Rates (applicable forthe area of the work and current at the time of award of contract) plus or minus the overall percentageof the original tendered rates over the current Schedule of Rates prevalent at the time of award ofcontract.

31.3 	If there is no rate for the additional, substituted or altered item of the work in the BOQ, efforts wouldbe made to derive the rates from those given in the BOQ or the Schedule of Rates (applicable for thearea of the work and current at the time of award of contract) and if found feasible the payment wouldbe made at the derived rate for the item plus or minus the overall percentage of the original tenderedrates over the current Schedule of Rates prevalent at the time of award of contract

31.4 	If the rates for additional, substituted or altered item of work cannot be determined either as at 31.1,31.2 or 31.3 above, the Contractor shall be requested to submit his quotation for the items supportedby analysis of the rate or rates claimed, within 7 days.

31.5 	If the Contractor's quotation is determined unreasonable, the Employer may order the Variation andmake a change to the Contract Price which shall be based on Employer’s own forecast of the effects ofthe Variation on the Contractor's costs.

31.6 	If the Employer decides that the urgency of varying the work would prevent a quotation being givenand considered without delaying the work, no quotation shall be given and the Variation shall betreated as a Compensation Event.

31.7 	Under no circumstances the Contractor shall suspend the work on the plea of non-settlement of ratesfor items falling under this Clause.

32. Submission of bills for payment

32.1 	The Contractor shall submit to the Employer monthly bills of the value of the work completed less thecumulative amount paid previously.

32.2 	The Employer shall check the Contractor's bill and determine the value of the work executed whichshall comprise of (i) value of the quantities of the items in the BOQ completed and (ii) valuation ofVariations and Compensation Events.

32.3	 The Employer may exclude any item paid in a previous bill or reduce the proportion of any itempreviously paid in the light of later information.

33. Payments

33.1 	Payments shall be adjusted for deductions for retention, other recoveries in terms of the contract andtaxes, at source, as applicable under the law. The Employer shall pay the Contractor the within 60days of submission of bill. (subject to the availability of the grant).

33.2 	Items of the Works for which no rate or price has been entered in will not be paid for by the Employerand shall be deemed covered by other rates and prices in the Contract.

34. Compensation events

34.1 	The following are Compensation events unless they are caused by the Contractor:

(a) 	The Employer does not give access to a part of the Site by the Site Possession Date statedin the Contract Data.

(b) 	The Employer orders a delay or does not issue drawings, specifications or instructions

required for execution of works on time.

(c) 	The Employer instructs the Contractor to uncover or to carry out additional tests upon

work which is then found to have no Defects.

(d) 	The Employer gives an instruction for dealing with an unforeseen condition, caused by theEmployer, or additional work required for safety or other reasons.

(e) 	The effect on the Contractor of any of the Employer’s Risks.

(f) 	The Employer unreasonably delays issuing a Certificate of Completion.

(g) 	Other Compensation Events listed in the Contract Data or mentioned in the Contract.

34.2 	If a Compensation Event would cause additional cost or would prevent the work being completedbefore the Intended Completion Date, the Contract Price shall be increased and/or the IntendedCompletion Date is extended. The Employer shall decide whether and by how much the Contract Priceshall be increased and whether and by how much the Intended Completion Date shall be extended.

34.3 	As soon as information demonstrating the effect of each Compensation event upon the Contractor'sforecast cost has been provided by the Contractor, it is to be assessed by the Employer and theContract Price shall be adjusted accordingly. If the Contractor's forecast is deemed unreasonable, theEmployer shall adjust the Contract Price based on Employer’s own forecast. The Employer willassume that the Contractor will react competently and promptly to the event.

34.4 	The Contractor shall not be entitled to compensation to the extent that the Employer's interests areadversely affected by the Contractor not having given early warning or not having cooperated with theEmployer.

35. Tax

35.1	The rates quoted by the Contractor shall be deemed to be inclusive of the sales and other taxes (Excluding Applicable GST) that theContractor will have to pay for the performance of this Contract. The Employer will perform suchduties in regard to the deduction of such taxes at source as per applicable law.

36. Liquidated damages

36.1	 The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the ContractData for each day that the Completion Date is later than the Intended Completion Date. The totalamount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employermay deduct liquidated damages from payments due to the Contractor. Payment of liquidated damagesdoes not affect the Contractor's liabilities.

36.2 	If the Intended Completion Date is extended after liquidated damages have been paid, the Employershall correct any overpayment of liquidated damages by the Contractor by adjusting the next paymentof bill.

37. Cost of repairs

37.1 	Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date andtheend of the Defects Correction periods shall be remedied by the Contractor at the Contractor's cost ifthe loss or damage arises from the Contractor's acts or omissions.

E. Finishing the Contract

38. Completion

38.1 	The Contractor shall request the Employer to issue a Certificate of Completion of the Works and theEmployer will do so upon deciding that the Work is completed.

39. Taking over

39.1 	The Employer shall take over the Site and the Works within seven days of issuing a certificate ofCompletion.

40. Final account

40.1 	The Contractor shall supply to the Employer a detailed account of the total amount that the Contractorconsiders payable under the Contract before the end of the Defects Liability Period. The Employershall issue a Defect Liability Certificate and certify any final payment that is due to the Contractorwithin 90 days of receiving the Contractor's account if it is correct and complete. If it is not, theEmployer shall issue within 90 days a schedule that states the scope of the corrections or additions thatare necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Employershall decide on the amount payable to the Contractor and make payment within 60 days of receivingthe Contractor’s revised account.

41. As built drawings

41.1 	If “as built” Drawings are required, the Contractor shall supply them by the dates stated in theContract Data.

41.2 	If the Contractor does not supply the Drawings by the dates stated in the Contract Data, or they do notreceive the Employer’s approval, the Employer shall withhold the amount stated in the Contract Datafrom payments due to the Contractor.

42. Termination

42.1 	The Employer or the Contractor may terminate the Contract if the other party causes a fundamentalbreach of the Contract.

42.2 	Fundamental breaches of Contract include, but shall not be limited to the following:

(a) 	the Contractor stops work for 45 days when no stoppage of work is shown on the currentProgram and the stoppage has not been authorized by the Employer;

(b) 	the Employer instructs the Contractor to delay the progress of the Works and the

instruction is not withdrawn within 60 days;

(c) 	The Contractor becomes bankrupt or goes into liquidation other than for a reconstructionor amalgamation;

(d)	a payment due to the Contractor is not paid by the Employer within 90 days of the date ofthe submission of the Bill by Contractor;

(e) 	the Employer gives Notice that failure to correct a particular Defect is a fundamental

breach of Contract and the Contractor fails to correct it within a reasonable period of timedetermined by the Employer;

(f) 	the Contractor does not maintain a security which is required;

(g)	 the Contractor has delayed the completion of works by the number of days for which themaximum amount of liquidated damages can be paid as defined in the Contract data; and

(h)	 if the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulentpractices in competing for or in the executing the Contract.For the purpose of this paragraph : “corrupt practice” means the offering, giving, receivingor soliciting of any thing of value to influence the action of a public official in theKPPP process or in contract execution. “Fraudulent practice” means amisrepresentation of facts in order to influence a KPPP process or the execution of acontract to the detriment of the Borrower, and includes collusive practice among Tenderers(prior to or after Tender submission) designed to establish Tender prices at artificial non-competitive levels and to deprive the Borrower of the benefits of free and opencompetition.”

42.3 	When either party to the Contract gives notice of a breach of contract to the Employer for a cause otherthan those listed under Sub Clause 42.2 above, the Employer shall decide whether the breach isfundamental or not.

42.4 	Notwithstanding the above, the Employer may terminate the Contract for convenience.

42.5 	If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secureand leave the Site as soon as reasonably possible.

43. Payment upon Termination

43.1 	If the Contract is terminated because of a fundamental breach of Contract by the Contractor, theEmployer shall prepare bill for the value of the work done less advance payments received up to thedate of the bill, less other recoveries due in terms of the contract, less taxes due to be deducted atsource as per applicable law and less the percentage to apply to the work not completed as indicated inthe Contract Data. Additional Liquidated Damages shall not apply. If the total amount due to theEmployer exceeds any payment due to the Contractor the difference shall be a debt payable to theEmployer.

43.2 	If the Contract is terminated at the Employer's convenience or because of a fundamental breach ofContract by the Employer, the Employer shall prepare bill for the value of the work done, thereasonable cost of removal of Equipment, repatriation of the Contractor's personnel employed solelyon the Works, and the Contractor's costs of protecting and securing the Works and less advancepayments received up to the date of the certificate, less other recoveries due in terms of the contract,and less taxes due to be deducted at source as per applicable law and make payment accordingly.

44. Property

44.1 	All materials on the Site, Plant, Equipment, Temporary Works and Works are deemed to be theproperty of the Employer, if the Contract is terminated because of a Contractor’s default.

45. Release from performance

45.1 	If the Contract is frustrated by any event entirely outside the control of either the Employer or theContractor the Employer shall certify that the Contract has been frustrated. The Contractor shall makethe Site safe and stop work as quickly as possible after receiving this certificate and shall be paid forall work carried out before receiving it and for any work carried out afterwards to which commitmentwas made.

F. Special Conditions of Contract

1. 	Labour :

The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for theengagement of all staff and labour, local or other, and for their payment, housing, feeding andtransport.

The Contractor shall, if required by the Employer, deliver to the Employer a return in detail, in suchform and at such intervals as the Employer may prescribe, showing the staff and the numbers of theseveral classes of labour from time to time employed by the Contractor on the Site and such otherinformation as the Employer may require.

- Compliance with labour regulations :

During continuance of the contract, the Contractor and his sub contractors shall abide at all times by allexistinglabour enactments and rules made there under, regulations, notifications and bye laws of theState or Central Government or local authority and any other labour law (including rules), regulations,bye laws that may be passed or notification that may be issued under any labour law in future either bythe State or the Central Government or the local authority. The Contractor shall keep the Employerindemnified in case any action is taken against the Employer by the competent authority on account ofcontravention of any of the provisions of any Act or rules made there under, regulations ornotifications including amendments. If the Employer is caused to pay or reimburse, such amounts asmay be necessary to cause or observe, or for non-observance of the provisions stipulated in thenotifications/bye laws/Acts/Rules/regulations including amendments, if any, on the part of theContractor, Employer shall have the right to deduct any money due to the Contractor including hisamount of security deposit. The Employer shall also have right to recover from the Contractor anysum required or estimated to be required for making good the loss or damage suffered by theEmployer.

The employees of the Contractor and the Sub-Contractor in no case shall be treated as the employeesof the Employer at any point of time.

3. 	Protection of Environment:

The contractor shall take all reasonable steps to protect the environment on and off the Site and toavoid damage or nuisance to persons or to property of the public or others resulting from pollution,noise or other causes arising as a consequence of his methods of operation. During continuance of thecontract, the contractor and his sub-contractors shall abide at all times by all existing enactments onenvironmental protection and rules made there under, regulations, notifications and bye-laws of theState or Central Government, or local authorities and any other law, bye-law, regulations that may bepassed or notification that may be issued in this respect in future by the State or Central Government orthe local authority.

- In case of the death of a contractor after executing the agreement/ commencement of the work, his legalheir, if an eligible registered contractor and willing can execute complete the work at the accepted tender rates irrespective of the cost of the work.

SECTION 5: CONTRACT DATA

Items marked "N/A" do not apply in this Contract.

The following documents are also part of the Contract: Clause Reference

The Employer is :

Name:Executive engineer,	[1.1]

Address: CNNL, V C  Division.

MANDYA.

Name of authorized Representative:…………………………..

The name and identification number of the Contract is

Improvements to vulnerable reaches in Karssavadi G Pickup under 8th distributary of Cauvery branch canal in Mandya Taluk.(Indent No. 5017)

tender notification No 04/2026-27, Dated:22.06.2026.

The Works consistof  Improvements to canal

The start date shall be the date of issue of notice to proceed with the work. [1.1]

The Intended Completion Date for the whole of the Works is  60DAYS[15, 22]

from the issue of notice to proceed with the work

The following documents also form part of the Contract: [2.2]

…………………………………………………………..

…………………………………………………………..

…………………………………………………………..

…………………………………………………………..

The Site Possession Date is :one week after issue of work order                               [18]

The Site is located at Mandya taluk	[1.1]

and is defined in drawings nos. …………………………………..

The Defects Liability Period is 365 DAYS from the date of completion of the work. [27]

The liquidated damages for the whole of the works are 0.1%Per day            (36)

The maximum amount of liquidated damages for the whole of the works [36]

isten percent of final contract price.

The date by which “as-built” drawings (in scale …) in 2 sets are required is within

30 days of issueof certificate of completion. ..             [41]

The amount to be withheld for failing to supply “as built” drawings by the date

required isRs5000/-[41]

1% of the tender amount will be deducted from the work bill towards

Construction  Workers  Welfare cess besides the other statutory deductions.

Royalty on construction materials and other taxes will be deducted

as per prevailing Government orders. Contractor should follow strictly

the prevailing rules of labour act.

The following events shall also be fundamental breach of the contract : [42.2]

1. The contractor has contravened Sub-clause 7.1 and Clause 9 of CC.

The percentage to apply to the value of the work not completed representing                       [43.1]

the Employer's additional cost for completing the Works shall be 30 percent.

SECTION 7: DRAWINGS

- Separate Sheet Enclosed -

SECTION 8: BILL OF QUANTITIES

| Sl. No. | Description of item (with brief specification and reference to Book of specification) | Quantity | Unit | Rate (Rs) |  | Amount (Rs) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | In figures | In words |  |
|  | - Separate Sheet Enclosed - |  |  |  |  |  |
| Total Tender Price (in figures) |  |  |  |  |  |  |
| (in words) |  |  |  |  |  |  |

Note:

(1) 	Item for which no rate or price has been entered in will not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities (refer: ITB Clause 7.2 and CC Clause 33.2).

(2) 	Unit rates and prices shall be quoted by the Tenderer in Indian Rupees.

(3) 	Where there is a discrepancy between the rate in figures and words, the rates in words will govern.[ITB Clause 19.1(a)]

(4) 	Where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by quantity, the unit rate quoted shall govern [ITB Clause 19.1 (b)]

SECTION 10: FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT

To: ______________________________________________ [name of Employer]

_________________________________________ [address of Employer]

WHEREAS _________________________ [name and address of Contractor] (hereinafter called "the Contractor") has undertaken, in pursuance of Contract No. _____ dated ________________ to execute __________________________ [name of Contract and brief description of Works] (hereinafter called "the Contract");

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of Rs.____________________ [amount of guarantee] 29_Rupees__________________________ __________________________[in words], and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ____________________ [amount of guarantee]30 as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until 30 days from the date of expiry of the Defects Liability Period.

Signature and seal of the guarantor _____________________________

Name of Bank ____________________________________________

Address ____________________________________________

Date ____________________________________________

29 An amount shall be inserted by the Guarantor, representing the percentage of the Contract Price specified in the Contract