GOVERNMENT OF KARNATAKA

(e-ProcurementTender)

TENDER FOR THE WORK OF

PACKAGE-149 Providing FHTC's to 103 Households in Havenahalli Habitation of Havenahalli Village, 58 Households in Basavanapura Habitation of Basavanapura Village, Rangapura Grampachayth of Tiptur taluk, Tumkur district MVS of providing water supply facility to 390 Habitation in Tiptur taluk, Tumkuru district from Hemavathi River (CAT-II(A) RWSSD/2025-26/WS/WORK_INDENT9867

TENDER DOCUMENT

Office of the Executive Engineer,

RURAL DRINKING WATER & SANITATION DEPARTMENT

TUMKUR  DISTRICT,KARNATAKA

TENDER FOR THE WORK OF

PACKAGE-149 Providing FHTC's to 103 Households in Havenahalli Habitation of Havenahalli Village, 58 Households in Basavanapura Habitation of Basavanapura Village, Rangapura Grampachayth of Tiptur taluk, Tumkur district MVS of providing water supply facility to 390 Habitation in Tiptur taluk, Tumkuru district from Hemavathi River (CAT-II(A) RWSSD/2025-26/WS/WORK_INDENT9867

TENDER REFERENCE:2024-25                			Tender No:  23/2025-26

| PERIOD OF DOWNLOAD OF TENDER DOCUMENT (https://Kppp.karnataka.gov.in) | From: 03-03-2026 |
| --- | --- |
| PREBID MEETING DATE AND VENUE |  |
| LAST DATE AND TIME FOR RECEIPT OF TENDERS | 16-03-2026 gÀAzÀÄ ¸ÀAeÉ 5.00 UÀAmÉªÀgÉUÉ |
| Pre Bid Meeting | Date: 11-03-2026 at 11.00 A M Venue, Executive Engineer, Rural Drinking water & Sanitation Division Tumkur |
| TIME AND DATE OF OPENING OF TENDERS “Technical Tender“ | 17-03-2026 gÀAzÀÄ ¸ÀAeÉ 5.30 gÀ £ÀAvÀgÀ |
| TIME AND DATE OF OPENING OF TENDERS “Financial Tender“ | 18-03-2026 gÀAzÀÄ ¸ÀAeÉ 5.30 gÀ £ÀAvÀgÀ |
| ADDRESS FOR COMMUNICATION | The Executive Engineer, Rural Drinking Water & Sanitation Department, TUMKUR District, Karnataka – 572102 Phone: ……………. Email-eejjmtmk@gmail.com |

Contents

| Section No | Description | Page Number |
| --- | --- | --- |
| 1 | Invitation for Tenders (IFT) | 6 |
| 2 | Instructions to Tenderers (ITT) | 9 |
| 3 | Qualification Information | 21 |
| 4 | Form of Tender, Letter of Acceptance, Notice to Proceed with the work and Agreement Form | 28 |
| 5 | Conditions of Contract (CC) | 33 |
| 6 | Contract Data | 49 |
| 7 | Technical Specifications | 50 |
| 8 | Drawings | 51 |
| 9 | Bill of Quantities – Price Tender | 53 |
| 10 | Format of Bank Guarantee for Security Deposit | 55 |

Disclaimer

The information contained in this Tender document or subsequently provided to Tenderer(s), whether verbally or in documentary or any other form by or on behalf of the Employer or any of its employees or advisors, is provided to Tenderer(s) on the terms and conditions set out in this tender document and such other terms and conditions subject to which such information is provided.

This Tender document is not an agreement and is neither an offer nor initiation by the Employer to the prospective Tenderers or any other person. The purpose of this Tender document is to provide interested parties with information that may be useful to them in making their Price Tenders pursuant to this Tender document. This Tender document includes statements, which reflect various assumptions and assessments arrived by the Employer in relation to the Project. Such assumptions, assessments and statements do not purport to contain all the information that each Tenderer may require. This Tender document may not be appropriate to all persons, and it is not possible for the Employer, its employees or advisors to consider the investment objectives, financial situation and particular needs of each party who reads or uses this Tender document. The assumptions, assessments, statements and information contained in all sections of this Tenderdocument may not be complete, accurate, adequate or correct. Each Tenderer should, therefore, conduct its own investigations and analysis and should check the accuracy, adequacy, correctness, reliability and completeness of the assumptions, assessments, statements and information contained in this Tender document and obtain independent advice from appropriate sources.

Information provided in this Tender document to the Tenderer(s) is on a wide range of matters, some which may depend upon interpretation of law. The information given is not intended to be an exhaustive account of statutory requirements and should not be regarded as a complete or authoritative statement of law. TheEmployer accepts no responsibility for the accuracy or otherwise for an interpretation or opinion on law expressed herein.

The Employer, its employees and advisors make no representation or warranty and shall have no liability to any person, including any Tenderer under the law, statute, rules or regulations or tort, principles of restitution or unjust enrichment or otherwise for any loss, damages, cost or expenses which may arise from or be incurred or suffered on account of anything contained in this Tender document or otherwise, including the accuracy, adequacy, correctness, completeness or reliability of the Tender document and any assessment, assumption, statement or information contained therein or deemed to form part of this Tender document or arising in any way for participation in this Tender Stage.

The Employer also accepts no liability of any nature whether resulting from negligence or otherwise howsoever caused arising from reliance of any Tenderer upon the statements contained in this Tender document.The Employer may in its absolute discretion, but without being under any obligation to do so, update, amend or supplement the information, assessment or assumptions contained in this Tender document.

The issue of this Tender document does not imply that the Employer is bound to select a Tenderer or to appoint the selected Tenderer, as the case may be, for the Project and the Employer reserves the right to reject all or any of the Tenderers or Tenders without assigning any reason whatsoever.

The Tenderer shall bear all its costs associated with or relating to the preparation and submission of its Tender including but not limited to preparation, copying, postage, delivery, fees, expenses associated with any demonstrations or presentations which may be required by the Employer or any other costs incurred in connection with or relating to its Tender. All such costs and expenses will remain with the Tenderer and the Employer shall not be liable in any manner whatsoever for the same or for any other costs or other expenses incurred by a Tenderer in preparation or submission of the Tender, regardless of the conduct or outcome of the Tendering Process.

SECTION 1:

INVITATION FOR TENDERS (IFT)

## SECTION 1:INVITATION FOR TENDERS (IFT)

(Through  Kppp  Mode)

Date :03-03-2026	Notification No: 23/ 2025-26

- The Executive Engineer Rural Drinking Water & Sanitation Department, TUMKUR District, Karnataka invites tenders from eligible Tenderers, for the below detailed work. Two Tender document procedure as per Rule 28 of the Karnataka Transparency in Public Procurement Act, 1999 and Rules, 2000 shall be followed. The Tenderers are required to submit all the documents required for the Tender through  Kppp  mode, through portal-https://Kppp.karnataka.gov.in.The Tenderers are required to submit two separate tender documents, one containing the Earnest money deposit and the details of their capability to undertake the tender (as detailed in ITT Clause 3and 6), which will be opened first and the second cover containing the Price Tender which will be opened only if the Tenderer is found to be qualified to execute the tendered works. The Tenderers are advised to note the minimum qualification criteria specified in Clause 3 of the Instructions to Tenderers to qualify for award of the contract.

- Manual submission of Tenders or documents is not allowed and such submissions shall be ignored and Tender of a Tenderer making such submissions shall be rejected as disqualified.

- Tender documents may be downloaded &submitted in the  Kppp  Portal of e- Governance Department, https://Kppp.karnataka.gov.infrom the date specified, along with a non-refundable Tender fee as prescribed by Kppp  Portal in the form and manner as prescribed by  Kppp  Platform. The Executive Engineer Rural Drinking Water &Sanitation Department, TUMKUR District, Karnataka will not be held responsible for the technical issues with the said Portal. The technical issues and resultant of any delay leading to non-submission of Tender shall be responsibility of the Tenderer. The Tenderer is required to ensure browser compatibility of the computer well in advance to the last date and time for receipt of the Tenders. It is the Tenderer’s responsibility to verify the  Kppp  portal for the latest information related to the Tender. E-mail address of the helpdesk is support@eprochelpdesk.com.  Kppp  portal helpdesk telephones numbers are 080-46010000/68948777who may be contacted during office hours.

- Tenders must be accompanied by Earnest Money Deposit specified for the work in the Table below. Earnest money deposit will have to be in any one of the forms as specified in the Tender document and shall have to be valid for 45 (forty-five) days beyond the validity of the Tender. The EMD shall be deposited through  Kppp  Portal, https://Kppp.karnataka.gov.in as mentioned in Clause 11.2 of Instructions to Tenderers.

- Tenders must be correctly and properly uploaded in  Kppp  Portal (https://Kppp.karnataka.gov.in) on or before the date and time specified in  Kppp  portal and Technical Tender of the Tenders will be opened on the specified time and date, in the presence of the Tenderers who wish to attend. If the office happens to be closed on the any specified date of the Tenders, the said action shall be taken on the next working day at the same time and venue

- Other details are available in the Tender documents.

| Sl No | Name of work | Approximate value of work(INR) | E.M.D* (INR) | Tender Processing Fee | Period of Completion |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |
| 01 | PACKAGE-149 Providing FHTC's to 103 Households in Havenahalli Habitation of Havenahalli Village, 58 Households in Basavanapura Habitation of Basavanapura Village, Rangapura Grampachayth of Tiptur taluk, Tumkur district MVS of providing water supply facility to 390 Habitation in Tiptur taluk, Tumkuru district from Hemavathi River (CAT-II(A) RWSSD/2025-26/WS/WORK_INDENT9867 | Rs 56.66 Lakhs | 56660/- | As per Kppp portal | 06 Months |

Sd

Executive Engineer,

Rural Drinking Water & Sanitation Department,

TUMKURDistrict, Karnataka State

SECTION 2:

INSTRUCTIONS TO TENDERERS (ITT)

## SECTION 2:INSTRUCTIONS TO TENDERERS (ITT)

Table of Clauses

Contents

A.	General	10

1.	Scope of Tender	10

2.	Eligible Tenderer	10

3.	Qualification of the Tenderer:	10

B.	Tender Documents	12

4.	Content of Tender documents	12

5.	Amendment of Tender documents	12

C. 	Preparation of Tenders	12

6.	Documents comprising the Tender	12

7.	Tender prices	13

8.	Tender validity	13

9.	Earnest Money Deposit	13

10.	Format and signing of Tender	14

D. 	Submission of Tenders	14

11.	Online Tender Submission	14

12.	Deadline for submission of the Tenders	15

13.	Late Tenders	15

14.	Modification and Withdrawal of Tenders – As per e-portal	15

E. 	Tender opening and evaluation	16

15.	Opening of Technical Tender  of all Tenders and evaluation to determine technically qualified Tenderers: As per e-Portal	16

16.	Opening of Price Tender of qualified Tenderers and evaluation: As per e-Portal	16

17.	Process to be confidential	17

18.	Clarification of Tenders	17

19.	Examination of Tenders and determination of responsiveness	17

20.	Correction of errors	17

21.	Evaluation and comparison of Tenders	18

F. 	Award of Contract	18

22.	Award criteria	18

23.	Employer's right to accept any Tender and to reject any or all Tenders	18

24.	Notification of award and signing of Agreement	18

25.	Unconditional Security Deposit	19

26.	Corrupt or Fraudulent practices	19

#### General

#### Scope of Tender

##### The EXECUTIVE ENGINEER, Rural Drinking Water & Sanitation Department, TUMKUR District Karnataka, (referred to as employer in these documents invitesTender following the Two DocumentTender procedure through  Kppp  Portal of e-Governance Department, Government of Karnataka (https://Kppp.karnataka.gov.in), from eligible Tenderers, for the work (as defined in these documents and referred to as "the Works") detailed in the Table given in the Instructions to Tenderers.

#### Eligible Tenderer

##### Tenderers shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued by the Government of Karnataka.

##### Tenders from Joint ventures are not acceptable. The Tenderer shall be mandatorily registered with PWD as Class III Contractor or above(certificate to be submitted).

#### Qualification of the Tenderer:

##### All Tenderers shall provide the requested information accurately and in sufficient detail in Section 3: Qualification information. Requirements as listed in Clause 3.2 are minimum qualification conditions and any Tenderer failing to meet the same shall stand disqualified at the technical evaluation stage.

##### To qualify for this Tender, each Tenderer should have in the last five years i.e. from2020-21 to2024-25.

- Achieved in at least One  financial years a minimum financial turnover (in all classes of civil engineering construction works only) of Rs.   56.66   Lakhs. [(usually not less than One times the Amount Put to Tender  ]

(The Consolidated Annual Financial turnover certificate for the relevant financial years certified by an ICAI registered Chartered Accountant along with UDIN number (also the audited financial statements for each of the financial years to be submitted). The certificate should be affixed with the seal of the office of the Chartered Accountant with the registration number.).

- Satisfactorily completed (at least 50% of the contract value), as Prime Contractor ,at least one Any    work of value not less than Rs. 14.17 Lakhs.

- Should possess required valid electrical license ortie up with a sub-consultant having valid electrical license with experience of executing similar electrical works of value not less than Rs.------- Lakhs[not less than 50% of the water supply/sanitary engineering works]in any one year--------------Deleted.

- Domicile certificate

- CAT-II(A)  Category reservation certificate

##### The Tenderer should further demonstrate:

- Availability by owning/hired (50:50) key and critical equipment for this work. Following are the key and critical equipment required for this work----Deleted.

| Sl. No. | Description of Equipment / Machineries | Quantity in nos. |
| --- | --- | --- |

[Provide the list of key and critical equipment required for the work in the above table]

- Liquid assets and/or availability of credit facilities of not less than Rs.  17.00    Lakhs through submission of  unconditional Credit line/letter of credit/ certificates from banks for meeting the fund requirement etc.

##### To qualify for a package of contracts made up of this and other contracts for which Tenders are invited in this IFT, the Tenderer must demonstrate having experience and resources to meet the aggregate of the qualifying criteria for the individual contracts.

##### Sub-contractors’ experience and resources shall not be taken into account in determining the Tenderer’s compliance with the qualifying criteria except to the extent stated in 3.2 (d)above.

##### Tenderer who meets the above specified minimum qualifying criteria, will only be qualified, if their available Tender capacity is more than the Amount put to  Tender value. The available Tender capacity will be calculated asunder:

Assessed available Tender capacity = (A*N*5.00 - B) where

A=Maximum value of civil engineering works executed in any one year during the last five years (updated to _____price level) taking into account the completed as well as works in progress.

N = Number of years prescribed for completion of the works for which Tenders are invited.(N = ___years in this Tender).

B = Value, at _____price level, of existing commitments and on-going works to be completed during the next years

Note:The statements showing the value of existing commitments and on-going works as well as the stipulated period of completion remaining for each of the works listed should be countersigned by the Employer in charge, not below the rank of an Executive Engineer or equivalent.

##### Even though the Tenderers meet the above criteria, they are subject to be disqualified if they have:

- made misleading or false representations in the forms, statements and attachments submitted in proof of the qualification requirements; and/or

- record of poor performance such as abandoning the works, not properly completing the contract, inordinate delays in completion, litigation history, or financial failures etc.

- participated in the previous Tender for the same work and had quoted unreasonably high tender prices and could not furnish rational justification.

##### The work done experience in similar drinking water project executed by the Tenderer in any of the Central/State Government Departments/Quasi Government Organizations and Government Undertakings shall have to be submitted along with the tender. Work done certificates issued by the concerned officer not below the rank of Executive Engineer fromCentral/State Government Department/Undertaking/ Quasi Government Organization should be submitted for each qualifying project submitted by the Tenderer as part of evaluation under Clause 3.2. The experience certificates issued by an officer below the rank of Executive Engineer or on behalf of Executive Engineer will not be considered.

#### Tender Documents

#### Content of Tender documents

##### The Tender documents comprises of the following sections:

###### Section 1 – Invitation for Tenders

###### Section 2 – Instructions to Tenderers

###### Section 3 – Qualification Information

###### Section 4 – Forms of Tender, Letter of Acceptance, Notice to Proceed with the Work and Agreement Form

###### Section 5 – Conditions of Contract

###### Section 6 – Contract Data

###### Section 7 – Technical Specifications

###### Section 8 – Drawings

###### Section 9 – Bill of Quantities (Price Tender)

###### Section 10 – Format of Bank Guarantee for Security Deposit

##### The Tender document is available online on the website,https://Kppp.karnataka.gov.in from where the Tender document can be downloaded free of cost.

#### Amendment of Tender documents

##### Before the dead line for submission of Tenders, the Employer may modify the Tender documents by issuing addenda.

##### Any addendum thus issued shall be part of the Tender documents and shall be communicated in writing or by cable or by email of e portal to all the purchasers of the Tender documents.

##### To give prospective Tenderers reasonable time in which to take an addendum into account in preparing their Tenders, the Employer shall extend as necessary the deadline for submission of Tenders, in accordance with Clause 12.2.

#### C. Preparation of Tenders

#### Documents comprising the Tender

##### The Tender submitted by the Tenderer shall be in twoparts to be submitted on the  Kppp  portal and shall contain the documents as mentioned below. :

###### Technical Tender comprising of :

- The Tender Documents duly filled and signed by the tenderer.

- List of Enclosures/ Annexures

  - Performance of the Tenderer showing value of Civil Engineering work for the past five financial years –Annexure-I

  - Average Annual Construction Turnover (Civil Engineering works) for the last five financial years –Annexure- I &II

  - Experience in works of similar nature and Magnitude within a period of 5 financial years –Annexure-I

  - Commitment of works on hand – Annexure-I

  - Works for which Tenders are already submitted –Annexure-I

  - Proposals for subcontracting components of works –Annexure-I

  - Details of Litigation –  Annexure-I

  - Certificate from Chartered Accountant for Annual Turnover – Annexure–II

  - Availability of credit facilities –Annexure-III.

  - Declaration by the Tenderer about black-listing –Annexure-IV

List of Certificates (notarized by notary public).

- Certificate of registration with PWD as Class III Contractor or above.

- Audited Balance Sheets &ITR Filed copy of last five years.

- GST Verification Certificate

- Any other material required to be completed and submitted by the Tenderers in accordance with these instructions.

###### Price Tender in the form of Priced Bill of Quantities (Section 9) to be filled up and submitted directly on the  Kppp  portal. The documents listed under Sections 3, 4, 6 and 9 shall be filled in without exception.

##### Tenderers submitting tenders together with other contracts stated in the IFT to form a package will so indicate in the tender together with any discounts offered  for the award of more than one contract.

#### Tender prices

##### The contract shall be for the whole works as described in Sub-Clause 1.1 of Instruction to Tenderers for the work detailed in ITT, based on the priced Bill of Quantities submitted by the Tenderer.

##### The Tenderer shall fill in rates and prices and line-item total (both in figures and words)for all items of the Works described in the Bill of Quantities along withtotal Tenderprice (both in figures and words).Items for which no rate or price is entered by the Tenderer will not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities.

##### All applicable duties, taxes, and other levies payable by the contractor under the contract, or for any other cause, shall be included in the rates, prices and total Tender Price submitted by theTenderer.

##### The rates and prices quoted by the Tenderer shall not be subject to adjustment during the performance of the Contract in accordance with the provisions of Conditions of Contract.

#### Tender validity

##### Tenders shall remain valid for a period not less than 90 (ninety) days after the deadline date for Tender submission specified in Clause12.A Tender valid for a shorter period shall be rejected by the Employer asnon-responsive.

##### In exceptional circumstances, prior to expiry of the original time limit,the Employer may request the Tenderers to extend the period of validity for a specified additional period. The request and the Tenderers' responses shall be made in writing or by cable. A Tenderer may refuse the request without forfeiting his Earnest Money Deposit. A Tenderer agreeing to the request will not be required or permitted to modify his Tender, but will be required to extend the validity of his earnest money deposit for a period of the extension, and incompliance with Clause 9 in all respects.

#### Earnest MoneyDeposit

##### The Tenderer shall furnish, as part of his Tender, earnest money deposit in the amount as shown in column 4 of the Table of ITT for this particular work. This earnest money deposit shall be submitted in  Kppp  Portal as per prescribed form & procedure in thisregard.

##### Instruments having fixed validity issued as Earnest Money Deposit for the Tender shall be valid for 45 (forty-five) days beyond the validity period of theTender.

##### Any Tender not accompanied by an acceptable earnest money deposit and not secured as indicated in Sub-Clauses 9.1 and 9.2 above shall be rejected by the Employer as non-responsive.

##### The earnest money deposited through  Kppp  of unsuccessful Tenderers will be returned/released within 30 days of the end of the Tender validity period specified in Sub-Clause8.1 or upon issue of Letter of Acceptanceto the Successful Tenderer.

##### The Earnest Money Deposit of the successful Tenderer will be discharged when the Tenderer has signed the Agreement and furnished the required Performance Security.

##### The Earnest Money Deposit shall be forfeited:

- If theTenderer withdraws the Tender after Tender opening during the period of Tender validity

- If the Tenderer does not accept the correction of the Tender Price, pursuant to Clause 19.

- in the case of a successful Tenderer, if the Tenderer fails within the specified time limit to

  - sign the Agreement

  - furnish the required Security deposit

- If the Tenderer submitted any morphed / forged / fail / wrong documents with respect the claims made under tender proposals.

#### Format and signing of Tender

##### The Tenderer shall prepare the documents comprising the Tender as described in Clause 6of these Instructions to Tenderers, and upload into the  Kppp  Portal. Ordinarily, the document as uploaded in  Kppp  Portal shall form the basis to decide the Tender.

##### The documents comprising the Tender shall be typed or written in indelible ink and shall be signed by a person or persons duly authorized to sign on behalf of the Tenderer. All pages of the Tender where entries or amendments have been made shall be initialed by the person signing the Tender and uploaded on to  Kppp  Portal(https://Kppp.karnataka.gov.in).

##### The Tender shall contain no alterations or additions, except those to comply with instructions issued by the Employer, or as necessary to correct errors made by the Tenderer, in which case such corrections shall be initialed by the person signing the Tender.

#### D. Submission of Tenders

#### Online Tender Submission

##### The Tenderer shall submit their tenders on  Kppp  portal of e- Governance Department of Government of Karnataka (https://Kppp.karnataka.gov.in).Manual tender submission is NOT PERMITTED. Any tender received manually shall be rejected and the Tenderer submitting such tender shall be disqualified.

##### Process of e-Tender Submission

###### Tender Processing Fees and Downloading of Tender Document

Tenderer can download the Tender document from the portal (https://Kppp.karnataka.gov.in) till the due date and time for Tender submission.Tenderer shall pay the Tender processing fees prescribed in the  Kppp  portal to participate in this Tender. The Tender processing fee has to be paid through any ofthe four e-payment options in the portal:

- Credit Card

- Direct Debit

- National Electronic Funds Transfer(NEFT)

- Over the Counter (OTC) – designated bank branches located across the country.

Please note that payments submitted through cheque or demand draft shall not be accepted. Further details regarding e-Payment, please refer to  Kppp  portal at the above-mentioned website or call  Kppp  helpline.

Note: It will be in the interest of the Tenderers to familiarize themselves with the e- Procurement system to ensure smooth preparation and submission of the Tender documents.

##### Authentication of Tender

The responsive Tender shall be signed by the Tenderer or a person duly authorized to sign by the Tenderer. A letter of authorization shall be supported by a written power-of-attorney accompanying the Tender. All pages of the Tender, except for un-amended printed literature, shall be initialed and stamped by the person or persons signing the Tender.

##### Validation of interlineations in Tender

The Tender shall contain no interlineations, erasures or overwriting except as necessary to correct errors made by the Tenderer, such corrections shall be initiated by the person or persons signing the Tender.

#### Deadline for submission of theTenders

##### Tenders must be received by the Employer on the  Kppp  Portal (https://Kppp.karnataka.gov.in) no later than the date and time specified in the  Kppp  Portal.

##### The Employer may extend the deadline for submission of Tenders by issuing an amendment in accordance with Clause 5, in which case all rights and obligations of the Employer and the Tenderers previously subject to the original deadline will then be subject to the new deadline.

#### Late Tenders

##### Any Tender received by the Employer after the deadline prescribed in Clause 12will be rejected.

#### Modification and Withdrawal of Tenders – As per e-portal

##### Tenderers may modify Tenders in  Kppp  Portal or withdraw their Tenders before the deadline prescribed in Clause 12through  Kppp  Portal (https://Kppp.karnataka.gov.in).

##### Deleted.

##### No Tender can be modified after the deadline for submission of Tenders.

##### Withdrawal or modification of a Tender between the deadline for submission of Tenders and the expiration of the original period of Tender validity specified in Clause 8.1 or as extended pursuant to Clause 8.2 may result in the forfeiture of the Earnest Money Deposit pursuant to Clause 9.

##### Tenderers may only offer discounts to, or otherwise modify the prices of their Tenders by submitting Tender modifications in accordance with this clause, or included in the original Tender submission.

#### E. Tender opening and evaluation

#### Opening of Technical Tender of all Tenders and evaluation to determine technically qualified Tenderers: As pere-Portal

##### The Employer will open the Technical Tenderof all the Tenders received at the specified date and time mentioned in the  Kppp  Portal. The intimation regarding opening of tenders shall be communicated to the registered email ID from  Kppp  automatically. In the event of the specified date of Tender opening being declared a holiday for the Employer, the Tenders will be opened at the appointed time and location on the next working day.

##### The Employer shall first undertake evaluation of the (I) Technical Tenderas per this Tender document and details contained hereinafter.

##### The Employer will evaluate and determine whether each Tender-

- meets the eligibility criteria defined in Clause 2of ITT & is not otherwise disqualified as per this Tender;

- is accompanied by the required earnest money deposit as per stipulations in ITT Clause

- meets the minimum qualification criteria stipulated in Clause3.2 of ITT.

##### The Employer shall prepare minutes of the Tender opening, including the information disclosed to those present in accordance with Sub-Clause 15.3.

##### Deleted.

##### The Employer will evaluate and determine whether each tender (a) meets the eligibility criteria defined in ITT Clause 2;  (b) is accompanied by the required earnest money deposit as per stipulations in ITT Clause 9 and (c) meets the minimum qualification criteria stipulated in ITT Clause 3. The Employer will draw out a list of qualified Tenderers.

#### Opening of Price Tender of qualified Tenderers and evaluation: As per e-Portal

##### The Employer will inform all the Qualified Tenderers the time, date and venue fixed for the opening of the Price Tender. The Employer will open the Price Tender of only the technically qualified Tenderers at the specified time and date mentioned on  Kppp  portal. In the event of the specified date of Price Tender opening being declared a public holiday, the Price Tender shall be opened on the next working-day.

##### Deleted.

##### The Tenderers' names, the Tender prices, the total amount of each Tender, any discounts, Tender modifications and withdrawals, and such other details as the Employer may consider appropriate, will be announced by the Employer at the opening.  No Tender shall be rejected at Tender opening.

##### The Employer shall prepare minutes of the Price Tender opening, including the information disclosed to those present in accordance with Sub-Clause 16.3.

#### Process to be confidential

##### Information relating to the examination, clarification, evaluation, and comparison of Tenders and recommendations for the award of a contract shall not be disclosed to Tenderers or any other persons not officially concerned with such process until the award to the successful Tenderer has been announced. Any effort by a Tenderer to influence the Employer's processing of Tenders or award decisions may result in the rejection of his Tender.

#### Clarification ofTenders

##### To assist in the examination, evaluation, and comparison of Tenders, the Employer may, at its discretion, ask any Tenderer for clarification of his Tender, including break downs of unit rates. The request for clarification and the response shall be in writing or by cable, but no change in the price or substance of the Tender shall be sought, offered, or permitted except as required to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Tenders in accordance with Clause20.

##### Subject to sub-clause 18.1, no Tenderer shall contact the Employer on any matter relating to its Tender from the time of the Tender opening to the time contract is awarded. If the Tenderer wishes to bring additional information to the notice of the Employer, it shall be in writing.

##### Any effort by the Tenderer to influence the Employer in the Employer’s Tender evaluation, Tender comparison or contract award decisions may result in the rejection of its Tender.

#### Examination of Tenders and determination ofresponsiveness

##### Prior to the detailed evaluation of Tenders, the Employer will determine whether each Tender; (a) has been properly signed (b) is substantially responsive to the requirements of the Tender documents.

##### A substantially responsive Tender is one which conforms to all the terms, conditions, and specifications of the Tender documents, without material deviation or reservation. A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of the Works; (b)which limits in any substantial way, inconsistent with the Tender documents, the Employer's rights or the Tenderer's obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other Tenderers presenting substantially responsive Tenders.

##### If a Tender is not substantially responsive, it will be rejected by the Employer at the technical evaluation stage itself, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation. All conditional Tenders shall summarily be rejected irrespective of their pre-qualification.

#### Correction of errors

##### Tenders which are determined to be substantially responsive will be checked by the Employer for any arithmetic errors. Errors will be corrected by the Employer as follows:

- where there is a discrepancy between the rates in figures and in words, the lower of the two shall prevail/govern; and

- where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by the quantity, the unit rate as quoted will govern.

##### The amount stated in the Tender will be adjusted by the Employer in accordance with the above procedure for the correction of errors and, with the concurrence of the Tenderer, shall be binding upon the Tenderer. If the Tenderer does not accept the corrected amount the Tender will be rejected, and the earnest money deposit may be forfeited in accordance with Sub-Clause 9.6(b).

#### Evaluation and comparison of Tenders

##### The Employer will evaluate and compare only the Tenders determined to be substantially responsive in accordance with Clause 19.

##### In evaluating the Tenders, the Employer will determine for each Tender the evaluated Tender Price by adjusting the Tender Price as follows:

##### (a)      making any correction for errors pursuant to Clause 20;  and

##### (b)	making appropriate adjustments to reflect discounts or other price modifications offered in accordance with Sub Clause 14.5.

##### The Employer reserves the right to accept or reject any variation, deviation, or alternative offer.

#### F. Award of Contract

#### Award criteria

##### Subject to Clause 24, the Employer will award the Contract to the Tenderer whose Tender has been determined to be substantially responsive to the Tender document and who has offered the lowest evaluated Tender Price, provided that such Tenderer has been determined to be (a) eligible in accordance with the provisions of Clause 2, (b) qualified in accordance with the provisions of Clause 3.

#### Employer's right to accept any Tender and to reject any or all Tenders

##### Notwithstanding Clause 22, the Employer reserves the right to accept or reject any Tender,canceltheTenderprocessandrejectallTenders,atanytimeprior to the award of Contract without thereby incurring any liability to the affected Tenderer or Tenderers or any obligation to inform the affected Tenderer or Tenderers of the grounds for the Employer's action.

#### Notification of award and signing of Agreement

##### The Tenderer whose Tender has been accepted will be notified of the award by the Employer prior to expiration of the Tender validity period by cable, telex, e-mail or facsimile confirmed by registered letter. This letter (hereinafter and in the Conditions of Contract called the "Letter of Acceptance") will state the sum that the Employer will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the "Contract Price").

##### The notification of award will constitute the formation of the Contract, subject only to the furnishing of unconditional Security Deposit in accordance with the provisions of Clause 25.

##### The Agreement will incorporate all agreements between the Employer and the successful Tenderer. It will be kept ready for signature of the successful Tenderer in the office of Employer within 30 days following the notification of award along with the Letter of Acceptance. Within 30 days of receipt, the successful Tenderer will sign the Agreement and deliver it to the Employer.

##### Upon furnishing of Performance Security by the successfulTenderer, the Employer will promptly notify the other Tenderers that their Tenders have been unsuccessful.

#### Unconditional SecurityDeposit

##### Within 20 days from the date of issue of Letter of Acceptance, the successful Tenderer shall deliver to the Employer an unconditional Security deposit in any of the forms given below for an amount equivalent to 5% of the Contract price.

    - Banker’s cheque /Demand draft in favor of Executive Engineer RDW&SD, TUMKUR District payable at  TUMKUR _; or,

    - A bank guarantee in the form given in Section10 (Form of Bank Guarantee)

##### If the Security Deposit is provided by the successful Tenderer in the form of a Bank Guarantee, it shall be issued by a Scheduled Bank.

##### The Security Deposit if furnished in cash or demand draft can, if requested, by contractor be converted to interest bearing securities at the cost of the contractor.

##### Failure of the successful Tenderer to comply with the requirements of Sub-Clause25.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Earnest Money Deposit.

#### Corrupt or Fraudulent practices

##### The GOK requires that the Tenderers/Suppliers/Contractors, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, GOK:

- WillrejectaproposalforawardifitdeterminesthattheTendererrecommended for award has engaged in corrupt or fraudulent practices in competing for the contract in question;

- will declare a firm ineligible, either indefinitely or for a stated period of time, to be awarded a GOK contract if it at any time determines that the firm has engaged in corrupt or fraudulent practices in competing for, or in executing a GOK contract.

##### Further more, Tenderer shall be aware of the provision stated in sub-clause 42.2 of the Conditions of Contract.

SECTION 3:

QUALIFICATION INFORMATION

## SECTION 3:QUALIFICATION INFORMATION

#### ANNEXURE I

Qualification Information

The information to be filled in by the Tenderer hereunder will be used for purposes of computing Tender capacity as provided for in Clause 3 of the Instructions to Tenderers. This information will not be incorporated in the Contract.

  - Constitution or legal status of Tenderer	[Attach copy]

Place of Registration

Principal place of business:

  - Total value of civil engineering construction works executed and payments received in the last five years ………….. (inRs.Lakhs)

2019-20 ……………….

2020-21 ……………….

2021-22 ……………….

2022-23 ……………….

2023-24-----------------

  - Work performed as Prime Contractor (in the same name) on works of DRINKING WATER SUPPLY during the five years specified in 1.2above.

| Project Name | Name of Employer | Description of Work | Contract Number | Value of Contract (Rs. Lakhs) | Date of issue of work order | Specified period of completion | Actual Date of completion | Remarks explaining reason for delay/ incompletion of work |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |

  - Quantities of work executed as prime contractor (in the same name) during the last five years specified in 1.2above:

| Sl No | Year | Name of Work | Name of Employer | Quantity of work performed |  |  |  | Remarks (Indicate contract reference) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Pipeline work (CI/MS/DI/ PVC/HDPE/GI) of atleast ___ Kms* length | Construction of atleast one OHT of ___ KL* capacity | Earthwork excavation of atleast ____ Cum* | Concrete work of atleast ____ Cum* |  |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) (9) | (9) |

[*Values as per Clause 3.2 (c)]

  - Information on works for which Tenders have been submitted and works which are yet to be completed as on the date of this Tender.

- Existing commitments and on-going works:

| SL NO. | Description of Work | Place & State | Contract No. & Date | Name and Address of Employer | Value of Contract (Rs.Lakhs) | Stipulated period of completion | Value of works remaining to be completed (Rs. Lakhs) | Anticipated date of completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |

- Works for which Tenders already submitted:

| SL NO. | Description of Work | Place & State | Name and Address of Employer | Estimated value of works (Rs. Lakhs) | Stipulated period of completion | Date when decision is expected | Remarks if any |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |

  - The following items of equipment are considered essential for successfully carrying out the works. The Tenderer should furnish all the information listed below

| Item of Equipment | Requirement |  | Owned | Owned and available |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | No | Capacity |  | Number/Capacity | Age/Condition |  |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) |

  - Reports on the financial standing of the Tenderer, such as profit and loss statements and auditor’s reports for the last five years;

  - Qualification and experience of the key technical and management personnel in permanent employment with the Tenderer and those proposed to be deployed on this contract, if awarded.

  - Name, address, telephone, telex, and fax numbers of the Tenderers’ bankers who may provide references if contacted by the Employer.

  - Evidence ofaccess to financial resources to meet the qualification requirement specified in ITT Clause3.3 (b): Cash in hand, Letter of Credit etc. List them below and attach certificate from the Banker in the suggested format provided at Annexure - III:

  - Proposals for sub-contracting components of works amounting to more than 20% of the contract price:

| Sl No. . | Item of Work | Value of Sub-Contract | Identified Sub-Contractor# | Experience of similar work* |
| --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) |

#The Tenderer should enter into proper agreement with sub-contractor proposed to be sublet and furnish the documentary evidence along with Tender.

*Enclose certificates from the  respective Employers

  - Information on litigations in which the Tenderer is involved:

| Sl No. | Other Party/ies | Employer | Details of dispute | Amount involved | Remarks showing present status |
| --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) |

#### ANNEXURE-II

#### Certificate from Chartered Accountant for Annual Turnover

#### (To be on the letterhead of the Chartered Accountant)

#### This is to certify that M/s__________________________________________ registered under__________________________________________and having it head office at __________________________________has the following Annual Turnover in the last five years.

#### withUDIN no:_____________

2019- 20………………. Rs Lakhs

2020- 21………………. Rs Lakhs

2021- 22………………. Rs Lakhs

2022- 23………………. Rs Lakhs

2023-24………………. Rs Lakhs

#### ANNEXURE-III

Banker’s Certificate

This is to certify that M/s. ………………………is a reputed company with a good financial standing. If the contract for this work, namely ……………………………… (Name of the work) is awarded to the above firm, we shall be able to provide overdraft/credit facilities to the extent of Rs. …………… to meet the working capital requirements for executing the above contract

Sd/-

Name of the Bank, Senior Bank Manger

Address:……………………………….

#### ANNEXURE-IV

Declaration by the Tenderer:

Itistocertifythatourfirm……………………………..................has not been black  listed  /banned / debarred by any Central/ State / UT Government Department or Undertaking / Organization.

Seal Tenderer

...................................... .......................................

(Signature of the Tenderer)

SECTION 4:

FORMS OF TENDER, LETTER OF ACCEPTANCE, NOTICE TO PROCEED WITH THE WORK AND AGREEMENT FORM

## SECTION 4:FORMS OF TENDER, LETTER OF ACCEPTANCE, NOTICE TO PROCEED WITH THE WORK AND AGREEMENT FORM

Form of Tender

Description	of	the	Works:

Tender

To	:

Address:

GENTLEMEN,

We offer  to execute the Works described above in accordance with the Conditions of Contract accompanying	thisTenderfortheContractPriceof Rs.___ [in figures] (_______________) [in words].

This Tender and your written acceptance of it shall constitute a binding contract between us. We understand that you are not bound to accept the lowest or any Tender you receive.

We undertake that, in competing for (and, if the award is made to us, in executing) the above contract, we will strictly observe the laws against fraud and corruption in force in India namely “Prevention of Corruption Act 1988”.

We hereby confirm that this Tender complies with the Tender validity and Earnest money deposit required by the Tender documents.

We attach here with our current incometax clearancecertificate.

Yours faithfully,

Authorized Signature: Name & Title of Signatory:

Name of Tenderer		 Address:

Letter of Acceptance

[On the Letterhead of the Employer]

[Date]

To:

[Name and address of the Contractor] Dear Sir,

This is to notify you that yourTender dated________ for execution of the_______ [name  of  the  contract  and  identification  number,  as  given  in  the  Instructions toTenderers]	fortheContractPriceofRupees ______ [amount in words and figures], as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted by our Agency.

You are hereby requested to furnish unconditional Security deposit in the form detailed in Clause 25.1 of ITT for an amount of Rs._______ within 20 days of the receipt of this Letter of Acceptance valid up to 30 days from the date of expiry of Defects Liability Period, i.e. up to ............ and sign the contract, failing which action as stated in Para 25.4 of ITT will be taken.

Yours faithfully, Authorized Signature

Name and Title of Signatory Name of Agency

Issue of Notice to proceed with the work

[On the Letter head of the Employer]

To

————— (date)

—————————————— (name and address of the Contractor)

——————————————

——————————————

Dear Sirs:

Pursuant to your furnishing the requisite security deposit as stipulated in ITTClause 29.1 and signing of the contract agreement for the construction of __________ forTender Price of Rs_______, you are hereby instructed to proceed with the execution of the said works in accordance with the contract documents.

Yours faithfully,

(Signature, name and title of signatory authorized to sign on behalf of Employer)

Agreement Form

Thisagreementmade on this the	dayof	20	, between _____________ [Name andaddressof  Employer](hereinaftercalled“theEmployer”)oftheonepartand_________Name andaddress of contractor] (hereinafter called “the Contractor”) of the other part.

WhereastheEmployerisdesirousthattheContractorexecute ___________ [name and identification number of Contract] (hereinafter called “theWorks”) and the Employer has accepted the Tender by the Contractor for the execution and completion of such Works and the remedying of any defects therein at a Contract Price of Rupees_____ [in Figures] (_____________) [in Words].

NOW THIS AGREEMENT WITNESSETH as follows:

- In this Agreement, words and expression shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

- In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all aspects with the provisions of the Contract.

- The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

- The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

  - Letter of Acceptance;

  - Notice to proceed with the works;

  - Contractor’s Tender including responses to pre-tender queries and addendums;

  - Contract Data;

  - Conditions of contract (including Special Conditions ofContract)

  - Specifications;

  - Drawings

  - Bill of Quantities/Schedules;and

  - Any other document listed in the Contract Data as forming part of the contract.

In witness whereof the parties thereto have caused this Agreement to be executed the day and (year first) before written.

The Common Seal of _________ was here unto affixed in the presence of:

Binding Signature of Employer

Binding Signature of Contractor

Signed, Sealed and Delivered

SECTION 5:

CONDITIONS OF CONTRACT

## SECTION 5: CONDITIONS OF CONTRACT

Table of Contents

A.	General	34

B.	Time Control	37

C.	Quality Control	38

D.	Cost Control	39

E.	Finishing the Contract	41

F.	Special Conditions of Contract	44

Conditions of Contract

### General

#### Definitions

  - Terms which are defined in the Contract Data are not also defined in the Conditions of Contract but keep their defined meanings. Bold letters are used to identify defined terms.

| Bill of Quantities | means the priced and completed Bill of Quantities forming part of the Tender. |
| --- | --- |
| Compensation events | are those defined in Clause 38 hereunder. |
| The Completion Date | is the date of completion of the Works as certified by the Employer in accordance with Sub Clause 45.1 |
| The Contract | is the contract between the Employer and the Contractor to execute, complete and maintain the Works. It consists of the documents listed in Clause2.2 below. |
| Contract Data | defines the documents and other information which comprise the Contract. |
| Commencement Date | shall be the date at which the following precedent conditions have all been fulfilled - signature of the Contract Agreement by both Parties - receipt of Performance Security - Certificates for Insurance taken (if any) |
| Contractor | is a person or corporate body who’s Tender to carry out the Works has been accepted by the Employer. |
| Contractor's Tender | is the completed Tender document submitted by the Contractor to the Employer. |
| Contract price | is the price stated in the Letter of Acceptance and Thereafter as adjusted in accordance with the provisions of the Contract. |
| Days | are calendar days |
| Months | are calendar months |
| Construction period | shall be period as indicated by the Employer in the Contract from the date of signing of contract including construction, testing and Trial Run Period. |
| Defect | is any part of the Works not completed in accordance with the Contract. |
| DefectsLiability Period | is the period named in the Contract Data and calculated from the Completion Date. |
| Employer | is the party who will employ the Contractor to carryout the Works. |
| Employer Representative | is the person authorised by the Employer for the Contract |
| Force Majeure | is an event or effect that can neither be anticipated nor controlled (such as Act of God). |
| Equipment | is the Contractor's machinery and vehicles brought temporarily to the Site to construct the Works. |
| Initial Contract price | is the Contract Price listed in the Employer's Letter of Acceptance |
| Intended Completion Date | is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Contract Data. The Intended Completion Date may be revised only by the Employer by issuing an extension of time. |
| Materials | are all supplies, including consumables, used by the contractor for incorporation in the Works. |
| Plant | is any integral part of the Works which is to have a mechanical, electrical, electronic or chemical or biological function etc. |
| Site | is the area defined as such in the Contract Data |
| Specification | means the Specification of the Works included in the Contract and any modification or addition made or approved by the Employer. |
| Start Date | is given in the Contract Data. It is the date when the Contractor shall commence execution of the works. It does not necessarily coincide with any of the Site Possession Dates. All milestones and intended completion dates will depend on this date. |
| Sub-contractor | is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract which includes work on the Site. |
| Trial Run Period | shall be period as indicated by the Employer in the Contract before the completion of Construction Period and commencement of Defect Liability Period. |
| Variation | is an instruction given by the Employer which varies the scope of Works. |
| Works | what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the Contract Data. |

#### Interpretation

  - 2.1  		In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter, and vice-versa. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Employer will provide instructions clarifying queries about the Conditions of Contract.

  - 2.2  		The documents forming the Contract shall be interpreted in the following order of priority:

    - Agreement

    - Letter of Acceptance, notice to proceed with the works

    - Contractor’s Tender, responses to pre-tender queries and addendum

    - Contract Data

    - Conditions of Contract including Special Conditions of Contract

    - Specifications

    - Drawings

    - Bill of quantities/Schedules and

    - Any other document listed in the Contract Data as forming part of the Contract.

#### Law governing contract

3.1    	The law governing the Contract is the Laws of Indiasupplanted by the Karnataka Local Acts.

#### Employer's decisions

4.1    	Except where otherwise specifically stated, the Employer will decide contractual matters between the Employer and the Contractor.

#### Delegation

5.1    	The Employer may delegate any of his duties and responsibilities to other people after notifying the Contractor and may cancel any delegation after notifying the Contractor.

#### Communications

6.1     	Communications between parties which are referred to in the conditions are effective only when in writing. A notice shall be effective only when it is delivered (in terms of Indian Contract Act).

#### Subcontracting

7.1     	The Contractor may subcontract with the approval of the Employer but may not assign the Contract without the approval of the Employer in writing. Subcontracting does not alter the Contractor's obligations.

#### Other Contractors

8.1     	The Contractor shall co-operate and share the Site with other contractors, public authorities, utilities, and the Employer.

#### Personnel

9.1	The Contractor shall employ the technical personnel (of number and qualifications) as may be stipulated by GOK from time to time during the execution of the work. The technical staff so employed shall be available at site as may be stipulated by the Employer.

9.2	If the Employer asks the Contractor to remove a person who is a member of the Contractor’s staff or his work force stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract.

#### Employer’s and Contractor's risks

10.1   	The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’ srisks.

#### Employer's risks

  - 11.1 	The Employer is responsible for the excepted risks which are (a) in so far as  rebellion,  riot commotion or disorder  or (b) a cause due solely to the design of the Works, other than the Contractor’s design.

#### Contractor’s risks

12.1    	All risks of loss of or damage to physical property and of personal injury and death which arise during and in consequence of the performance of the Contract other than the excepted risks are the responsibility of the Contractor.

#### Queries about the Contract Data

13.1	The Employer will clarify queries on the Contract Data.

#### Contractor to construct the Works

14.1     	The Contractor shall construct the Works in accordance with the Specification and Drawings as approved by the Chief Engineer

#### The Works to be completed by the Intended Completion Date

15.1    The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the program submitted by the Contractor, as updated with the approval of the Employer, and complete them by the Intended Completion Date.

#### Safety

16.1	The Contractor shall be responsible for the safety of all personnel and activities at the Site.

#### Discoveries

17.1   	Anything of historical or other interest or of significant value unexpectedly discovered at the Site is the property of the Employer. The Contractor is to notify the Employer of such discoveries and carry out the Employer's instructions for dealing with them.

#### Possession of the Site

  - The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the Contract Data the Employer is deemed to have delayed the start of the relevant activities and this will be Compensation Event.

#### Access to the Site

19.1    	The Contractor shall allow the Employer and any person authorized by the Employer to have access to the Site, to any place where work in connection with the Contract being carried out or intended to be carried out and to any place where materials or plant are being manufactured / fabricated / assembled for the works.

#### Instructions

20.1  	The Contractor shall carry out all instructions of the Employer which comply with the applicable laws where the Site is located.

### TimeControl

#### Program

21.1 	Within the time stated in the Contract Data the Contractor shall submit to the Employer for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works.

21.2 	The Employer's approval of the Program shall not alter the Contractor's obligations. The Contractor may revise the Program and submit it to the Employer again at any time. A revised Program is to show the effect of Variations and Compensation Events.

#### Extension of the Intended Completion Date

22.1 	The Employer shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date.

22.2 	The Employer shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Employer for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information.

#### Delays ordered by the Employer

23.1    	The Employer may instruct the Contractor to delay the start or progress of any activity within the Works.

#### Management meetings

24.1 	The Employer may require the Contractor to attend a management meeting. The business of a management meeting shall be to review the progress achieved and the plans for remaining work.

24.2 	The responsibility of the parties for actions to be taken is to be decided by the Employer either at the management meeting or after the management meeting and stated in writing to be distributed to all who attended the meeting.

### Quality Control

#### Identifying defects

25.1    	The Employer or its authorized representatives shall check the Contractor's work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor's responsibilities. The Employer may instruct the Contractor to search for a Defect and to uncover and test any work that the Employer considers may have a Defect.

#### Tests

26.1     	If the Employer instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect the test shall be a Compensation Event.

#### Correction of defects

27.1 	The Employer shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion and is defined in the Contract Data. The Defects Liability Period shall be extended for as long as Defects remain to be corrected.

27.2 	Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Employer’s notice.

#### Uncorrected defects

28.1    	If the Contractor has not corrected a Defect within the time specified in the Employer’s notice, the Employer will assess the cost of having the Defect corrected, and the Contractor will pay this amount and any delays caused to other works due to this shall be attributed to the Contractor.

### Cost Control

#### Bill of Quantities(BOQ)

29.1 	The BOQ shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor.

29.2 	The BOQ issued to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the BOQ for each item

#### Variations

30.1 	The Employer shall have power to order the Contractor to do any or all of the following as considered necessary or advisable during the progress of the work by him

    - Increase or decrease of any item of work included in mutually agreed Bill of Quantities (BOQ);

    - Omit any item of work;

    - Change the character or quality or kind of any item of work;

    - Change the levels, lines, positions and dimensions of any part of the work;

    - Execute additional items of work of any kind necessary for the completion of the works; and

    - Change in any specified sequence, methods or timing of construction of any part of the work.

30.2 	The Contractor shall be bound to carry out the work in accordance with any instructions in this connection, which may be given to him in writing by the Employer and such alteration shall not vitiate or invalidate the contract.

30.3 	Variations shall not be made by the Contractor without an order in writing by the Employer, provided that no order in writing shall be required for increase or decrease in the quantity of an item appearing in the BOQ so long as the work executed conforms to the approved drawings.

30.4 	The Contractor shall promptly request in writing the Employer to confirm verbal orders and if no such confirmation is received within 15 days of request, it shall be deemed to be an order in writing by the Employer.

#### Payments for Variations

31.1 	Payment for increase in the quantities of an item in the BOQ up to 25% of that provided in the Bill of Quantities shall be made at the rates quoted by the Contractor.

31.2 	For quantities in excess of 125% of the Tender quantity of an item as given in the BOQ, the Contractor shall be paid at the rate entered in or derived from in the Schedule of Rates (applicable for the area of the work and current at the time of award of contract) plus or minus the overall percentage of the original Tendered rates over the current Schedule of Rates prevalent at the time of award of contract.

31.3 	If there is no rate for the additional, substituted or altered item of the work in the BOQ, efforts would be made to derive the rates from those given in the BOQ or the Schedule of Rates (applicable for the area of the work and current at the time of award of contract) and if found feasible the payment would be made at the derived rate for the item plus or minus the overall percentage of the original Tendered rates over the current Schedule of Rates prevalent at the time of award of contract

31.4 	If the rates for additional, substituted or altered item of work cannot be determined either as at 35.1 or 35.2 or 35.3 above, the Contractor shall be requested to submit his quotation for the items supported by analysis of the rate or rates claimed, within 7days.

31.5 	If the Contractor's quotation is determined unreasonable, the Employer may order the Variation and make a change to the Contract Price which shall be based on Employer’s own forecast of the effects of the Variation on the Contractor's costs.

31.6 	If the Employer decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event.

31.7 	Under no circumstances the Contractor shall suspend the work on the plea of non-settlement of rates for items falling under this Clause.

#### Submission of bills for payment

32.1 	The Contractor shall submit to the Employer monthly bills,in the electronic spread sheet, of the value of the work completed less the cumulative amount paid previously.

32.2 	The jurisdictional authority shall check the Contractor's bill and determine the value of the work executed which shall comprise of (i)value of the quantities of the items in the BOQ completed and (ii) valuation of Variations and Compensation Events and forward to the payment authority.

32.3 	The PMC appointed shall assist the jurisdictional authority in certifying the bills submitted by the contractor.

36.4	The Employer/ authorized representative may exclude any item paid in a previous bill or reduce the proportion of any item previously paid in the light of later information.

#### Payments

33.1 	Payments shall be adjusted for deductions for retention, other recoveries in terms of the contract and taxes, at source, as applicable under the law. The Employer/ authorized representative shall pay the Contractor the bills within the period, as specified in the contract data.

33.2 	Items of the Works for which no rate or price has been entered in will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract.

#### Compensation events

34.1	The following are Compensation events unless they are caused by theContractor:

    - The Employer does not give access to a part of the Site by the Site Possession Date stated in the Contract DataThe Employer orders a delay or does not issue drawings, specifications or instructions required for execution of works on time.

    - TheEmployerinstructstheContractortouncoverortocarryoutadditional tests upon work which is then found to have no Defects.

    - The Employer gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons.

    - The effect on the Contractor of any of the Employer’s Risks.

    - The Employer unreasonably delays issuing a Certificate of Completion.

    - Other Compensation Events listed in the Contract Data or mentioned in the Contract.

34.2 	If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date is extended. The Employer shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended.

34.3 	As soon as information demonstrating the effect of each Compensation event upon the Contractor's forecast cost has been provided by the Contractor, it is to be assessed by the Employer and the Contract Price shall be adjusted accordingly. If the Contractor's forecast is deemed unreasonable, the Employer shall adjust the Contract Price based on Employer’s own forecast. The Employer will assume that the Contractor will react competently and promptly to the event.

34.4 	The Contractor shall not be entitled to compensation to the extent that the Employer's interests are adversely affected by the Contractor not having given early warning or not having cooperated with the Employer.

#### Tax

35.1   	The rates quoted by the Contractor shall be deemed to be inclusive of all taxes that the Contractor will have to pay for the performance of this Contract. The Employer will perform such duties in regard to the deduction of such taxes at source as per applicable law.

#### Liquidated damages

36.1 	The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the Contract Data for each day that the Completion Date is later than the Intended Completion Date (for the whole of the works or the mile stone as stated in the Contract Data). The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages does not affect the Contractor's liabilities.

36.2 	If the Intended Completion Date is extended after liquidated damages have been paid, the Employer shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment of bill.

#### Cost of Repairs:

37.1 	Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remediedbytheContractorattheContractor'scostifthelossordamagearises from the Contractor's acts or omissions.

### Finishing the Contract

#### Completion

38.1    	The Contractor shall request the Employer to issue a Certificate of Completion of the Works and the Employer will do so upon deciding that the Work is completed.

#### Taking over

39.1    	The Employer shall take over the Site and the Works within seven days of issuing a certificate of Completion.

#### Final account

40.1   	The Contractor shall supply to the Employer a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Employer shall issue a Defect Liability Certificate and certify any final payment that is due to the Contractor within 90 days of receiving the Contractor's account if it is correct and complete. If it is not, the Employer shall issue within 90 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Employer shall decide on the amount payable to the Contractor and make payment within 60 days of receiving the Contractor’s revised account.

#### As built drawings and /or Operating and Maintenance Manuals

41.1	“As built” 2D Drawings and/or operating and maintenance manuals are required.The Contractor shall supply them by the dates stated in the Contract Data.

41.2 	If the Contractor does not supply the Drawings by the dates stated in the Contract Data with theEmployer’s approval, the Employer shall withhold the amount stated in the Contract Data from payments due to the Contractor.

#### Termination

42.1 	The Employer may terminate the Contract if the other party causes a fundamental breach of the Contract.

42.2 	Fundamental breaches of Contract include, but shall not be limited to the following:

    - the Contractor stops work for 45 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Employer;

    - the Employer instructs the Contractor to delay the progress of the Works and the instruction is not withdrawn within 60 days;

    - The Contractor becomes bankrupt or goes into liquidation other than for a reconstruction or amalgamation;

    - a payment due to the Contractor is not paid by the Employer  within 90 days of the date of the submission of the Bill by Contractor;

    - the Employer gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Employer;

    - the Contractor does not maintain a security which is required;

    - the Contractor has delayed the completion of works by the number of days for which the maximum amount of liquidated damages can be paid as defined in the Contract Data; and

    - if the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulent practices in competing for or in executing the Contract. For the purpose of this paragraph : “corrupt practice” means the offering, giving, receiving or soliciting of anything of value to influence the action of a public official or another party in the procurement process or in contract execution. “Fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract in  detriment of the Borrower, and includes collusive practice among Tenderers (prior to, during or after Tender submission) designed to establish Tender prices at artificial non-competitive levels and to deprive the Borrower of the benefits of free and open competition.”

  - When either party to the Contract gives notice of a breach of contract to theEmployer for a cause other than those listed under Sub Clause 49.2 above, the Employer shall decide whether the breach is fundamental or not.

  - Notwithstanding the above, the Employer may terminate the Contract for convenience.

  - If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secure and leave the Site as soon as reasonably possible.

#### Payment upon Termination

  - 43.1	If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Employer shall prepare bill for the value of the work done less advance payments received up to the date of the bill, less other recoveries due in terms of the contract, less taxes due to be deducted at source as per applicable law and less the percentage to apply to the work not completed as indicated in the Contract Data. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor the difference shall be a debt payable to the Employer.

  - 43.2	If the Contract is terminated at the Employer's convenience or because of a fundamental breach of Contract by the Employer, the Employer shall prepare billforthevalueoftheworkdone,thereasonablecostofremovalofEquipment, repatriation of the Contractor's personnel employed solely on the Works, and the Contractor's costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the contract, and less taxes due to be deducted at source as per applicable law and make payment accordingly.

#### Property

44.1	All materials on the Site, Plant, Equipment, Temporary Works and Works are deemed to be the property of the Employer, if the Contract is terminated because of a Contractor’s default.

#### Release from performance

45.1 	If the Contract is frustrated by any event entirely outside the control of either the Employer or the Contractor the Employer shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which commitment was made.

### Special Conditions of Contract

#### Labour:

The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for the engagement of all staff and labour, local or other, and for their payment, housing, feeding and transport.

The Contractor shall, if required by the Employer, deliver to the Employer a return in detail, in such form and at such intervals as the Employer may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the Contractor on the Site and such other information as the Employer may require.

#### Compliance with labour regulations:

During continuance of the contract, the Contractor and his sub-contractors shall abide at all times by all existing labour enactments and rules made there under, regulations, notifications and bye laws of the State or Central Government or local authority and any other labour law (including rules), regulations, bye laws that may be passed or notification that may be issued under any labour law in future either by the State or the  Central Government or the local authority. The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authority on account of contravention of any of the provisions of any Act or rules made there under, regulations or notifications including amendments. If the Employer is caused to pay or reimburse, such amounts as may be necessary to cause or observe, or for non-observance of the provisions stipulated in the notifications/bye laws/Acts/Rules/regulations including amendments, if any, on the part of the Contractor, Employer shall have the right to deduct any money due to the Contractor including his amount of security deposit. The Employer shall also have right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by the Employer.

The employees of the Contractor and the Sub-Contractor in no case shall be treated as the employees of the Employer at any point of time.

#### Protection of Environment:

The contractor shall take all reasonable steps to protect the environment on and off the Site and to avoid damage or nuisance to persons or to property of the public or others resulting from pollution, noise or other causes arising as a consequence of his methods of operation. During continuance of the contract, the contractor and his sub-contractors shall attend at all times by all existing enactments on environmental protection and rules made there under, regulations, notifications and bye-laws of the State or Central Government, or local authorities and any other law, bye-law, regulations that may be Passed or notification that may be issued in this respect in future by the State or Central Government or the local authority.

#### Force Majeure

  - Force Majeure Event

Any of the following events which is beyond the control of the party claiming to be affected thereby (“Affected Party”) and which the Affected Party has been unable to overcome or prevent despite exercise of due care and diligence, and prevents the Affected Party from performing or discharging its obligations under this Agreement, shall constitute Force Majeure Event:

- act  of God or

- any war, hostility, acts of public enemy, civil commotion, sabotage, fires, floods, explosions, epidemics quarantine restrictions, strikes, labour disruptions, riots or any other industrial disturbances not arising on account of the acts or omissions of the Contractor, for which no offsetting compensation is payable to the Contractor/s.

- acts of expropriation, compulsory takeover of the Project Site and Project Facilities by the Government or any part thereof or

- Any judgement or any order of a court of competent jurisdiction or statutory authority in India made against the Contractor in any proceedings which is non-collusive and duly prosecuted by the Contractor.

  - Obligations of Parties

- As soon as practicable and in any case within 7 (seven) days of the date of occurrence of a Force Majeure Event or the date of knowledge thereof, the Affected Party shall notify the other party of the same setting out, inter alia, the following in reasonable detail:

- the nature and extent of the Force Majeure Event;

- the estimated Force Majeure Period;

- the nature of and  the extent to which, performance of any of its obligations under this Contract is affected by the Force Majeure Event;

- the measures which the Affected Party has taken or proposes to take to alleviate/mitigate the impact of the Force Majeure Event and to resume performance of such of its obligations affected thereby; and

- any other relevant information concerning the Force Majeure Event, and /or the rights and obligations of the parties under this Contract.

- As soon as practicable and in any case within 5 (five) days  of notification  by the Affected party in accordance with the preceding Clause 6.2 (a), the parties shall meet and hold discussions in good faith and where necessary conduct physical inspection/survey of the project site in order to:

- assess the impact of the underlying Force Majeure Event,

- to determine the likely duration of Force Majeure Period and,

- to formulate damage mitigation measures and steps to be undertaken by the parties for resumption of obligations, the performance of which shall have been affected by the underlying Force Majeure Event.

- The Affected Party shall during the Force Majeure Period provide to the other Party with regular (not less than fortnightly) reports concerning the matters set out in the preceding Clause 6.2 (b) as also any information, details or document, which the Parties may reasonably require.

  - Performance of Obligations

If the Affected Party is rendered wholly or partially unable to perform any of its obligations under this Contract because of a Force Majeure Event, it shall be excused from performance of such obligations to the extent it is unable to perform the same on account of such Force Majeure Event provided that:

- due notice of the Force Majeure Event has been given as required by the preceding Article 6.2;

- the excuse from performance shall be of no greater scope and of no longer duration than is necessitated by the Force Majeure Event;

- the Affected Party has taken  all reasonable efforts to avoid, prevent, mitigate and  limit damage, if any, caused or is likely to be caused to the Project as a result of the Force Majeure Event and to restore  the Project, in accordance with the Good Industry Practice and its relative obligations under this Contract;

- when the Affected Party is able to resume performance of its obligations under this Agreement, it shall give to the other party written notice to that effect and shall promptly resume performance of its obligations hereunder, the non-issue of such notice being no excuse for any delay for resuming such performance;

- the Affected Party shall continue to perform such of its obligations which are not affected by  the Force Majeure Event and which are capable of being performed in accordance with this Agreement;

- any insurance proceeds received shall be entirely applied to repair, replace or restore the Project Site & Project Facilities damaged on account of the Force Majeure Event, in accordance with Good Industry Practice, unless otherwise agreed to by the Employer.

  - Termination due to Force Majeure Event

- Termination

- If a Force Majeure Event, is an event described under Clause 6.1(a), (b) and (d), continues or is in the reasonable judgement of the Parties likely to continue beyond a period of 120 (one hundred and twenty) days, the parties may mutually decide to terminate this Contract or continue this Contract on mutually agreed revised terms. If the parties are unable to reach an agreement in this regard, the Affected Party shall after the expiry of the said period of 120 (one hundred and twenty) days, be entitled to terminate this Agreement.

- If the Force Majeure Event is an event described in Clause 6.1 (c) and the Contractor having exhausted the remedies available to him under the Applicable Laws, has been unable to secure the remedy, the Contractorshall be entitled to terminate this Agreement.

Provided further, the Employer may at its sole discretion have the option to terminate this Contract at any time after the occurrence of any event described under Clause 6.1(c)

- Termination Notice

If either party, having become entitled to do so, decides to terminate this Contract pursuant to the preceding Clause6.4 (a) (i) or 6.4 (a) (ii), it shall issue Termination Notice setting out ;

- in sufficient detail the underlying Force Majeure Event;

- the Termination Date which shall be a date occurring not earlier than 60 (sixty) days from the date of Termination Notice;

- the estimated Termination Payment including the details of computation thereof and;

- any other relevant information.

- Obligation of Parties

Following issue of Termination Notice by either Party, the Parties shall promptly take all such steps as may be necessary or required to ensure that;

- the Termination Payment, if any, payable by the Employer in accordance with the following Clause 6.4 (d) is paid to  the Contractor on the Termination Date and

- the Project Site along with the Project Facilities are handed back to the Employer by the Contractor on the Termination Date free from all Encumbrance.

- Payment upon Termination

Upon Termination of this Contract due to a Force Majeure Event, Employer shall pay to the Contractor the appropriate amount until such Termination as per the milestone achieved by the Contractor and progress,provided the Employershall be entitled to deduct from this payment any amount due and recoverable by the Employerfrom the Contractoras on the Termination Date and release the Performance Security.

  - Liability for other losses, damages etc.

  - Save and except as expressly provided in this Article, neither party hereto shall be liable in any manner whatsoever to the other party in respect of any loss, damage, cost, expense, claims, demands and proceedings relating to or arising out of occurrence or existence of any Force Majeure Event.

SECTION 6:

## CONTRACT DATA
SECTION 6:CONTRACT DATA

| Clause Reference | Description |
| --- | --- |
| CC 1.1 | The Employer is: The Executive Engineer, Rural Drinking Water & Sanitation Department, ________ District, Karnataka |
|  | The name and identification number of the Contract is: [insert name and number as indicated in the Invitation for Tenders] |
|  | The Works consist of --------------------------------------------------------------- [brief summary, including relationship to other contracts under the Project] |
|  | The start date shall be the date of issue of notice to proceed with the work |
| CC 2.2 | The following documents also form a part of the Contract: [List the documents such as Methodology & Program of Construction, site investigation reports, Schedule of Key and Critical Equipment to be deployed on the work as per agreed program of construction, etc.] |
| CC 15, 26 | The Intended Completion Date for the whole of the work is ____ |
| CC 18 & 1.1 | The Site Possession Date is: ____ days after issue of Letter of Acceptance [Please indicate the date of handing over of possession of site] The Site is located at ________ and is defined in drawing nos._______ |
| CC 27 | The Defects Liability Period is 365 days. |
| CC 33 | The time limit for payment to the contractor is 45 days from the date of submission of the bill. |
| CC 35.1 | Taxes shall mean all taxes and duties applicable for execution of the Contract excluding only GST that shall be paid by the Employer at then prevailing rates. |
| CC 36 | The liquidated damages for the whole of works shall be 0.1% of the Contract Price per day. The maximum amount of liquidated damagesfor the whole of the works is 10% of Contract Price. |
| CC 41 | “As-built” drawings (in scale ____) in 5 sets and soft copy shall be submitted to the Employer in appropriate format within 30 days of issue of certificate of completion of whole or section of the work as the case may be. |
|  | Operating and Maintenance Manuals in 5 sets and soft copy shall be submitted to the Employer in appropriate format within 30 days of issue of certificate of completion of whole or section of the work as the case may be. |
|  | The amount to be withheld for failing to supply “as built” drawings or supply of Operation and Maintenance Manuals by the date specified is 1% of Contract Price. |
| CC 42.2 | The following events shall also be fundamental breach of the contract - The contractor has contravened Sub-clause 7.1 and Clause 9 of CC. |
| CC 43.1 | The percentage to apply to the value of the work not completed representing the Employer's additional cost for completing the Works shall be 30%. |

## SECTION 7:

## TECHNICALSPECIFICATIONS

## (Enclosed Separately)

## SECTION 8:

## DRAWINGS

## (Enclosed Separately)

## SECTION 9

## BILL OF QUANTITIES (PRICE TENDER)

## SECTION 9: BILL OF QUANTITIES (BoQ) - PRICE TENDER

Preamble:

      - The Tenderer shall submit the BoQ on  Kppp  portal only. Any tender with scanned copies of the BoQ (Price Tender) along with the Technical Tendershall be summarily rejected and such Tenderers shall be disqualified from further evaluation.

      - The BoQ do not generally give a full description of the Construction Details, Plant and Materials to be supplied and the services to be performed under each item.  The entered rates and prices shall be deemed to include for the full compliance with all provisions of the Contract.

      - The Contractor shall quote for each item indicated in the BoQ. The Contractor shall be responsible for making suitable assumptions for any item not indicated in the BoQ and shall include the cost of such item/s while quoting the price.

      - The Contractor shall make his own arrangements and include in the costs towards disposing off of surplus excavated earth, debris etc., without causing any infringements.

      - Rates for all the items in BoQ shall be filled up.  Items left blank or missed are deemed to have been included in other items quoted.

      - The taxes and duties referred in the “Price Schedules” shall cover all the taxes and duties applicable excluding onlyGST that shall be paid by the Employer at then prevailing rates.

## SECTION 10

## FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT

## SECTION 10:FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT

To:		[name of Employer]

[Address of Employer]

WHEREAS	 [name and address of Contractor] (herein after called "the Contractor") has undertaken, in pursuance of Contract No. dated_______ to execute [name of Contract and brief description of Works] (herein after called "the Contract");

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOWTHEREFORE where by affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total    of Rs.	[amount of guarantee]

_Rupees			[in    words],   and we undertake to pay you, upon your first written demand and without caveat or argument, any sum or sums within the limits of		[amount of guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until 30 days from the date of expiry of the Defects Liability Period.

Signature and seal of the guarantor		 
Name of Bank

Address

Date

To bring to the FY in which the Tenders are invited, financial turnover of previous years shall be given a weight of 10% per year bring them to the price level of the FY in which the Tender are invited.

Prime Contractor means that the Tenderer should have carried out the entire activities of the project solely or as a Lead Member of a Joint Venture.

To bring to the FY in which the Tenders are invited, the value of the completed works in previous years shall be given a weight of 10% per year bring them to the price level of the FY in which the Tender are invited.

The value of the electrical works shall be given a weight of 10% per year to bring them to the price level of the FY in which the Tender is invited.