Page 1 of 14

FORM 'A'

NAGAR PALIKA PARISHAD BHATAPARA DISTRICT BALODABAZAR-BHATAPARA (C.G.)

PUBLIC WORKS DEPARTMENT

Issued to Shri/M/s. …………………………………………………………………………

Class of Contractor. ..................E-Registration No...........................Date.....................

Name of Work – DEVELOPMENT WORKS FOR PATHWAY (ATAL PARISAR TO DOBY PLOT)

Amount of Contract Rs. 49.00 Lacs

Amount of E.M. Rs. 37000.00

Cost of Tender Form Rs. 1500.00

Vide M.R. No. & Date ……………………………………………………………………………

Time allowed for Completion  06 Months

Date of opening Tender ………………………....................................................................

Nagar Palika Parisad Bhatapara

PERCENTAGE RATE TENDER AND CONTRACT FOR WORKS

(Based on applicable Schedule of Rates)

General Rules and Direction for the Guidance of Contractors

1. Tenders must be invited for all works proposed to be given on contract unless the amount of

works proposed to be given on contract is Rs 50,000 or less. The N.I.T. shall be posted in public

places signed by the authority inviting the tenders.

N.I.T. will state the work to be carried out as well as the date for submitting and opening tenders

and the time allowed for carrying out the work, also the amount of earnest money to be

deposited with the tender and the amount of the security deposit to be deposited by the

successful tenderer & the percentage, if any to be deducted from bills, it will also state whether,

royalties and ground rents will be granted. Copies of the specifications, designs and drawings

and a schedule of items quantities and rates of the various description of work and any other

documents required in connection with the work signed for the purpose of identification by the

authority competent to approve the tender shall also be open for inspection by the contractor at

the office of the authority selling the tender forms during office hours.

Further that the schedule of items along with the quantities and rates payable shall be attached

to the tender documents and in the event of variation in rates given in such list with the

schedule of Rates the rates given in the S.O.R. approved by the competent authority shall

prevail.

2. In the event of the tender being submitted by a firm it must be signed separately by each

member thereof, in the event of the absence of any partner it must be signed on its behalf by a

person holding a power of attorney authorizing him to do so, such power of attorney should be

produced with the tender and it must disclose that the firm is duly registered under the Indian

partnership Act.

3. Any person who submits a tender shall fill up above or below the S.O.R. specified in rule he is

willing to undertake the work. Only one rate of percentage above or below the S.O.R. on all the

scheduled terms shall be named. Tenders that propose any alteration in the work specified in

the said N.I.T. or in the time allowed for carrying out the work or which contain any other

conditions of any sort will be liable to rejection. No single tender shall include more than one

work but contractors who wish to tender for two or more works shall submit a separate tender

for each Tenders shall have the name and number of the work to which they refer written

outside the envelope.

4. The authority receiving tenders or his duly authorised assistant will open tenders in the

presence of any intending contractors who may be present at the time and will enter the amount

of the several tenders in a comparative statement in a suitable form. Receipts for earnest

money will be given to all tenders except those whose tenders are rejected and whose earnest

money is refunded on the day the tenders are opened.

5. The Officers competent to dispose of the tenders shall have right of rejecting all or any of the

tenders without assigning any reason thereof.

6. The receipt of a clerk for any money paid by the contractor will not be considered as any

acknowledgement of payment to the Commissioner/CMO authority selling the tender form and

the contactor shall be responsible for seeing that he procures a receipt signed by that authorit or any other person duly authorised by him.

7. The memorandum of work tendered for be filled in and completed before the tender form is

issued. If a form is issued to an intending tenderer without having been so filled in and

completed he shall request the office to have this done before he completes and delivers his

tender.

Tender for Works

I/We hereby tender for the execution, of the work specified in under written memorandum within

time specified in such memorandum at

(In Figures):………………………………………………………………………………………….

(In Words:……………………………………………………………………………………………..

Percent below / above/at par with the applicable Schedule of Rates and in accordance in all

respects with the specifications, designs, drawings and instructions in writing referred to in rule

1 thereof and in clause 12 of the annexed conditions and with such materials as are provided

for by, and in all other respects in accordance with such conditions as far as applicable.

Memorandum

(a) Name of work - DEVELOPMENT WORKS FOR PATHWAY (ATAL PARISAR TO DOBY PLOT)

(b) Cost of work put to Tender - Rs.  49.00 Lacs

(c) Earnest money - Rs. 37000.00

(d) Security deposit  of Cost of Work 5%

(e) Percentage, if any to deducted from bills (Performance Gurantee) .....................................................

(f) Time allowed for the work 06 Month from the reckoned date including rainy season

(From 16th June to 15th October) (Delete whichever is not applicable.)

Should this tender be accepted I/we hereby agree to abide by and fulfil all terms and provisions of the

said condition of the contract annexed hereto as far as applicable or in default, thereof to forfeit & pay

to the Nagar Nigam/Nagar Palika/Nagar panchayat or his successors in office the sums of money

mentioned in the said conditions. A separate sealed cover duly super scribed containing the sum of

Rs. …………………………………………… as earnest money the full value of which is to be absolutely

forfeited to the said Nagar Nigam/Nagar Palika/Nagar Panchayat or his successors in office without

prejudice to any other rights or remedies of the said Nagar Nigam/Nagar Palika/Nagar Panchayat or

his successors in office should I/we fail to commence the work specified in the above memorandum or

should I/we not deposit the full amount of security deposit specified in the above memorandum, in

accordance with clause 1 of the said conditions of the contract, otherwise the said sum of Rs.

……………………………… shall be retained by Nagar Nigam/Nagar Palika/Nagar Panchayat on

account of such security deposit as aforesaid or the full value of which shall be retained by Nagar

Nigam/Nagar Palika/Nagar Panchayat on account of the security deposit specified in clause 1 of the

said conditions of the contract.

Signature of witness to Contractor’s Signature Signature of the Contractor before

submission of tender (with name and seal)

Dated the day of Dated the day of

………………………………… 20 …………………………….. 20

Name and Address of the witness: ………………………………………………………………………

Occupation of the witness:……………………………………………………………………

The above tender is hereby accepted by me for and on behalf of the Nagar Palik Nigam/Nagar Palika

Parishad/Nagar Panchayat

Dated the …………………. day of ………………… 20

……………………………………………..

Signature of the Officer by whom accepted

With designation and seal of office

CONDITIONS OF CONTRACT

Definition

1. The contract means the documents, forming the notice inviting tenders and tender documents

submitted by the tenderer and the acceptance thereof including the formal agreement executed

between the Nagar Nigam/Nagar Palika/Nagar panchayat and the contractor.

2. In the contract the following expressions shall unless otherwise required by the context have the

meanings hereby respectively assigned to them: -

(a) The expression “works” or “work” shall unless thereby mean something either in the subject or

context repugnant to such construction be construed and taken to mean the works or by virtue

of the contract contracted to be executed whether temporary or permanent and whether

original, altered, substituted or additional.

(b) The “site” shall mean the land and/or other places on, into or through which work is to be

executed under the contract or any adjacent land path or street through which work is to be

executed under the contract or any adjacent land, path, or street which may be allotted or used

for the purpose of carrying out the contract.

(c) The “Commissioner/CMO” means Commissioner/Chief Municipal officer of The Nagar

Nigam/Nagar Palika/Nagar panchayat and his successors in Office.

(d) The “Officers/Engineer-in-Charge” means the Commissioner/CMO/Engineer as the case may

be who shall supervise and be in charge of the work and who shall sign the contract on behalf

of the Nagar Nigam/Nagar Palika/Nagar Panchayat.

(e) “Competent Authority mean Commissioner/CMO, MIC/PIC, General Body/Parishad as the case

may be.

(f) The term “Engineer-In Charge” means the Engineer of the Nagar Nigam/Nagar Palika/Nagar

Panchayat

Note: - “Words” importing the singular number include plural number and vice-versa,

SECURITY DEPOSIT

Clause 1 - The person whose tender may be accepted (hereinafter called the contractor which

expression shall unless excluded by or repugnant to the context include his heirs

executers, administrators representatives and assigns) shall permit Nagar Palik

Nigam/Nagar Palika Parishad /Nagar Panchayat at the time of making any payments to

him for the value of work done under the contract to deduct the security deposit as

under.

The Security Deposit to be taken for the due performance of the contract under the

terms & conditions printed on the tender form will be the earnest money plus a deduction

of 5 (Five) percent from the payment made in the running bills.

COMPENSATION FOR DELAY

Clause 2 - The time allowed for carrying out the work, as entered in the tender form, shall be strictly

observed by the contractor and shall be deemed to be the essence of the contract and

shall be reckoned from the fifteenth day after the date on which the order to commence

the work is issued to the contractor, for a work where completion is up to 01 Years

For works, for which the completion period is beyond Four months: -

The period will be reckoned from the thirtieth day after the date on which the order to

commence the work is issued to contractor.

The work shall throughout the stipulated period of contract be proceeded with all due

diligence, keeping in view that time is the essence of the contract. The contractor shall

be bound in all cases, in which the time allowed for any work exceeds one month, to

complete 1/8th of the whole work before 1/4th of the whole time allowed under the

contract has elapsed, 3/8th of the work before 1/2 of such time has elapsed and 3/4th

of the work before 3/4th of such time has elapsed. In the event of the contractor failing

to comply with the above conditions, the Commissioner/CMO shall levy on the

contractor, as compensation an amount equal to: 0.5% (zero point five percent) of the

value of work (contract sum) for each week of delay, provided that the total amount of

compensation under provision of this clause shall be limited to 6% (six percent) of value

of work. (Contract sum)

Provided further that if the contractor fails to achieve 30% (thirty percent) progress in

1/2 (half) of original or validly extended period of time (reference clause 5 below) the

contract shall stand terminated after due notice to the contractor and his contract

finallised, with earnest money and or security deposit forfeited and levy of further

compensation at the rate of 10% of the balance amount of contract left incomplete,

either from the bill, and or from available security/performance guarantee or shall be

recovered as "Arrears of land revenue".

The decision of the Commissioner/CMO in the matter of grant of extension of time only

(reference clause 5 below) shall be final, binding and conclusive. But he has no right to

change either the rate of compensation or reduce and or condone the period of delayonce

such an order is passed by him (on each extension application of the contractor) it

shall not be open for a revision.

Where the Commissioner/CMO decides that the contractor is liable to pay compensation

for not giving proportionate progress under this clause and the compensation is

recommended during the intermediate period, such compensation shall be kept in

deposit and shall be refunded if the contractor subsequently makes up the progress for

the lost time, within the period of contract including extension granted, if any failing which

the compensation amount shall be forfeited in favour of the Nagar Nigam/Nagar Palika/Nagar Panchayat.

Action when the work is left incomplete abandoned or delayed beyond the

time limit permitted by the Commissioner/CMO

Clause 3:-

(i) The Commissioner/CMO may terminate the contract if the contractor causes a fundamental

breach of the contract.

(ii) Fundamental breach of contract shall include, but not be limited to, the following: -

(a) The contractor stops work for four weeks, when no stoppage of work is shown on the current

programme or the stoppage has not been authorised by the Commissioner/CMO.

(b) The Commissioner/CMO gives notice that failure to correct a particular defect is a

fundamental breach of contract and the contractor fails to correct it within reasonable period

of time determined by the Commissioner/CMO in the said notice.

(c) The contractor has delayed the completion of work by the number of weeks [12 (Twelve)

weeks] for which the maximum amount of compensation of 6% of contract sum is exhausted.

(d) If the contractor has not completed at least thirty percent of the value of construction work

required to be completed in half of the completion period (Including validly extended period if

any).

(e) If the contractor fails to appoint the technical staff and if appointed do not function properly for

4 weeks even after due written notice by the Commissioner/CMO.

(f) If he violates labour laws.

(g) If the Contractor fails to set up field laboratory * with appropriate equipments, within 30 day

from the reckoned date. (* for each contract valued more than Rupees 3 crores)

(h) Any other deficiency which goes to the root of the contract Performance

(iii) If the contract is terminated, the contractor shall stop work immediately, make the site safe and

secure and leave the site as soon as reasonably possible.

(iv) The Commissioner/CMO shall cause recording and checking of measurements of all items of

work done (taking in to account quality and quantity of items actually executed) and prepare the

final bill after adjusting all pervious outstanding dues. Such recording of measurements shall be

done after due notice regarding time and date of recording measurement and directing the

contractor to either remain present himself or his authorised representative so as to satisfy

himself that the recording of measurement is just and proper. Failure on his parts either to

attend and or refusing to acknowledge the measurement so recorded in the department

measurement book, shall be at his sole risk and responsibility.

(v) In addition to the provision contained in clause 2 above the Commissioner/CMO shall forfeit the

earnest money and or security deposit and further recover/deduct/adjust a compensation @

10% (ten percent) of the balance value of work left incomplete either from the bill, and or from

available security/performance guarantee or shall be recovered as "Arrears of land revenue"

Power to take possession of or require removal of Materials Tools

and Plants or sale of Contractor’s Plants etc

Clause 4: In any case in which any of the powers, conferred upon the Commissioner/CMO by

clause - 3 hereof shall have become exercisable and the same shall not be exercised,

the non-exercise thereof shall not constitute a waiver of any of the conditions hereof and

such powers shall notwithstanding be exercisable in the event of any future case of

default by the contractor for which by any clause or clauses hereof he is declared liable

to pay compensation shall remain unaffected. In the event of the Commissioner/CMO

putting in force either of the power clause 3 vested in him under the preceding clause he

may, if he so desires, take possession of all or any tools, plant materials, and stores in

or upon the works, or the site thereof or belonging to the contractor or procured by him

and intended to be used for the execution of the work or any part thereof paying or

allowing for the same in account at the contract rates, or in case of these not being

applicable, at current market rates to be certified by Commissioner/CMO, whose

certificate thereof shall be final; otherwise the Commissioner/CMO may by notice in

writing to the contractor or his clerk of the works foreman or authorised agent require

him to remove such tools plant, materials or stores from the premises (within a time to

be specified in such notice) and in the event of the contractor failing to comply with any

such requisition, the Commissioner/CMO may remove them at the contractors expense

sell them by auction or private sale on account of the contractor & at his risk in all

respects and the certificate of the Commissioner/CMO as to the expense of any such

removal and the amount of the proceeds and expense of any such sale shall be final

and conclusive against the contractor.

EXTENSION OF TIME

Clause 5

5.1 - If the Contractor shall desire an extension of time for completion of work on ground of his

having been "UNAVOIDABLY" hindered in its execution or on any other ground, he must

apply giving all and complete details of each of such hindrances or other causes in

writing, to the Commissioner/CMO positively within 15 days of occurrence of such

hindrance(s) and seek specific extension of time (period from .................... to ................)

In case the grounds shown by the contactor are reasonable, the

Commissioner/CMO shall be competent to grant the extension himself :-

Once the Commissioner/CMO/Competent Authority has decided the case of

extension of time with reference to the particular application of the contractor, it will not

be competent for them to review/change such a decision later on. However, the

Competent Authority and the Commissioner/CMO shall give the contractor an

opportunity to be heard (orally and or in writing), before taking any final decision either of

granting extension of time or permitting the contractor to complete the work by the

delayed date (under clause 2 of the contact) or before refusing both. Provided further

where the Commissioner/CMO has recommended grant of extension of particular time

under clause 5.1 of the contract or has refused to recommend extension of time but has

recommended permitting the contractor for delayed completion, (clause 2) the contractor

shall continue with the work till the final decision by Commissioner/CMO/Competent

Authority.

Failure on the part of the contractor for not applying extension of time even within 30

days of the cause of such an hindrance, it shall be deemed that the contractor does not

desire extension of time and that he has "Waived" his right if any, to claim extension of

time for such cause of hindrance. Once the Commissioner/CMO/Competent Authority

has heard (oral and or in writing) the contractor on this subject matter of extension of

time and if Commissioner/CMO/Competent Authority fails to communicate his decision

within a period of 30 days of such hearing, it shall be deemed that the contractor has

been granted extension of time for the period as applied by him.

5.2 Compensation Events: - Compensation Events for consideration of extension of time

without penalty.

The following mutually agreed Compensation Events unless they are caused by the contractor

would be applicable;

(a) The Commissioner/CMO does not give access to a part of the site.

(b) The Commissioner/CMO modifies the schedule of other contractor in a way, which affects the

work of the contractor under the contract.

(c) The Commissioner/CMO orders a delay or does not issue drawings, specification or instructions

/decisions/approval required for execution of works on time.

(d) The Commissioner/CMO instructs the contractor to uncover or to carry out additional tests upon

work, which is then found to have no defects.

(e) The Commissioner/CMO gives an instruction for additional work required for safety or other

reasons.1

(f) The advance payment and or payment of running bills (complete in all respect) are delayed.

(g) The Commissioner/CMO unreasonably delays issuing a Certificate of Completion

(h) Other compensation events mentioned in contract if any

FINAL CERTIFICATE:

Clause 6 - On completion of the work the contractor shall be furnished with a certificate by the

Commissioner/CMO (hereinafter called the Commissioner/CMO) of such completion in the

form appended at the end, but no such certificate shall be given, nor shall the work be

considered to be complete until the contractor shall have removed from the premises on which

the works shall be executed, all scaffolding surplus materials and rubbish, and cleaned off the

dirt from all wood-work, doors windows walls, floors or other parts of any building in upon or

about which the work is to be executed or of which he may have had possession for the

purpose of the execution there of nor until the work; shall have been measured by the

Engineer-in-Charge whose measurements shall be binding and conclusive against the

contractor. If the contractor shall fail to comply with the requirements of this clause as to

removal of scaffolding surplus materials and rubbish and cleaning of dirt on or before the date

fixed for the completion of the work, the Engineer-in-Charge may, at the expense of the

contractor remove such scaffolding, surplus materials and rubbish and dispose of the same as

he thinks fit and clean off such dirt as aforesaid and the contractor shall forthwith pay the

amount of all expenses so incurred, and shall have no claim in respect of any such scaffolding

or surplus materials as aforesaid, except for any sum actually realised by the sale thereof.

PAYMENT ON INTERMEDIATE CERTIFICATE TO BE REGARDED AS ADVANCES:

Clause 7 - No payments shall ordinarily be made for work estimated to cost less then Rs. 1,000/-

(Rs. One Thousand) till after the whole of the works shall have been completed and certificate

of completion given but if intermediate payment during the course of execution of works is

considered desirable in the interest of works, the contractor may be paid at the discretion of

the Commissioner/CMO But in the case of works estimated to cost more then rupees one

thousand, the contractor shall on submitting the bill therefore be entitled to receive a monthly

payment proportionate to the part thereof then approved by the Engineer - in -charge and

passed by Commissioner/CMO whose certificate of such approval and passing of the sum so

payable shall be final and conclusive against the contractor. But all such intermediate

payments shall be regarded as payments by way of advance against the final payment for

works actually done and completed and shall not preclude the requiring of bad unsound and

imperfect or unskillful work to be removed and taken away and reconstructed or erected or be

considered as an admission of the due performance of the contract or any such part thereof, in

any respect, or the accruing of any claim, nor shall it conclude determine, or affect in any way

the powers of the Commissioner/CMO under these conditions or any of them as to the final

settlement and adjustment of the accounts or otherwise or in any other way vary or affect the

contract. The final bill shall be submitted by the contractor within one month of the date fixed

for completion of the work, otherwise the Engineer -in-charge’s certificate of the measurement

and of the total amount payable for work accordingly shall be final and binding on all parties.

Clause 8 - Bills to be submitted monthly:

"A bill shall be submitted by the contractor by 15th day of each month for all works executed

by him till the end of previous month less the gross amount received by him till the last

previous month. This bill must be supported by records of detail measurement of quantities of

all executed items of work along with true copies of record and result of all tests conducted in

the previous month (date wise). The Commissioner/CMO shall take or cause to be taken the

requisite measurement for purpose of having the same verified/checked by the sub

Engineer/Assistant Engineer Commissioner/CMO concern for quantity, quality and

specification and examining all the "test results" and record the same in the Departmental

measurement, book. Based on above record measurement bill shall be corrected /prepared

afresh. The contractor shall sign the measurement and the bill. The Commissioner/CMO shall

pay running bills by 25th day of the month subject to availability of the funds If the contractor

fails to submit, the bill on or before the day prescribed, the Commissioner/CMO after waiting

for another 15 days shall depute a subordinate to measure the said work in the presence of

contractor and or his authorised Engineer/Representative, whose counter signature to the

measurement recorded with quantity and quality remark will be sufficient proof for acceptance

of the same and shall be binding on the contractor

All such running bill payments are by way of "Advances" and shall be subject to final

adjustment.

Clause 9 - BILLS TO BE ON PRINTED FORMS:

The contractor shall submit all bills on printed forms to be had on application at the office of the

Engineer- in -charge, and the charges in the bills shall always be entered at the rates specified

in the tender or in the case of any extra work ordered in pursuance of these conditions, and not

mentioned or provided for in the tender at the rates hereinafter provided for such work.

The deduction or addition as the case may be of the percentage will be calculated on the

amount of the bill for the work done, after deducting the cost of materials supplied

departmentally at rates specified in the agreement.

Clause 10 - RECEIPTS TO BE SIGNED BY PARTNERS OF PERSONS HAVING AUTHORITY TO

DO SO:

Receipts for payments made on account of a work when executed by a firm must also be signed

by the several partners, except where the contractors are described in their tender as a firm in

which case the receipt must be signed in the name of-the firm by one of the partners, or by

some other person having authority to give effectual receipt for the firm.

CLAUSE 11 Reimbursement/Refund on Variation in Prices of Materials / P. O. L. and Labour Wages,

only for the works contract value more then Rs.3 Cr.

Price Adjustment: -

(A) Contract price shall be adjusted for increase or decrease in rates and price of labour,

materials, POL, in accordance with the following principles and procedure and as per formula

given below.

Note: - Price adjustment shall be applicable from reckoned date and upto validly extended period

under clause 5.1 above but shall not apply to the period when, work is carried out under

clause 2 above.

(B) The price adjustment shall be determined during each month from the formula given in the

hereunder.

(C) Following expressions and meanings are assigned to the work done during each month:

To the extent that full compensation for any rise or fall in costs to the contractor is not

covered by the provisions of this or other clauses in the contract, the unit rates and prices

included in the contract shall be deemed to include amounts to cover the contingency of such

other rise or fall in costs.

The formula (e) for adjustment of prices are: -

R= Total value of work done during the month. It would include the amount of secured advance

granted, if any, during the month, less the amount of secured advance recovered, if any during

the month. It will exclude value for works executed under variations for which price adjustment

will be worked separately based on the terms mutually agreed.

Adjustment for labour component

(i) Price adjustment for increase or decrease in the cost due to labour shall be paid in accordance

with the following formula:

VL = 0.85 x P1/100 x R x (Li –L0)/L0

VL = increase or decrease in the cost of work during the month under consideration due to

changes in rates for local labour.

L0 = the consumer price index for industrial workers at the town nearest to

the site or work as published by Labour Bureau, Ministry of Labour, Govt. of India. on

the date of inviting tender

Li = The consumer price index for industrial workers at the town nearest to the site of work

for the month under consideration as published by Labour Bureau, Ministry of Labour,

Government of India.

P1 = Percentage of labour component of the work.

Adjustment for cement component

(ii) Price adjustment for increase or decrease in the cost of cement procured by the contractor

shall be paid in accordance with the following formula;

Vc = 0.85 x Pc/100 x R x (Ci –C0)/C0

Vc = increase or decrease in the cost of work during the month under consideration due to

changes in rates for cement

C0 = The all India wholesale price index for cement as published by the Ministry of Industrial

Development, Government of India, New Delhi.

on the date of inviting tender.

Ci = The all India average wholesale price index for cement for the month under

consideration as published by Ministry of Industrial Development, Govt. of India, New Delhi.

PC = Percentage of cement component of the work.

Adjustment for steel component

(iii) Price adjustment for increase or decrease in the cost of steel procured by the Contractor shall

be paid in accordance with the following formula;

Vs = 0.85 x Ps/100 x R x (Si – S0)/S0

Vs = increase or decrease in the cost of work during the month under

consideration due to changes in the rates for steel.

S0 = The all India wholesale price index for steel (Bar and Rods) as published by the Ministry

of Industrial Development, Government of India, New Delhi. on the date of inviting

tender

Si = The all India average wholesale price index for steel (Bar and Roads)

for the month under consideration as published by Ministry of Industrial Development,

New Delhi.

Ps = Percentage of steel component of the work.

Note:- for the application of this clause, index of Bars and Rods has been to represent steel group.

Adjustment of bitumen component

(iv) Price adjustment for increase or decrease in the cost of bitumen shall be paid in accordance

with the following formula;

VL = 0.85 x Pb/1 00 x R x (Bi –B0) / B0

Vb = Increase or decrease in the cost of work during the month under consideration due to

changes in rates for bitumen.

B0 = The official retail price of bitumen at the IOC depot at nearest centre on the date of

inviting tender.

Bi = The official retail price of bitumen of IOC depot at nearest center for the 15th day of the

month under consideration.

Pb = Percentage of bitumen component of the work.

Adjustment of POL (fuel and lubricant) component

(v) Price adjustment for increase or decrease in cost of POL (fuel and lubricant) shall be paid in

accordance with the following formula;

Vf = 0.85 x Pf/100 x R x (Fi – F0)/F0

Vf = Increase or decrease in the cost or work during the month under

consideration due to changes in rates for fuel and lubricants.

F0 = The official price of High Speed Diesel (HSD) at the existing

consumer Diesel pumps out let at nearest center on the date of inviting tender

Fi = The official retail price of HSD at the existing consumer pumps of

IOC at nearest center for the 15th day of month under consideration.

Pf = Percentage of fuel and lubricants component of the work.

Note: - For the application of this clause, the price of High speed Diesel Oil has been chosen to

represent fuel and lubricants group.

Adjustment of Other Materials Component

(vii) Price adjustment for increase or decrease in cost of local materials other than Cement, steel,

Bitumen and POL procured by the contractor shall lay in accordance with the following formula;

Vm = 0.85 x Pm /100 X R x (Mi – M0)/M0

Vm = Increase or decrease in the cost of work during the month under

consideration due to changes in rates for local materials other than cement, steel,

bitumen and POL.

M0 = The all India wholesale price index (all commodities) as published by the Ministry of

Industrial Development, Govt. of India, New Delhi. on the date of inviting tender

Mi = The all India Wholesale price index (all commodities) for the month under consideration

as published by Ministry of Industrial Development, Govt. of India, New Delhi.

Pm = Percentage of local material component (Other than cement, steel, bitumen and POL) of

the work.

The following percentages will govern the price adjustment for the entire contract:

Sl. No.

Components For road For Building For bridge

1 Lbour- P1 25% 35% 30%

2 Cement – Pc 5% 10% 25%

3 Steel – Ps 5% 10% 25%

4 Bitumen – Pb 10% - -

5 POL – Pf 10% 10% 10%

6 Other materials - Pm 45% 35% 10%

Total: -

100% 100% 100%

Note :-If in the execution of contract for Road works use of certain material(s) is/are not involved (Viz

cement, steel, Bitumen etc.), then the percentage of other material-Pm shall be increased to that extent

Example: - Say in a contract of roadwork steel is not required (Ps-5%).Pm shall become 45%+5%=50%

Or

Say cement & steel not required then Pm shall become 45%+5%+5%=55% and so on

Work to be executed in Accordance with Specification, Drawing, Order, etc.:

Clause 12: The contractor shall execute the whole and every part of work in the most substantial and

workman like manner, and both as regards materials and otherwise in every respect in strict

accordance with the specifications. The contractor shall also conform exactly fully and

faithfully to the designs, drawings and instructions in writing relating to the work signed by the

Engineer-in-charge and lodged in his office and to which the contractor shall be entitled to

have access at such office or on the site of the work for the purpose of inspection during

office hours and the contractor shall, if he so requires, be entitled at his own expense to take

or cause to be made copies of the specifications, and of all such designs, drawings and

instructions as aforesaid. MORTH/IRC specifications for road and bridges, specifications for

rural roads and other I.R.C. publications and their manual, latest CPWD specifications/I.S.I.

codes for buildings or special specifications whenever enclosed separately shall apply in the

case of any variance the following:-

Order of Precedence Shall Prevail:-

1. Specifications as per NIT.

2. Specifications as per S.O.R.

3 MORTH/IRC specifications for road and bridges, Specifications for rural roads and other I.R.C.

Publications and their manual, latest CPWD specifications/I.S.I. codes for buildings or special

specifications whenever enclosed separately

4 Mode of measurements for building shall be as provided in the S.O.R. applicable to the

contract. Where such mode of measurement is not specified in the S.O.R. it shall be done as

per l.S.l. Code of building measurement. However if any mode of measurement is specifically

mentioned in the N.l.T. the same will get precedence over all the above.

Clause 12 -A: In respect of all bearings, hinges or similar part intended for use in the superstructure of

any bridge, the contractor shall, whenever required, in the course of manufacture, arrange and

afford all facilities for the purpose of inspection and test of all or any of the part and the material

used therein to any officer of the Directorate of inspection of the Ministry of works production

and supply of the Government of India and such bearings, hinges or similar parts shall not be

used in the superstructure of any bridge except on production of a certificate of acceptance

thereof from the Directorate of inspection. All inspection charges will be payable by the

contractors. (This clause may be struck off if the tender is not for bridgework).

Variations

Clause 13 - Additions, Alterations in Specifications and Designs.

The Commissioner/CMO shall have power to make any alterations in, omissions from,

additions to, or substitutions for, the original specifications, drawings, designs and instruction,

that may appear to him to be necessary or advisable during the progress of the work, and the

contractor shall be bound to carry out the work in accordance with any instruction which may be

given to him in writing, signed by the Commissioner/CMO and such alterations, omissions,

additions or substitution shall not invalidate the contract and any altered, additional or

substituted work, which the contractor may be directed to do in the manner above specified as

part of the work; shall be carried out by the contractor on the same conditions in all respects on

which he agreed to do the main work and at the same rates as are specified in the tender for

the main work, provided the total value of all such increased or altered or substituted work does

not exceed 25% of the amount put to tender inclusive of contractor percentage. if such value

exceeds 25% it shall be open to the contractor either to determine the contract or apply for

extension.

Note: - Such additions, alterations, substitution, shall have to be within the Scope of work tendered for

Rates for works not in schedule of rates

If during the course of execution, where it is found necessary that certain item/items of work

not provided for in the S.O.R. required to be carried out then the Engineer-in-Charge shall

identify such item / items including approximate quantity of the contract and ask the

contractor to submit his rates in writing supported by the requisite data within a period of 7

days. The Engineer-in-Charge shall obtain approval/ modification of the proposed rate from

the Competent Authority after recommendation of Commissioner/CMO and communicate

the same within a period of 4 weeks to the contractor, in case the contractor agrees to the

above rates as fixed by the Competent Authority then they shall form a part of

supplementary schedule of the contract agreement .lf the contractor does not agree to the

rate of the Competent Authority then it shall be open for the Commissioner/CMO to get the

work executed through any other agency. The contractor will not however be entitled to any

compensation due to delay or hindrance or loss of profit accruing on account of this extra

work executed by alternative agency.

If the contractor commences non-schedule work or incur expenditure in regard thereto

before the rates shall have been determined by the Competent Authority, then he shall be

entitled for payment for the work done as decided by the Competent Authority. the decision

of the Competent Authority shall be final. Such a decision shall be given by the Competent

Authority. Within a period of 30 (Thirty) days and it shall be open to the contractor not to

continue that item further. In such an event that item shall be got executed by other agency

at such an approved rate by Competent Authority Contractor may either determine his

contract if variations exceeds 10 (Ten) % of the Administrative approval, or may apply for

extension.

Extension of time in consequence of variations

The time for the completion of work shall be extended in proportion of the variation of the

work bear to the original contract work and certificate of Commissioner/CMO shall be

conclusive as to such proportion.

NO CLAIM TO ANY PAYMENT OR COMPENSATION FOR ALTERATION IN OR

RESTRICTION OF WORKS:

Clause 14 - If at any time after the execution of the contract documents, the Commissioner/CMO

shall for any reason whatsoever require the whole or any part of the work as specified in the

tender to be stopped for any period or shall not require the whole or part of the work to be

carried out at all or to be carried out by the contractor he shall give notice in writing of the fact to

the contractor who shall there upon suspend or stop the work totally or partially, as the case

may be.

If any such case, except as provided hereunder, the contractor shall have no claim to any

payment or compensation what so ever on account of any profit or advantage which he might

have derived from the execution of the work in full, but which he did not so derive in

consequence of the full amount of the work not having been carried out, or on account of any

loss that he may be put to on account of materials purchased or for unemployment of labour

recruited by him. He shall not also have any claim for compensation by reason of any alteration

having been made in the original specifications, drawing, designs and instructions, which may

involve any curtailment of the work as originally contemplated. Where, however, materials have

already been purchased or agreed to be purchased by the contractor shall be paid for such

materials at the rates determined by the Commissioner/CMO, provided they are not in excess of

requirement and of approved quality and / or shall be compensated for the loss, if any that he

may be put to, in respect of materials agreed to be purchased by him, the amount of such

compensation to be determined by the Commissioner/CMO whose decision shall be final. If the

contractor suffers any loss on account of his having to pay labour charges during the period

during which the stoppage of work has been ordered under this clause, the contractor shall, on

application be entitled to such compensation on account of labour charges as the

Commissioner/CMO, whose decision shall be final, may consider reasonable provided that the

contractor shall not be entitled to any compensation on account of labour charges, if in the

opinion of the Commissioner/CMO, the labour could have been employed by the contractor

elsewhere for the whole or part of the period during which the stoppage of the work has been

ordered as aforesaid.

If the total duration of suspension of the work is more than the six months, then this suspension

of the work will be considered as permanent stoppage of the work, and the contractor can

determine the contract, if he so desires.

ACTION AND COMPENSATION PAYABLE IN CASE OF BAD WORK:

Clause 15 -If at any time before the security deposit is refunded to the contractor, it shall appear to the

Commissioner/CMO or his subordinate in charge of the work, that any work has been executed

with unsound, imperfect or unskillful workmanship or with material of inferior quality or that any

materials or articles provided by him for the execution of the work are unsound, or of a quality

inferior to that contracted for, or are otherwise not in accordance with the contract, it shall be

lawful for the Commissioner/CMO to intimate this fact in writing to the contractor and then

notwithstanding the fact that the work, materials or articles complained of may have been

Inadvertently passed, certified and paid for contractor shall be bound forthwith to rectify, or

remove and reconstruct the work so specified in whole or in part, as the case may require, or if

so required, shall remove the materials or articles so specified and provide other proper and

suitable materials or articles at his own proper charge and cost, and in the event of his failing to

do so with in a period to be specified by the Commissioner/CMO in the written intimation

aforesaid ,the contractor shall be liable to pay compensation at the rate of one percent on the

amount of contract put to tender every day not exceeding ten days, during which the failure so,

continues and in the case of any such failure the Commissioner/CMO may rectify or remove

and, re-execute the work or remove and replace the materials or articles complained of as the

case may be at the risk and expense in all respects of the contractor. Should the

Commissioner/CMO consider that any such inferior work or materials as described above may

be accepted or made use of it shall be within his discretion to accept to the same at such

reduced rates as he may fix therefore

WORK TO BE OPEN FOR INSPECTION-CONTRACTOR OR RESPONSIBLE AGENT

TO BE PRESENT:

Clause 16-All work under or in course of execution or executed in pursuance of the contract shall at all

time be open to the inspection and supervision of the Commissioner/CMO and his subordinates

and the contractor shall at all time during the usual working hours, and at all other times at

which reasonable notice of the intention of the Commissioner/CMO or his subordinate to visit

the work shall have been given to the contractor, either himself be present to receive orders and

instruction or have a responsible agent duly accredited in writing present for that purpose.

Orders given to the contractor’s agent shall be considered to have the same force as if they had

been given to the contractor himself.

NOTICE TO BE GIVEN BEFORE WORK IS COVERED UP:

Clause 17 -The contractor shall give not less than five days notice in writing to the Commissioner/CMO

or his subordinate in charge of the work before covering tip or otherwise placing beyond the

reach of measurement any work in order that the same may be measured, and correct

dimensions thereof be taken before the same is so covered up or placed beyond the reach of

measurement, any work without the consent in writing of the Commissioner/CMO or his

subordinate in charge of the work and if any work shall be covered up or placed beyond the

reach of measurement without such notice having been given or consent obtained, the same

shall be uncovered at the contractors expenses, or in default thereof, no payment or allowance

shall be made for such work or the materials with which the same was executed.

Clause18- CONTRACTOR LIABLE FOR DAMAGE DONE AND FOR IMPERFECTIONS AFTER

CERTIFICATE OF COMPLETION

1.If the contractor or his work people or servants shall break, deface injure or destroy any part of

building in which they may be working or any building, road, road curbs, fences, enclosures,

water pipes, cables drains, electric or telephone posts or Wires trees grass or grassland or

cultivated ground continuous to the premises on which the work or any part of it is being

executed, or if any damage shall happen to the work while in progress, from any cause

whatever, or any imperfections become apparent ,the contractor shall make good the same at

his own expense or in default, the Commissioner/CMO may cause the same to be made good

by other workmen and deduct the expense of which certificate of the Commissioner/CMO shall

be final) from any sums that may be then or at any time thereafter, may become due to the

contractor or from his security deposits, or the proceeds of sale thereof or of a sufficient portion

thereof.

Clause 19 - CONTRACTOR TO SUPPLY PLANT, LADDERS, SCAFFOLDING, ETC.:

The contractor shall supply at his own cost materials (except such special materials if

any, as may in accordance with the contractor be supplied from the Commissioner/CMO

’s Stores) plants, tool, appliances, implements, ladders, cordage, tackle, Scaffolding and

temporary work requisite for the proper execution the work whether original, or altered or

substituted, and whether included in the specification or other documents forming part of

the contractor referred to in these condition or not or which may be necessary for the

purpose of satisfying or complying with the requirement of the Commissioner/CMO as to

any matter as to which under these conditions he is entitled to be satisfied, or which he

is entitled to require together with carriage there for to and from the work. The contractor

shall also supply without charge requisite number of persons with the means and

materials necessary for the purpose of setting out works, and counting, weighing&

assisting in the measurement or examination at any time and from time to time of the

work, or materials. Failing his so doing the same may be provided by the

Commissioner/CMO at the expenses of the contractor and the expenses may be

deducted from any money due to the contractor under the contract, or from his security

deposit or the proceeds of sale thereof, or of a sufficient portion thereof.

Contractor is liable for damages arising from non-provision of lights fencing etc. The

contractor shall also provide at his own cost except when the contract specifically

provides otherwise and except for payments due under clause all necessary fencing and

lights required to protect the public from accident and shall be bound to bear the

expenses of defence of every suit, action or proceedings at law that may be brought by

any person for injury sustained owing to neglect of the above precautions & to pay any

damage and costs which may be awarded in any such suit, action or proceedings to any

such person or which may with the consent of the contractor be paid to compromise any

claim by any such person.

Clause 20 - COMPENSATION UNDER SECTION 12 SUB-SECTION (1) OF THE WORKMAN’S

COMPENSATION ACT 1923:

ln every case in which by virtue of the provisions of section 12 sub-section (1) of the

workman’s compensation Act 1923 Commissioner/CMO is obliged to pay compensation

to a workman employed by the contractor in execution of the works and will recover from

the contractor the amount of compensation so paid Commissioner/CMO shall be at

liberty to recover the amount or any part there of by deducting it from the security

deposit or from any sum due by Commissioner/CMO to the contractor whether under

this contract or otherwise. Commissioner/CMO may not be bound to contest any claim

made against them under section - 12 sub-sections (1) of the said Act except on the

written request of the contractor and upon his giving to Commissioner/CMO full security

for all cases for which Commissioner/CMO might become liable in consequence

contesting such claim.

LABOUR:

Clause 21 - The contractor should get himself registered under contract - labour regulations and

abolition Act 1970 including its amendments after getting a certificate from the principal

employer.

Clause 22 - Labour below the age of 14 years - No labour below the age of 14 years shall be

employed on the work.

FAIR WAGE:

Clause 23 - The contractor shall pay not less than fair wage to labour engaged by him on the work.

Explanation -

(a) Fair wage’ means wage(s) whether for time or piece work notified during the period of execution

of contract for the work and where such wages have not been so notified, the wages prescribed

by the revenue Commissioner/Collector for that period

(b) The contractor shall, notwithstanding the provisions of any contract to the contrary cause to be

paid a fair wage to labourers indirectly engaged on the work including any labour engaged by

his sub-contractors in connection with the said work, as if the labourers had been immediately

employed by him.

(c) In respect of labour directly or indirectly employed on the work for the performance of the

contractors part of this agreement the contractor shall comply with or cause to be complied with

the Labour Act in force.

(d) The Commissioner/CMO shall have the right to deduct, from the moneys due to the contractor,

any sum required or estimated to be required for making good the loss suffered by a worker or

workers by reasons of non-fulfilment to the conditions of the contract for the benefit of the

workers non payment of wages or deductions made from his or their wages, which are not

justified by the terms of the contract or non observance of the regulations.

(e) The contractor shall be primarily liable for all payments to be made under and for observance of

the regulations afore said with out prejudice to his right to claim indemnity from his subcontractors.

(f) The regulations aforesaid shall be deemed to be a part of this contract and any breach thereof

shall be deemed to be a breach of this contract.

Subletting of works

Clause 24 :- The contract may be rescinded and security deposit forfeited, for subletting the work

beyond permissible limits as per clause 7.1 of appendix 2.10 or if contractor becomes

insolvent: -

"Note : Such subletting/assignment shall not be made to any other Contractor registered in

Class AI to A5 Category in the Public Works Department of Chhattisgarh or in similar

Category in other Deptt. of the State or in other organization or Agency (Class with

about similar financial capacity) by whatever name these are called."

24.1 The contract shall not be assigned or sublet without prior sanction of the authority who has

accepted the tender in writing. And if the contractor assign or sublet his contract, for more than

permissible limits as per clause 7.1 of appendix 2.10 or attempt to do so, or become insolvent

commence any insolvency proceedings or make any composition with his creditors, or attempt

to do so or if any gratuity, gift, loan, perquisite, reward of and advantage pecuniary or

otherwise, shall either directly or indirectly be given, promised or offered by the contractor, or

any of his servants or agents or to any public officer or person in the employ of Government in

any way relating to his office or employment, or if any such officer or person shall become in

any way directly or indirectly interested in the contract, the Commissioner/CMO may there

upon by notice in writing rescind the contract, and the S.D. of the contractor shall there upon

stand forfeited and be absolutely at the disposal of Nagar Nigam/Nagar Palika/Nagar

Panchayat and the same consequences shall ensure as if the contract had been rescinded

under clause 3 thereof, and in addition the contractor shall not be entitled to recover or be paid

for any work thereto for actually performed under the contract. Any such assignment/subletting

within the limit of 25% by the authority who has accepted the tenders OR 50 % by the next

higher authority accepting the tender or Govt. as the case may be ,shall not diminish or dilute

the liability/ responsibility of the contractor. If the contractor gets item / items of work executed

on a task rate basis without materials, this shall not amount to subletting of the contract.

Any subcontracted work, done in Chhattisgarh state with prior approval of competent

authority, such subcontractor will also get the credit for work towards his experience.

24.2 The Commissioner/CMO shall be empowered to terminate any contract if the contractor

sublets the works to some other person on the basis of power of attorney.

24.3 Subletting of work shall result in reduction in experience of the main contractor to the

extent of the sublet.

Clause 25:Sum payable by way of Compensation to be considered as Reasonable Compenstion

Without Reference to Actual Loss:

All sums payable by way of compensation under any of these conditions shall be considered

as reasonable compensation to be applied to the use of Nagar Nigam/Nagar Palika/Nagar

Panchayat without reference to the actual loss or damage sustained, and whether or not any

damage shall have been sustained.

Clause 26 - CHANGE IN THE CONSTITUTION OF FIRM:

In the case of tender by partners any change in the constitution of the firm shall be

forthwith notified by the contractor to the Commissioner/CMO for his information, and

contractor shall initiate steps for fresh & new registration which shall be assessed &

decided by the competent authority for fresh registration.

Clause 27 - WORK TO BE UNDER DIRECTION OF ENGINEER/COMMISSINOR/CMO:

All works to be executed under the contract shall be executed under the direction and

subject to the approval in all respect of the Commissioner/CMO of the Nagar Palik

Nigam/Nagar Palika/Nagar Panchayat for the time being who shall be entitled to direct at

what point or points and in what manner they are to commenced and from time to time

carried on.s

Clause 28 ARBITRATION CLAUSE:

Except as otherwise provided in this contract all question and dispute relating to the

meaning of the specification, designs, drawings and instruction herein before mentioned as

to thing whatsoever in any way arising out of or relating to the contract designs, drawings,

specification, estimate, concerning the works, or the execution or failure to execute the

same, whether arising during the progress of the work, or a after the abandonment there of

shall be referred to the Commissioner/CMO for his decision, within a period of 30 (thirty)

days of such an occurrence (s). There upon the Commissioner/CMO shall give his written

instructions and/or decisions, after hearing the contractor and Engineer-in-Charge within a

period of 15 (fifteen) days of such request. This period can be extended by mutual consent

of parties.

Upon receipt of written instructions or decisions, of Commissioner/CMO the parties shall

promptly proceed without delay to comply such instructions or decisions. If the

Commissioner/CMO fails to give his instruction or decisions in writing within a period of 15

(fifteen) days or mutually agreed time after being requested and/or, if the party (es) is/are

aggrieved against the decision of the Commissioner/CMO , the aggrieved party may within

30 days prefer an appeal to the Competent Authority, who shall afford an opportunity to the

parties of being heard and to offer evidence in support of his appeal. The, Competent

Authority will give his decision within 30 (thirty) days, or such, mutually agreed period.

If any party is not satisfied with the decision of the Competent Authority he can file a

petition for resolving the dispute through arbitration in the arbitration tribunal

A reference to Arbitration Tribunal shall be no ground for not continuing the work on the

part of the Contractor. Payment as per original terms and condition of the agreement shall

be continued by the Commissioner/CMO in accordance with clause 8 above.

Clause 29 - LUMP SUM IN ESTIMATE:

When the estimate on which a tender is made includes lump sums in respect of part of the

works, the contractor shall be entitled to payment in respect of the items of work involved or

the part of the work in the question at the same rates as are payable under this contract for

such items, or if the part of the work in question is not, in the opinion of the

Commissioner/CMO , capable of measurement, the Commissioner/CMO may at the his

discretion pay the lump sum amount entered in the estimates , and the certificate in writing

of the Commissioner/CMO shall be final and conclusive against the contractor with regard

to any sum or sums payable to him under the provisions of this clause.

Action where no specification:

Clause 30 - In the case of any class of work for which there is no specification as is mentioned in

Rule such work shall be carried out in accordance with the specification approved by

Competent Authority /Engineer-in-Charge for application to works.

Contractor’s Percentage whether Applied to Net or Gross Amounts of Bills:

Clause 31 - The percentage referred to at Para 7 of the tender will be deducted from/added to the

gross amount of the bills for work done after deduction of the cost of materials supplied

by the department.

Claim for Quantities Entered in the Tender or Estimate:

Clause 32 - Quantities shown in the tender are approximate and no claim shall be entertained for

quantities of work executed being either more or less than those entered in the tender of

estimate. This is subject to the limitations as provided for in clause 13 and 14 above.

Claim for Compensation for Delay In Starting the Work:

Clause 33 - No compensation shall be allowed for any delay caused, except as provided under

clause 5.3, in starting of the work on any other ground or reasons whatsoever.

EMPLOYMENT OF SCARCITY LABOUR:

Clause 34- If Government declare a state of Scarcity or famine to exist in any village situated within

sixteen kilometres of the work the contractor, shall employ upon such parts of the work

as are suitable for unskilled labour, any person certified to him by the Competent

Authority or by any person to whom the Competent Authority may have delegated this

duty in writing to be in need of relief and shall be bound to pay to such persons wages

not below the minimum which Government may have fixed in this behalf. Any dispute,

which may arise in connection with the implementation of this clause, shall be decided

by the Competent Authority whose decision shall be final and binding on the contractor.

Royalty on Minor Minerals

Clause 35: - The contractor shall pay all quarries, Royalty charges etc.Royalty Clearance.- The concerned works department should deduct, the amount equivalent to the market value of minor minerals used in construction work done through contractors in Government/semigovernment works department, from the bills of contractors. Contractors may be obtain Royalty Clearance Certificate through Collector concerned, by submitting an application to mining office along with valid transit passes of the mineral used, after which amount deducted by the works department may be returned and final bills settled to contractors: Provided that the contractors fail to submit valid transit passes of the minor minerals used, agtion shall be taken under Section 2l to 23-B of the Mines and Minerals (Development and Regulation) Act, 1957 (No. 67 of 1957)."

Any change in the royalty rates of minor minerals notified by the state government, after

the date of submission of financial offer by the bidder/contractor, then this

increase/decrease in the rates shall be reimbursed/deducted on actual basis.

TECHNICAL EXAMINATION

Clause 36 - The Commissioner/CMO shall have the right to cause Audit and Technical Examination

of the works and the final bills of the contractor including all supporting vouchers,

abstracts etc. to be made as per payments of the final bills and if as a result of such

Audit & Technical Examination the sum is found to have been overpaid in respect of any

work done by the contractor under the contract or any work claimed by him to has been

done under contract and found not to have been executed, the contractor shall be liable

to refund the amount of over payment and it shall be lawful for the Commissioner/CMO

to recover the same from the security deposit of the contractor or from any dues payable

to the contractor from the Commissioner/CMO account if it is found that the contractor

was paid lesser than what was due to him under the contract in respect any work

executed by him under it, the amount of such under payment shall be duly paid by the

Commissioner/CMO to the contractor.

In the case of any audit examination and recovery consequent on the same the

contractor shall be given an opportunity to explain his case and decision of the

Competent Authority shall be final.

DEATH OF PERMANENT INVALIDITY OF CONTRACTOR:

Clause 37 - If the contractor is an individual or a proprietary concern, partnership concern, dies

during the currency of the contract or becomes permanently incapacitated, where the

surviving partners are only minors the contract shall be closed without levying any

damages/compensation as provided for in clause 3 of the contract agreement.

However, if Commissioner/CMO is satisfied about the competence of the surviving, then

the Commissioner/CMO shall enter into a fresh agreement for the remaining work strictly

on the same terms and conditions, under which the contract was awarded.

PENALTY FOR BREACH OF CONTRACT:

Clause 38 - On the breach of any term or condition of this contract by the contractor the said the

Nagar Palik Nigam/Nagar Palika/Nagar Panchayat shall be entitled to forfeit the

Security deposit or the balance thereof that may at the time be remaining, and to realise

and retain the same as damages and compensation for the said breach but without

prejudice to the right of the the Nagar Palik Nigam/Nagar Palika/Nagar Panchayat to recover further sums as damages from any sums due or which may become due to the contractor by.