BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED

Corporate Office, K R Circle,

Bengaluru – 560 001.

(Corporate Identity Number (CIN): U04010KA2002SGC030438)

| Address | : | Office of the Chief General Manager, Ele |
| --- | --- | --- |
|  |  | Procurement, 2nd Floor, Block II |
|  |  | Corporate Office, KR Circle |
|  |  | Bengaluru- 560001 |
| Telephone | : | 080-22352704 |
| Email Id | : | cgmproc@bescom.co.in |

Enquiry No: BESCOM/2026-27/EL/WORK_INDENT1146

TENDER FOR THE WORK OF “STRENGTHENING OF HT/LT NETWORK IN ELEPHANT HABITAT & ELEPHANT CORRIDORS BY CREATING SAFE CORRIDORS FOR ELEPHANTS AND OTHER WILDLIFE IN RAMANAGARA DIVISION OF RAMANAGARA CIRCLE OF BRAZ AREA OF BESCOM JURISDICTION FOR A PERIOD OF EIGHTEEN MONTHS ON TOTAL TURNKEY PERCENTAGE QUOTING BASIS.”

CONTRACT DATA

Items marked "N/A" do not apply in this Contract.                           Reference

The following documents are also part of the Contract:                         clause of CC

- The Schedule of Operating and Maintenance Manuals (Clause - 48)

- The Methodology and Program of Construction (Clause - 25)

- Site Investigation Reports (Clause - 14)

- The Schedule of Key and Critical Equipment to be deployed on the work as per agreed program of construction (Clause - 25)

- Tender Inviting Authority:

Name & Address         :   Office of the Chief General Manager, Ele

Procurement, 2nd Floor, Block II

Corporate Office, KR Circle

Bengaluru- 560001

- The name and identification number of the Contract:

Tender Enquiry No     BESCOM/2026-27/EL/WORK_INDENT1146

- The Works consist of:

“STRENGTHENING OF HT/LT NETWORK IN ELEPHANT HABITAT & ELEPHANT CORRIDORS BY CREATING SAFE CORRIDORS FOR ELEPHANTS AND OTHER WILDLIFE IN RAMANAGARA DIVISION OF RAMANAGARA CIRCLE OF BRAZ AREA OF BESCOM JURISDICTION FOR A PERIOD OF EIGHTEEN MONTHS ON TOTAL TURNKEY PERCENTAGE QUOTING BASIS.”

- Start Date:

The start date shall be the date of issue of Detailed Work Award for the item wise Rate contract.  (Refer clause 1.1 of CC of tender Document)

- Intended Completion Date:

5.1 The Contract is valid for a period of 18 months from the date issue of Detailed Work Award. (Refer clause 17, 26 of CC of tender Document)

- Site Possession Date:

The Site Possession Date is from the date of issue of detailed work award. (Refer clause 21 of CC of tender Document)

- Site Location:

The Site is located at: Ramanagara Divisional Jurisdiction.  (Refer clause 1.1 of CC of tender Document)

- Defect Liability Period :

The Defect Liability Period shall be Sixty (60) months for LT AB Cable & Covered Conductor and Twelve (12) months for all the materials under the scope of the contractor, as detailed in Clause 6 of the Special Conditions of Contract (SCC). (Refer clause 31 of CC of tender Document)

- Insurance requirement are as under :

|  | Type of Cover | Minimum cover for insurance |
| --- | --- | --- |
| (i) | Works and of plant and materials | The sum stated in the agreement plus 20% |
| (ii) | Loss or damage to equipment | Full replacement cost |
| (iii) | Loss or damage to property of the Third party | Full replacement cost |
| (iv) | Personnel injury or death insurance - For Third party | Rs.20 Lakhs to cover 4 persons @ Rs.5 lakh each |
|  | - For Contractor’s employees or labour | In accordance with the statutory requirements applicable to Karnataka |

(Refer clause 13 of CC of tender Document)

- Price Adjustment :

  - The Prices are variable only for AB Cable and Covered Conductor throughout the period of contract as per IEEMA formula and indices, as detailed in Clause 40 of Conditions of Contract. (Refer clause 40 of CC of tender Document)

- Penalty:

  - The Bidder shall clearly note that time is the essence of the Contract and the works specified under the contract shall be completed within the Period specified in Clause No.5 of Contract data. If the Contractor fails to successfully complete the Trial Operation in terms of the Contract, within the time fixed under the Contract or any extension thereof granted by the BESCOM by way of Amendment to the Notification of Award/Contract Agreement, the Contractor shall pay to the BESCOM, as Penalty. (Refer clause 41 of CC of tender Document)

  - The penalty for delay shall be ½ % per WEEK of the portion of the individual work award/order that is not completed for beneficial use within the time stipulated in the relevant clause of the Contract, subject to a maximum of 10% of the cost of the individual work award/order.

  - The total amount of Penalty for delay under the Contract shall be subject to a Maximum of Ten percent (10%) of the total Contract Price and BESCOM has every right to terminate the Contract without any liability if it crosses 10%.

  - In the event that the successful bidder fails to execute the works as per the approved program or the works progress at a slow pace, the Owner reserves the right to get the balance or part of the supplies/works executed through other agencies at the risk and cost of the Contractor. This is in addition to BESCOM’s right to recover any damages from the bidder and to blacklist the bidder.

- The Bank guarantee/ Electronic Bank Guarantee (e-BG) should be in favour of Chief General Manager, Procurement, BESCOM. (Refer clause 42 of CC of tender Document)

Chief General Manager (Ele)

Procurement, BESCOM