## TITLE
Karnataka Power Transmission Corporation Limited
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
TECHNO - COMMERCIAL SHEETS
NOTE
BIDDERS TO READ CAREFULLY
IN ADDITION TO UPLOADING ON TO THE WEBSITE, ORIGINALS OF FOLLOWING DOCUMENTS [ DULY SIGNED BY AUTHORISED PERSON, WHEREVER NECESSARY] ARE TO BE SENT TO CHIEF ENGINEER, ELECTY, TRANSMISSION ZONE,BANGALORE SO AS TO REACH AFTER THE LAST SUBMISSION DATE AND ON OR BEFORE THE DATE AND TIME OF OPENING OF TECHNO COMMERCIAL BIDS. IF NOT RECEIVED, THE TECHNO-COMMERCIAL BIDS WILL NOT BE OPENED. 1) NO DEVIATION CERTIFICATE(SCHEDULE-16). 2) BANK GUARANTEE (IF APPLICABLE). 3) LETTER OF UNDERTAKING (SCHEDULE-18) 4) CONSORTIUM AGREEMENT (IF APPLICABLE-SCHEDULE-19). 5) POWER OF ATTORNEY (SCHEDULE-20) 6) ANY OTHER AGREEMENTS/ UNDERTAKINGS SPECIFIED IN THE TENDER.

## BPS
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
BID PROPOSAL SHEET
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bidder's Name & Address alongwith GSTIN no. :
Bid Proposal Reference :
Person to be contacted :
Designation :
Telephone No:
E-Mail Address:
Telex / Cable
Fax
To,
The Chief Engineer Electy.,
Transmission (Operations) Zone
KPTCL, Tumakuru
Dear Sir,
| Sub : | Proposal
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
a) | * We have submitted bid as individual Bidder. (Indicate Name of the Individual Bidder)
b) | * We have submitted bid in Consortium with the following Bidders. (Key in Consortium) |  | VOID
| Name of the Consortium Partner |  | Scope / Participation of each Consortium Partner
i) | VOID |  | VOID
ii) | VOID |  | VOID
(* Fill-up whichever is applicable)
1 | We, the undersigned Bidder, having read and examined in detail the specifications and all the Bidding documents of the said work and hereby propose to design, manufacture/fabricate, shop test, supply on FOR site basis, and carry out the erection, testing and commissioning including civil, structural and architectural works for
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
2 | PRICES AND VALIDITY :
2.1 | We declare that the Prices stated in our Proposal are in accordance with subject Bid Documents (including Clause No.40 of "Conditions of Contract (CC)" & Clause No.12 of Instruction to Tenderers (ITT) of Bid Documents. We further declare that all Ex-works price/CIF components of Spares, Maintenance and Testing Equipments and other charges viz., Freight and Insurance, Type Test charges and other charges stated in our proposal shall be as per the Tender conditions. All the Price and other terms and conditions of this Proposal are valid during the Performance of the Contract.
2.2 | All Duties, such as Custom Duties on imports, Levies, Surcharge/Cess etc., if any applicable on the transaction excluding GST are included in the Bid Price and shall be to Our account and the Owner is not having any liability whatsoever on this account, whatever may be the contrary elsewhere in the Bid documents. However the component of Duties included in the Bid Price are separately indicated in Schedule - 2 for TDS purpose. We further confirm that our Bid Prices as quoted in Schedule-I, include all import Duties and levies including Licence fees lawfully payable by us on imported items and all other Duties and Levies applicable on Bought-out Components, Materials, Equipment and other items and confirm that any such Duties and Levies additionally payable shall be to our account. We further confirm that, no Sales Tax in any form shall be payable by Owner either for Bought-out items which are despatched by our Sub-Suppliers directly to the Project Site or for items Supplied directly by us. We confirm that, the Prices quoted by us are excluding GST.
2.3 | We declare that we have noted and considered Clause No.39 of Conditions of Contract (CC ), Clause No. 11.11 of Instruction to Tenderers(ITT) of Bid Documents regarding Taxes and Duties and quoted our Prices accordingly. We further agree for TDS as per Statutory stipulations.
2.4 | The Bid Prices, the Price components of the various items in our Scope of Supply, Erection including Testing & Commisisoning, Civil and Mandatory spares is quoted in Itemwise Financial Bid in e-Procurement Portal for this proposal..
3 | CONSTRUCTION OF THE CONTRACT : We, declare that we are making the Offer on the basis of Single Contract for the entire Scope of the Package in accordance with Clause No.26.2 of Instruction to Tenderers (ITT) of Bid Document.
4 | We having studied Clause No.39 of Conditions of Contract (CC ), Clause No. 11.11 of Instruction to Tenderers(ITT) of Bid Documents , relating to Tax and we hereby, declare that if any income-tax, surcharge on income tax or any other corporate tax is attracted under the law, we agree to pay the same.
5 | Bids shall be accompanied by bid security/ Guarantee (EMD) of Rs.(Rs. 30,000/-) Which shall be paid through e-payment mode of KPPP. Any other form of payment will not be accepted. Permanent EMD Holders are also not exempted from paying of the above EMD. Tender Processing Fee: Tender processing fee as prescribed by KPPP portal shall be paid through e-payment mode of KPP portal. Any other form of payment will not be accepted.. (Mode of Payment towards EMD is as detailed in CLAUSE NO. 13 of ITT & Clause No. 5 of NIT)
We have also ensured that the above Bid Guarantee furnished by us is in line with the Bid Documents and complete in respect of following :
1. Value of Non judicial Stamp Paper purchased in the name of executing Bank is as per Stamp Act.
2. Power of Attorney Number and Date as well as Signature and Full Name and Designation of Executant along with Bank's Stamp are there.
3. Signature, Full Name, Designation and address of Witness are there.
4. Completed Mailing address of the Head Office of the Bank is indicated.
6 | Deviations :
6.1 | We declare that the Works shall be performed strictly in accordance with the Specifications and Documents except for the variations and Deviations, all of which have been detailed out exhaustively in the following Schedules, irrespective of whatever has been stated to the contrary anywhere else in our Proposal.
a | Commercial Deviations Schedule |  | Schedule - 5
b | Technical Deviations Schedule |  | Schedule - 6
6.2 | We further confirm that Specified Stipulation of following Clauses are acceptable to us and No Deviation / Exceptions are taken on any account whatsoever in the following Clauses.
a. | Terms of payment | Clause No. 37 of Section-5,Conditions of Contract (CC) and Clause No.8 of Special Conditions of Contrac (SCC)
b. | EMD/Bid Security | Clause No. 6, Section :1, Invitation for Tenders (IFT) and Clause No. 13, Section :2, Instruction to Tenderer (ITT)
c. | Contract Performance Guarantee | Clause No. 29 of Section:2, Instruction to Tenderers (ITT).
d. | Penalty for delay | Clause No. 41 of Section-5 : Conditions of Contract (CC).
e. | Price Basis/ Price adjustment | Clause No. 40 of Section-5 :Conditions of Contract (CC).
f. | Defects Liability Period/Guarantee | Clause No. 10 of Section-5 Special Conditions of Contract (SCC)
g. | Work Schedule | Clause No.17 of Section:5 Conditions of Contract (CC)
h. | Taxes and Duties | Clause No. 11.11 of Section-2: Instruction to Tenderers (ITT).
Further, we agree that additional conditions, if any, found in the Proposal Documents other than those stated in Deviation Schedules, save that pertaining to any rebates offered, shall not be given effect to.
7 | PERFORMANCE GUARANTEE ; We declare that the ratings and performance figures of the equipment to be supplied and erected by us are guaranteed. The Guaranteed particulas of different equiment in our Scope are enclosed in Data Requirement Sheets.
8 | BID PRICING : We further, declare that the Prices stated in our Proposal are in accordance with your ITT & SCC & all other relevant clauses of Bid Documents.
9 | PRICE ADJUSTMENT : We declare that the Prices quoted by us are in accordance Clause No. 40 of Section-5 :Conditions of Contract (CC)
10 | SPECIAL TOOLS AND TACKLES : We have given a list of Special Tools and Tackles in Schedule - 7 and Prices thereof are included in our lumpsum Bid Price. We further agree that any items of Special Tools and Tackles, though not included in the aforesaid list, but required for effective Erection, Testing, Commissioning & Operation of the Equipments of Substations & Transmission lines shall also be furnished by us, at no extra cost to you.
11 | ADDITIONAL INFORMATION : In addition to the information called for in these Proposal Sheets, we have included with this Proposal, additional information as listed in Schedule - 8. We further confirm that such additional information does not imply any additional deviation beyond those covered in Schedule - 5 & 6 and in case of any contraction between these additional information and other provisions of Bid, the later will prevail.
12 | QUALIFICATION DATA : We confirm having submitted the Qualification Data, as required by you in your Bid Documents in e-Procurement Portal along with this Proposal. Further we have filled in the information for Qualification Requirements in Schedule 9. In case you require any further information in this regard, We agree to furnish the same in time.
13 | WORK SCHEDULE : If this Proposal is accepted by you, we agree to submit Engineering Data, Provide Services and complete the entire Work from time to time, in accordance with Schedules indicated in the Proposal. We fully understand that the Time Schedule stipulated in this Proposal is the essence of the Contract, if awarded. The completion schedule of the various Major Key Phases of the Work is indicated in Schedule - 11.
14 | CONTRACT PERFORMANCE GUARANTEE ; We further agree that if our Proposal is accepted, we shall provide an irrecoverable Contract Performance Guarantee, of value equivalent to Five percent (5%) of the Amount Put to Tender (Excluding GST) plus additional security for unbalanced tenders in accordance with Clause 29 of Instructions To Tenderers (ITT) of the tender valid up to the end of ninety (90) days after the end of the Contract Guarantee Period mandatorily in the form of electronic Bank Guarantee (e-BG) from the Banks which are integrated with NeSL in the form attached as Annexure-III (Section 4: Formats of Annexures) in your favour in accordance with Clause 25.5 of ITT and Clause 43 of the CC (Conditions of Contract), as per the format given in Section 4 and enter into a formal agreement with you within Twenty (20) days from the date of issue of Letter of Intent to Award the Contract.
15 | VOID
16 | BID PRICE : We declare that our lumpsum Price for the entire scope of work specified in the specifications and documents, shall be as indicated in Schedule - 1.
17 | CHECK LIST : We have included a Checklist duly filled in Schedule 22
18 | We, hereby, declare that only the Persons or Firms interested in this Proposal are named herein as Principals and that no other Persons are interested in the Proposal or in the Contract to be entered into, if we are awarded the Contract, and that this proposal is made without any connection with any other Person, Firm or Party likewise submitting a Proposal and that this Proposal is in all respect for and in good faith, without collusion or fraud.
19 | We declare, in case our bid is accepted, that until a formal Contract is prepared & executed, this bid together with your written letter of acceptance thereof and your notification of award /Letter of Intent to Award the Contract shall constitute a binding contract between us. We further understand that you are not bound to accept the lowest or any bid you may receive.
Dated this …………………...…………………...………….day of………...……………………………20...
Thanking you, we remain,
Yours faithfully,
| Date |  | Signature
| Place |  | Printed Name
Designation
Common Seal
| Business Address |  |  | Country of Incorporation (State or Province to be indicated)
Name and Address Principal Officer

## Sch-1
Karnataka Power Transmission Corporation Limited
SCHEDULE - 1
SHEET FOR TECHNO COMMERCIAL OPENING (Unpriced)
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
FILL ONLY IN LIGHT BLUE COLOURED CELLS.
Name of work
Bidder's Name & Address alongwith GSTIN no. : |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Dear Sir,
We declare that in terms of Clause No. 11 of ITT, Bid documents, the following are our lumpsum price in Rupees for the entire scope of work as specified in the Specifications and Documents.( Inclusive of all Taxes (Excluding GST) & Duties).
Total Lumpsum Price : ( In Figures) Note: Fill as "YES" against this column in case Prices are indicated in the Item-Wise Bid Financial Offer in figures
| Date | Name
| Place | Designation
Name of the Company

## Sch-2 (2 of 2)
Karnataka Power Transmission Corporation Limited
SCHEDULE - 2 ( 2 of 2 ) - TAXES(Excluding GST), DUTIES & OTHER LEVIES
SHEET FOR TECHNO COMMERCIAL OPENING (Unpriced)
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Fill IN LIGHT BLUE COLOURED CELLS.
(Name of work)
Bidder's Name & Address alongwith GSTIN no. : |  |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Estimates of Indian Taxes (Excluding GST), Duties and Levies included in the Total Bid Price are as follows:
SL. No. | Description of Applicable Tax (Excluding GST) / Duty / Levy
|  | Rate of Tax (Excluding GST)/ Duty / Levy | Amount of Taxes (Excluding GST) / Duties in Rupees | Rate of Tax (Excluding GST) / Duty / Levy | Amount of Taxes (Excluding GST)/ Duties in Rupees
1 | SGST/UTGST | Applicable taxes (Excluding GST), duties & levies prevailing as on the last date of bid submission shall be quoted
i. Supply Portion
ii. Erection Portion
iii. Civil Portion
2 | CGST
i. Supply Portion
ii. Erection Portion
iii. Civil Portion
3 | IGST
i. Supply Portion
ii. Erection Portion
iii. Civil Portion
6 | Building and other construction workers welfare Cess for Supply, Erection and Civil Portion works
7 | Other Levies
8 | a. Applicable Customs Duty (*) (Bidders shall also clearly indicate the breakup of Customs duty such as BCD, Cess,etc.,)
b. If there is any existing Treaty between India and the country from where the goods required for this project are proposed to be imported, then copy of the treaty shall be uploaded.
9 | Other Taxes & duties if any (Specify) **
10 | Other Taxes & duties if any (Specify) **
11 | Total (Sum of 1 to 10)
(*) | In case of CIF portion of Supply.
** | Please Specify the nature of the other Taxes (Excluding GST) along with the details in the "Rate" Column.
Date |  |  | Name
Place |  |  | Designation
Name of the Company
Note on C21: Author: Applicable Taxes, Duties & levies as on the Date of Bid Submission shall be quoted in 'item-wise Bid Financial Offer'

## Sch-2A
Karnataka Power Transmission Corporation Limited
SCHEDULE - 2A : SCHEDULE OF DISCOUNT
SHEET FOR TECHNOCOMMERCIAL OPENING (UN - PRICED)
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
FILL ONLY IN LIGHT BLUE COLOURED CELLS.
Bidder's Name & Address alongwith GSTIN no. : |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
We hereby offer an unconditional discount on our quoted price in Schedule 2 (1 of2) as under. Any discounts offered anywere else in Bid shall not be considered.
Sl.No | Nature of Discount
|  | Percentage of discount | Amount (in Rs.) (Fill in as 'YES' in case Prices are indicated in the Item-Wise Bid Financial Offer) | Remarks
I | Supply Schedules a) Ex-works prices
b) Freight & Insurance (Not Applicable)
II | Erection Schedules
III | Civil Works Schedules
| Date | Name
| Place | Designation
Name of the Company

## Sch-2B
Karnataka Power Transmission Corporation Limited
SCHEDULE- 2 B - STATEMENT OF COMMERCIAL TERMS AND CONDITIONS
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Details of payments made in the form of Credit card/Debit card/NEFT/RTGS/OTC (over the counter) as per the tender conditions should be keyed in against column no. 3 (a) . BG Amount, BG No. and date, Name and address of the bank issuing the BG, validity of the BG should be keyed in against column no. 3 (b) .
FILL ONLY IN LIGHT BLUE COLOURED CELLS.
Bidder's Name & Address alongwith GSTIN no. : |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
STATEMENT OF COMMERCIAL TERMS AND CONDITIONS
| Sl. No. | Particulars | Details
| 1 | 2 | 3
| 1 | Bid proposal form Uploaded.
| 2 | No deviation certificate Uploaded.
| 3. a). | EMD / Bid Security Bids shall be accompanied by bid security (EMD); 1) Rs.30,000 /- The following modes of payment will be provided as a part of e-Payment services. • Credit Card/Debit Card • Net Banking • NEFT/RTGS • Over-the-Counter (OTC) • IMPS For further detail regarding mode of e-payment of EMD in e-procurement platform, contact e-procurement cell, Government of Karnataka.
| b). | EMD amount above Rs.10Lakh by Bank Guarantee
| 4 | Validity of the Bid.
| 5 | Qualifying Requirements.
| 6 | Financial capability
| 7 | Price Basis.
| 8 | Taxes & Duties.
| 9 | Completion Schedule
| 10 | Defects Liability Period/Guarantee
| 11 | Payment Terms
Date |  | Name
Place |  | Designation
Name of the Company

## Sch-3A(i)-Stn-Sup
Karnataka Power Transmission Corporation Limited
SCHEDULE - 3A(i) - Price Breakup for - Supply portion
SHEET FOR TECHNO COMMERCIAL OPENING (Unpriced)
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bidder's Name & Address alongwith GSTIN no. :
To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
BIDDERS SHALL FILL ONLY IN THE LIGHT BLUE COLOURED CELLS.
Supply portion :
| SUPPLY PORTION: |  | Unit | Quantity | Indicate whether "Own manufactured Iem" or "Bought Out Item" | Indicate country of Origin
| Sl No. | Name of the Equipment/Materials
| 1 | 2 | 3 | 4 | 5 | 6
Power Transformer
| A1 | Power Transformer
| 1 | 20 MVA, 66/11kV, Delta/Star, Vector Group Dyn11, 3-Ph, 50Hz, Core Type, 2 Winding Delta/Star transformer, vector group DYn11 with OLTC ONAN/ONAF with fan control cubicle, RTCC Panel, Numerical RTCC panel, first filling of Oil and 10% spare oil in non-returnable drums etc., complete with Terminal connectors suitable for Single Drake ACSR on primary side of Transformer and copper flats on 11kV side and on neutral side as per specifications. | Nos | 2 | KPTCL Supply
| A2 | Nitrogen Injection Fire Extinguishing System (NIFPS) |  |  | KPTCL Supply
| 1 | Supplying, erection & including civil Engineering works, soak pit etc, as per the recommendation of the supplier of the fire lighting system for power transformer below 100MVA | Nos | 2
| A3 | CURRENT TRANSFORMER: Current transformers including marshalling boxes. Single phase, oil filled outdoor type with rigid bimetallic terminal connectors suitable for Drake ACSR conductor
| 1 | 11 KV CT: with Ratio1200-800/1-1-1A | Nos | 6
| 2 | 11 KV class, 25kA, NCT of Ratio 1200-800/1-1-1A for REFR protection (similar rating as that of incomer of 11kV switchgear ) with terminal connector suitable for 2 No's of 50x8 mm copper flats | Nos | 2
Note:- 1)All the CTs in each kV class shall be of one and the same make for interchangeability & reliability of performance. 2)The make and characteristics of 11kV NCT should be the same as that of the incomer CT of 11kV switchgear. To ensure this, the 11kV NCT should be procured from the supplier of 11kV switchgear only.
| A4 | Isolator:
Isolators including Marshalling Box and suitable terminal connectors, as per technical specification with solid core, cylindrical post insulators
| 1 | 11kV isolator Double break 1200 A, 25 KA capacity with rigid bi-metalic terminal connector suitable for Drake ACSR (Bank-2Set & Bus Coupler-1Set) | Set | 3
| A5 | 1.1KV class PVC Insulated Copper Control Cable with lugs/ferrules/glands as per technical specification:
| 1 | 19c x 2.5 sqmm | Mtrs | 750
| 2 | 2c x 2.5 sqmm | Mtrs | 280
| 3 | 2c x 6 sqmm | Mtrs | 190
| 4 | 4c x 6sqmm | Mtrs | 1055
| 5 | 4c x 2.5 sqmm | Mtrs | 150
| A6 | Conductor
| 1 | Drake ACSR | Mtrs | 320
| A7 | Hardwares
| 1 | CT clamp for Drake ACSR | Nos | 18
| 2 | Pad clamps for Drake ACSR | Nos | 8
| 3 | NCT Pad Clamps | Nos | 6
| 4 | Bolted Type Suspension Clamp suitable for Single Drake ACSR Conductor | Nos | 6
| 5 | Post insulator clamps suitable for Single Drake ACSR Conductor | Nos | 12
| NOTE | 1. Any clarifications / hard copy of drawings can be obtained from the office of the Chief Engineer Electy, Transmission(Operations), KPTCL, Tumakuru
2. Spacers shall be provided wherever necessary and no extra charges is payable on account of the same.
3. Supply of equipment/materials and the Erection charges shall include loading and unloading.
4. Copper Flat and GI Flat required for Power Transformers (if supply is in Bidder's scope) shall be supplied alongwith the Transformers and no extra cost is payable on this account.
5. The Bidder shall take necessary action to ensure that all the materials supplied shall be properly housed to ensure satisfactory commissioning.
7. Released materials shall be transported to the nearest Major Works Store of KPTCL without any additional cost as per the directions of the Engineer in charge of the work.
8. The Bidder shall clearly indicate whether the materials/equipments are “Own manufactured” or “Bought out item”.
Date |  |  |  | Name
Place |  |  |  | Designation
Name of Company

## Sch-3A(ii)-Stn-Ere
Karnataka Power Transmission Corporation Limited
SCHEDULE - 3A(ii) - Price Breakup for - ERECTION PORTION INCLUDING TESTING & COMMISSIONING and DISMANTLING PORTION.
SHEET FOR TECHNO COMMERCIAL OPENING (Unpriced)
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bidder's Name & Address alongwith GSTIN no. :
To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
BIDDERS SHALL FILL ONLY IN THE LIGHT BLUE COLOURED CELLS.
ERECTION PORTION INCLUDING TESTING & COMMISSIONING and DISMANTLING PORTION:
| ERECTION PORTION INCLUDING TESTING & COMMISSIONING and DISMANTLING PORTION: |  |  | Quantity
| Sl No. | Name of the Equipment/Materials | Unit
| 1 | 2 | 3 | 4
| B1 | Erection of Power Transformer
| 1 | Moving of transformer to the plinth. Maximum allowable distance is 50Mtrs.(43MT*10.52481Mtr*1)=452.567 | MT/Mtr | 905.134
| 2 | Assembling of transformer parts like bushings,Radiators,filling oil in to transformer Etc,for the total wt of the transformer. (For 02 Transformers) | MT | 86
| 3 | Filtration of oil using filter set of the contractor, to bring the insulation value to I.E. specifications. (For 02 Transformers) | Ltrs | 25600
| 4 | Wiring of C&R panels:Identification, ferruling, crimping, termination of wires in C&R panels (without SAS) | Per Panel | 2
| 5 | Wiring of Transformer marshalling box, bucholtz relay, fixing thermometer, OLTC upto control panel and assisting in testing and commissioning by RT/MT/Firm Engineer | per transfor mer | 2
| 6 | Erection of control panel,auxilary panel, carrier cabinet,marshalling bay kiosk etc.,alignment and fixing properly to foundation base including movement from the point of unloading to the point of erection | Per Panel | 2
| B2 | ERECTION OF CT and NCT
| 1 | 11 KV CT with Ratio1200-800/1-1-1A Erection of CTs and wiring including movement from the point of unloading to the point of erection | NO | 6
| 2 | 11 KV NCT with Ratio1200-800/1-1-1A for REFR protection (similar rating as that of incomer of 11kV switchgear ) with terminal connector suitable for 2 No's of 50x8 mm copper flats Erection of NCTs including movement from the point of unloading to the point of erection with grounding connections | NO | 2
| B3 | Erection of GOS
|  | GOS: 11 kV GOS : D/B 1200 A Fixing of 11 kV GOS Double Break including wiring on old existing Structure With Suitable Drake Pad Clamps . (2 nos for bank and 1 no for Bus coupler) | Set | 3
| B4 | Laying of control cables from equipments to panels.
| 1 | 19c x 2.5 sqmm | Mtrs | 750
| 2 | 2c x 2.5 sqmm | Mtrs | 280 | Done by KPTCL Staff
| 3 | 2c x 6 sqmm | Mtrs | 190
| 4 | 4c x 6sqmm | Mtrs | 1055
| 5 | 4c x 2.5 sqmm | Mtrs | 150
| B5 | Earth Mat Formation :
| 1 | Grounding of equipment with 50X6 mm G.I flat and connecting Equipment to the earth mat/ground pit. Each point of earthling with all formation works like bending, twisting, drilling of holes and connecting by welding (inclusive of all T&P and consumables) to the earth mat/ground pit/ point of earth connection, all the materials supplied by the contractor | RMts. | 110
| 2 | Providing cast iron pipes of 100 mm ID ,13mm thickness,2.75 mts long with 2 part clamps out of GI flat 50 X 6 mm continuously welded around the pipe using cast iron welding electrodes as per drawing including cost of excavation ( all materials to be supplied by the contractor ). (Material +Labour). | set | 3
| 3 | Supplying & Providing 450mm dia 450mm height 1.5" to 2" thick Hume pipe collar (non pressure type) for earth pits including all lead and lifts etc., | No | 3
| B6 | Releasing and Re-erection:
| 1 | i)NCTs (11kV)(0.157 MT per structure)(Releasing and Re-erection) | No/MT | 2/0.157
| B7 | DE- COMMISSIONING
| 1 | Dismantling of 12.5 MVA, 66/11kV, Transformer along with RTCC panel with complete accessories complete with oil. | No/t | 1 Nos. / 37 MT
| 2 | Moving the released 12.5 MVA Transformer from the plinth to the loading point as per the directions of the site engineer. | t/Mtrs | 37/50
|  | Dismantling of 8 MVA, 66/11kV, Transformer along with RTCC panel with complete accessories complete with oil | No/t | 1 Nos. / 21MT
|  | Moving the released 8 MVA Transformer from the plinth to the loading point as per the directions of the site engineer. | t/Mtrs | 21/50
| 3 | 11KV CT 800-400/1-1-1A | Nos | 6
| 4 | 11kV class, 25KA, NCT | Nos | 2
| 5 | Releasing of 11kV 800A GOS | Set | 3
| A16 | PART C : TESTING AND COMMISSIONING PORTION
| 1 | 20 MVA, 66/11kV, Delta/Star, Vector Group Dyn11, 3-Ph, 50Hz, Core Type, 2 Winding Delta/Star transformer, vector group DYn11 with OLTC ONAN/ONAF with fan control cubicle, RTCC Panel, Numerical RTCC panel, first filling of Oil and 10% spare oil in non-returnable drums etc., complete with Terminal connectors suitable for Single Drake ACSR on primary side of Transformer and copper flats on 11kV side and on neutral side as per specifications.(39.1 MT) | No | 2
| 2 | 11KV CT:1200-800/1-1-1 | NO | 6
| 3 | 11 KV NCT with Ratio1200-800/1-1-1A for REFR protection (similar rating as that of incomer of 11kV switchgear ) with terminal connector suitable for 2 No's of 50x8 mm copper flats | NO | 2
1. Any clarifications / hard copy of drawings can be obtained from the office of the The Chief Engineer Electy., Operations Zone, KPTCL, Tumakuru
2. The Erection charges shall include transportaion to site, loading and unloading.
3. Released materials shall be transported to the nearest Major Works Store of KPTCL without any additional cost as per the directions of the Engineer in charge of the work.
| Date |  | Name
| Place |  | Designation
Name of the Company

## Sch-3C(i)-Stn-Civil
Karnataka Power Transmission Corporation Limited
SCHEDULE - 3C(i) - Price Breakup for - Station Civil Portion.
SHEET FOR TECHNO COMMERCIAL OPENING (Unpriced)
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bidder's Name & Address alongwith GSTIN no. :
To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
BIDDERS SHALL FILL ONLY IN THE LIGHT BLUE COLOURED CELLS.
CIVIL WORKS PORTION
| Sl. No. | Specifications | Unit | Quantity
| 1 | 2 | 3 | 4
| C1 | MODIFICATION OF POWER TRANSFORMER FOUNDATION (2 Nos.)
| 1 | Earth work excavation by manual means for drains, canals, waste weir, draft, approach channels, key trenches, foundation of Buildings & bridges and such simillar works in all kinds of soils, as per drawing and technical specifications, including setting out, shoring, strutting, barricading, caution lights, removal of stumps and other deleterious matter, excavated surface leveled and sides neatly dressed disposing off the excavated stuff or sorting & stacking the selected stuff for reuse in a radius of 50 m and lift upto 1.5 m including cost of labour, tools & other appurtenaces required to complete the work., In all kinds of soils Depth upto 1.5 m | Cum | 43.07
| 2 | Providing and laying in position Cement Concrete for levelling course for all works in foundation. The granite/trap/basalt crushed graded coarse aggregates and fine aggregates as per relevant IS Codes machine mixed, laid in layers not exceeding 150 mm thickness, well compacted using plate vibrators, including all lead & lifts, cost of all materials of quality, labour, Usage charges of machinery, curing, and all the other purtenances required to complete the work as per technical specifications. Mix 1:3:6 Using 20 mm nominal size graded crushed coarse aggregates | Cum | 3.42
| 3 | Providing and laying in position Cement Concrete for all Foundation works. The granite/trap/basalt crushed graded coarse aggregates and fine aggregates as per relevant IS Codes machine mixed with super plasticizers laid in finished layers, well compacted using needle vibrators, including all lead & lifts, cost of all materials, quality confirming to the requirements of relevant IS codes, labour, Usage charges of machinery, curing and all the other appurtenances required to complete the work as per technical specifications. M25 Design Mix Using 20 mm nominal size graded crushed coarse aggregates,( Footing ) including form work 3% | Cum | 25.84
| 4 | Providing and laying in position Cement Concrete for all Foundation works. The granite/trap/basalt crushed graded coarse aggregates and fine aggregates as per relevant IS Codes machine mixed with super plasticizers laid in finished layers, well compacted using needle vibrators, including all lead & lifts, cost of all materials, quality confirming to the requirements of relevant IS codes, labour, Usage charges of machinery, curing and all the other appurtenances required to complete the work as per technical specifications. M25 Design Mix Using 20 mm nominal size graded crushed coarse aggregates,(Footing) including form work 50%. | Cum | 2.44
| 5 | Providing and laying in position Cement Concrete for all Foundation works. The granite/trap/basalt crushed graded coarse aggregates and fine aggregates as per relevant IS Codes machine mixed with super plasticizers laid in finished layers, well compacted using needle vibrators, including all lead & lifts, cost of all materials, quality confirming to the requirements of relevant IS codes, labour, Usage charges of machinery, curing and all the other appurtenances required to complete the work as per technical specifications. M25 Design Mix Using 20 mm nominal size graded crushed coarse aggregates,(Footing) including form work 70%. | Cum | 2.79
| 6 | Supplying, fitting and placing TMT FE 550 / 550D Steel Reinforcement including cost of all materials, machinery, labour, cleaning, straightening, cutting, bending, hooking, laping/welding joints, tying with binding wire / soft annealed steel wire and other ancilary operations complete as per drawing andtechnical specification | Kgs | 1591.36
| 7 | Finishing walls with 100% Premium acrylic emulsion paint having VOC less than 50 g/L and UV resistance as per IS 15489:2004, Alkali & fungal resistance, dirt resistance exterior paint of required shade (Company Depot Tinted) with silicon additives, New work (Two coats applied @ 1.43 L/ 10 m². Over and including priming coat of exterior primer applied @ 0.90 L/10 m² with paint of approved quality to give an even shade, after thoroughly brooming the surface to remove all dirt, dust, mortar drops and foreign matter including preparing the surface even and sand paper smooth, cost of materials, labour complete as per specifications and as per directions of Engineer-in-charge. | sqm | 97.58
| 8 | Providing Brick work with common burnt clay modular bricks of class designation 3.5 in foundation and plinth in Cement mortar 1:6 (1 cement : 6 coarse sand) including cost of all materials, labour, scaffolding and usage charges of machinery & other incidental charges complete as per the direction of engineer incharge of work | Cum | 11.95
| 9 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundations and other similar works etc. in layers not exceeding 20cm in depth, consolidating each deposited layer by ramming and watering, lead up to 50 m and lift upto 1.5 m. | Cum | 1.555
| 10 | Providing and fixing Structural Steel work riveted, bolted or welded in built up sections, trusses and framed work, including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer all complete including cost of materials, labour, usage charges of machinery complete as per specifications and as per directions of the Engineer-in- Charge. | Kgs | 127.2
| 11 | Providing and fixing SFRC Frame and cover confirming to IS 12592(Part-I) -1988 and IS 112592 (Part-II)-1991 with latest ammendment incuding cutting slabs to required size for the opening and fixing the cover in CC 1:2:4 and size for the opening and fixing the cover in CC 1:2:4 and CM 1:3 plastering 20mm thick to all exposed faces, curing for 10 days with all lead and lift with appurtenances complete medium duty . | Set | 1
| 12 | Dismantling of existing structures like culverts, bridges, retaining walls and other structure comprising of masonry, cement concrete, wood work, steel work, including T&P and scaffolding wherever necessary, sorting the dismantled material, disposal of unserviceable material and stacking the serviceable material with all lifts and lead prestressed /reinforced cement grade M20 & Above. | Cum | 13.65
Note:
1) The land will be handed over " As is where is condition".
| Date |  | Name
| Place |  | Designation
Name of the Company

## Sch-5-COMM
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE-5 COMMERCIAL DEVIATION
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Please fill Only in the Light Blue Couloured Cell.
Please key in the SlNo.,Section , Clause , Description as given in bid sheets and finally your Statement of Deviation/Variations.
This Sheet would be opened at the Techno-Commercial Opening. Please refer Vendor Manual attached for further details.
For any further assistance for submitting your bids please call up KPTCL Office.
We agree to provide all original Documents in support of the information provided for verification upon request. (Key in as YES in the space provided)
We understand that the electonic bid submitted by us is a valid offer in accordance with IT Act. (Key in as YES in the space provided)
We are fully aware of the electronic bid formalities and abide by the same. (Key in as YES in the space provided)
If you are not deviating from any of the clauses mentioned please key in as 'NO DEVIATION' in the space provided.
Bidder's Name & Address alongwith GSTIN no. : |  |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Dear Sir,
I/we have read each of the Clauses mentioned in INVITATION FOR TENDERS , INSTRUCTION TO TENDERERS , CONDITIONS OF CONTRACT, SPECIAL CONDITIONS OF CONTRACT and COMMERCIAL TERMS AND CONDITIONS and all the sections of Bid documents.
The following are the commercial Deviations and Variations from and exceptions to the Specifications and documents for
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
These deviations and variations are exhaustive. Except these deviations, the entire work shall be performed as per your specifications and documents.
Sl. NO. | SECTION | CLAUSE NO. | DESC. AS PER SPECIFICATION | STATEMENT OF DEVIATIONS/VARIATIONS
Note : Deviations specified elsewhere in the specification will not be considered.
Date |  |  | Name
Place |  |  | Designation
Name of the company

## Sch-6-TECH
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE-6 : TECHNICAL DEVIATION
SHEET FOR TECHNO-COMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Please key in the SlNo., Section , Clause , Description as given in Bid sheets and finally your Statement of Deviation/Variations.
This Sheet would be opened at the Techno-Commercial Opening.
For any further assistance for submitting your bids please call up KPTCL office. Please fill only in the blue coloured cells.
We agree to provide all original Documents in support of the information provided for verification upon request. (Key in as YES in the space provided)
We understand that the electonic bid submitted by us is a valid offer in accordance with IT Act. (Key in as YES in the space provided)
We are fully aware of the electronic bid formalities and abide by the same. (Key in as YES in the space provided)
If you are not deviating from any of the clauses mentioned please key in as 'NO DEVIATION' in the space provided.
Bidder's Name & Address alongwith GSTIN no. : |  |  | TO,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Dear Sir,
The following are the Technical Deviations and Variations from and exceptions to the Specifications and documents for
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
These deviations and variations are exhaustive.Except these deiviations and variations, the entire work shall be performed as per your specification and documents.
Sl. NO. | SECTION | CLAUSE NO. | DESC. AS PER SPECIFICATION | STATEMENT OF DEVIATIONS/VARIATIONS
Note : Deviations specified elsewhere in the specification will not be considered.
Date |  | Name
Place |  | Designation
Name of the company

## Sch-7
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE 7(List of special tools and tackles )
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bidder's Name & Address alongwith GSTIN no. : |  |  | TO,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
List of special tools and tackles the price of which is included in bid price.
Sl. No. | For equipment | Description of item | Unit | Quantity
Date |  |  | Name
Place |  |  | Designation
Name of the Company

## Sch-8
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE 8
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
NOTE: 1 ) SHALL BE UPLOADED WITHOUT PRICES
Bidder's Name & Address alongwith GSTIN no. : |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
We have uploaded with our proposal the following additional information.
Sl. No. | Brief Description of information | Ref. and Page No.
Date |  | Name
Place |  | Designation
Company seal

## Sch-9(1 of 5)
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE - 9 (1 of 5) : QUALIFYING REQUIREMENTS
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
| BIDDER'S NAME AND ADDRESS: | [6 empty] | TO,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Dear Sir,
a) | * We have submitted bid as individual Bidder. (Key in Individual Bidder )
b) | * We have submitted bid in Consortium with the following Bidders. (Key in Consortium ) |  |  |  | VOID
| Name of Consortium Partner |  |  |  | Scope / Participation of each Consortium Partner
i) | VOID |  |  |  | VOID
ii) | VOID |  |  |  | VOID
(* Fill-up whichever is applicable)
1 | GENERAL INFORMATION
The Bidder, bidding for this package are requested to complete the information in the following form.
Sl. No. | Particulars | Bidder Details
1 | Name of the Firm
2 | Address of Head Office / Registered Office GST no.
3 | Telephone
4 | Fax
5 | Name of Contact person with Designation
6 | Place of Incorporation/Registration
7 | Year of Incorporation/Registration
8 | Constitution or legal status of Tenderer [Upload copy]
9 | Place of Registration [Upload copy]
10 | Principal place of business
2 | We are furnishing the following details/documents in support of Qualifying requirement for above mentioned project
Sl.No. | Bidder Details | Indicate Yes/No | In case of Consortium -VOID
(a) | Written power of attorney of the signatory on the bid to commit the bidder.
1 | Uploaded / Not
(b) | Certificate of Registration of the Company. Please mention the date of incorporation of the company
1 | Uploaded / Not
(c ) | Valid Super Grade Electrical Contractor’s License issued by the Government of Karnataka as on the date of techno commercial Bid opening. Please mention the date of expiry of the License certificate issued by GOK/ Undertaking to this effect
1 | Uploaded / Not
(d) | Self declaration regarding Litigation w.r.t KPTCL contracts over the last five years (refer IFT)
1 | Uploaded / Not
(e) | Self declaration for ‘not being disqualified regarding non-performance in any of the Government utilities in the past five years’. (refer IFT)
1 | Uploaded / Not
(f) | An undertaking to source the supply of equipment/ material from KPTCL approved vendors only as per QR for Vendor registration, available in the KPTCL website ie., kptcl.karnataka.gov.in, Link Tender and Procurement-Application for Vendor.
1 | Uploaded / Not
(g) | Self declaration regarding no action against the bidder have been taken by KPTCL in respect of Risk & Cost clause
1 | Uploaded / Not
(h) | Self declaration regarding 'Eligibility clauses in respect of restrictions on procurement from a bidder of a country which shares a land border with India as per Annexure-XVI
1 | Uploaded / Not
(i) | Self declaration regarding RESTRICTIONS ON SOURCING OF EQUIPMENTS/MATERIALS BY THE BIDDER FROM A VENDOR OF A COUNTRY WHICH SHARES A LAND BORDER WITH INDIA as per Annexure -XVII
1 | Uploaded / Not
Section 3 : 1.3 Work performed of similar nature in the last Ten years of Bidder as per Clause No: 3.2 (b) (i) of ITT
Project Name | Name & Address of the Employer | Description of Work | Voltage class | Number of Sub-Stations/TBs/Length of the Line | Contract Number | Value of contract Rs. Lakh | Date of issue of work order | Specified period of completion | Actual date of commissioning | Remarks explaining reasons for delay in commisioning of work
1 | 2 | 3a | 3b | 3C | 4 | 5 | 6 | 7 | 8 | 9
Name of Bidder
Note : 1 . The documentary proof of fulfilling the qualifying requirements shall be uploaded along with the bid. The bidder shall upload the P.O,LOI/LOA, DWA, Work done, Performance Certificates issued by the end users not below the rank of Executive/ Divisional Engineer along with the bid.
2. The qualifying experience of the Bidder who is having qualifying experience shall be furnished in the above performa and Documentary Proof in support of above shall be uploaded in the form of certificates issued by authorized officers of concerned organisations.
3. IF this sheet is insufficient for furnishing the qualifying experience of the Bidder then similar sheets shall be seperately uploaded.
| Date | [5 empty] | Name
| Place | [5 empty] | Designation
Name of the Company

## Sch-9 (2 of 5)
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE - 9 (2 of 5) : QUALIFYING REQUIREMENTS
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
| BIDDER'S NAME AND ADDRESS: |  |  |  | TO,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Section 3 : 1.5 Information on works for which Tenders have been submitted and works which are yet to be completed as on the date of this Tender of a Bidder
(A) Existing commitments and on-going works:
Description of work | Place & State | Contract No & Date | Name and Address of Employer | Value of contract (Rs. Lakh) | Stipulated period of cof Completion | Value of works remaining to be completed ( Rs.Lakhs) (Attach Certificates from Engineers –in- Charge) |  |  | Anticipated date of commissioning
[6 empty] | Ex-Works | GST | Total(Ex-works+GST)
1 | 2 | 3 | 4 | 5 | 6 | 7a | 7b | 7c=7a+7b | 8
Name of Bidder
Note:Attach Certificates from Engineers –in- Charge
B)Works for which Tenders already submitted
Description of work | Place & State | Name and Address of Employer | Estimated value of works (Rs. Lakh) |  |  | Stipulated period of Completion | Date when decision is expected | Remarks if any
|  |  | Ex-works | GST | Total(Ex-works+GST)
1 | 2 | 3 | 4a | 4b | 4c=4a+4b | 5 | 6 | 7
Note:
i) The statements showing the value of existing commitments and on-going works as well as the stipulated period of completion remaining for each of the works listed should be countersigned by the Employer in charge, not below the rank of an Executive Engineer or equivalent. OR The statements showing the value of existing commitments and on-going works as well as the stipulated period of completion remaining for each of the works listed should be verified and certified by Chartered Accountant/ Cost Auditor. However, the Bidder has to upload the PO/Work Award copies for existing commitments and on-going works
ii) A self-declaration is to be uploaded by the bidder stating that "the information with regard to assessed available tender capacity (Works on Hand) furnished are correct”.
iii. Bidders shall furnish Certificate from Chartered Accountants for split details of Ex-works values and GST of Contract values of the works in the prescribed format as at Clause No. 1.5 of Section-3: Qualification Information
Date |  |  |  | Name
Place |  |  |  | Designation
Name of the Company

## Sch-9(3 of 5)
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE - 9 (3 of 5) : QUALIFYING REQUIREMENTS
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
| BIDDER'S NAME AND ADDRESS: | [5 empty] | TO,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Following is the list of major supplied subsation equipments/accessories which are type tested and designed, manufactured by us in accordance with internationally recognised standards.
Sl. No. | Item rating, type and Designation | Qty | Customer | Date of Order | Date of Supply | Date of Commissioning | Ref. of Cusomer's certificate of successful operation enclosed | Ref. of layout & Customer's certificae for successful commission
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Note: Documentary Proof in support of above shall be uploaded in the form of certificates issued by authorized officers of concerned organisations. .
Date |  |  | Name
Place |  |  | Designation
Name of the Company

## Sch-9(4 of 5)
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE - 9 (4 of 5) : QUALIFYING REQUIREMENTS
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bidder's Name & Address alongwith GSTIN no. : | [6 empty] | To
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Section 3 : 1.7 Reports on the financial standing of the tenderer, such as Profit and Loss Statements and Auditor’s reports in the preceeding last five years, Audited Financial statements i.e Balance sheets, P&L statements, Turnover certificates duly certified by chartered Accountant as documentary evidence shall be uploaded.
SLNo. | Particulars | Year | Bidder |  |  |  | Consortium Member - VOID
|  |  | Mention Year | Turnover excluding GST (in Rs.) | GST Amount (in case GST is included in Turnover) (in Rs.) | Turnover including GST (in Rs.) | Mention Year | Turnover excluding GST (in Rs.) | GST Amount (in case GST is included in Turnover) (in Rs.) | Turnover including GST (in Rs.)
| Names of the constituent Firm | [5 empty] | VOID
1 | Annual turn over for the last Five years | Year(1) | 2020-21 |  |  |  | 2020-21
|  | Year(2) | 2021-22 |  |  |  | 2021-22
|  | Year(3) | 2022-23 |  |  |  | 2022-23
|  | Year(4) | 2023-24 |  |  |  | 2023-24
|  | Year(5) | 2024-25 |  |  |  | 2024-25
2 | Liquid Assets / Credit availability or access to evidence of assets
3 | Whether Audited Balance sheets and Profit & Loss statement are enclosed for the last Five Years ? (yes/No)
4 | Whether Bankers certificate enclosed for credit facilities? (Yes/No)
Date |  |  | Name
Place |  |  | Designation
Name of the Company
.
. .

## Sch-9(5 of 5)
Karnataka Power Transmission Corporation Limited
SCHEDULE - 9 (5 of 5) : QUALIFYING REQUIREMENTS
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
|  | BIDDER'S NAME AND ADDRESS: |  |  | TO,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
The information to be filled in by the Tenderer hereunder will be used for purposes of computing Tender capacity as provided for in Clause 3 of the Instructions to Tenderers. This information will not be incorporated in the Contract.
1.1 |  | Constitution or legal status of Tenderer [Upload copy]
Place of Registration [Upload copy]
Principal place of business
Section - 3: 1.2 Total value of works executed (KPTCL & NON KPTCL works) and payments received in the last Five years (in Rs. Lakhs)
1.2 | Total value of works executed (KPTCL & NON KPTCL works) and payments received in the last five years (in Rs. Lakhs) of Bidder | Financial Year | Details
|  |  | KPTCL works | Non KPTCL works
|  |  | Total value of works in Rs. Lakh | Total value of works in Rs. Lakh
2020-21
2021-22
2022-23
2023-24
2024-25
Note: Attach relevant Certificate/s from Chartered Accountant.
Section 3: 1.9 Name, address, telephone number & e-mail id of the Tenderers' bankers who may provide references if contacted by the Employer:
1.9 |  | Sl.No |  | Name, address, telephone number & e-mail id of the Tenderers' bankers
1
|  | 2 | 2
|  | 3 | 3
|  | 4 | 4
|  | 5 | 5
|  | 6 | 6
|  | 7 | 7
|  | 8 | 8
Section 3: 1.12 Information on litigations in which the Tenderer is involved:
Other Party(ies) |  | Employer |  | Details of Dispute | Amount involved | Remarks showing Present Status
1 |  | 2 |  | 3 | 4 | 5
Date |  |  |  | Name
Place |  |  |  | Designation
Name of the Company

## Sch-10(1 of 3)
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE-10 (1 of 3) Details of Tools and Plants available
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
BIDDER'S NAME AND ADDRESS: |  |  |  |  | To
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Following are the details of the Tools and Plants available with us.
Sl. No. | Description | Quantity | Make | Present Location / Project | Remarks (if any)
1 | 2 | 3 | 4 | 5 | 6
Date |  |  | Name
Place |  |  | Designation
Name of the Company

## Sch-10(2 of 3)
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE 10 (2 of 3) Details of Technical staff employed
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
BIDDER'S NAME AND ADDRESS: |  |  |  |  | To
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Section 3: 1.8 Qualification and experience of the key technical and management personnel in permanent employment with the tenderer and those that are proposed to be deployed on this contract, if awarded
Sl. No. | Name of the employee | Designation | Branch (Degree/Diploma) | Year of Passing | Since when employed in erection division | Past Experience
1 | 2 | 3 | 4 | 5 | 6 | 7
Date |  |  | Name
Place |  |  | Designation
Name of the Company

## Sch-10(3 of 3)
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE 10 (3 of 3 )
SHEET FOR TECHNOCOMMERCIAL OPENING
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
BIDDER'S NAME AND ADDRESS:
We propose the following deployment of manpower for the substation and Line package.
Sl. No. | Category | MONTHS AFTER PLACEMENT OF AWARD LETTER
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Project manager
2 | Sr. Project Manager
3 | Supervisor
4 | Technicians
5 | Skilled labour
6 | No skilled labour
Date |  | MONTHS AFTER PLACEMENT OF AWARD LETTER 2: Name
Place |  | MONTHS AFTER PLACEMENT OF AWARD LETTER 2: Designation
Name of the Company

## Sch-11 A
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE-11 (A) : COMPLETION SCHEDULE FOR STATION/TERMINAL BAYS
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bidders Name and Address: |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
We hereby declare that following schedules shall be followed by us for the above work. The period of various activities from the date of placement of award letter shall be as follows
SL.NO | Activity | STATION PORTION
|  | Commencement | Completion
1 | Detailed engineering
2 | Procurement of bought out items / raw materials
3 | Manufacturing & Testing
4 | Shipments
5 | Setting up of site office, Sheds & stores etc.
6 | Excavation
7 | Concreting for
a)Structure Foundations
b)Equipment and mounting structure foundadions
c)Cable trenches
1. Civil Works
2. Installation
8 | Receipt(at site) of
a)Main equipment / spares
b)Structures
c)Insulators & Hardwares
d)Clamps & Connectors
e)Marshalling kiosks
f)Cables & Cabling Materials
9 | Erection of
a)Main structures
b)Equipment support structures
10 | Equipment Erection
11 | Earthmat
12 | Bus bar erection
13 | Stringing
14 | Cabling
15 | Completion of testing and ready for commissioning
16 | Commissioning
Date |  | Name
Place |  | Designation
Name of the Company

## Sch-11B
KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
SCHEDULE-11B : COMPLETION SCHEDULE FOR TRANSMISSION LINES
SHEET FOR TECHNOCOMMERCIAL OPENING
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Bidders Name and Address: |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
We hereby declare that following shedules shall be followed by us for the above work. The period of various activities from the date of placement of award letter shall be as follows.
SL.NO | Activity | Construction of Transmission Line
|  | Commencement | Completion
I | SUPPLY
1 | Submission of Drawings
2 | Completion of detailed engineering
3 | Commencement of Manufacturing
4 | Completion of Manufacturing | VOID
5 | Readiness for testing
6 | Readiness for Shipment
7 | Receipt at Site
8 | Completion of Shipment
II | ERECTION
1 | Detailed Survey
2 | Setting up of site office, sheds and stores etc.
3 | Exacavation for foundations.
4 | Foundations and other Civil Works
5 | Erection of Tower alongwith accessories
6 | Stringing of conductor/ groundwire alongwith accessories
7 | Testing , Commissioning and Handing over.
Date |  | Name
Place |  | Designation
Name of the Company

## Sch-12
Karnataka Power Transmission Corporation Limited
SCHEDULE - 12 TYPE TESTS & TEST CHARGES OF EQUIPMENT/MATERIALS
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
BIDDERS SHALL INDICATE VARIOUS TYPE TESTS IN LIGHT BLUE COLOURED CELLS
ALL THE TYPE TESTS APPLICABLE FOR EACH OF THE EQUIPMENTS SHALL BE INCLUDED.
Bidders Name and Address |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
SL.No | Details of Equipments | Type Test | Test Charges ( in Rs )
1 | Power Transformers:
a) 20MVA, 110/33-11kV
2 | SF6 Circuit Breakers:
a)145kV Class
3 | Surge Arrestors
a) 96kV class
b) 60kV class
c) 30kV class
d) 9kV class
4 | Isolators:
a) 110kV Class
b) 66kV Class
c) 33kV Class
d) 11kV Class
5 | Control & Relay Panels / Relay & Protection Panels
6 | L.T. A.C Panel
7 | Station Battery
8 | Station Battery Charger
9 | 1.1KV Power Cables
10 | 1.1kV Copper Control cables
11 | 11kV U.G Cable
12 | Insulators a) 90KN Disc Insulator Strings
13 | Equipment / Station Structures
14 | Aluminium pipe and Clamps
15 | Hardware Materials
16 | Yard lighting equipments
17 | Fire Fighting equipments
18 | AC DISTRIBUTION BOX
19 | DC DISTRIBUTION BOX
20 | D.G. Set
21 | Auxiliary Transformer
NOTE: The Type Test / Special Tests, if repeated at the insistance of owner, the applicable testing charges shall be paid by the successful Bidder upfront to the laboratory and the same shall be reimbursable by KPTCL as per actuals on submission of Bills along with proof of payment and on successful completion of all the Type Tests, specified and on approval of the same by the owner. In case equipment/material fails in the type tests during testing then the testing charges paid by the Bidder to the laboratory will not be reimbursed by KPTCL. The above Clause is applicable for all the equipments/materials, in case, the Type Test / Special Tests, are repeated at the insistance of owner(KPTCL).
Date |  | Signature
Place |  | Printed Name
Designation
Company seal

## Sch-13
Karnataka Power Transmission Corporation Limited
Schedule -13-List of Optional Spares
SHEET FOR TECHNOCOMMERCIAL OPENING
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
BIDDERS SHALL NOTE THAT QUANTITIES INDICATED IN THE ITEM_WISE FINANCIAL BID OFFER SHALL BE INDICATED HERE ALSO.
Bidders Name and Address
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
List of optional spares required to meet the specified performance for a period of three years
Sl. No. | For Equipments | Details of item | Unit | Quantity
Date |  | Name
Place |  | Designation
Name of the Company

## Sch-14
Karnataka Power Transmission Corporation Limited
SCHEDULE - 14-Guaranteed Losses :
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bidders Name and Address along with GSTIN No.: |  |  | To,
The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Dear Sir, i) We Declare that the ratings and performance figures of the transformer furnished by us under the Turnkey Package are Guaranteed. We further declare that in the event of any deficiencies in meeting the guarantees in repect of the characteristics mentioned below as established after conducting the factory test, you may at your discretion,reject or accept the equipment after assessing the liquidated damages as specified in relevant clause of Bid Document.
Equipment | Guaranteed Losses at rated output(KW)
| Max No Load loss at rated voltage and rated frequency | Max Load loss at rated current and frequency and at 75 deg C at principal tap | Max I2 R loss at rated current and frequency and at 75 deg C at principal tap | Max Auxiliary loss at rated voltage and frequency for Power Transformer
20MVA,66/33-11kV Power Transformer | VOID
Note:(i) Refer Technical Specifications (ii)The loss quoted shall be consistent in Schedule 14 and GTPs(DRS)of Power Transformer
Date |  | Name
Place |  | Designation
Name of the Company

## Sch-15
Karnataka Power Transmission Corporation Limited
SCHEDULE-15
LIST OF VENDORS
SHEET FOR TECHNOCOMMERCIAL OPENING
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
BIDDERS NAME AND ADDRESS |  |  |  |  | The Chief Engineer Electy, Transmission (Operations) Zone, KPTCL, Tumakuru
Sl. No. | EQUIPMENT/ MATERIAL | NAME OF THE VENDOR
|  | VENDOR 1 | VENDOR 2 | VENDOR 3 | VENDOR 4
1 | Power Transformer 20MVA, 110/33-11kV Transformer
2 | SF6 Circuit Breakers: 145kV
3 | SURGE ARRESTERS
4 | Control & Relay Panels / Relay & Protection PANELS
5 | Station / Equipment Support structures
6 | Aluminium pipe and Clamps
7 | ACSR CONDUCTOR
8 | Earth wire
9 | Solid Core Insulator
10 | Disc Insulator Strings
11 | Insulator Hardware Clamps & Power connectors
12 | Auxiliary Transformer
13 | LTAC PANEL
14 | 1.1kV POWER CABLES
15 | AC DISTRIBUTION BOX
16 | DC DISTRIBUTION BOX
17 | BATTERY
18 | BATTERY CHARGER
19 | CONTROL CABLES
20 | 11KV Switchgear
21 | 11kV UG CABLE
22 | FIRE FIGHTING EQUIPMENTS
23 | Illumination Equipments / Fixtures
24 | Tower Parts
25 | Tower Accessories
26 | Insulator Hard Wares
27 | Conductor Accessories
28 | Earth Wire Accessories
29
30
31
32
33
34
35
36
37
38
39
40
41
Note : Any Other Materials name & its vendors are to be entered.
| Date |  | Name
| Place |  | Designation
Name of the Company

## Sch-16
SCHEDULE-16 : NO DEVIATION CERTIFICATE (ANNEXURE-I)
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
NOTE: SCHEDULE DULY SIGNED BY THE AUTHORIZED PERSON SHALL BE UPLOADED
| With reference to our Bid Proposal No |  |  |  | dated
for
We hereby confirm that we have read the provisions of the contract, the stipulation of these clause are acceptable to us,
and we have not taken any deviation whatsoever to these clauses:
|  | a) | Terms of payment | Clause No. 37 of Section-5,Conditions of Contract (CC) and Clause No.8 of Special Conditions of Contrac (SCC)
|  | b) | EMD/Bid Security | Clause No. 6, Section :1, Invitation for Tenders (IFT) and Clause No. 13, Section :2, Instruction to Tenderer (ITT)
|  | c) | Contract Performance Guarantee | Clause No. 29 of Section:2, Instruction to Tenderers (ITT).
|  | d) | Penalty for delay | Clause No. 41 of Section-5 : Conditions of Contract (CC).
|  | e) | Price Basis/ Price adjustment | Clause No. 40 of Section-5 :Conditions of Contract (CC).
|  | f) | Defects Liability Period/Guarantee | Clause No. 10 of Section-5 Special Conditions of Contract (SCC)
|  | g) | Work Schedule | Clause No.17 of Section:5 Conditions of Contract (CC)
|  | h) | Taxes and Duties | Clause No. 11.11 of Section-2: Instruction to Tenderers (ITT).
We further confirm that any deviation to the above clauses at SI.No. (a) to (h) found anywhere in our bid proposal, implicit or explicit, shall stand unconditionally withdrawn, without any cost implication whatsoever to KPTCL.
| Date |  |  | Name
| Place |  |  | Designation
Name of the Company

## Sch-17
Karnataka Power Transmission Corporation Limited
SCHEDULE-17 FORM FOR BID SECURITY/EMD (ANNEXURE-II) (To be stamped on Rs.300/- Non-Judicial stamp paper in accordance with KPTCL Circular No. KPTCL/GMT/CIVIL (B7)/35/2024-MANAGER ESTATE (E-106992) dated 02.03.2024)
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
NOTE: SCHEDULE DULY SIGNED BY THE AUTHORIZED PERSON SHALL BE UPLOADED AND SENT ALONG WITH ORIGINAL BANK GUARANTEE AND ORIGINAL DD (TOWARDS BID GUARANTEE ) TO CHIEF GENERAL MANAGER (TECH),KPTCL BANGALORE SO AS TO REACH AFTER THE LAST SUBMISSION DATE & ON OR BEFORE THE DATE & TIME OF OPENING TECHNO COMMERCIAL BIDS.
Ref No. |  |  |  | Bank Guarantee No.
Date
Dear Sirs,
In accordance with Invitation to Bid under your specification
No. |  | M/s |  |  | having its Registered /
Head Office at |  | (hereinafter called the 'Bidder') wish
to participate in the said Bid or |  |  |  | and you, as a special favour have agreed
to accept an irrevocable and unconditional bank guarantee for an amount of
valid up to |  | on behalf of Bidder in lieu of the Bid deposit required to be made
by the Bidder as a condition predecent for participation in the said Bid,in addition to the Demand draft No.
| dated |  | .
we the |  | Bank at |  |  | having our Head office at
(local address) guarantee and undertake to pay immediately on demand by Karnataka Power Transmission Corporation
the amount of | [5 empty] | (in figures and words)
without any reservation, protest, demur and recourse. Any such demand made by said `Owner' shall be conclusive and binding on us irrespective of any dispute or difference raised by the Bidder.
This Guarantee shall be irrevocable and shall remain valid up to and including
@
If any further extension of this guarantee is required, the same shall be extended to such required period (not exceeding one year) on receiving instructions
from M/s |  |  |  |  | on whose behalf this guarantee is issued.
This Guarantee has been issued using SFMS Platform and the requisite communication in this regard has been forwarded to the Beneficiary Bank.
In witness whereof the Bank, through its authorised officer, has set its hand and stamp on this
| day of |  |  |  | at
Witness
Signature |  | Signature
Name |  | Name
Official Addressess |  | Designation with Bank Stamp.
Attorney as per Power of Attorney No.
Date
Note : 1) Both the Bank Guarantee and Demand Draft shall be scanned and uploaded along with Electronic sheets. 2) This date shall be Forty Five (45) days after the last date for which the bid is valid.

## Sch-18
Karnataka Power Transmission Corporation Limited
SCHEDULE-18 PROFORMA OF LETTER OF UNDERTAKINGS (ANNEXURE-V)
SHEET FOR TECHNOCOMMERCIAL OPENING
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
NOTE: SCHEDULE DULY SIGNED BY THE AUTHORIZED PERSON SHALL BE UPLOADED
(To be executed on Non-Judicial paper of RequisiteValue)
Ref |  |  |  | Date
To,
Dear Sirs,
1. I*/We* have read and examined the following bid documents relating to the
(full Scope of Work)
a) Notice Inviitng Tender
b) Conditions of Contract containing section 'Invitation for Tenders’, 'Instructions to Tenderers’, ‘Conditions of Contract’ and Contract Data.
c) Special Conditions of Contract along with Annexure |  |  |  | to
d) Drawings No.
e) Technical Specifications
2 . I / We hereby submit our Bid and undertake to keep our Bid Valid for a period of One Hundred and Eighty days (180 days) from the Last date of bid submission as notified (either original or extended). I*/We* hereby further undertake that during said period I/We shall not vary/alter or revoke my/our Bid.
This undertaking is in consideration of KPTCL agreeing to open my/ our Bid and consider and evaluate the same for the purpose of award of Work in terms of provisions of clause entitled "Award of Construct" 'cl.no. 26 of Section ITT and cl.no. 18 of SCC of the Bid Documents.
Should this bid be accepted, I*/We* also agree to abide by and fulfil all the terms, conditions of provision of the above mentioned bid.
Signature along with Seal of Co.
(Duly Authorised to sign the Tender on Behalf of the Contractor.)
NAME
DESIGNATION
NAME OF THE COMPANY (in Block Letters)
WITNESS
SIGNATURE |  | Date and Postal Address
DATE |  | Telegraphic Address
NAME AND ADDRESS |  | Telephone No.
Telex No.

## Sch-19
Karnataka Power Transmission Corporation Limited
SCHEDULE-19 CONSORTIUM AGREEMENT ON NON JUDICIAL STAMP PAPER OF Rs.500/-(ANNEXURE -XIII) - VOID
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
NOTE: SCHEDULE DULY SIGNED BY THE AUTHORIZED PERSON SHALL BE UPLOADED.
CONSORTIUM AGREEMENT AMONGST M/s |  |  | M/s
For Bid Specification No. |  |  |  | OF KARNATAKA POWER TRANSMISSION CORPORATION LIMITED
This consortium agreement executed on this | [5 empty] | day |  | Month of Two thousand Twenty Four
amongst M/s |  | a company incorporated under the laws of |  |  | (Country) and having its registered office at
(hereinafter called the "Lead Company" which expression shall include its successors ,executors and permitted assigns),
M/s |  | a company incorporated under the laws of |  |  | (Country) and having its registered office at
(hereinafter called the "Constituent Company" which expressions shall include its successors,executors and permitted assigns)
for the purpose of making a bid and entering into a contract (In case of award) against the specification no.
For | [6 empty] | NAME OF THE WORK
for Karnataka Power Transmission Corporation Ltd. having its registered office at Kaveri Bhavan , Bangalore 560 009 , Karnataka (hereinafter called the "Owner"). The leader of the consortium shall abide by the general terms and conditions specified by the Purchaser. WHEREAS the Owner invited bids as per the above mentioned specifications for the design, manufacture, supply and erection, testing and commissioning of Equipments/Materials stipulated in the bidding documents under subject package
NAME OF THE WORK
AND WHEREAS Section-I ( Volume-1: Clause No. 11:- Qualifying Requirement), forming part of the bidding documents, stipulates that a consortium meeting the requirements of Section-I, ( Invitation of Bid) applicable may bid, provided the Consortium fulfills all other requirements of specification and in such a case, the Bid shall be signed by the members so as to legally bind the members and who will be jointly and severally liable to perform the Contract and all obligations hereunder.
The above clause further states that the consortium agreement shall be attached to the bid and the contract performance guarantee will be as per the format enclosed with the bidding document without any restriction or liability for either party.
AND WHEREAS the bid has been submitted to the Owner vide proposal No |  |  |  |  | dated
by Lead Company based on the Constituent agreement between all the consortium under these presents and the bid in accordance with the requirements of Specifications (Qualification Requirements).
NOW THEREFORE THIS UNDERTAKING WITNESSETH AS UNDER:
In consideration of the above premises and agreements all the partners to this consortium members do hereby now agree as follows:
1 | In Consideration of the award of the Contract by the Owner to the Consortium members, we , the members to the consortium agreement do hereby agree that M/s
shall act as Lead Company and further declare and confirm that we shall jointly and severally be bound up to the Owner for the successful performance of the contract and shall be fully responsible for the design, manufacture, supply and successful performance of the equipments in accordance with the Contract.
2 | In case of any breach of the said contract by the Lead company or other constituent of the Consortium agreement, the Lead company do hereby agree to be fully responsible for the successful performance of the contract and to carryout all the obligations and responsibilities under the contract in accordance with the requirements of the Contract
3 | Further, if the Owner suffers any loss or damage on account of any breach in the contract or any shortfall in the performance of the equipment in meeting the performance guaranteed as per the specification in terms of the contract, the Lead company of these presents undertake to promptly make good such loss or damages caused to the Owner, on its demand without any demur. It shall not be necessary or obligatory for the Owner to proceed against Lead Partner to these presents before proceeding against or dealing with the other Partner (s).
4 | The Financial liability of the members of the consortium agreement to the Owner, with respect to any of the claims arising out of performance or non-performance of the obligations set forth in the said agreement, read in conjunction with the relevant conditions of the contract shall, however not be limited in any way so as to restrict or limit the liabilities of any of the members of the agreement.
5 | It is expressly understood and agreed between the members to this consortium agreement that the responsibilities and obligations of each of the partners shall be as delineated hereunder (To be incorporated suitably by the member to this agreement). However, each member of the consortium will be severally and jointly responsible for the faithful performance of the contract. It is further agreed by the member that the above sharing of responsibilities and obligations shall not in any way be a limitation of joint and several responsibilities of the members under this contract.
|  | Sl.No. | Name of the Lead Bidder/Consortium Partner. |  | Scope of the work/Participation
1
2
We further declare ourselves bound to execute our scope of work/participation as stated above;
6 | This Consortium agreement shall be constructed and interpreted in accordance with the laws of India and the courts of Bangalore shall have the exclusive jurisdiction in all matters arising there under.
7 | In case of an award of a Contract, we the Consortium members do hereby agree that we shall be jointly & severally responsible for the works respectively executed and Lead company shall furnishing a contract performance security from a bank in favor of the PURCHASER in the forms acceptable to purchaser for value of Five percent (5%) of the total Contract Price plus additional security for unbalanced tenders in accordance with Clause 25.5 & 29 of ITT and Clause 43 of the CC (Conditions of Contract).
8 | It is further agreed that the Consortium agreement shall be irrevocable and shall form an integral part of the contract, and shall continue to be enforceable till the owner discharges the same. It shall be effective from the date first mentioned above for all purposes and intents.
IN WITNESS WHEREOF the partners to the Consortium have through their authorized representatives executed these presents and affixed Common seals of their companies, on the day, month and year first mentioned above.
WITNESS | [5 empty] | for Lead Company
1
| (Signature) |  |  |  |  | (Signature of the authorized representative)
| (Name in Block Letters) |  |  |  |  | (Name)
| Designation |  |  |  |  | (Designation)
Common Seal of the Company
2 | [5 empty] | ( For Constituent 1)
(Signature)
(Signature of the authorized representative)
| (Name in Block Letters) |  |  |  |  | (Name)
(Designation)
| Designation |  |  |  |  | Common Seal of the Company

## Sch-20
Karnataka Power Transmission Corporation Limited
SCHEDULE-20 POWER OF ATTORNEY (ANNEXURE-XI)
Bid Enquiry No: KPTCL/CEE/TR(O)Z/TKR/ SEE(O)/ AEE-4/2025-26/Bid Enq-0092 Dated: 06.01.2026
Augmentation of 1X8MVA + 1X12.5MVA 66/11KV Power Transformer by 2X20 MVA, 66/11kV Power Transformers at 66/11KV Chitrahalli Sub-Station in Holalkere Taluk and Chitradurga District including supply of equipments/materials, Dismantling and erection (including civil works), under Partial turnkey basis, on Percentage Tender Basis (Excluding the supply of Major materials such as Power Transformer & NIFS, which will be supplied by KPTCL. Testing & commissioning, done by KPTCL RT Staff).
NOTE: SCHEDULE DULY SIGNED BY THE AUTHORIZED PERSON SHALL BE UPLOADED.
POWER OF ATTORNEY
(To be stamped on Rs.500/- Non Judicial stamp paper in accordance with KPTCL Circular No. KPTCL/GMT/CIVIL (B7)/35/2024-MANAGER ESTATE (E-106992) dated 02.03.2024)
KNOW ALL MEN BY THESE PRESENTS that we
a Company incorporated
under the laws of
and having its Registered Office / Head Office at
"Manufacturer / Bidder" which expression shall unless repugnant to the
Context or meanig thereof, include its successors, administrators and assigns)
acting through Mr | [5 empty] | its constitute, nominate and appoint
M/s |  |  |  |  | a Company incorporated under the laws of
and having its Registered / Head Office at
as its duly constituted lawful Attorney (hereinafter called "Attorney"
or "Authorized Representative") to exercise all or any of the powers for and on
behalf of the "Manufacturer / Bidder" in regard to Specification No.
Package
the bids for which have been invited by
(Address "Owner") to undertake the following acts:
i. | To submit proposal and participate in the aforesaid Bid Specification of the Owner on behalf of the "Manufacturer / Bidder".
ii. | To negotiate with the "Owner" the terms and conditions including price for award of the contract pursuant to the aforesaid Bid and to sign the contract with the "Owner" for and on behalf of the Manufacturer / Bidder.
iii. | To receive accept and execute the contract for and on behalf of the "Manufacturer / Bidder".
iv. | To do any other act or submit any document related to the above.
It is expressly understood that the Power of Attorney shall remain valid, binding and irrecoverable till submission of the Contract performance guarantee in terms of the Contract. The "Manufacturer / Bidder" hereby agrees and undertakes to ratify and confirm all the whatsoever the said "Attorney" / "Authorised Representative" quotes in the Bid, negotiates and signs the contract with the "Owner" and / or purports to act on behalf of the "Manufacturer / Bidder" by virtue of this Power of Attorney and the same shall bind the "Manufacturer / Bidder" as if done by itself.
IN WITNESS WHEREOF THE "Manufacturer / Bidder" has executed these presents at
|  |  | on this day of | [5 empty] | under
the Common Seal of the Manufacturer company / Bidder.
Specimen Signature of Attorney Holder
(Name & Designation)
For and on behalf of
Common Seal of the above Manufacturer/Bidder
Has been affixed thereto in the presence of :
WITNESSES :
1 | Signature
Name
Designation
Occupation
2 | Signature
Name
Designation
Occupation