## PHY + FIN
TENTATIVE PHYSICAL/FINANCIAL ACTIVITY CHART
PÁªÀÄUÁjAiÀÄ ºÉ¸ÀgÀÄ:- Repair of Left bank canal Sluice of Byramangala Reservoir in Bidadi Hobli, Ramanagara taluk, Ramanagara District
SL NO | ITEM NAME | UNIT | QUANTITY | RATE (INR) | TOTAL (INR) | 1st MONTH |  | 2nd MONTH |  | 3rd MONTH |  | 4th MONTH |  | 5th MONTH |  | 6th MONTH |  | 7th MONTH |  | 8th MONTH |  | 9th MONTH
[6 empty] | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL
1 | Clearing and grubbing road land including uprooting rank vegetation, grass, bushes, shrubs, saplings and trees girth up to 300 mm, removal of stumps of trees cut earlier and disposal of unserviceable materials and stacking of serviceable material to be used or auctioned, including removal and disposal of top organic soil not exceeding 150 mm in thickness. By Mechanical Means using Dozer ( In area of thorny jungle) as per the directions of the engineer incharge of work. | 100 sqm | 940 | 503.36 | 473158.4 | 940 | 473158.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473158.4 | 0
2 | Providing and placing sand bags consisting of empty cement bags filled with 35 to 40 kg locally available sand for forming ring bund including cost of all materials, labour, plugging joints with selected earth, and all other ancillary operations complete as per the directions of the engineer incharge of work. | Each | 74057 | 70.72 | 5237311.04 | 10579.5714 | 748187.2914 | 10579.5714 | 748187.2914 | 10579.5714 | 748187.2914 | 10579.5714 | 748187.2914 | 10579.5714 | 748187.2914 | 10579.5714 | 748187.2914 | 10579.5714 | 748187.2914 | 0 | 0 | 0 | 0 | 5237311.04 | 0
3 | Filling clayey soil between two rows of sand bags placed for forming ring bund including cost of all materials, labour,tamping, plugging leakage points and all other ancillary operations complete as per the directions of the engineer incharge of work. | cum | 8380 | 501.28 | 4200726.4 | 1197.1429 | 600103.7714 | 1197.1429 | 600103.7714 | 1197.1429 | 600103.7714 | 1197.1429 | 600103.7714 | 1197.1429 | 600103.7714 | 1197.1429 | 600103.7714 | 1197.1429 | 600103.7714 | 0 | 0 | 0 | 0 | 4200726.4 | 0
4 | Design, fabrication, supply, erection and commissioning of embedded parts consisting of sill beam, wheel tracks, seal seats, guide rails, breast wall liner ( upto one vent height plus 1 m above the roof of vent) with all accessories for river / canal sluice service gate including cost of all materials, machinery, labour, cutting, aligning, anchoring, welding, finishing, cleaning, applying one coat zinc rich epoxy primer and four coats of cold applied coal tar epoxy paint and all other ancillary operations complete as per specifications and approved drawings. without groove liner as per the directions of the engineer incharge of work. | Tonne | 1.4803 | 226928 | 335921.5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4803 | 335921.5184 | 0 | 0 | 335921.5184 | 0
5 | Design, fabrication, supply, erection, testing and commissioning of fixed wheel type vertical lift service gate consisting of skin plate, vertical and horizontal girders, wheels, stiffeners, lifting brackets, guide rollers, ballast blocks, teflon claded rubber seals with all accessories for river sluice /canal sluice vent including cost of all materials,machinery, labour, cutting, aligning, welding, finishing, cleaning, applying one coat of zinc rich epoxy primer and three coats cold applied coal tar epoxy paint, seal fixing and all other ancillary operations complete as per specifications and approved drawings as per the directions of the engineer incharge of work. | Tonne | 1.6544 | 153400 | 253784.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6544 | 253784.96 | 0 | 0 | 253784.96 | 0
6 | Design, fabrication, supply, erection and commissioning of structural steel hoist bridge consisting of columns, beams, bracings, stiffeners, ties, chequered plate covering, hand railing, ladder with all other accessories for supporting rope drum hoist for operating barrage gates including cost of all materials,machinery, labour, cutting, aligning, anchoring, welding, finishing, cleaning, applying two coats of zinc chromate red oxide primer and three coats of approved synthetic enamel paint and all other ancillary operations complete as per specifications and approved drawings as per the directions of the engineer incharge of work. | Tonne | 4.777 | 141648 | 676652.496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.777 | 676652.496 | 0 | 0 | 676652.496 | 0
7 | Cleaning gates / hoists / embedded parts to expose fresh metal surface for repainting by sand blasting method as per specifications including cost of all materials, labour, machinery, scaffolding, applying a coat of rust inhibitive compound with all other ancillary operations complete. as per the directions of the engineer incharge of work. | sqm | 34 | 876.72 | 29808.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 29808.48 | 0 | 0 | 29808.48 | 0
8 | Providing primer painting to structural steel surfaces with epoxy primer paint of approved quality including cleaning the surface, cost of all materials, labour, etc., complete with all leads and lifts. Base coat as per the directions of the engineer incharge of work. | sqm | 34 | 213.2 | 7248.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 7248.8 | 0 | 0 | 7248.8 | 0
9 | Providing primer painting to structural steel surfaces with epoxy primer paint of approved quality including cleaning the surface, cost of all materials, labour, etc., complete with all leads and lifts. and one additional coatas per the directions of the engineer incharge of work. | sqm | 34 | 208 | 7072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 7072 | 0 | 0 | 7072 | 0
10 | Removal of Unserviceable Soil with Disposal upto a suitable distance as directed by the Engineer incharge of work as per the directions of the engineer incharge of work. | cum | 10000 | 88.4 | 884000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 884000 | 884000 | 0
TOTAL |  |  |  |  | 12105684.0944 | 12716.7143 | 1821449.4629 | 11776.7143 | 1348291.0629 | 11776.7143 | 1348291.0629 | 11776.7143 | 1348291.0629 | 11776.7143 | 1348291.0629 | 11776.7143 | 1348291.0629 | 11776.7143 | 1348291.0629 | 109.9117 | 1310488.2544 | 10000 | 884000 | 12105684.0944
|  |  |  | GST | 2179023.137 |  | 327860.9033 |  | 242692.3913 |  | 242692.3913 |  | 242692.3913 |  | 242692.3913 |  | 242692.3913 |  | 242692.3913 |  | 235887.8858 |  | 159120
| Tota including GST |  |  |  | 14284707.2314 |  | 2149310.3662 |  | 1590983.4542 |  | 1590983.4542 |  | 1590983.4542 |  | 1590983.4542 |  | 1590983.4542 |  | 1590983.4542 |  | 1546376.1402 |  | 1043120
LOC | [6 empty] | 4518031.5886 |  | 4044873.1886 |  | 4044873.1886 |  | 4044873.1886 |  | 4044873.1886 |  | 4007070.3801 |  | 3542779.3173 |  | 3542779.3173 |  | 3542779.3173 | 12105684.0944
[6 empty] | 1st Milestone | [5 empty] | 2nd Milestone | [5 empty] | 3nd Milestone
[6 empty] | 4518031.5886 | [5 empty] | 4044873.1886 | [5 empty] | 3542779.3173
[6 empty] | 4518031.5886 | [5 empty] | 8562904.7771 | [5 empty] | 12105684.0944
|  |  |  | LOC | 4842273.6378 |  |  |  | Milestones and liquidity damages
[5 empty] | 3631705.2283 |  |  |  | MILESTONES | AMOUNT | Liquidity damage
[9 empty] | Mile Stone 1 | 4518031.5886 | 4518 | 4518.0316 | 45.1803
[9 empty] | Mile Stone 2 | 4044873.1886 | 4045 | 8562.9048 | 40.4487
[9 empty] | Mile Stone 3 | 3542779.3173 | 3543 | 12105.6841 | 35.4278
[6 empty] | EMD |  |  |  | 12105684.0944 |  | Per day | 121.0568
[6 empty] | 181585.2614 |  | Providing and placing Sand Bags |  | 74057 | Each | 59245.6
[6 empty] | 200000 |  | Earthwork both in excavation, Embankment /Filling combined qty |  | 8380 | Cum | 6704
[8 empty] | Annual turn over |  | 242.1137
[8 empty] | Line of credit |  | 45.1803
[8 empty] | Similar nature of work |  | 60.5284