## Package
TENTATIVE PHYSICAL/FINANCIAL ACTIVITY CHART
MI/2026-27/DA/WORK_INDENT11976
Construction of Series of Check dam in sy.no.39 of Thonnalapura village in Chikkanayakanahalli Taluk, Tumkuru District.
SL No. | Item | Unit | Rate | Qty | Amount | 1st month |  | 2nd month |  | 3rd month |  | 4th month |  | 5th month |  | 6th month |  | 7th month |  | 8th month |  | 9th month |  | 10th month |  | 11th month
[6 empty] | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL
1 | Clearing and grubbing road land including uprooting rank vegetation, grass, bushes, shrubs, saplings and trees girth up to 300 mm, removal of stumps of trees cut earlier and disposal of unserviceable materials and stacking of serviceable material to be used or auctioned, including removal and disposal of top organic soil not exceeding 150 mm in thickness. (ii )By mechanical means using Dozer (a)In area of light jungle.Complete with all lead and lifts, loading and unloading as per specification, drawing and direction of engineer in charge of work | 100 Sqm | 393 | 370 | 145410 | 185 | 72705 | 185 | 72705
2 | De-siltingofFeederChannel/Canal in dry condition by excavating the deposited bedmaterial and loading the same to transport vehicle (excluding cost of transportation) including cost of all machinery, labour & all necessary works as directed and complete as per specification | Cum | 54 | 21357 | 1153278 | [14 empty] | 5339.25 | 288319.5 | 5339.25 | 288319.5 | 5339.25 | 288319.5 | 5339.25 | 288319.5
3 | EarthworkexcavationforFoundation by mechanica lmeansforallworks& depthupto3m,asperdrawingand technical specifications, including setting out, shoring, strutting, barricading, caution lights, including dressing of excavated surfaces, disposing off or levelling the excavatedearthorsorting&stacking the selected earth for reuse in a radius of 50mand lift upto1.5m includingcostof labour, tools,usage ofmachinery&other appurtenaces requiredtocompletetheworkInall kindsof | Cum | 102 | 2576.47 | 262799.94 | 858.8233 | 87599.98 | 858.8233 | 87599.98 | 858.8233 | 87599.98
4 | Supplying, fittingandplacingTMTFE 550 / 550D Steel Reinforcement including cost of all materials, machinery, labour, cleaning, straightening, cutting, bending, hooking, laping/welding joints, tying with binding wire / soft annealed steel wire and other ancilary operations completeasper drawing and technical specification.(e) Dam and Allied Works | Tonne | 89836 | 24.26 | 2179421.36 |  |  | 2.6956 | 242157.9289 | 2.6956 | 242157.9289 | 2.6956 | 242157.9289 | 2.6956 | 242157.9289 | 2.6956 | 242157.9289 | 2.6956 | 242157.9289 | 2.6956 | 242157.9289 | 2.6956 | 242157.9289 | 2.6956 | 242157.9289
5 | Providingand laying in-situvibrated M-15 grade cement concrete using 40mmdownapproved, clean,hard, gradedaggregates forplainconcrete works includingcostofallmaterials, machinery, labour, cleaning, providingmortar layer for lift joints, batching,mixing,placinginposition, levelling, vibrating, finishing, curing with all other ancillary operations complete. | Cum | 5989 | 145.27 | 870022.03 |  |  | 72.635 | 435011.015 | 72.635 | 435011.015
6 | Providingand laying insitu vibrated M-20 (28 days cube compressive strengthnot lessthan20N/sqmm) gradecementconcreteusing20mm down size approved, clean, hard, gradedaggregatesasperrelevant IS Codes machine mixed with super plasticisers, laid in layers, well compacted using needle vibrators, including cost of all materials of quality, confirming to the requirements of relevant IS codes, labour,Usagechargesofmachinery, curing, centering, formwork and scafolding and all other appurtenances required to complete the work as per technical specificationsforcheckdam/pickups /irrigation tanks/wasteweir/ sluice, sluice canal and other alliedworks like abutments/wing walls/returns/cutoffwallsworks&all necessary works as directed and complete as per specification. | Cum | 6843 | 2003.62 | 13710771.66 |  |  | 222.6244 | 1523419.0733 | 222.6244 | 1523419.0733 | 222.6244 | 1523419.0733 | 222.6244 | 1523419.0733 | 222.6244 | 1523419.0733 | 222.6244 | 1523419.0733 | 222.6244 | 1523419.0733 | 222.6244 | 1523419.0733 | 222.6244 | 1523419.0733
7 | Providingrubblestone/boulder filling betweenor behindabutment below apron includingcostofallmaterials, labour, hand packing, finishing top surface & all necessary works as directed and complete as per specification | Cum | 1278 | 256.7 | 328062.6 | [14 empty] | 85.5667 | 109354.2 | 85.5667 | 109354.2 | 85.5667 | 109354.2
8 | Providing and constructing 75mm diaPVCpipeweepholesforconcrete /masonrywalls includingproviding 200 x 200 x 200mmsize porous concreteblockmadeof cement and 20mmdowncoarseaggregatein1: 4proportion including100mmthick sandbackingat the junctionofwall and soil back fill, cost of all materials, machinery, labour & all necessary works as directed and complete as per specification. | M | 337 | 134.3 | 45259.1 | [8 empty] | 44.7667 | 15086.3667 | 44.7667 | 15086.3667 | 44.7667 | 15086.3667
9 | Providingandconstructingdryrubble stone pitching with pin headers at2 perm2usingstonesandstonechips fromapprovedsource includingcost ofallmaterials, labour,handpacking /wedgingstonechips, finishingand all other ancillary operations complete.(300mm thick) | Sqm | 455 | 600 | 273000 | [16 empty] | 200 | 91000 | 200 | 91000 | 200 | 91000
10 | Providing casingembankment using semi-pervious / pervious soil from dumpareas in layersof 250 to300 mm (before compaction) including cost of all materials, machinery, labour, all other operations suchas collection of soil, spreading soil in layer of specified thickness, sorting out, breaking clods, levelling, sectioning edges / sides, watering, compacting each layer to density controlofnot lessthan95percentor asstipulatedusingpower roller and all other ancillary operations complete. | cum | 225 | 4923 | 1107675 | [18 empty] | 2461.5 | 553837.5 | 2461.5 | 553837.5
TOTAL |  |  |  |  | 20075699.69 |  | 160304.98 |  | 2360892.9972 |  | 2288187.9972 |  | 1765577.0022 |  | 1780663.3689 |  | 1780663.3689 |  | 1780663.3689 |  | 2163250.7022 |  | 2254250.7022 |  | 2808088.2022 |  | 933157
LOC | [6 empty] | 4809385.9744 |  | 6414657.9967 |  | 5834428.3683 |  | 5326903.74 |  | 5341990.1067 |  | 5724577.44 |  | 6198164.7733 |  | 7225589.6067 |  | 5995495.9044 |  | 3741245.2022 |  | 933157
[6 empty] | 1st milestone | [7 empty] | 2nd milestone | [7 empty] | 3rd milestone
[6 empty] | 6574962.9767 | [7 empty] | 14080203.7856 | [7 empty] | 20075699.69
Milestones and liquidity damages
[11 empty] | MILESTONES |  | AMOUNT | Liquidity damage
[11 empty] | Mile Stone 1 |  | 6574962.9767 | 6600
[11 empty] | Mile Stone 2 |  | 14080203.7856 | 14100
[11 empty] | Mile Stone 3 |  | 20075699.69 | 20100
[9 empty] | Earthwork both in excavation & Embankment combined quantities |  |  |  | 28856.47 | Cum | 23086
[9 empty] | Cement concrete both RCC and PCC |  |  |  | 2148.89 | Cum | 1720
[9 empty] | Reinforcement of Steel |  |  |  | 24.26 | Tonne | 19.5
[9 empty] | Revitment/Pitching |  |  |  |  | sqm | 0
[9 empty] | EMD |  |  |  | 301500
[9 empty] | Annual turn over |  |  |  | 401.6
[9 empty] | Line of credit |  |  |  | 7225589.6067 | 72.3
[9 empty] | Similar nature of work |  |  |  | 100.4
702649.4892
722725.1888