## Sheet1
GR - 75
NAGAR PARISHAD, SHEIKHPURA (BIHAR)
okMZ ua0& 30 es 'kaHkq 'kj.k flag ds ikl ls gksrs gq, d`".k ;kno ds ?kj rd ,oa jsyos ykbZu ds ikl ls fot; th ds ?kj rd ,oa xaxk th ds ?kj ls tksxh ;kno rd iFk ,oa ukyk fuekZ.k dk;ZaA
Estimated Cost:- |  |  | 1452216
Earnest Money :- |  |  | 34000
Time of Completion :- |  |  | three month from the date of work order
Cost of BOQ :- |  |  | 2500
S,No | SOR . | Items of work | Unit | Rate | Quantity | Amount
1 | 2.8.1 | Earth work in excavation in foundtion trenches or drains (not exceeding 1.5m in width or 10 sqm on plan) including dressing of sides and ramming of bottoms, lift up to 1.5m, including getting out the excavated soil and disposal of surplus excavated soil as directed, within a lead of 50m. | cum | 360.7 | 101.9426 | 36770.6858
2 | 2.28 | Supplying and filling in plinth with local sand and under floor,watering ,ramming, consolidating and dressing complete
|  |  | cum | 287.3 | 37.2657 | 10706.428
3 | 11.72 | Providing designation 100A one brick flat soling joints filled with local sand including cost of watering texes royalty all complete as per building specification and direction of E/I.
|  |  | sqm | 283.3 | 282.5279 | 80040.1487
4 | 4.1 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering-All work up to plinth level:
| 4.1.3 | 1:2:4(1 Cement:2 coarse sand: 4 graded stone aggregate 20mm nominal size)
|  |  | cum | 3998.1 | 11.2137 | 44833.4258
5 | 5.3 | Reinforced cement concrete work in beams, suspended floors, roofs having slope upto 15, landings, balconiec, shelves, chajjas, lintels, bands, plain window sills, staircasees and spiral staircases upto floor five level excluding the cost of centring, shuttering, finishing & reinforcement - all work upto plinth level.
|  |  | cum | 5335.9 | 26.3456 | 140577.5354
6 | 6.1A | Brick work with bricks of class designation 100A in foundation and plinth in:
| 6.1.12A | Cement mortar 1:4(1 cement:4 coarse sand) | cum | 5017.9 | 33.3739 | 167466.9953
7 | 13.11 | 12mm cement plaster of mix:
| 13.11.2 | 1:4(1 cement:4 coarse sand)
| 13.26 | Neat cement punning | Sqm | 192.2 | 226.7658 | 43584.3866
8 | 5.22.7B | Reinforcement for RCC work including straightening, cutting, bending, placing in position and bonding all complete.(wt @ 90kg/cum)
|  |  | Kg | 92.6 | 2107.6487 | 195168.272
9 | 5.9.1 | Centring and shuttering including strutting, propping etc. and removal of form for lintel, beams, plinth beams, griders, bressumers and contilevers.
|  |  | sqm | 211.6 | 204.461 | 43263.9405
10 | 2.29.1 | Surface dressing of the ground including removing vegetation and inequalities not exceeding 15 cm deep and disposal of rubbish, lead upto 50 m and lift upto 1.5 m
|  | All kinds of soil | 100sqm | 1355.4 | 483.2714 | 6550.2602
11 | 2.2.1-(2.5+2.4) | Banking excavated earth in layers not exceeding 20 cm in depth, breaking clods, watering .rolling each layer with 1/2 tonne roller, or wooden or steel rammers, and rolling every 3rd and top-most layer with power roller of minimum 8 tonnes and dressing up ; in embankments for roads, flood banks, marginal banks, and guide banks etc . lead upto 50 m and lift upto 1.5 m.
|  |  | cum | 364.4 | 26.052 | 9493.3454
12 | 16.42 | Providing and laying in position cement concrete of specified grade exluding the cost of centring and shuttering-all work upto plinth level1:1.5:3(1 Cement :1.5 coarse sand:3 graded stone aggregate 20 mm nominal size)
|  |  | cum | 4420.8 | 73.6252 | 325482.245
15 |  | Carriage of materials
|  | a.Bricks | Thous. | 995.29 | 25601.0661 | 25480.4851
|  | b.Coarse Sand | cum | 1143.38 | 64.2257 | 73434.398
|  | c.Stone chips | cum | 493.08 | 98.9542 | 48792.332
|  | d.Cement | MT | 0 | 43.8332 | 0
|  | e.Local sand | cum | 336.17 | 37.2657 | 12527.6015
16 |  | Extra cost of building materials
|  | a.Bricks | thous | 365.45 | 25601.0661 | 9355.9096
|  | b.Cement | MT | 18.55 | 43.8332 | 813.106
|  | Inouguration Board |  |  |  | 3500
|  | TOTAL |  |  |  | 1277841.5011
17 |  | Seigniorage Fee
|  | a.Bricks | Thous. | 5285 | 25601.0661 | 135301.6345
|  | b.Coarse Sand | cum | 175.8 | 64.2257 | 11290.8807
|  | c.Stone chips | cum | 556.33 | 98.9542 | 55051.1845
|  | d.L.Sand | cum | 141.85 | 37.2657 | 5286.1358
206929.8356
|  | Seigniorage Fee @10% |  |  |  | 20692.9836
|  | GRAND TOTAL |  |  |  | 1370014.74
|  |  | GST 6% |  |  | 82200.8844
1452215.6244
[5 empty] | Say | 1452216