## Technical
NIT No – 02/2026-27/O&M-PHED/HILSA
TECHNICAL BID SHEET
Name of Work | Comprehensive operation and maintenance, routine repairs and Special repairs of i.) Rural Piped Water Supply Scheme (PWS). Total No. Scheme - 35 ii.) Single Village piped water supply schemes (SVS). Tatal No. Of Scheme - 14 iii.) Ward level Piped Water Supply Schemes in quality affected wards (WLS_Quality) Total No. Of Scheme – 5 and iv.) Ward level Piped Water Supply Schemes in non quality affected wards (WLS_Non Quality) Total No. Of Scheme – 226. based on item rates; constructed by the Public Health Engineering Department including payment to the pump operators, electricity bills for five years. | Cost of Work as per BOQ(Rs in Lakhs) | 4989.79 |  |  |  | Time of Completion in months | 60 | ALL COLOURED CELL TO BE FILLED ACCORDINGLY
Sanctioned Amount (in Lakh) | 5517.456 | As per Technical Approval |  |  |  |  | Date of Tender | 11.05.2026
Sl No. | Items | Requirement |  |  | Requirement | Cl. No.
Name of the Contractor
Address of the Contractor
1 | Bid Validity | Bids shall remain valid for a period not less than 180 days after the deadline date. A Bid valid for a shorter period shall be rejected by the Employer as non-responsive |  |  | 180 Days | 15.1 Page/17 | Bid validity periods In days
2 | Bid Security | Unconditional bank guarantee from any scheduled Indian bank issued within the state in the format given (If issued from any bank outside state will be converted to any bank within the state before executing the agreement, duly pledged in favour of the Executive Engineer, P.H. Division,Hilsa,Nalanda. |  |  |  | 16.1 Page-17 | Amount To be entered (Rs in Lakhs)
|  | Bid Security Amount - (Rs. In Lakhs) | 59.9 |  |  |  | Bid Security Amount - Rs. | 0
DISQUALIFY
3 | (i) Legal Status of Bidder. |  |  |  |  | 4.3(a) Page-12
(ii) Place of Registration.
(iii) Principal place of Business
| (iv) Power of attorney of signatory Bid | Attached or Not |  |  |  | 4.2(iv) Page-11
4 | Total value of civil engineering construction work performed in last five years. | (a) Achieved in any one year a minimum annual financial turnover (in all classes of civil engineering construction works only) volume of construction work of at least the amount equal to the 50% (fifty percent) estimated cost of works for which bid has been invited. The turnover will be indexed at the rate of 8% for a year. The certificates attached in support of turnover attached shall have valid Unique Document Identification Number (UDIN). |  |  | 2494.895 | 4.5A (a) Page-16
| 2020-21 | [5 empty] | Amount To be entered (Rs in Lakhs)
| Escalation Factor= 1.47 | [6 empty] | 0
| 2021-22 | [5 empty] | Amount To be entered (Rs in Lakhs)
| Escalation Factor= 1.36 | [6 empty] | 0
| 2022-23 | [5 empty] | Amount To be entered (Rs in Lakhs)
| Escalation Factor= 1.26 | [6 empty] | 0
| 2023-24 | [5 empty] | Amount To be entered (Rs in Lakhs)
| Escalation Factor= 1.17 | [6 empty] | 0
| 2024-25 | [5 empty] | Amount To be entered (Rs in Lakhs)
| Escalation Factor= 1.08 | [6 empty] | 0 | 0
5 | Work Experience of Similar nature | (b) Satisfactorily completed as a prime contractor (or as a nominated sub contractor, where the sub contract involved execution of all main items of work described in the bid document, provided further that all other qualification criterion are satisfied) at least one similar work of value not less than the amount indicated in the appendix (Not less than 10% (Ten percent) estimated value of contract). or Satisfactorily completed water supply scheme (Piped water supply or lift irrigation or water supply in building) at least one work of value not less than 10% (ten percent) of the estimated cost of the works for which bid has been invited. |  |  | 498.979 | 4.5A (b) Page -16 | Amount To be entered (Rs in Lakhs)
|  | (c) Executed the minimum quantities of the following item of work as indicated in the appendix: |  |  |  | 4.5A (c) Page -16
|  | Description of item | Units | Total Quantity in BoQ | Quantity required to have been executed
|  | 1.) Maintenance of water supply schemes in water quality affected areas. | Years | 5 Year | 2.50 Years
|  | 2.) Maintenance of water supply schemes in non water quality affected areas. | Years | 5 Year | 2.50 Years
Note: Item 1 of the above table shall be mandatorily applicable for bids having quality affected water supply schemes and for non water quality affected water supply schemes any one of the above two items tabulated above is mandatory.
6 | Bidding Capacity: | Should be more than Available Bid capacity = (A x N x 3 - B)= Rs. _____, Where A= Maximum Value of work executed in any one year during last 5 yrs. , N = Number of years prescribed for completion of the works (Design Build Period) for which bids are invited, B= Value (updated to the price level of the year indicated in Appendix) of existing commitments and on-going works to be completed during the period of completion of the works for which bids are invited. |  |  | 4989.79 | 4.7 Page-20 | Amount To be entered (Rs in Lakhs)
7 | (a) Existing commitments and ongoing works |  |  |  |  | Page - 20 | Amount To be entered (Rs in Lakhs)
| (b) Work for which Bid already submitted |  |  |  |  | Page - 20 | Amount To be entered (Rs in Lakhs)
8 | Availability of key items of Contractor's Equipment | Type of Equipment/Maximum age No. Required | Nos. | Max. Age |  | 4.5(B) (b) Page-26 Annexure-I |  | Nos./ Max. Age
|  | Concrete Mixer | 2 | 5
|  | Vibrator | 4 | 5
|  | Rotary Drilling / Reverse Rotary / DTH Rig Machine | 2 | 10
|  | Compressor | 2 | 5
|  | Truck/Tractor with trailer | 2 | 5
|  | Hydraulic Excavator | 1 | 5
9 | Key Personnel |  |  | Rs. 30 –50 Crores |  | 4.5(B) (b) Page-34 Annexure-II |  | Name of the Personnel and Experience in years
|  | Project Manager B.E. Civil + 10Years Exp. (5 years as Manager in PHED works) or retired E.E. & above of PHED |  | 1
|  | Site Engineer B.E. Civil + 07Years Exp. (3 years as Manager in PHED works) or retired A.E. & above of PHED |  | 2
|  | Site Supervisor B.E. Mech./Civil + 05 Years Exp. Or Dip. Mech./Civil + 07 years Exp. Or or retired J.E. & above of PHED |  | 10
|  | Surveyor .B E. Civil + 03 Years Exp. orDip. Civil + 05 years Exp. |  | 1
10 | Evidence of accesses to Financial Resources | Evidence of access to or availability of credit facilities (10% of estimated cost), certified by bankers (Not more than 3 months old). (Rs in Lakhs). |  |  | 498.979 | Page 15 4.3 (g) | Amount To be entered (Rs in Lakhs)
11 | Proposed methodology and programme of construction. | Justifying their capability of execution and completion of the work as per technical specifications within the stipulated period of completion as per milestones. (Attached or not) |  |  |  | Page 15 4.3 (l)
12 | Litigation History | Information regarding any litigation, current or during the last five years, in which the Bidder is involved, the parties concerned, and disputed amount. (Attached or not) |  |  |  | Page 15 4.3 (j)
13 | Affidavit | Regarding statements made in the required attachments are true and correct. |  |  |  | Page 23 12.1 (iv)
14 | Undertaking | Able to invest a minimum of cost upto 25% of contract value of work. During implementation of contract. |  | 25 % of B.O.Q.Amount | 1247.4475 | Page 12 4.3 (h)
15 | PAN No.
16 | GST No.
17 | Character Certificate
18 | No Dues Certificate | The bidders are required to submit a duly “Notarized affidavit” stating that there are no outstanding electricity dues pending for payment against all electric consumer numbers in their completed or ongoing operation & maintenance contracts till 31.03.26. The affidavit shall be duly supported/ substantiated by a “no due certificate” that there are no outstanding electricity dues pending for payment against all electric consumer numbers in their completed or ongoing operation & maintenance contracts till 31.03.2026 duly issued by the concerned Executive Engineer(s). (Attached or not) |  |  | Attached or Not | NIT Clause (31)
19 | Time of Completion | 60 Months |  |  |  |  | To be entered in months
Executive Engineer,
P.H. Division, Hilsa,Nalanda.

## 1.0
QUALIFICATION INFORMATION
The information to be filled in by the Bidder in the following pages will be used for purposes of post qualification as provided for in Clause 4 of the Instructions to Bidders. This information will not be incorporated in the Contract.
NAME OF THE CONTRACTOR
1 | For Individual Bidders
1.1 | Constitution or legal status of Bidder (Attach copy)
Place of registration :
Principal place of business :
Power of attorney of signatory of Bid (Attach)
1.2 | Total value of Civil Engineering construction work performed in the last five years** (in Rs. Million)
|  | 200_____ | 200_____
|  | 200_____ | 200_____
|  | 200_____ | 200_____
|  | 200_____ | 200_____
|  | 200_____ | 200_____

## 1.3.1
1.3.1 Work performed as prime contractor, work performed in the past as a nominated sub- contractor will also be considered provided the sub-contract involved execution of all main items of work described in the bid document, provided further that all oth
NAME OF THE CONTRACTOR
Project Name | Name of the Employer* | Description of work | Contract No. | Value of Contract (Rs. In Crore) | Date of issue of work order | Stipulated period of completion | Actual date of completion* | Remarks explaining reasons for delay & work completed)
NOTE:
* Attach certificate(s) from the Engineer(s)-in-Charge
** Immediately preceding the financial year in which bids are received.
 Attach certificate from Chartered Accountant.

## 1.3.2
1.3.2 Quantities of work executed as prime contractor, work performed in the past as a nominated sub-contractor will also be considered provided the sub-contract involved execution of all main items of work described in the bid document, provided further that all other qualification criteria are satisfied (in the same name and style) in the last five years.
NAME OF THE CONTRACTOR
Year | Name of the work | Name of the Employer* | Quantity of work performed
Remarks* (indicate contract Ref)
200__200__
200__200__
200__200__
200__200__
200__200__

## 1.4
1.4 Information on Bid Capacity (works for which bids have been submitted and works which are yet to be completed) as on the date of this bid.
(A) Existing commitments and on-going works:
NAME OF THE CONTRACTOR
Description of works | Place & State | Contract No. | Name & Address of Employer | Value of Contract (Rs Cr) | Stipulated Period of Completion | Value of works* remaining to be completed (Rs Cr) | Anticipated date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
NOTE:
* Attach certificate(s) from the Engineer(s)-in-Charge
The item of work for which data is requested should tally with that specified in ITB clause 4.5A ©
** Immediately preceding the financial year in which bids are received.
# Delete, if prequalification has been carried out.
(B) Works for which bids already submitted :
Description of works | Place & State | Name & Address of Employer | Estimated value of works (Rs Cr) | Stipulated period of completion | Date when decision is expected | Remarks, if any
1 | 2 | 3 | 4 | 5 | 6 | 7

## 1.5
1.5 Availability of key items of Contractor’s Equipment essential for carrying out the Works [Ref. Clause 4.5(B)(a)]. The Bidder should list all the information requested below. Refer also to Sub Clause 4.3 (d) of the Instruction to Bidders.
NAME OF THE CONTRACTOR
Description of works | Requirement |  | Availability proposals |  |  | Remarks (from whom to be purchased)
| No. | Capacity | Owned/Leased to be procured | Nos./Capacity | Age/ Condition
1 | 2 | 3 | 4 | 5 | 6 | 7

## 1.6
1.6 Qualifications and experience of key personnel required for administration and execution of the Contract [Ref. Clause 4.5(B)(b)]. Attach biographical data. Refer also to Sub Clause 4.3 (e) of instructions to Bidders and Sub Clause 9.1 of the Condition
NAME OF THE CONTRACTOR
Position | Name | Qualification | Year of Experience (General) | Years of experience in the proposed position
Etc.

## 1.7, 1.8, 1.9 and 1.10
1.7 Proposed sub-contracts and firms involved. [Refer ITB Clause 4.3(k)]
NAME OF THE CONTRACTOR
Sanction of the works | Value of Sub-contract | Sub-contractor (Name & Address) | Experience in similar work
1 | 2 | 3 | 4
NOTE:
Attach copies of certificates on possession of valid license for executing water supply/ sanitary work/ building electrification works [Reference Clause 4.5(d) & Clause 4.5(e)]
*1.8 Financial reports for the last five years: balance sheets, profit and loss statements, auditors' reports (in case of companies/corporation), etc. List them below and attach copies.
1.9 Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List them below and attach copies of support documents.
1.10 Name, address and telephone, telex and fax numbers of the Bidders' bankers who may provide references if contacted by the Employer.

## 1.11
1.11Information on litigation history in which the Bidder is involved.
NAME OF THE CONTRACTOR
Other Party(ies) | Employer | Cause of Dispute | Amount involved | Remarks showing Present Status
1.12 Statement of compliance under the requirements of Sub Clause 3.2 of the instructions to Bidders. (Name of Consultant engaged for project preparation is ** ........................ …………….............................)
Proposed work method and schedule. The Bidder should attach descriptions, drawings and charts as necessary to comply with the requirements of the Bidding documents. [Refer ITB Clause 4.1 & 4.3(1)]
1.14 Programme
1.15 Quality Assurance Programme
2 Additional Requirements
2.1 Bidders should provide any additional information required to fulfill the requirements of Clause 4 of the Instructions to the Bidders, if applicable.
(i) Affidavit
(ii) Undertaking
*** (iii) Update of original prequalification application
*** (iv) Copy of original prequalification application
*** (v) Copy of prequalification letter
* Delete, if prequalification has been carried out.
** Fill the Name of Consultant.
*** Delete, if prequalification has not been carried out.

## 1.12 CHECK LIST
Check List for Submission Of Tender
Evaluation will be done as per the information provided in the document attached with tender. Bidder may disqualified, if documents are not attached properly.
Name of the Bidder
Sl. No. | Checklist Items (Attach Documents in Edit Attachment Folder) | Document attached
1 | BIDSECURITY PHOTO COPY
2 | LAST 5 YEARS ANNUAL TURN OVER
3 | EXPERIENCE Of SIMILAR NATURE Of W0RKS
4 | QUANTITY OF WORK OF SIMILAR NATURE EXECUTED DURING LAST 5 YEARS)
5 | BALANCE VALUE OF ON GOING WORKS
6 | EXISTING COMMITMENTS
7 | BANKER'S CERTIFICATE FOR ACCESS OF FINACIAL RESOURCES
8 | AFFIDAVIT
9 | UNDERTAKING
10 | LITIGATION HISTORY
11 | PLANT and MACHINARIES
12 | KEY PERSONNEL
13 | Registration
14 | Power of Attoney
15 | Legal Status Of Bidder
16 | PROGRAMME Of CONSTRUCTION
17 | NOC FOR DEBAR
18 | LABOUR LICENCE
19 | PAN CARD
20 | GST CERTIFICATE
21 | Character Certificate
22 | Any other Documens required as per NIT/ Standard Bidding Documents Required
IF YOU HAVE NOT BEEN DEBARED WRITE "NOT APPLICABLE" IN YOUR LETTER HEAD SCAN AND UPLOAD IN THE IN NOC FOR DEBAR LINK
Note:-Attachment should be self attested and should be attached as per above instruction, otherwise it may be rejected.
I, the undersigned, do hereby certify that all the statements made in the required attachments are true and correct.
Signature & Seal of the Bidder