## B.O.Q.
Bill of Quantity
योजना का नाम:- नगर निगम मोतिहारी क्षेत्रांतर्गत वार्ड संख्या 22 में अवधेश राय के घर से मनोज साह के घर तक आरसीसी नाला एवं पीसीसी सड़क का निर्माण कार्य
|  | Estimated Cost:- |  | Rs.
|  | E/M to be Deposited:- |  | Rs.
|  | Cost of BOQ:- |  | Rs.
Time of completion:-
Date of Tender:-
E-Tendering Fee
Sl No. | SOR | Item of Works | Unit | Quantity | Rate | Amount
1 | BCD/2.25(A ) | Providing E/W filling in road side embankment including dressing of sides and ramming of bottoms with all complete.job | m3 | 144.33 | 411.7 | 59420.66
2 | BCD/ 15.2.1 | Demolishing cement concrete including disposal of materials within 50m lead 1:3:6 or richer mix | m3 | 30.36 | 970.9 | 29476.52
3 | BCD/ 2.8.1 | Earth work in excavation infoundation trenches or drains (not excluding 1.5m in width or 10spen or plain) including dressing of sides and raiming of bottoms liftup to 1.5m including gating out the excavated soil and disposal of surplus excavated soil dorected with in of 50m. | m3 | 224.32 | 360.7 | 80912.22
4 | BCD/ 2.28 | Supply and filling inplinth with local sand under floor including watering ramming can soil dating and dressing comp. | m3 | 150.58 | 287.3 | 43261.63
5 | BCD/ 11.72 | Providing designation 100A one brick flat soling joint filled with local sand including cost of watering taxes royality all complete as per building specification and direction E/I. | m2 | 236.99 | 283.3 | 67139.27
6 | BCD/11.73 | Providing designation 100 A one brick on edge soling and Joints filled with local sand in proper grade, camber or super elevation including cost of providing high barrier danger signals and chaukidar taxes and royality all jobs as per specification direction of E/I | m3 | 868.96 | 444.8 | 386513.41
7 | BCD/16.42 | Providing cement concrete 1:2:4 (1 cement:2 coarse sand :4 graded stone aggregates 40mm nominal size) in pavements ,laid to required slope and camber in panels as required including consolidation, finishing tamping all complete job and direction of E/I | m3 | 132.51 | 4649 | 616038.99
8 | BCD/5.9.2 | Providing shuttering and centring including strutting ,propping etc. and removal of form for walls including attached pilasters ,buttrusses ,plinth and string courses with all complete jobs and direction of E/I. | m2 | 1217.66 | 375.1 | 456744.27
9 | BCD/5.1.2 | Providing and laying RCC in Drain (1:1.5:3) 1 cement 1.5course sand 4 graded stone agregate 20mm nominal size. | m3 | 147.05 | 4688.3 | 689414.52
10 | BCD/5.22.7B | Reinforcement for R.C.C. work including straigheining, cutting, bending placing inposition and binding all complete TMTC 500 - 10mm dia | kg | 12859.43 | 92.6 | 1190783.22
11 | BCD/10.2 | Structural steel work riveted or bolted in built up sections ,trusses and framed work including cutting ,hoisting fixing in position and applying primer coat of approved ateef primer all complete | kg | 617.32 | 95.4 | 58892.33
| TOTAL RS. |  |  |  |  | 3678597.04
12 |  | Add extra cost of materials:
A |  | bricks | Nos | 54358 | 359.04 | 19516.7
B |  | cement | MT | 101.22 | 231.56 | 23438.5
|  | TOTAL RS. |  |  |  | 42955.2
13 |  | Add carriage cost of materials:
A |  | bricks. | Nos | 54358 | 919.21 | 49966.42
B |  | local sand | m3 | 180.2 | 310.47 | 55946.69
C |  | coarse sand | m3 | 122.86 | 2941.19 | 361354.6
D |  | stone aggregates | m3 | 237.63 | 2547.88 | 605452.72
|  | Sub Total: |  |  |  | 4794272.67
|  | Adding 5.36% for 18% GST |  |  |  | 256973.02
|  | Total (1) |  |  |  | 5051245.69
15 |  | Add S. Fee cost of material:
A |  | Bricks | Nos | 54358 | 512.8 | 27874.78
B |  | Local Sand | m3 | 180.2 | 14.2 | 2558.84
C |  | Coorse Sand | m3 | 122.86 | 17.6 | 2162.34
D |  | Stone Chips | m3 | 237.63 | 59.5 | 14138.99
E |  | E/Work | m3 | 0 | 3.3 | 0
|  | SUB TOTAL RS. |  |  |  | 46734.95
|  | Add 18% GST |  |  |  | 8412.291
|  | TOTAL(2) RS |  |  |  | 55147.241
|  | TOTAL (1+2) RS |  |  |  | 5106392.931
|  | say |  |  |  | 5106393