## 700
BIILL OF QUANTITY (BOQ) FOR HIGH LEVEL BRIDGE ACROSS
CHATANIYA TO JHALBASA AT CH 700
4SPANS OF 20 M. =80 M.
Name of Bridge :- Bridge Across sukha nalla onChatniya to Jhalbasa at CH-700 M.
| Package No. :- CG LSB 24-65 |  |  | District- Balrampur (C.G.)
| Length of Bridge = 80 M. |  |  | Block- Kusmi
Total Road Length Approach = 145 + 114 = 259 M
SOR enforced from 01st Jan 2015 Amendment issue by CGRRDA Raipur Letter No. 1307 Dated 03.02.2016 for PMGSY Bridge work.
ESTIMATE BASED ON CGRRDA ROAD SOR 2018
S.No. | Ref. From SOR | Description | Unit | Rate | Quantity | Amount
FOUNDATION
1 |  | Excavation
| 2..1 | Earth work in excavation of foundation of structures as per drawing and technical specification, including setting out, construction of shoring and bracing, removal of stumps and other deleterious matter, dressing of sides and bottom and backfilling with approved material including dewatering etc. complete.
| I | Ordinary soil
| (i) | Upto 3 m depth | Cum | 131.4 | 1926.6095 | 253156.4933
| (ii) | 3 m to 6 m depth | Cum | 150.3 | 0 | 0
| (iIi) | Above 6 m depth | Cum | 184.5 | 0 | 0
| III | Ordinary rock (not requiring blasting) | Cum | 221.4 | 0 | 0
| III | Hard rock (requiring blasting) | Cum | 610.2 |  | 0
Dewatering
Add extra 20% in the rates of above items for dewatering (Assessment of dewatering shall be made as per site condition).
| I | Ordinary soil
| (i) | Upto 3 m depth | Cum | 26.28 | 1926.6095 | 50631.2987
| (ii) | 3 m to 6 m depth | Cum | 30.06 | 0 | 0
| (iIi) | Above 6 m depth | Cum | 36.9 | 0 | 0
| II | Ordinary rock (not requiring blasting) | Cum | 44.28 | 0 | 0
2 | 2.16 | MS Liner for Piles |  |  |  | 0
|  | Providing steel liner 10 mm thick for curbs and 6mm thick for steining of wells including fabricating and setting out as per detailed drawing and specifications as per section 1200 and 1900. | MT | 65286 | 22.782 | 1487345.652
3 | 2.17(iii) | Bored Cast in-situ Piles
|  | Bored cast-in-situ M35 grade R.C.C. pile excluding reinforcement complete as per drawing and technical specifications and removal of excavated earth with all lifts and lead upto 1000 m as per section 1100 and 1700. | Rm | 14123.7 | 516 | 7287829.2
4 | 2.21 (i) | Pile Load Test
|  | Pile Load Test on single Vertical Pile in accordance with IS:2911(Part-IV) in static load method only | ton | 1350 | 1255.75 | 1695262.5
5 | 2.22 A(iii) | Reinforced Cement Concrete in foundations - M35
|  | Cement concrete for reinforced concrete in pile cap complete as per drawing and Technical Specifications per clause 1100,1500 and 1700. | Cum | 5297.4 | 294.678 | 1561027.2372
6 | 2.24 | HSD bar Reinforcement
|  | Supplying, fitting and placing HSD (High Strength Deformed Steel) bar reinforcement in foundation complete as per drawing and technical specifications as per section 1600. | ton | 61823.7 | 105.5546 | 6525774.6875
7 | 2.6 | M15 grade PCC below foundation
| 2.6 A (i) | Plain/Reinforced cement concrete in open foundation complete as per drawing and technical specifications. | Cum | 4151.7 | 93.8894 | 389800.6851
8 | 2.25 | Exploratory boring
Taking trail boring 100mm dai. For detailed investigation with diamound drill double tube in all sorts of soil like sand,soft soil, ,moorum, gravels, boulders and soft rock including all materials such as casing pipes, accessories, grease and other such materials and or as required including conveying the loose sample and core sample serially numbered at the site of work and conveying the head quarters of concerned office as directed and submission of detailed bore log sheet as per I.R.C. 78-2014 and section 2400 including testing of sample as per specification.
| (i) | Upto 1.0 m below bed level | RM | 5355.9 | 5 | 26779.5
| (ii) | Beyond 1.0 m upto 5.0 depth | RM | 1170 | 20 | 23400
| (iii) | Beyond 5.0 m | RM | 1327.5 | 75 | 99562.5
SUBSTRUCTURE
9 |  | Reinforced Cement Concrete in substructure - M30
| 3.6 E (a) (iii) | Providing and laying Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications section 1500, 1700 and 2200 (Newly laid concrete shall be covered by gunny bags). | Cum | 5894.1 | 522.2603 | 3078254.7106
10 |  | HSD bars reinforcements in substructure
| 3.7 | Supplying, fitting and placing HSD (High Strength Deformed Steel) bars reinforcement in sub-structure complete as per drawing and technical specifications section 1600 and 2200. | MT | 62101.8 | 62.6712 | 3891996.9133
11 |  | Weap Holes
| 3.8 | Providing weep holes in Brick masonry/ Plain/ Reinforced concrete abutment, wing wall/return wall with 100 mm dia AC pipe, extending through the full width of the structure with slope of 1V :20H towards drawing face. Complete as per drawing and Technical specifications section 2706 and 2200. | m | 288.9 | 96.3974 | 27849.1966
12 |  | Back Filling Behind abutment
| 3.9 | Back filling behind abutment, wing wall and return wall complete as per drawing and Technical specification 710.1.4 of I.R.C. 78 and 2200. | Cum | 814.5 | 143.9855 | 117276.1898
13 |  | Elastomeric Bearing |  |  |  | 0
| 3.14 | Supplying, fitting and fixing in position true to line and level elastomeric bearing conforming to IRC: 83 (Part-II) section IX and clause 2005 of MORT&H specifications complete including all accessories as per drawing and Technical Specifications section 2000 and 2200. | Cucm | 0.9 | 187200 | 168480
SUPERSTRUCTURE
14 |  | Reinforced Cement Concrete in Deck slab and Diaphrags, M30
| 4.1 B II (a) (ii) | Furnishing and Placing Reinforced/Prestressed cement concrete in super-structure as per drawing and Technical Specification sections 1500, 1600 and 1700 (Newly laid concrete shall be covered by gunny bags). | Cum | 6798.6 | 189.6819 | 1289571.5693
Reinforced Cement Concrete in RCC Girder, M30
| 4.1 B II (a) (ii) | Furnishing and Placing Reinforced/Prestressed cement concrete in super-structure as per drawing and Technical Specification sections 1500, 1600 and 1700 (Newly laid concrete shall be covered by gunny bags). | Cum | 6798.6 | 164.2113 | 1116406.9442
15 |  | HSD bars reinforcement in Superstructure
| 4.2 | Supplying, fitting and placing HSD (High Strength Deformed Steel) bar reinforcement in super-structure complete as per drawing and technical specifications. | MT | 63090.9 | 56.6229 | 3572390.7815
16 |  | RCC railing of M30 Grade,
| 4.5 | Concrete M30
|  | Construction of precast RCC railing of M30 Grade, aggregate size not exceeding 12 mm, true to line and grade, tolerance of vertical RCC post not to exceed 1 in 500, centre to centre spacing between vertical post not to exceed 2000 mm, leaving adequate space between vertical post for expansion, complete as per approved drawings and technical specifications as per relevant clauses of section 1500, 1600, 1700 and 2703 (vide drawing No. SD/202, SD/304) | m | 1686.6 | 174.08 | 293603.328
| 4.2 | HSD bars reinforcement for RCC Crash Barrier
|  | Supplying, fitting and placing HSD (High Strength Deformed Steel) bar reinforcement in super-structure complete as per drawing and technical specifications. | MT | 63090.9 | 0 | 0
17 |  | Cement Concrete Wearing Course
| 4.4 | Providing and laying Cement concrete wearing coat M-30 grade including reinforcement complete as per drawing and Technical Specifications as per relevant clause of section 2700. | Cum | 10662.3 | 48.96 | 522026.208
16 |  | RCC railing of M30 Grade
| 4.5 | Construction of precast RCC railing of M30 Grade, aggregate size not exceeding 12 mm, true to line and grade, tolerance of vertical RCC post not to exceed 1 in 500, centre to centre spacing between vertical post not to exceed 2000 mm, leaving adequate space between vertical post for expansion, complete as per approved drawings and technical specifications as per relevant clauses of section 1500, 1600, 1700 and 2703 (vide drawing No. SD/202, SD/304) | m | 1686.6 | 0 | 0
18 |  | Drainage Spout
| 4.9 | Supplying and installing drainage spouts complete as per drawing and Technical specification clause 2705. | Nos | 1806.3 | 54 | 97540.2
19 |  | M15 grade PCC below Approach Slab
| 4.1 | PCC M15 Grade leveling course below approach slab complete as per drawing and Technical specification and as per relevant section 2700 | Cum | 3993.3 | 8.82 | 35220.906
RCC in Approach Slab, including reinf
| 4.11 | Providing and laying M-30 grade Reinforced cement concrete approach slab including reinforcement and formwork complete as per drawing and Technical specification and as per relevant sections 1500, 1600, 1700 and 2704 | Cum | 8520.3 | 17.64 | 150298.092
20 |  | Strip seal type expansion joint
| 4.18 | Strip Seal Expansion Joint (Providing and laying of a strip seal expansion joint catering to maximum horizontal movement upto 70 mm, complete as per approved drawings and standard specifi cations to be installed by the manufacturer/supplier or their authorized representative ensuring compliance to the manufacturer's instructions for installation.) | m | 10011.6 | 42 | 420487.2
21 |  | Filler joint
| 4.14 (D) | Providing and filling joint sealing compound ( 12 m long x 100 mm wide x 10 mm deep recess) as per drawings and technical specifications with coarse sand and 6% bitumen by weight | Sqm | 198 | 42 | 8316
22 |  | Testing of span of bridge
| 4.24 | Testing of span of bridge for deflection due to live load with platform for loading arrangements, apparatus for measurement etc. complete as per drawing and specifications (As per IRC : SP-51) | Ton | 765 | 77 | 58905
20 |  | Bituminous Wearing Coat
| 5.5 A (iii)-PWD ROAD SOR 2015 | Bituminous Concrete (Providing and laying bituminous concrete with minimum 40-60 TPH capacity hot mix plant using crushed aggregates of specified grading, premixed with bituminous binder @ 5.0 to 6.0% by weight of total mix of mix and filler, transporting the hot mix to work site, laying with a hydrostatic paver finisher with sensor control to the required grade, level and alignment, rolling with smooth wheeled, vibratory and tandem rollers to achieve the desired compaction as per MORTH specification clause No. 507 complete in all respects).A.With sensor paver finisherfor (iii) Grading II (13.2 mm nominal size) with bitumen 6.0 % | Cum | 9082.8 | 0 | 0
Mastic Asphalt Layer
| 5.10 PWD ROAD SOR 2015 | Mastic Asphalt (Providing and laying 25mm thick mastic asphalt wearing course with paving grade bitumen meeting the requirements given in table 500-39 prepared by using mastic cooker and laid to required level and slope after cleaning the surface, including providing antiskid surface with fine-grained hard stone chipping of 13.2 mm nominal size pre- coated with bitumen at the rate of 0.005cum per 10 sqm and at an approximate spacing of 10 cm center to center in both directions, pressed into surface when the temperature of surfaces not less than 1000C, protruding 1 mm to 4 mm over mastic surface, all complete as per clause-516.) | Sqm | 459.9 | 0 | 0
23 |  | Cement Concrete Blocks Of Size 0.3x0.3x0.3 m Cast In Cement Concrete Of Grade M15
| 5.4 B | Providing and lying Pitching on slopes laid over prepared filter media in front of toe of embankement complete as per drawing and technical specification as per section 2504. | Cum | 4234.5 | 59.8674 | 253508.4896
24 |  | Filter Media
| 3.10 | Providing and laying of Filter media with granular materials/stone crushed aggregates satisfying the requirements laid down in clause 2504.2.2. of MORT&H specifications to a thickness of not less than 600 mm with smaller size towards the soil and bigger size towards the wall and provided over the entire surface behind abutment, wing wall and return wall to the full height compacted to a firm condition complete as per drawing and technical specifications 710.1.4 of I.R.C. 78 and 2200. | Cum | 1733.4 | 71.9278 | 124679.6347
| 5.5 | Providing and laying Filter material underneath pitching in slopes complete as per drawing and Technical specification including trimming of slopes to proper profile and preparation of bed as per section 2504. | Cum | 1871.1 | 39.9116 | 74678.5901
25 |  | Embankment Earthwork
| 3.4(ii)-Road ‐2018 CGRRDA | Construction of embankment with approved material obtained from borrow pits, transporting to site, spreading, grading to required slope and compacting to meet requirement of Tables 300.1 and 300.2 (Beyond 250m)with all leads as per Technical Specification Clause 301.5(Having CBR more than 5) | Cum | 176 | 268.2505 | 47212.0936
26 |  | Traffic Sign Boards
| 9.2 A Road ‐2018 CGRRDA | Semi-Reflective Traffic signs upto 0.90 sqm Direction and place indentification signs up to 0.9 sqm size board Providing and erecting direction and place identifications of semi reflective sign boards as per IRC:67 made of 2 mm thick M.S. Sheet duly stove enameled paint in white colour in front and grey colour on back with red reflective border of 70 mm width and required message, letters, figures with reflective engineering grade tape as per MORD specifications of required shade and colour. Supported and welded on 47 mm x 47mm of 12 SWG Square tube of 3050 mm height duly strengthened by 25 mm x 5 mm M/s flat iron on edges on back firmly fixed to the ground by means of properly designed foundations with M-15 grade cement concrete 450 mm x 450 mm x 600 mm, 600 mm below ground level as per approved drawing and Technical Specification Clause 1701 | Sqm | 4729 | 2 | 9458
| 9.2 B Road ‐2018 CGRRDA | Semi-Reflective Traffic signs more than 0.90 sqm sign board Providing and erecting direction and place identification of semi reflective sign boards as per IRC-67 made of 2 mm thick M.S. Sheet duly stove enameled paint white colour in front and grey colour on back with reflective border of 70 mm width and required message, letters, figures with reflective tape of engineering grade as per MORD specifications of required shade and colour. Supported and welded on two nos. 47 mm x 47 mm of 12 SWG square tube of 3050 mm height duly strengthened by 25 mm x 5 mm MS flat iron on edges on back firmly fixed to the ground by means of properly designed foundations with M-15 grade cement concrete 450 mm x 450 mm x 600 mm, 600 mm below ground level as per approved drawing and Technical Specification Clause 1701 | Sqm | 4667 | 2 | 9334
26 |  | PMGSY Information Board |  |  |  | 0
| 9.14 B Road ‐2018 CGRRDA | Providing and fixing of typical PMGSY informatory sign board with Logo as per MORD specifications and drawing. Three MS Plates of 1.6 mm thick, top and middle plate duly welded with MS flat iron 25mm x 5m size on back on edges. The lower plate will be welded with MS angle iron frame of 25mm x 25mm x 5mm. The angle iron frame of the lower most plate and flat iron frame of middle plate will be welded to 2 nos. 75mm x 75 mm of 12 SWG sheet tubes posts duly embedded in cement concrete M-15 grade blocks of 450mm x 450mm x 600mm, 600mm below ground level. The top most diamond plate will be welded to middle plate by 47mm x 47mm of 12 SWG steel plate tube. All M.S. will be stove enameled on both sides. Lettering and printing arrows, border etc. will be painted with ready mixed synthetic enamel paint of superior quality in required shade and colour. All sections of framed posts and steel tube will be painted with primer and two coats of epoxy paint as per drawing Clause 1701 and Annexure 1700. | Nos | 13749 | 1 | 13749
27 |  | PMGSY Citizen Information Board
| 9.15 A Road ‐2018 CGRRDA | Providing and fixing of typical " PMGSY Citizen Information Board" with Logo as per MoRD specifications & drawings, made of 75 mm square or 75 mm dia circular steel tube of 12 SWG 3.2 m height and cross member 2 nos 1m long, fixed with angle iron 50x50x5 mm MS angle on the back. | Nos | 14015 | 1 | 14015
27 |  | Marble Plate
| 4.22 | Providing and Fixing of Av. 20mm thick marble plate i/c cutting and polishing and inscribed details as per approved drawing i/c engraving the matter as desired. | Nos | 4500 | 1 | 4500
28 |  | Painting on Concrete Surfaces
| 9.5 Road ‐2018 CGRRDA | Painting two coats including prime coat with epoxy paint of approved brand on concrete/steel surfaces after through cleaning of surface to give an even shade as per drawing and Technical Specification Clause 1701 | Sqm | 105 | 2585.2096 | 271447.008
29 |  | Painting on Concrete Surfaces of R.C.C. Railing
| 4.21 | Painting on concrete surface of R.C.C. Railing (Providing and applying 2 coats of water based cement paint to unplastered concrete surface after cleaning the surface of dirt, dust, oil, grease, efflorescence and applying paint @ of 1 litre for 2 Sq.m. ) | Sqm | 135.9 | 450.3784 | 61206.4246
30 |  | Dismantling of existing structure
| 1.4 I (B) | Dismantling of existing structures like culverts, bridges, retaining walls and other structure comprising of masonry, cement concrete, wood work, steel work, including T&P and scaffolding wherever necessary, sorting the dismantled material, disposal of unserviceable material and stacking the serviceable material with all lifts and lead upto 1000 meters and as per relevant clauses of section-200 in ( Cement Concrete Grade M-15 & M-20) | Cum | 313.2 | 0 | 0
| 1.4 IX (A) | Removing all type of hume pipes and stacking within a lead upto 1000 meters including earthwork and dismantling of masonry works around pipes.(Up to 1000 mm dia) | m | 360 | 0 | 0
| 1.6 | Dismantling of cement concrete pavement i/c breaking to pieces not exceeding 0.02 cum in volume and stock piling at designated locations and disposal of dismantled materials lead upto 1000 meters, stacking serviceable and unserviceable materials separately and as per relevant clauses of section-200. | Cum | 993.6 | 0 | 0
Approach Road
31 | 3.5 (i) | Excavation
Excavation in
|  | Excavation for roadway in soil for carrying of cut earth to embankment site with a lift upto 1.5 m and lead upto 50 m as per Technical Specification Clause 302.3 | Cum | 65 | 546 | 35490
Excavation in
|  | Excavation for roadway in soil for carrying of cut earth to embankment site with a lift upto 1.5 m and lead upto 50 m as per Technical Specification Clause 302.3 | Cum | 65 | 695 | 45175
32 |  | Construction of embankment
| 3.4 (i) | Construction of embankment with approved material obtained form borrow pits, transported to site, spreading, grading to required slopes and compacting to meet requirement of Tables 300.1 & 300.2 with a lead up to 250 m as per technical specifications clause 301.5 | Cum | 170 | 5978 | 1016260
33 |  | Shoulders
| 3.12 (b) | Construction of subgrade and earthen shoulders with approved material (Granular material having CBR not less than 10) obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacted to meet requirement of Table 300.2 as per Technical Specification Clause 303.1.(To be used for side shoulder WBM) | Cum | 200 | 142 | 28400
34 |  | Construction of granular sub-base
| 4.1 (a) | Construction of granular sub-base by providing well graded material having CBR 20 or more, spreading in uniform layers with motor grader on prepared surface, mixing by mix in place method with rotavator at OMC, and compacting with vibratory rollers of 80 to 100KN static weight to achieve the desired density, complete as per Technical Specification Clause 401. For Grading mentioned in table 400.1 (Grading III) | Cum | 650 | 68 | 44200
35 | sor 2015 | Dry Lean Concrete
| 6.1 | Dry Lean Cement Concrete Sub-base as per IRC:SP-49 (Construction of dry lean cement concrete Sub-base over a prepared sub-grade with coarse and fine aggregate conforming to IS: 383, the size of coarse aggregate not exceeding 26.5 mm, aggregate cement ratio not to exceed 15:1, aggregate gradation after blending to be as per table 600-1, cement content not to be less than 150 kg/cum, optimum moisture content to be determined during trial length construction, concrete strength not to be less than 10 Mpa at 7 days, mixed in a batching plant, transported to site, laid with a paver with electronic sensor, compacting with 8-10 tonnes vibratory roller, finishing and curing as per clause 601.) | Cum | 2332 | 236 | 550352
36 |  | Cement Concrete Pavement
| 6.1 (i) | Construction of un-reinforced, dowel jointed at expansion and construction joint only, plain cement concrete pavement, thickness as per design, over a prepared sub base, with 43 grade cement or any other type as per Clause 1501.2.2 M30 (Grade), coarse and fine aggregates conforming to IS:383, maximum size of coarse aggregate not exceeding 25 mm, mixed in a concrete mixer of not less than 0.2 cum capacity and appropriate weigh batcher using approved mix design, laid in approved fixed side formwork (steel channel, laying and fixing of 125 micron thick polythene film, wedges, steel plates including eveling the formwork as per drawing), spreading the concrete with shovels, rakes, compacted using needle, screed and plate vibrators and finished in continuous operation including provision of contraction and expansion, construction joints, applying debonding strips, primer, sealant, dowel bars, near approaches to bridge/culvert and construction joints, admixtures as approved, curing of concrete slabs for 14-days,using curing compound (where specified) and water finishing to lines and grade as per drawing and Technical Specification Clause 1501. | Cum | 5903 | 315 | 1859445
37 |  | Pitching on slopes
| 10.5 (ii) | Providing and laying pitching on slopes laid over prepared filter media as per drawing and technical specifications Clause 1302. Cement concrete blocks of size as per Table 1300.2 cast in cement concrete of grade M 15. | Cum | 4356 | 511 | 2225916
38 |  | Filter Media
| 10.6 | Providing and laying filter material underneath pitching in slopes complete as per drawing and technical specifications Clause 1302 | Cum | 1660 | 256 | 424960
Diversion Road Qty Summary
39 |  | Clearing and grubbing
| 2.3 | Clearing and grubbing road land including uprooting wild vegetation, grass, bushes, shrubs, saplings and trees of girth upto 300 mm, removal of stumps of such trees cut earlier and disposal of unserviceable materials and stacking of serviceable material to be used or auctioned, upto a lead of 1000 m including removal and disposal of top organic soil not exceeding 150 mm in thickness as per Technical Specification Clause 201. (A) In area of non-thorny jungle | Sqm | 5 | 2543 | 12715
40 |  | Construction of subgrade
| 3.12 (a) | Construction of subgrade and earthen shoulders with approved material (Granular material having CBR not less than 7) obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacted to meet requirement of Table 300.2 as per Technical Specification Clause 303.1.For Item No.3.12(a) & (b) | Cum | 180 | 381 | 68580
41 |  | (For Profile Correction) Construction of embankment
| 3.4 (ii) | (For Profile Correction) Construction of embankment with approved material obtained from borrow pits, transporting to site, spreading, grading to required slope and compacting to meet requirement of Tables 300.1 and 300.2 (Beyond 250m)with all leads as per Technical Specification Clause 301.5(Having CBR more than 5) | Cum | 176 | 572 | 100672
42 |  | Construction of granular sub-base
| 4.1 (A) | Construction of granular sub-base by providing well graded material having CBR 20 or more, spreading in uniform layers with motor grader on prepared surface, mixing by mix in place method with rotavator at OMC, and compacting with vibratory rollers of 80 to 100KN static weight to achieve the desired density, complete as per Technical Specification Clause 401. | Cum | 650 | 201 | 130650
43 |  | Crushed stone aggregates
| 4.7 (B) | Providing, laying, spreading and compacting mechanically crushed stone aggregates of specific sizes to water bound macadam specification including spreading in uniform thickness, hand packing, rolling with three wheel 80-100 kN static roller in stages to proper grade and camber, applying and brooming, crushable screening to fill-up the interstices of coarse aggregate, watering and compacting to the required density Grading 2 as per Technical Specification Clause 405. | Cum | 1415 | 100 | 141500
44 |  | Semi-Reflective Traffic signs
| 9.2 (B) | Semi-Reflective Traffic signs more than 0.90 sqm sign board. Providing and erecting direction and place identification of semi reflective sign boards as per IRC-67 made of 2 mm thick M.S. Sheet duly stove enameled paint white colour in front and grey colour on back with reflective border of 70 mm width and required message, letters, figures with reflective tape of engineering grade as per MORD specifications of required shade and colour. Supported and welded on two nos. 47 mm x 47 mm of 12 SWG square tube of 3050 mm height duly strengthened by 25 mm x 5 mm MS flat iron on edges on back firmly fixed to the ground by means of properly designed foundations with M-15 grade cement concrete 450 mm x 450 mm x 600 mm, 600 mm below ground level as per approved drawing and Technical Specification Clause 1701 | Sqm | 4667 | 2 | 9334
45 | 7.1 (I) (i) | Excavation for Structure of 1000mm pipe
|  | Excavation for Structure of 1000mm pipes as per drawing and technical specifications Clause 305.1 including setting out, construction of shoring and bracing, removal of stumps and other deleterious material and disposal upto a lead of 50 m, dressing of sides and bottom and backfilling in trenches with excavated suitable material. | Cum | 253 | 38 | 9614
46 |  | cement concrete pipe NP3
| 7.6 (a) | Providing and laying reinforced cement concrete pipe NP3 for Culverts/ Burried conduits on first class bedding of granular material including fixing collar with cement mortar 1:2 but excluding excavation, protection works, backfilling, concrete and masonry works in head walls and parapets as per Clause 1106. | Rm | 2928 | 30 | 87840
47 |  | Filling in Foundation Trenches
| 7.8 (I) | Providing and laying reinforced cement concrete pipe NP3 for Culverts/ Burried conduits on first class bedding of granular material including fixing collar with cement mortar 1:2 but excluding excavation, protection works, backfilling, concrete and masonry works in head walls and parapets as per Clause 1106. | Nos | 911 | 7 | 6377
48 |  | Backfilling behind abutment
| 7.23 (i) | Backfilling behind abutment, wing wall and return wall complete as per drawings & technical specification Clause 1204.3.8. Granular Material | Cum | 732 | 22 | 16104
|  |  | TOTAL |  |  | 41946565.2337 |  | Maintenance cost total Without gst & Prepration DPR
|  |  | GST 18% |  |  | 7550381.7421 |  | 1048664.1308
|  |  | TOTAL |  |  | 49496946.9758
|  |  | Says Lack |  |  | 494.9695
MAINTENANCE COST
| 1 | 1st Year Maintenance | 15% |  |  | 157299.6196
| 2 | 2nd Year Maintenance | 15% |  |  | 157299.6196
| 3 | 3rd Year Maintenance | 20% |  |  | 209732.8262
| 4 | 4th Year Maintenance | 25% |  |  | 262166.0327
| 5 | 5th Year Maintenance | 25% |  |  | 262166.0327
| Total 5 Year Maintenance Amounts |  |  |  |  | 1048664.1308
| GST 18% | ADD GST 18% |  |  |  | 188759.5436
| Total Maintenance Amount |  |  |  |  | 1237423.6744 | 12.3742
| Grand Total (Construction + Maintenace ) |  |  |  |  | 50734370.6502
| SAYS. LACK |  |  |  |  | 507.3437
Sub Engineer CGRRDA, PIU-Rajpur Distt. Balrampur |  | Assistant Engineer CGRRDA, PIU-Rajpur Distt. Balrampur | Executive Engineer CGRRDA, PIU-Rajpur Distt. Balrampur

## COMPRATIVE (hidden)
Comperative Statement
ISSUED BY ENGINEER IN-CHIEF C.G.P.W.D RAIPUR
INFORCE FORM 01.01.2016
COMPRETIVE STATEMENT FOR HIGH LEVEL BRIDGE ACROSS
REVISED ESTIMATE FOR HIGH LEVEL BRIDGE ACROSS GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.(CG05077)
7 SPAN @ 21.43 M = 150 M., ABUTMENT 2 x 5.0 = 10 M. WALL TYPE PIER & R.C.C. BOX TYPE ABUTMENT
ISSUED BY CHIEF ENGINEER C.G.R.R.D.A. RAIPUR
INFORCE FORM 01.09.2014
Parsodikala Side =250.00 M. & Sukhari Side = 100.00 m.
Sr. no. | Item Id | BOQ Description | Unit | As Per DPR |  |  | As per Revised/Actual |  |  | Saving |  |  | Excess |  |  | Reason
|  |  |  | Qty | Rate | Amount | Qty | Rate | Amount | Qty | Rate | Amount | Qty | Rate | Amount
1 | 2.1 | Excavation for Structures (Earth work in excavation of foundation of structures as per drawing and technical specification, including setting out, construction of shoring and bracing, removal of stumps and other deleterious matter, dressing of sides and bottom and backfilling with approved material.)
| A | Ordinary soil
| (i) | Up to 3m depth | cum | 3726 | 131.4 | 489596.4 | #REF! | #REF! | #REF! | #REF! | 131.4 | #REF! | 0 | 131.4 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | 3m to 6 depth | cum | 1046 | 150.3 | 157213.8 | 0 | 150.3 | 0 | 1046 | 150.3 | 157213.8 | 0 | 150.3 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | Above 6 m depth | cum | 51 | 184.5 | 9409.5 | 0 | 184.5 | 0 | 51 | 184.5 | 9409.5 | 0 | 184.5 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| C | Hard rock (requiring blasting) | cum | 552 | 721.8 | 398433.6 | 0 | 721.8 | 0 | 552 | 721.8 | 398433.6 | 0 | 721.8 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
Add extra 20% in the rates of above items for dewatering (Assessment of dewatering shall be made as per site condition )
| (i) | Up to 3m depth | cum | 1104 | 26.28 | 29013.12 | #REF! | #REF! | #REF! | #REF! | 26.28 | #REF! | 0 | 26.28 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | 3m to 6 depth | cum | 784 | 30.06 | 23567.04 | 0 | 30.06 | 0 | 784 | 30.06 | 23567.04 | 0 | 30.06 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | Above 6 m depth | cum | 51 | 36.9 | 1881.9 | 0 | 36.9 | 0 | 51 | 36.9 | 1881.9 | 0 | 36.9 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| C | Hard rock (requiring blasting) | cum | 552 | 144.36 | 79686.72 | 0 | 144.36 | 0 | 552 | 144.36 | 79686.72 | 0 | 144.36 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
2 | 2.3 | Sand Filling in Foundation Trenches as per Drawing & Technical Specifications. | cum | 0 | 1110.6 | 0 | #REF! | 1110.6 | #REF! | 0 | 1110.6 | 0 | #REF! | 1110.6 | #REF! | दोनो अबटमेन्ट बाक्स टाईप होने के FILTER Media की जगह sand Filling लेने के कारण मात्रा बढ़ रही है।
3 | 2.6 A(i) | Plain/Reinforced cement concrete in open foundation complete as per drawing and technical specifications. and technical specifications. A Using concrete mixer PCC Grade M15 | cum | 483.75 | 4151.7 | 2008384.875 | #REF! | #REF! | #REF! | #REF! | 4151.7 | #REF! | 0 | 4151.7 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा कम हो रही है।
4 | 2.6 B(III) | Plain cement concrete in sub-structure complete as per drawing and Technical Specifications (iii) RCC Grade M- 30 | cum | 623.84 | 5417.1 | 3379403.664 | #REF! | #REF! | #REF! | #REF! | 5392.8 | #REF! | 0 | 5392.8 | 0 | कार्य स्थल पर आवश्यकतानुसार RETAINING WALL कार्य होने के कारण मात्रा कम हो रही है।
5 | 2.16 | Providing steel liner 10 mm thick for curbs and 6mm thick for steining of wells including fabricating and setting out as per detailed drawing and specifications as per section 1200 and 1900. | MT | 0 | 65286 | 0 | #REF! | 65286 | #REF! | 0 | 65286 | 0 | #REF! | 65286 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से Pile Foundation देने के कारण मात्रा बढ़ रही है।
6 | 2.17 (iii) | Bored cast-in-situ M35 grade R.C.C. pile excluding reinforcement complete as per drawing and technical specifications and removal of excavated earth with all lifts and lead upto 1000 m as per section 1100 and 1700. | cum | 0 | 14123.7 | 0 | #REF! | 14123.7 | #REF! | 0 | 14123.7 | 0 | #REF! | 14123.7 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से PILE FOUNDATION देने के कारण मात्रा बढ़ रही है।
7 | L.S. | SAFE BEARING CAPACITY TEST | Nos | 0 | 3000 | 0 | 9 | 3000 | 27000 | 0 | 3000 | 0 | 9 | 3000 | 27000 | निर्माण स्थल में हार्ड राँक नही मिलने से SAFE BEARING CAPACITY TEST की आवश्यकता होने के कारण मात्रा बढ़ रही है।
8 | 2.21 | Pile Load Test on single Vertical Pile in accordance with IS:2911(Part-IV) in static load method only Lateral load test | Each Test | 0 | 67500 | 0 | #REF! | 67500 | #REF! | 0 | 67500 | 0 | #REF! | 67500 | #REF! | PILE FOUNDATION देने के कारण एक Dynomic Test होना आवश्यक है, जिस कारण मात्रा बढ़ रही है।
9 | 2.22 A (iii) | Cement concrete for reinforced concrete in pile cap complete as per drawing and Technical Specifications per clause 1100,1500 and 1700. RCC Grade M35 | cum | 0 | 5297.4 | 0 | #REF! | 5297.4 | #REF! | 0 | 5297.4 | 0 | #REF! | 5297.4 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से PILE FOUNDATION देने के कारण मात्रा बढ़ रही है।
10 | 2.23 | Levelling course for Pile cap (Providing and laying of P.C.C.M-15 levelling course 100mm thick below the pile cap.) | cum | 0 | 4067.1 | 0 | #REF! | 4067.1 | #REF! | 0 | 4067.1 | 0 | #REF! | 4067.1 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से PILE FOUNDATION देने के कारण मात्रा बढ़ रही है।
11 | 2.24 | Supplying, fitting and placing HSD (High Strength Deformed Steel) bar reinforcement in foundation complete as per drawing and technical specifications as per section 1600. | MT | 0 | 61823.7 | 0 | #REF! | 61823.7 | #REF! | 0 | 61823.7 | 0 | #REF! | 61823.7 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से PILE FOUNDATION देने के कारण मात्रा बढ़ रही है।
12 | 2.25 | Taking exploratory boring 100 mm dia. at the location of piers and abutments or for high embankments in approaches in all types of strata as per I.R.C. 78-2014 and section 2400 of specifications for collection of samples at different depth (rock sample and undisturbed soil sample) and test including preserving core samples as per specifications.
| (i) | Upto 1.0 m below bed level | each | 12 | 5355.9 | 64270.8 | #REF! | 5355.9 | #REF! | #REF! | 5355.9 | #REF! | 0 | 5355.9 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | Beyond 1.0 m upto 5.0 m depth | meter | 60 | 1170 | 70200 | #REF! | 1170 | #REF! | #REF! | 1170 | #REF! | 0 | 1170 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा कम हो रही है।
| (iii) | Beyond 5.0 m depth | meter | 28.99 | 1327.5 | 38484.225 | #REF! | 1327.5 | #REF! | 0 | 1327.5 | 0 | #REF! | 1327.5 | #REF! | निर्माण स्थल में HARD ROCK नही मिलने के कारण मात्रा बढ़ रही है।
13 | 3.6 | Providing and laying Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications section 1500, 1700 and 2200
| D(a)(iii) | Height upto 5m (RCC Grade M30) | cum | 674 | 5733 | 3864042 | #REF! | 5733 | #REF! | #REF! | 5733 | #REF! | 0 | 5733 | 0 | PILE FOUNDATION देने के कारण के कारण मात्रा कम हो रही है।
| E(a)(iii) | Height upto 5m (RCC Grade M30) | cum | 373 | 5894.1 | 2198499.3 | #REF! | 5894.1 | #REF! | #REF! | 5894.1 | #REF! | 0 | 5894.1 | 0 | PILE FOUNDATION देने के कारण के कारण मात्रा कम हो रही है।
| F(a)(iii) | Height upto 10m (RCC Grade M30) | cum | 132 | 6175.8 | 815205.6 | #REF! | 6175.8 | #REF! | #REF! | 6175.8 | #REF! | 0 | 6175.8 | 0 | PILE FOUNDATION देने के कारण के कारण मात्रा कम हो रही है।
14 | 3.7 | Supplying, fitting and placing HYSD bar reinforcement in sub-structure complete as per drawing and technical specifications section 1600 and 2200 | tonne | 121 | 62101.8 | 7514317.8 | #REF! | 62101.8 | #REF! | #REF! | 62101.8 | #REF! | 0 | 62101.8 | 0 | BRIDGE की HIGHT बढ़ने के कारण मात्रा बढ़ हो रही है।
15 | 3.8 | Providing weep holes in Brick masonry/ Plain/ Reinforced concrete abutment, wing wall/return wall with 100 mm dia AC pipe, extending through the full width of the structure with slope of 1V :20H towards drawing foce. Complete as per drawing and Technical specifications section 2706 and 2200 | meter | 122 | 288.9 | 35245.8 | #REF! | 288.9 | #REF! | 0 | 288.9 | 0 | #REF! | 288.9 | #REF! | कार्य स्थल पर आवश्यकतानुसार RETAINING WALL कार्य होने के कारण मात्रा बढ़ रही है।
16 | 3.9 | Back filling behind abutment, wing wall and return wall complete as per drawing and Technical specification 710.1.4 of I.R.C. 78 and 2200 (i) Granular material | cum | 224 | 814.5 | 182448 | #REF! | 814.5 | #REF! | 0 | 814.5 | 0 | #REF! | 814.5 | #REF! | BRIDGE की HIGHT बढ़ने के कारण मात्रा बढ़ हो रही है।
17 | 3.1 | Providing and laying of Filter media with granular materials/stone crushed aggregates satisfying the requirements laid down in clause 2504.2.2. of MoRTH specifications to a thickness of not less than 600 mm with smaller size towards the soil and bigger size towards the wall and provided over the entire surface behind abutment, wing wall and return wall to the full height compacted to a firm condition complete as per drawing and technical specifications 710.1.4 of I.R.C. 78 and 2200 | cum | 879 | 1733.4 | 1523658.6 | #REF! | 1733.4 | #REF! | #REF! | 1733.4 | #REF! | 0 | 1733.4 | 0 | कार्य स्थल पर आवश्यकतानुसार RETAINING WALL पे ही Filter media उपयोग होने के कारण मात्रा कम हो रही है।
18 | 3.14 | Supplying, fitting and fixing in position true to line and level elastomeric bearing conforming to IRC: 83 (Part-II) section IX and clause 2005 of MoRTH specifications complete including all accessories as per drawing and Technical Specifications section 2000 and 2200 | cum | 234000 | 0.9 | 210600 | #REF! | 0.9 | #REF! | #REF! | 0.9 | #REF! | 0 | 0.9 | 0 | स्लैब की संख्या कम होने के कारण मात्रा कम हो रही है।
19 | 4.1 B | Furnishing and Placing Rein forced / Pressse Cement Concrete in Super Structure as per drawing and Technical RCC Grade M30 (i) Height upto 5m
| c | RCC GRADE M 30
|  | (i) Height upto 5m. | cum | 1026 | 6301.8 | 6465646.8 | 0 | 6301.8 | 0 | 1026 | 6301.8 | 6465646.8 | 0 | 6301.8 | 0 | SOLID SLAB की जगह T-BEAM & SLAB होने के कारण मात्रा कम हो रही है।
20 | 4.1 B | SUPER STRUCURE Furnishing and Placing Reinforced/Prestressed cement concrete in super-structure as per drawing and Technical Specification sections 1500, 1600 and 1700 B. RCC Grade M 30 (II)SUPER - STRUCTURE II For T-beam & slab (a) Using Concrete Mixer (Iii)Height above 10m | cum | #REF! | 7059.6 | #REF! | #REF! | 7059.6 | #REF! | 0 | 7059.6 | 0 | #REF! | 7059.6 | #REF! | SOLID SLAB की जगह T-BEAM & SLAB होने के कारण मात्रा बढ़ रही है।
21 | 4.2 | Supplying Fitting and placing un-coated HYSD bar reinforcement in foundation complete as per drawing and technical as per section 1600 | tonne | 86.81 | 63090.9 | 5476921.029 | #REF! | 63090.9 | #REF! | 0 | 63090.9 | 0 | #REF! | 63090.9 | #REF! | SOLID SLAB की जगह T-BEAM & SLAB होने के कारण मात्रा बढ़ रही है।
22 | 4.4 | Providing and laying Cement concrete wearing coat M-30 grade including reinforcement complete as per drawing and Technical Specification | cum | 91 | 10662.3 | 970269.3 | #REF! | 10662.3 | #REF! | #REF! | 10662.3 | #REF! | 0 | 10662.3 | 0 | ABUTMENT TOP SLAB की लम्बाई कम होने के कारण मात्रा कम हो रही है।
23 | 4.6 | Construction of RCC railing of M30 Grade in-situ with 20 mm nominal size aggregate, true to line and grade, tolerance of vertical RCC post not to exceed 1 in 500, centre to centre spacing between vertical post not to exceed 2000 mm, leaving adequate space between vertical post for expansion, complete as per approved drawings and technical specifications. (vide drawing No. SD/201, SD/304) | meter | 322 | 1637.1 | 527146.2 | #REF! | 1637.1 | #REF! | #REF! | 1637.1 | #REF! | 0 | 1637.1 | 0 | ABUTMENT TOP SLAB की लम्बाई कम होने के कारण मात्रा कम हो रही है।
24 | 4.9 | Drainage Spouts complete as per drawing and Technical specifications of section 2705 | each | 60 | 1806.3 | 108378 | #REF! | 1806.3 | #REF! | 0 | 1806.3 | 0 | #REF! | 1806.3 | #REF! | T-BEAM & SLAB की लम्बाई बढ़ने के कारण मात्रा बढ़ रही है।
25 | 4.1 | PCC M15 Grade leveling course below approach slab complete as per drawing and Technical specification and as per relevant section 2700 | cum | 9 | 3993.3 | 35939.7 | #REF! | 3993.3 | #REF! | #REF! | 3993.3 | #REF! | 0 | 3993.3 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
26 | 4.11 | Providing and laying M-30 grade Reinforced cement concrete approach slab including reinforcement and formwork complete as per drawing and Technical specification and as per relevant sections 1500, 1600, 1700 and 2704 | cum | 18 | 8520.3 | 153365.4 | #REF! | 8520.3 | #REF! | #REF! | 8520.3 | #REF! | 0 | 8520.3 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
27 | 4.14 | Filler joint (A)Providing & fixing 2 mm thick corrugated copper plate ( 12 m long x 25 cm wide ) in expansion joint complete as per drawing & Technical Specification.
| A | (A) Providing & fixing 20 mm thick Corrugated copper plate ( 12 m long x 25 cm deep ) in expansion joint complete as per drawing & Technical Specification. | sqm | 23.1 | 19674 | 454469.4 | 0 | 19674 | 0 | 23.1 | 19674 | 454469.4 | 0 | 19674 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
| B | (B) Providing & fixing 20 mm thick compressible fiber board ( 12 m long x 25 cm deep ) in expansion joint complete as per drawing & Technical Specification. | sqm | 75.02 | 1083.6 | 81291.672 | #REF! | 1083.6 | #REF! | #REF! | 1083.6 | #REF! | 0 | 1083.6 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
| D | (D)Providing and filling joint sealing compound ( 12 m long x 100 mm wide x 10 mm deep recess) as per drawings and technical specifications with coarse sand and 6% bitumen by weight | sqm | 9.24 | 198 | 1829.52 | #REF! | 198 | #REF! | 0 | 198 | 0 | #REF! | 198 | #REF! | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
28 | 4.18 | Strip Seal Expansion Joint (Providing and laying of a strip seal expansion joint catering to maximum horizontal movement upto 70 mm, complete as per approved drawings and standard specifi cations to be installed by the manufacturer/supplier or their authorized representative ensuring compliance to the manufacturer's instructions for installation.) | meter | 0 | 10011.6 | 0 | #REF! | 10011.6 | #REF! | 0 | 10011.6 | 0 | #REF! | 10011.6 | #REF! | T-BEAM & SLAB होने के कारण मात्रा बढ़ रही है।
29 | 4.21 | Painting on concrete surface of R.C.C. Railing (Providing and applying 2 coats of water based cement paint to unplastered concrete surface after cleaning the surface of dirt, dust, oil, grease, efflorescence and applying paint @ of 1 litre for 2 Sq.m. ) | sqm | 0 | 135.9 | 0 | #REF! | 135.9 | #REF! | 0 | 135.9 | 0 | #REF! | 135.9 | #REF! | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
30 | 4.22 | Providing and Fixing of Av. 20mm thick marble plate i/c cutting and polishing and inscribed details as per approved drawing i/c engraving the matter as desired. | Nos | 2 | 4500 | 9000 | #REF! | 4500 | #REF! | #REF! | 4500 | #REF! | #REF! | 4500 | #REF! | इस आयटम मे कोई विचलन नही आ रहा है।
31 | 4.24 | Testing of span of bridge for deflection due to live load with platform for loading arrangements, apparatus for measurement etc. complete as per drawing and specifications (As per I.R.C.S.P.51) | tonne | 77 | 765 | 58905 | #REF! | 765 | #REF! | #REF! | 765 | #REF! | #REF! | 765 | #REF! | इस आयटम मे कोई विचलन नही आ रहा है।
32 | 5.1 | Providing and laying boulders apron on river bed for protection against scour with stone boulders weighing not less than 40 kg each complete as per drawing and Technical specification as per relevant clauses of section 2503 | cum | 276.49 | 2171.7 | 600453.333 | 0 | 2171.7 | 0 | 276.49 | 2171.7 | 600453.333 | 0 | 2171.7 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
33 | 5.4 A | Providing and laying Pitching on slopes laid over prepared filter media including boulder apron laid dry in front of toe of embankment complete as per drawing and Technical specifications. | cum | 20 | 2171.7 | 43434 | 0 | 2171.7 | 0 | 20 | 2171.7 | 43434 | 0 | 2171.7 | 0 | Approch Road का RATE लगने के कारण मात्रा बच रही है।
34 | 5.5 | Providing and laying Filter material underneath pitching in slopes complete as per drawing and Technical specification. | cum | 10 | 1871.1 | 18711 | 0 | 1871.1 | 0 | 10 | 1871.1 | 18711 | 0 | 1871.1 | 0 | Approch Road का RATE लगने के कारण मात्रा बच रही है।
|  | PART-A GRAND TOTAL |  | G.Total | #REF! |  | G.Total | #REF! |  | G.Total | #REF! |  | G.Total | #REF!
| PART-B | [5 empty] | Excess | #REF! |  |  |  |  | Excess | #REF!
35 | 3.4 (ii) | Construction of subgrade and earthen shoulders with approved material (Granular material having CBR more than 7) obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacted to meet requirement of Table 300.2 as per Technical Specification Clause 303.1.For Item No.3.12(a) & (b) | cum | 4523 | 176 | 796048 | #REF! | 176 | #REF! | 0 | 176 | 0 | #REF! | 176 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
36 | 3.5 | Excavation in Cutting in Soil by manual means Excavation for roadway in soil for carrying of cut earth to embankment site with a lift upto 1.5 m and lead upto 50 m as per Technical Specification Clause 302.3 | cum | 0 | 76 | 0 | #REF! | 76 | #REF! | 0 | 76 | 0 | #REF! | 76 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
37 | 3.4(i) | 3.4 Construction of Embankment with Material Obtained from Pits (i) Construction of embankment with approved material obtained form borrow pits, transported to site, spreading, grading to required slopes and compacting to meet requirement of Tables 300.1 & 300.2 with a lead up to 250 m as per technical specifications clause 301.5 | cum | 483 | 118 | 56994 | #REF! | 152 | #REF! | 0 | 152 | 0 | #REF! | 152 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
38 | 3.12 (b) | Construction of Subgrade and Earthen Shoulders Construction of subgrade and earthen shoulders with approved material (Granular material having CBR more than 7) obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacted to meet requirement of Table 300.2 as per Technical Specification Clause 303.1. | cum | 0 | 176 | 0 | #REF! | 176 | #REF! | 0 | 176 | 0 | #REF! | 176 | #REF! | Approch Road में Earthen Shoulders की मात्रा नहीं होने के कारण मात्रा बढ़ रही है।
39 | 4.1 B | Granular Sub-base with Well Graded Material (CBR 20 or more) (Table 400.1) Construction of granular sub-base by providing well graded material having CBR 20 or more, spreading in uniform layers with motor grader on prepared surface, mixing by mix in place method with rotavator at OMC, and compacting with vibratory rollers of 80 to 100KN static weight to achieve the desired density, complete as per Technical Specification Clause 401. For Grading mentioned in table 400.1 (Grading III) Disintegrated rock i.e. mourum having CBR value not less then 15% and PI & LL not more then 6 and 25 respectively (with prior permission of Chief Engineer) | cum | 173 | 450 | 77850 | #REF! | 450 | #REF! | 0 | 450 | 0 | #REF! | 450 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
40 | 4.7 (ii) | Water Bound Macadam with Crushable Screenings WBM Grading 2 Providing, laying, spreading and compacting mechanically crushed stone aggregates of specific sizes to water bound macadam specification including spreading in uniform thickness, hand packing, rolling with three wheel 80-100 kN static roller in stages to proper grade and camber, applying and brooming, crushable screening to fill-up the interstices of coarse aggregate, watering and compacting to the required density Grading 3 as per Technical Specification Clause 405. | cum | 80 | 1583 | 126640 | #REF! | 1583 | #REF! | 0 | 1583 | 0 | #REF! | 1583 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
41 | 4.7 (iii) | Water Bound Macadam with Crushable Screenings WBM Grading 3 Providing, laying, spreading and compacting mechanically crushed stone aggregates of specific sizes to water bound macadam specification including spreading in uniform thickness, hand packing, rolling with three wheel 80-100 kN static roller in stages to proper grade and camber, applying and brooming, crushable screening to fill-up the interstices of coarse aggregate, watering and compacting to the required density Grading 3 as per Technical Specification Clause 405. | cum | 80 | 1694 | 135520 | 0 | 1694 | 0 | 80 | 1694 | 135520 | 0 | 1694 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
42 | 4.12 | Construction of hard shoulders as per Technical Specification Clause 407.Construction of hard shoulder with granular material having CBR value not less than 15 including all leads & lift, watering & compaction with smooth wheeled roller to achieve the desired density as per technical specification clause 407 & 401. | cum | 161 | 358 | 57638 | #REF! | 358 | #REF! | 0 | 358 | 0 | #REF! | 358 | #REF! | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
43 | 5.1 | Prime Coat Providing and applying primer coat with bitumen emulsion (SS-1) on prepared surface of granular base including cleaning of road surface and spraying primer at the rate of 0.70-1.0 kg/sqm using mechanical means as per Technical Specification Clause 502 | sqm | 1071 | 53 | 56763 | 0 | 53 | 0 | 1071 | 53 | 56763 | 0 | 53 | 0 | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बच रही है।
44 | 5.2 | Tack coat Providing and applying tack coat with Bitumen emulsion (RS-1) using emulsion distributor at the rate of 0.20 to 0.25 kg per sqm on the prepared bituminous surface cleaned with Hydraulic broom as per Technical Specification Clause 503 | sqm | 1071 | 15 | 16065 | 0 | 15 | 0 | 1071 | 15 | 16065 | 0 | 15 | 0 | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बच रही है।
45 | 5.3(ii) | 20mm thick Open-Graded Premix Carpet using Bituminous (VG/modified bitumen) Binder Providing, laying and rolling of open-graded premix carpet of 20 mm thickness composed of aggregate 13.2mm size (passing 22.4mm size sieve & retained on 11.2mm sieve and 11.2mm size (passing 13.2mm sieve and retained on 5.6mm sieve) either using penetration grade/ VG bitumen or emulsion to required line, grade and level to serve as wearing course on a previously prepared base, including mixing in a suitable plant, laying and rolling with a three wheel 80-100 kN static roller capacity, finished to required level and grades to be followed by seal coat of either Type A or Type B or Type C as per Technical Specification Clause 508., Viscocity grade (VG) Bitumen specification as per IS 73:2006 (ii) Bitumen (VG-30) | sqm | 1071 | 155 | 166005 | 0 | 155 | 0 | 1071 | 155 | 166005 | 0 | 155 | 0 | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बच रही है।
46 | 5.5 Case-(II) Type -B (II) | Seal Coat Providing and laying seal coat sealing the voids in a bituminous surface laid to the specified levels, grade and cross fall using Type A, Type B and Type C as per Technical Specification Clause 510, Viscocity grade (VG) Bitumen specification as per IS 73:2006 Bitumen (VG-30) | sqm | 1071 | 56 | 59976 | 0 | 56 | 0 | 1071 | 56 | 59976 | 0 | 56 | 0 | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बच रही है।
47 | 6.1 (ii) | Cement Concrete Pavement Construction of un-reinforced, jointed at expansion and construction joint only, plain cement concrete pavement, thickness as per design, over a prepared sub base, with 43 grade cement or any other type as per Clause 1501.2.2 M30 (Grade), coarse and fine aggregates conforming to IS:383, maximum size of coarse aggregate not exceeding 25 mm, mixed in a concrete mixer of not less than 0.2 cum capacity and appropriate weigh batcher using approved mix design, laid in approved fixed side formwork (steel channel, laying and fixing of 125 micron thick polythene film, wedges, steel plates including leveling the formwork as per drawing), spreading the concrete with shovels, rakes, compacted using needle, screed and plate vibrators and finished in continuous operation including provision of contraction and expansion, construction joints, applying, primer, sealant, using curing compound (where specified) and water finishing to lines and grade as per drawing and Technical Specification Clause 1501. | cum | 0 | 5097 | 0 | #REF! | 5097 | #REF! | 0 | 5097 | 0 | #REF! | 5097 | #REF! | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बढ़ रही है।
48 | 7.1 (I) | Excavation for Structure as per drawing and technical specifications Clause 305.1 including setting out, construction of shoring and bracing, removal of stumps and other deleterious material and disposal upto a lead of 50 m, dressing of sides and bottom and backfilling in trenches with excavated suitable material. (I) Ordinary soil( i). Upto 3 m depth | cum | 0 | 161 | 0 | #REF! | 161 | #REF! | 0 | 161 | 0 | #REF! | 161 | #REF! | Toe Wall कार्य होने के कारण मात्रा बढ़ रही है।
49 | 7.7 | Plain Cement Concrete M10 (1:3:6 nominal mix) in levelling course below open foundation of Head walls as per drawings & Technical Specification Clause 1109 Nominal Mix 1:3:6(with 40mm Graded metal | cum | 0 | 3963 | 0 | #REF! | 3963 | #REF! | 0 | 3963 | 0 | #REF! | 3963 | #REF! | Toe Wall कार्य होने के कारण मात्रा बढ़ रही है।
50 | 7.10(II) | Providing concrete for plain/reinforced concrete in open foundation complete as per drawings and technical specifications Clause 802, 803, 1202 & 1203 II. P.C.C grade M 15(Nominal mix (1:2.5:5) | cum | 0 | 3899 | 0 | #REF! | 3899 | #REF! | 0 | 3899 | 0 | #REF! | 3899 | #REF! | Toe Wall कार्य होने के कारण मात्रा बढ़ रही है।
51 | 10.5 | Providing and laying pitching on slopes laid over prepared filter media as per drawing and technical specifications Clause 1302 I. Stone/Boulder | cum | 0 | 1430 | 0 | #REF! | 1430 | #REF! | 0 | 1430 | 0 | #REF! | 1430 | #REF! | Pitching कार्य होने के कारण मात्रा बढ़ रही है।
52 | 10.6 | Providing and laying filter material underneath pitching in slopes complete as per drawing and technical specifications Clause 1302 | cum | 0 | 1337 | 0 | #REF! | 1657 | #REF! | 0 | 1337 | 0 | #REF! | 1337 | #REF! | Pitching कार्य होने के कारण मात्रा बढ़ रही है।
53 | 7.6 (C) | Laying Reinforced Cement Concrete Pipe NP3 as per drawing and technical specification Clause 1402.6 Providing and laying reinforced cement concrete pipe NP3 for culverts on first Class bedding in single row including fixing with cement mortar 1:2 but excluding excavation, bedding protection works, backfilling, concrete and masonry works in head walls and parapets Clause 1106. (C) 450 mm dia | meter | 0 | 1961 | 0 | #REF! | 1961 | #REF! | 0 | 5177 | 0 | #REF! | 5177 | #REF! | 450 mm dia Pipe कार्य होने के कारण मात्रा बढ़ रही है।
54 | 9.2 (B) | Cautionary, mandatory, informatory direction and place identification sign boards. (B)Semi-Reflective Traffic signs more than 0.90 sqm sign board Providing and erecting direction and place identification of semi reflective sign boards as per IRC-67 made of 2 mm thick M.S. Sheet duly stove enameled paint white colour in front and grey colour on back with reflective border of 70 mm width and required message, letters, figures with reflective tape of engineering grade as per MORD specifications of required shade and colour. Supported and welded on two nos. 47 mm x 47 mm of 12 SWG square tube of 3050 mm height duly strengthened by 25 mm x 5 mm MS flat iron on edges on back firmly fixed to the ground by means of properly designed foundations with M-15 grade cement concrete 450 mm x 450 mm x 600 mm, 600 mm below ground level as per approved drawing and Technical Specification Clause 1701 | Sqm | 0 | 4667 | 0 | #REF! | 4667 | #REF! | 0 | 4667 | 0 | #REF! | 4667 | #REF! | Semi-Reflective Traffic signs कार्य होने के कारण मात्रा बढ़ रही है।
55 | 9.9 | Boundary Pillar Reinforced cement concrete M15 grade boundary pillars/local stone of standard design as per IRC:25, fixed in position including finishing and lettering but excluding painting as per drawing and Technical Specification Clause 1704. | each | 102 | 489 | 49878 | #REF! | 489 | #REF! | 0 | 489 | 0 | #REF! | 489 | #REF! | Boundary Pillar कार्य होने के कारण मात्रा बढ़ रही है।
56 | 9.14 B | Providing and Fixing Informatory and Logo Board of PMGSY Project (B) Providing and fixing of typical PMGSY informatory sign board with Logo as per MORD specifications and drawing. Three MS Plates of 1.6 mm thick, top and middle plate duly welded with MS flat iron 25mm x 5m size on back on edges. The lower plate will be welded with MS angle iron frame of 25mm x 25mm x 5mm. The angle iron frame of the lower most plate and flat iron frame of middle plate will be welded to 2 nos. 75mm x 75 mm of 12 SWG sheet tubes posts duly embedded in cement concrete M-15 grade blocks of 450mm x 450mm x 600mm, 600mm below ground level. The top most diamond plate will be welded to middle plate by 47mm x 47mm of 12 SWG steel plate tube. All M.S. will be stove enameled on both sides. Lettering and printing arrows, border etc. will be painted with ready mixed synthetic enamel paint of superior quality in required shade and colour. All sections of framed posts and steel tube will be painted with primer and two coats of epoxy paint as per drawing Clause 1701 and Annexure 1700.1 be painted with ready mixed synthetic enamel paint of superior quality in required shade and colour. All sections of framed posts and steel tube will be painted with primer and two coats of epoxy paint as per drawing Clause 1701 and Annexure 1700.1 | each | 0 | 14930 | 0 | #REF! | 14930 | #REF! | 0 | 14930 | 0 | #REF! | 14930 | #REF! | Informatory and Logo Board कार्य होने के कारण मात्रा बढ़ रही है।
57 | 9.15(A) | Providing and fixing 'Citizen Information Board' of PMGSY Project (A) Providing and fixing of typical " PMGSY Citizen Information Board" with Logo as per MoRD specifications & drawings, made of 75 mm square or 75 mm dia circular steel tube of 12 SWG 3.2 m height and cross member 2 nos 1m long, fixed with angle iron 50x50x5 mm MS angle on the back | each | 0 | 14015 | 0 | #REF! | 14015 | #REF! | 0 | 14015 | 0 | #REF! | 14015 | #REF! | Citizen Information Board कार्य होने के कारण मात्रा बढ़ रही है।
58 | 9.16 | Providing & Fixing of PMGSY 'Logo' board Providing and fixing of typical PMGSY logo board as per MoRD specifications and drawings. | each | 2 | 6626 | 13252 | 1 | 6626 | 6626 | 1 | 6626 | 6626 | 0 | 6626 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
59 | 11.13 | Painting on Concrete Surfaces White washing two coats on parapet walls of CD and tree trunks including preparation of surface by cleaning scraping etc. as per technical specifications Clause 1915 | sqm | 383 | 15 | 5745 | #REF! | 15 | #REF! | #REF! | 15 | #REF! | 0 | 15 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
60 | 9.5 | Providing and laying Reinforced Cement Concrete pipe NP 3 / prestressed concrete pipe on first class bedding. (Laying Reinforced cement concrete pipe NP3 /prestressed concrete pipe for culverts on first class bedding of granular material including fixing collar with cement mortar 1:2 but excluding excavation, protection works, backfilling, concrete and masonry works in head walls and parapets . ) (D) 1000 mm dia | meter | 20 | 4833 | 96660 | 0 | 4833 | 0 | 20 | 4833 | 96660 | 0 | 4833 | 0 | गलत आयटम नं॰ होने के कारण मात्रा बच रही है।
[6 empty] | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF!
[8 empty] | Excess | #REF! |  |  |  |  | Excess | #REF!
|  | Sub Engineer |  | Assistant Engineer |  |  |  | Executive Engineer |  |  |  |  | Superintending Engineer
|  | CGRRDA, PIU - 01, Ambikapur |  | CGRRDA, PIU - 01, Ambikapur |  |  | CGRRDA, PIU - 01, Ambikapur | [5 empty] | CGRRDA,Project Circle No. -01,Ambikapur
|  | Distt. - Surguja |  | Distt. - Surguja |  |  |  | Distt. - Surguja |  |  |  |  | Distt. - Surguja ( C.G.)

## LEVEL (hidden)
LEVEL BOOK
Name Of Bridge:-GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
PACKAGE NO.:-CGLSB16-21
CH. | RL
| L3 | L2 | L1 | C | R1 | R2 | R3
0 | 101.215 | 101.215 | 101.215 | 100.58 | 100.285 | 99.415 | 98.905
20 | 100.915 | 100.165 | 99.755 | 100.035 | 99.565 | 98.265 | 98.165
40 | 101.015 | 99.815 | 99.075 | 99.355 | 98.915 | 98.165 | 97.965
60 | 100.215 | 99.115 | 98.285 | 98.705 | 98.585 | 97.915 | 97.925
80 | 99.585 | 99.075 | 97.795 | 98.065 | 97.665 | 96.965 | 96.715
100 | 99.715 | 99.015 | 97.495 | 97.635 | 97.535 | 97.245 | 97.315
120 | 99.415 | 98.815 | 97.265 | 97.495 | 97.815 | 97.425 | 96.815
140 | 99.415 | 98.715 | 97.075 | 97.365 | 97.615 | 96.865 | 96.715
160 | 95.755 | 96.155 | 97.005 | 97.125 | 96.975 | 97.075 | 96.705
180 | 96.155 | 96.905 | 96.375 | 96.365 | 96.245 | 95.985 | 95.825
200 | 96.295 | 95.945 | 95.735 | 95.945 | 96.005 | 95.935 | 95.755
220 | 95.935 | 95.445 | 95.415 | 95.575 | 95.805 | 95.305 | 95.005
240 | 95.015 | 95.115 | 95.215 | 95.225 | 95.235 | 95.435 | 95.725
260 | 95.675 | 95.355 | 95.015 | 94.855 | 94.835 | 94.155 | 93.905
270 | 94.795 | 94.795 | 94.315 | 93.355 | 93.935 | 94.795 | 94.795
280 | 94.395 | 93.295 | 91.695 | 92.675 | 92.795 | 92.995 | 94.195
290 | 94.795 | 94.795 | 94.795 | 90.815 | 94.795 | 94.795 | 94.795
300 | 94.795 | 94.795 | 94.795 | 91.195 | 94.795 | 94.795 | 94.795
310 | 94.795 | 94.795 | 94.795 | 91.535 | 94.795 | 94.795 | 94.795
320 | 94.795 | 94.795 | 94.795 | 91.585 | 94.795 | 94.795 | 94.795
330 | 94.795 | 94.795 | 94.795 | 91.815 | 94.795 | 94.795 | 94.795
340 | 94.795 | 94.795 | 94.795 | 91.905 | 94.795 | 94.795 | 94.795
350 | 94.795 | 94.795 | 94.795 | 91.905 | 94.795 | 94.795 | 94.795
360 | 94.795 | 94.795 | 94.795 | 91.805 | 94.795 | 94.795 | 94.795
370 | 94.795 | 94.795 | 94.795 | 91.825 | 94.795 | 94.795 | 94.795
380 | 94.795 | 94.795 | 94.795 | 92.095 | 94.795 | 94.795 | 94.795
390 | 94.795 | 94.795 | 94.795 | 92.495 | 94.795 | 94.795 | 94.795
400 | 94.795 | 94.795 | 94.795 | 93.145 | 94.795 | 94.795 | 94.795
410 | 96.785 | 96.585 | 96.285 | 96.175 | 95.885 | 96.085 | 95.185
420 | 97.245 | 97.075 | 96.935 | 97.055 | 96.885 | 96.585 | 96.285
430 | 98.965 | 99.005 | 99.665 | 99.915 | 99.095 | 98.345 | 98.265
440 | 100.865 | 100.965 | 101.035 | 100.705 | 100.485 | 100.385 | 100.445
450 | 101.145 | 101.215 | 101.285 | 101.345 | 101.205 | 101.015 | 100.715
470 | 100.115 | 100.375 | 100.465 | 100.525 | 100.535 | 100.565 | 100.655
490 | 100.495 | 100.965 | 101.315 | 101.215 | 101.225 | 100.875 | 100.665
510 | 101.085 | 101.215 | 101.545 | 101.885 | 101.565 | 101.285 | 101.105
530 | 101.165 | 101.265 | 101.375 | 101.575 | 101.415 | 101.165 | 101.045
550 | 100.885 | 101.165 | 101.405 | 101.685 | 101.625 | 101.185 | 100.515
Sub Engieer | [5 empty] | Assistant Engieer
CGRRDA, PIU -01, Ambikapur | [5 empty] | CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.) | [5 empty] | Distt- Surguja ( C.G.)
Executive Engineer
CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.)

## APPROCH ROAD (hidden)
FOR APPROCH ROAD CALCULATION SHEET
Name Of Bridge:-GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
PACKAGE NO.:-CGLSB16-21
S. No. | Chainage | Ground R.L. | Formation R.L. | Area |  | Comulative Area |  |  | Volume
|  |  |  | Cutting | Filling | Cutting | Filling | Length | Cutting | Filling
1 | 0 | 100.58 |  | 3.4202 | 0 | 1.7101 | 0 | 0 | 0 | 0
2 | 20 | 100.035 |  |  | 7.336 | 1.7101 | 3.668 | 20 | 34.202 | 73.36
3 | 40 | 99.355 |  |  | 20.2099 | 0 | 13.773 | 20 | 0 | 275.459
4 | 60 | 98.705 |  |  | 36.6888 | 0 | 28.4494 | 20 | 0 | 568.987
5 | 80 | 98.065 |  |  | 54.7186 | 0 | 45.7037 | 20 | 0 | 914.074
6 | 100 | 97.635 |  |  | 64.2053 | 0 | 59.462 | 20 | 0 | 1189.239
7 | 120 | 97.495 |  |  | 69.7632 | 0 | 66.9843 | 20 | 0 | 1339.685
8 | 140 | 97.365 |  |  | 82.1357 | 0 | 75.9494 | 20 | 0 | 1518.989
9 | 160 | 97.125 |  |  | 109.276 | 0 | 95.7058 | 20 | 0 | 1914.117
10 | 180 | 96.365 |  |  | 127.444 | 0 | 118.36 | 20 | 0 | 2367.2
11 | 200 | 95.945 |  |  | 136.112 | 0 | 131.778 | 20 | 0 | 2635.56
12 | 220 | 95.575 |  |  | 137.58 | 0 | 136.846 | 20 | 0 | 2736.92
13 | 240 | 95.225 |  |  | 174.204 | 0 | 155.892 | 20 | 0 | 3117.84
14 | 255 | 95.855 |  |  | 186.196 | 0 | 180.2 | 15 | 0 | 2703
15 | 260 | 94.855 |  |  | 0 | 0 | 93.098 | 5 | 0 | 465.49
16 | 270 | 93.355 |  |  | 0 | 0 | 0 | 10 | 0 | 0
17 | 280 | 92.675 |  |  | 0 | 0 | 0 | 10 | 0 | 0
18 | 290 | 90.815 |  |  | 0 | 0 | 0 | 10 | 0 | 0
19 | 300 | 91.195 |  |  | 0 | 0 | 0 | 10 | 0 | 0
20 | 310 | 91.535 |  |  | 0 | 0 | 0 | 10 | 0 | 0
21 | 320 | 91.585 |  |  | 0 | 0 | 0 | 10 | 0 | 0
22 | 330 | 91.815 |  |  | 0 | 0 | 0 | 10 | 0 | 0
23 | 340 | 91.905 |  |  | 0 | 0 | 0 | 10 | 0 | 0
24 | 350 | 91.905 |  |  | 0 | 0 | 0 | 10 | 0 | 0
25 | 360 | 91.805 |  |  | 0 | 0 | 0 | 10 | 0 | 0
26 | 370 | 91.825 |  |  | 0 | 0 | 0 | 10 | 0 | 0
27 | 380 | 92.095 |  |  | 0 | 0 | 0 | 10 | 0 | 0
28 | 390 | 92.495 |  |  | 0 | 0 | 0 | 10 | 0 | 0
29 | 400 | 93.145 |  |  | 0 | 0 | 0 | 10 | 0 | 0
30 | 410 | 96.175 |  |  | 0 | 0 | 0 | 10 | 0 | 0
31 | 415 | 97.055 |  |  | 150.048 | 0 | 75.024 | 5 | 0 | 375.12
32 | 420 | 97.055 |  |  | 140.344 | 0 | 145.196 | 5 | 0 | 725.98
33 | 430 | 99.915 |  |  | 81.416 | 0 | 110.88 | 10 | 0 | 1108.8
34 | 440 | 100.705 |  |  | 42.0758 | 0 | 61.7459 | 10 | 0 | 617.459
35 | 450 | 101.345 |  |  | 25.75 | 0 | 33.9129 | 10 | 0 | 339.129
52 | 470 | 103.155 |  |  | 30.402 | 0 | 28.076 | 20 | 0 | 561.52
53 | 490 | 101.655 |  |  | 12.1445 | 0 | 21.2733 | 20 | 0 | 425.465
54 | 510 | 100.835 |  |  | 1.4792 | 0 | 6.8119 | 20 | 0 | 136.237
[9 empty] | 34.202 | 26109.63
[9 empty] | Cutting | Filling
[9 empty] | 34.202 | 26109.63
DEDUCTION FOR RETAINING WALL EXCAVATION QTY. | [7 empty] | #REF! | 80% | #REF!
DEDUCTION FOR RETAINING WALL FILTER MEDIA QTY. | [7 empty] | #REF! | 100% | #REF!
DEDUCTION FOR TOE WALL EXCAVATION QTY. | [7 empty] | #REF! | 80% | #REF!
DEDUCTION FOR BACK FILLING QTY. | [7 empty] | #REF! | 100% | #REF!
[9 empty] | G.Total | #REF!
Sub Engieer | [8 empty] | Assistant Engineer
CGRRDA, PIU -01, Ambikapur | [8 empty] | CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.) | [8 empty] | Distt- Surguja ( C.G.)
Executive Engineer
CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.)

## DIVERSION ROAD (hidden)
FOR COFFER DAM CALCULATION SHEET
Name Of Bridge:-GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
S. No. | Chainage | Ground R.L. | Formation R.L. | Area |  | Comulative Area |  |  | Volume
|  |  |  | Cutting | Filling | Cutting | Filling | Length | Cutting | Filling
15 | 250 | 94.855 | 94 | 2.489 | 0 | 1.2445 | 0 | 0 | 0 | 0
16 | 270 | 93.355 | 94 |  | 3.7345 | 1.2445 | 1.8673 | 20 | 24.89 | 37.3455
17 | 280 | 92.675 | 94 |  | 9.4738 | 0 | 6.6041 | 10 | 0 | 66.0415
18 | 290 | 90.815 | 94 |  | 34.621 | 0 | 22.0474 | 10 | 0 | 220.4735
19 | 300 | 91.195 | 94 |  | 28.3586 | 0 | 31.4898 | 10 | 0 | 314.8975
20 | 310 | 91.535 | 94 |  | 23.245 | 0 | 25.8018 | 10 | 0 | 258.0175
21 | 320 | 91.585 | 94 |  | 22.532 | 0 | 22.8885 | 10 | 0 | 228.8845
22 | 330 | 91.815 | 94 |  | 19.381 | 0 | 20.9565 | 10 | 0 | 209.5645
23 | 340 | 91.905 | 94 |  | 18.2055 | 0 | 18.7933 | 10 | 0 | 187.9325
24 | 350 | 91.905 | 94 |  | 18.2055 | 0 | 18.2055 | 10 | 0 | 182.0555
25 | 360 | 91.805 | 94 |  | 19.5135 | 0 | 18.8595 | 10 | 0 | 188.5955
26 | 370 | 91.825 | 94 |  | 19.2487 | 0 | 19.3811 | 10 | 0 | 193.8115
27 | 380 | 92.095 | 94 |  | 15.8306 | 0 | 17.5396 | 10 | 0 | 175.3965
28 | 390 | 92.495 | 94 |  | 11.3025 | 0 | 13.5665 | 10 | 0 | 135.6655
29 | 400 | 93.145 | 94 |  | 5.3096 | 0 | 8.306 | 10 | 0 | 83.0605
30 | 420 | 95.185 | 94 | 2.108 | 0 | 1.054 | 2.6548 | 20 | 21.08 | 53.0955
Total Length | 170 | [7 empty] | 45.97 | 2534.8375
[9 empty] | Cutting | Filling
Sub Engieer | [8 empty] | Assistant Engineer
CGRRDA, PIU -01, Ambikapur | [8 empty] | CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.) | [8 empty] | Distt- Surguja ( C.G.)
Executive Engineer
CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.)

## V.S. Phy. (hidden)
Abstract Variation Statement Financial
CONSTRUCTION OF LONG SPAN BRIDGE ACROSS GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
PACKAGE No. CGLSB - 16-21
S.No. |  | Length of Bridge (In M) | Length of Approch (In M) | Cost of Bridge (Rs. In Lakh) | Cost of Approach Road ( Rs. In Lakh) | Total Cost (Rs. In Lakh) | Cost of Maintenance (Rs. In Lakh) | Total cost (Bridge + Approcah) - Rs. In Lakh | Add Above Tender 7.20 % | Total Tender Amount (Rs. In Lakh)
Particulars
1 | As per Agreement | 150 | 255 | 380.99 | 17.15 | 398.14 | 9.95 | 408.09 | 28.6661 | 436.7561
2 | As per Actual/Recvised | 150 | 350 | #REF! | #REF! | #REF! | 9.95 | #REF! | #REF! | #REF!
3 | Variation in amount | 0.00 M. | 95 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
4 | % of variation | 0% | 37.25% | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF!
|  | ZERO | EXCESS | EXCESS | EXCESS | EXCESS |  | EXCESS | EXCESS | EXCESS
| Sub Engineer |  | Assistant Engineer |  |  | Executive Engineer |  |  | Superintending Engineer
| CGRRDA, PIU - 01, Ambikapur |  | CGRRDA, PIU - 01, Ambikapur |  |  | CGRRDA, PIU - 01, Ambikapur |  |  | CGRRDA,Project Circle No. -01,Ambikapur
| Distt. - Surguja |  | Distt. - Surguja |  |  | Distt. - Surguja |  |  | Distt. - Surguja ( C.G.)

## approch road+ (hidden)
Name Of Bridge:-GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
S. No. | Chainage | Ground R.L. | Formation R.L. | Area |  | Comulative Area |  |  | Volume
|  |  |  | Cutting | Filling | Cutting | Filling | Length | Cutting | Filling
1 | 0 | 100.58 |  |  | 0.923 | 0 | 0.4615 | 0 | 0 | 0
2 | 20 | 100.035 |  |  | 4.765 | 0 | 2.844 | 20 | 0 | 56.88
3 | 40 | 99.355 |  |  | 30.35 | 0 | 17.5575 | 20 | 0 | 351.15
4 | 60 | 98.705 |  |  | 43.944 | 0 | 37.147 | 20 | 0 | 742.94
5 | 80 | 98.065 |  |  | 45.38 | 0 | 44.662 | 20 | 0 | 893.24
6 | 100 | 97.635 |  |  | 50.225 | 0 | 47.8025 | 20 | 0 | 956.05
7 | 120 | 97.495 |  |  | 56.645 | 0 | 53.435 | 20 | 0 | 1068.7
8 | 140 | 97.365 |  |  | 66.073 | 0 | 61.359 | 20 | 0 | 1227.18
9 | 160 | 97.125 |  |  | 89.596 | 0 | 77.8345 | 20 | 0 | 1556.69
10 | 180 | 96.365 |  |  | 106.22 | 0 | 97.908 | 20 | 0 | 1958.16
11 | 200 | 95.945 |  |  | 112.088 | 0 | 109.154 | 20 | 0 | 2183.08
12 | 220 | 95.575 |  |  | 135.396 | 0 | 123.742 | 20 | 0 | 2474.84
13 | 240 | 95.225 |  |  | 145.86 | 0 | 140.628 | 20 | 0 | 2812.56
14 | 255 | 95.855 |  |  | 157.828 | 0 | 151.844 | 15 | 0 | 2277.66
15 | 260 | 94.855 |  |  | 0 | 0 | 78.914 | 5 | 0 | 394.57
16 | 270 | 93.355 |  |  | 0 | 0 | 0 | 10 | 0 | 0
17 | 280 | 92.675 |  |  | 0 | 0 | 0 | 10 | 0 | 0
18 | 290 | 90.815 |  |  | 0 | 0 | 0 | 10 | 0 | 0
19 | 300 | 91.195 |  |  | 0 | 0 | 0 | 10 | 0 | 0
20 | 310 | 91.535 |  |  | 0 | 0 | 0 | 10 | 0 | 0
21 | 320 | 91.585 |  |  | 0 | 0 | 0 | 10 | 0 | 0
22 | 330 | 91.815 |  |  | 0 | 0 | 0 | 10 | 0 | 0
23 | 340 | 91.905 |  |  | 0 | 0 | 0 | 10 | 0 | 0
24 | 350 | 91.905 |  |  | 0 | 0 | 0 | 10 | 0 | 0
25 | 360 | 91.805 |  |  | 0 | 0 | 0 | 10 | 0 | 0
26 | 370 | 91.825 |  |  | 0 | 0 | 0 | 10 | 0 | 0
27 | 380 | 92.095 |  |  | 0 | 0 | 0 | 10 | 0 | 0
28 | 390 | 92.495 |  |  | 0 | 0 | 0 | 10 | 0 | 0
29 | 400 | 93.145 |  |  | 0 | 0 | 0 | 10 | 0 | 0
30 | 410 | 96.175 |  |  | 0 | 0 | 0 | 10 | 0 | 0
31 | 415 | 97.055 |  |  | 117.36 | 0 | 58.68 | 5 | 0 | 293.4
32 | 420 | 97.055 |  |  | 106.576 | 0 | 111.968 | 5 | 0 | 559.84
33 | 430 | 99.915 |  |  | 51.49 | 0 | 79.033 | 10 | 0 | 790.33
34 | 440 | 100.705 |  |  | 20.104 | 0 | 35.797 | 10 | 0 | 357.97
35 | 450 | 101.345 |  |  | 11.316 | 0 | 15.71 | 10 | 0 | 157.1
36 | 470 | 100.525 |  |  | 19.93 | 0 | 15.623 | 20 | 0 | 312.46
37 | 490 | 101.225 |  |  | 8.04 | 0 | 13.985 | 20 | 0 | 279.7
38 | 510 | 101.885 |  |  | 6.57 | 0 | 7.305 | 20 | 0 | 146.1
39 | 530 | 101.575 |  |  | 5.69 | 0 | 6.13 | 20 | 0 | 122.6
[9 empty] | 0 | 21973.2
[9 empty] | Cutting | Filling

## Sheet2 (hidden)
2578.25
1089.58
850.29
305.5
205.58
26.19
155.57
85.51
183.71
226.252
191.5
132.71
319.37
189.37
439.12
322
121.53
111.4
905.02
905.02
663.65
250.47
229.6
305.02
156.86
98.51
196.93
324.31
875.69
34.73
217.34
108.66
796.55
1975.44
887.33
375.41
557.2
1154.38
274.92
84.83
147.84
1269.95
528.69
288.04
21145.822
1057.2911
22200