## Index (hidden)
#REF!
INDEX
COST ESTIMATE OF
#REF!
S.no. | Particulars | Page No. |  | Remarks
|  | From | To
1 | General Abstract of Cost
2 | Cost Estimate of LSB
3 | Detail Estimate of LSB
4 | Cost Estimate of LSB Approach Road
5 | Detail Estimate of LSB Approach Road.
6 | Volume sheet, 'L' Sec. & 'X' Sec.
7 | Drawings |  |  | ATTACHED IN VOL. 4

## financial (hidden)
Abstract Statement Financial
#REF!
#REF!
S.No. |  | Length of Bridge (In M) | Length of Approch (In M) | Cost of Bridge (Rs. In Lakh) | Cost of Approach Road ( Rs. In Lakh) | Total Cost (Rs. In Lakh) | ADD GST 18% | Total cost I/c GST - Rs. In Lakh | Cost of Maintenance (Rs. In Lakh) | Total cost (Bridge + Approcah+Maintenance) - Rs. In Lakh | Consultancy Fee i/c 18% GST | TOTAL PROJECT COST WITH MAINTENANCE (Rs. In Lakh)
Particulars
1 | As per DPR | 45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Sub Engineer |  | Assistant Engineer |  |  | Executive Engineer |  |  |  |  | Superintending Engineer
| #REF! |  | #REF! |  |  |  | #REF! |  |  |  | #REF!
| #REF! |  | #REF! |  |  |  | #REF! |  |  |  | #REF!

## Bridge. Abst (2)
Bill Of Quantities
Construction of High level bridge across Dumam River @ RD 4000 on Bastanar dabbapara Badekaloor RD 8.0Km.- Rodapara Badebodenar, Block Bastanar Dist.Bastar
6 SPAN @ 15.00 M = 90 M., ABUTMENT 2 x 6.0 = 12 M. OPEN FOUNDATION PIER & OPEN FOUNDATION ABUTMENT
ABSTRACT
Sr. no. | SOR | Item No. | BOQ Description | Quantity | Unit | RATE | Amount
2 | PMGSY 2018 | 3.4 (ii) | Construction of embankment with approved material obtained from borrow pits, transporting to site, spreading, grading to required slope and compacting to meet requirement of Tables 300.1 and 300.2 (Beyond 250m)with all leads as per Technical Specification Clause 301.5(Having CBR more than 5) | 218.7 | cum | 211 | 46145.7
3 | PMGSY 2018 | 4.1 | Granular Sub-base with Well Graded Material (Table 400.1) Construction of granular sub-base by providing well graded material, spreading in uniform layers with motor grader on prepared surface, mixing by mix in place method with rotavator at OMC, and compacting with smooth wheel roller to achieve the desired density, complete as per Technical Specification Clause 401. | 75.94 | cum | 780 | 59233.2
4 | PMGSY 2018 | 7.4 | Laying Reinforced Cement Concrete Pipe NP3 as per drawing and technical specification Clause 1402.6 Providing and laying reinforced cement concrete pipe NP3 for culverts on first Class bedding in single row including fixing with cement mortar 1:2 but excluding excavation, bedding protection works, backfilling, concrete and masonry works in head walls and parapets Clause 1106. B 1000 mm Dia | 30 | m | 5558 | 166740
5 | Bridge 2025 | 2.1 (I) | Excavation for Structures (Earth work in excavation of foundation of structures as per drawing and technical specification, including setting out, construction of shoring and bracing, removal of stumps and other deleterious matter, dressing of sides and bottom and backfilling with approved material.) as per section 304. Ordinary soil (i) Upto 3 m depth | 1292.4 | cum | 161 | 208076.4
|  |  | Ordinary Rock (ii) 3m to 6m depth | 1090.8 | cum | 184 | 200707.2
|  |  | Ordinary Rock (iii) Above 6m depth | 1006.7832 | cum | 233 | 234580.4856
6 | Bridge 2025 | 2.1 A | Add extra in rates of dewatering of above items if dewatering is resorted. Ordinary Soil (i) upto 3m depth | 480.4668 | cum | 32.2 | 15471.031
|  |  | Ordinary Rock (ii) 3m to 6m depth | 1090.8 | cum | 36.8 | 40141.44
|  |  | Ordinary Rock (iii) Above 6m depth | 1006.7832 | cum | 46.6 | 46916.0971
7 | Bridge 2025 | 2.1 A | The cost of shoring and shuttering, when needed, be added at 1 percent on cost of excavation for open foundation. Ordinary Soil (i) upto 3m depth | 1292.4 | cum | 1.61 | 2080.764
|  |  | Ordinary Rock (ii) 3m to 6m depth | 1090.8 | cum | 1.84 | 2007.072
|  |  | Ordinary Rock (iii) Above 6m depth | 1006.7832 | cum | 2.33 | 2345.8049
8 | Bridge 2025 | 2.2 | Filling annular space around footing in rock ( lean cement concrete 1:3:6 nominal mix | 129.486 | m | 4791 | 620367.426
9 | Bridge 2025 | 2.6 A | Plain / Reinforced cement concrete in open foundation (complete as per drawing and specification as per section 1500, 1700 & 2100. Using batch type concrete Mixer with integrated weigher. |  |  |  | 0
|  | (i) | PCC Grade M-15 | 60.2255 | cum | 4791 | 288540.3106
10 | Bridge 2025 | 2.6 A | Plain / Reinforced cement concrete in open foundation (complete as per drawing and specification as per section 1500, 1700 & 2100. Using batch type concrete Mixer with integrated weigher. |  |  |  | 0
|  | (vii) | RCC Grade M-30 | 253.9218 | cum | 5740 | 1457510.845
11 | Bridge 2025 | L.S. | SAFE BEARING CAPACITY TEST | 0 | Nos | 3000 | 0
12 | Bridge 2025 | 2.25 | Supplying, fitting and placing HSD (High Strength Deformed Steel) bar reinforcement in foundation complete as per drawing and technical specifications as per section 1600. (Fe -500) | 19.3819 | MT | 79298 | 1536943.392
13 | Bridge 2025 | 2.26 | Taking trail boring 100mm dia. For detailed investigation with diamond drill double tube in all type of Hard rock including all material such as casing pipes, grease and other such material and or as required including accessories,coveying such material and machinery to site of work preserving the loose sample and core samples serially numbered at the site of work and conveying same to the head quarters of concerned office as directed and submission of detailed bore log sheet as per I.R.C.78-2014 and section 2400 including testing and preserving rock core sample in core boxes as per specification. |  |  |  | 0
|  | (i) | Upto 1.0 m below bed level | 5.2501 | each | 7141 | 37491.3
|  | (ii) | Beyond 1.0 m upto 5.0 m depth | 19.3846 | meter | 1690 | 32760 | 116713.8
|  | (iii) | Beyond 5.0 m depth | 19.3796 | meter | 1918 | 37170
14 | Bridge 2025 | 3.6 | Providing and laying Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications section 1500, 1700 and 2200 |  |  |  | 0
|  | E(b)(iii) | Height 5m to 10 m (RCC Grade M30) | 560.9606 | cum | 6456 | 3621561.66 |  | 16.1177
15 | Bridge 2025 | 3.7 | Supplying, fitting and placing HYSD bar reinforcement in sub-structure complete as per drawing and technical specifications section 1600 and 2200 (Fe 500) | 61.1468 | tonne | 79704 | 4873643.68 | 43.9325 | 7.7801 | 12.7493
16 | Bridge 2025 | 3.9 | Providing weepholes in Brick masonary / Plain/ Reinforced concrete abutment, wing wall/ return wall with 100 mm dia AC pipe, extending through the full width of the structure with slope of 1V : 20H towards drawing face . Complete as per drawing and technical specification and as per clause 2706 and 2200 | 163.2 | meter | 438 | 71481.6 |  |  | 68297.016
17 | Bridge 2025 | 3.1 | Back filling behind abutment, wing wall and return wall complete as per drawing and Technical specification 710.1.4 of I.R.C. 78 and 2200 (i) Granular material | 941.25 | cum | 1011 | 951603.75 |  |  | 120
18 | Bridge 2025 | 3.11 | Providing & laying of filter media with granular materials /stone crushed aggregates satisfying the requirements laid down in clause 2504.2.2 of MORTH specification to a thickness of not less than 600 mm with smaller towards the soil and bigger size towards the wall and provided over the entire surface behind abutment, wing wall and return wall to the full height compacted to a firm condition complete as per drawing and technical specifications 700.1.4 of I.R.C. 78 and 2200 | 176 | cum | 1968 | 346368
19 | Bridge 2025 | 3.15 | Supplying, fitting and fixing in position true to line and level elastomeric bearing conforming to IRC: 83 (Part-II) section IX and clause 2005 of MoRTH specifications complete including all accessories as per drawing and Technical Specifications section 2000 and 2200 towards the soil and bigger size towards the wall and | 187200 | cum | 1.1 | 205920 |  | sub structure
20 | Bridge 2025 | 4.1 B | Furnishing and Placing Reinforced/Prestressed cement concrete in super-structure as per drawing and Technical Specification sections 1500, 1600 and 1700 B. RCC Grade M 30 (I)SUPER - STRUCTURE For T-beam & slab (a) Using batch type concrete mixer with integrated weigher. |  |  |  | 0
|  |  | (i) Height upto 5 m | 572.94 | cum | 6788 | 3889116.72
21 | Bridge 2025 | 4.2 | Supplying, fitting and placing HSD (High Strength Deformed Steel) bar reinforcement in super-structure complete as per drawing and technical specifications 1600 (Fe 500) | 85.11 | tonne | 81366 | 6925060.26 |  | 177.3745 | 14271481.8541
22 | Bridge 2025 | 4.4 | Providing and laying Cement concrete wearing coat M-35 grade including reinforcement of 8 mm diameter @ 150 mm c/c spacing in both ways for each 75 mm thickness of concrete complete as per drawing and Technical Specifications as per section 2700 | 57.38 | cum | 12684 | 727807.92
22 | Bridge 2025 | 4.9 | Construction of RCC railing of M30 Grade in-situ with 20 mm nominal size aggregate, true to line and grade, tolerance of vertical RCC post not to exceed 1 in 500, centre to centre spacing between vertical post not to exceed 2000 mm, leaving adequate space between vertical post for expansion, complete as per latest IRC- 5 & IRC-6, approved drawings and technical specifications. | 204 | meter | 2008 | 409632
23 | Bridge 2025 | 4.13 | Drainage Spouts complete as per drawing and Technical specifications of section 2705 | 38 | each | 2688 | 102144
24 | Bridge 2025 | 4.15 | PCC M15 Grade leveling course below approach slab complete as per drawing and Technical specification and as per relevant section 2700 | 11.54 | cum | 4607 | 53164.78
25 | Bridge 2025 | 4.16 | Providing and laying M-30 grade Reinforced cement concrete approach slab including reinforcement and formwork complete as per drawing and Technical specification and as per relevant sections 1500, 1600, 1700 and 2704 | 30.24 | cum | 9867 | 298378.08
26 | Bridge 2025 | 4.22 | Strip Seal Expansion Joint (Providing and laying of a strip seal expansion joint catering to maximum horizontal movement upto 70 mm, complete as per approved drawings and standard specifi cations to be installed by the manufacturer/supplier or their authorized representative ensuring compliance to the manufacturer's instructions for installation.) | 58.8 | meter | 11567 | 680139.6
27 | Bridge 2025 | 4.26 | Painting on concrete surface of R.C.C. Railing (Providing and applying 2 coats of water based cement paint to unplastered concrete surface after cleaning the surface of dirt, dust, oil, grease, efflorescence and applying paint @ of 1 litre for 2 Sq.m. ) | 656.88 | sqm | 170 | 111669.6
28 | Bridge 2025 | 4.28 | Providing and Fixing of Av. 20mm thick Granite plate including cutting and polishing and inscribed details as per approved drawing i/c engraving the matter as desired. | 2 | Nos | 940 | 1880
29 | Bridge 2025 | 4.29 | Testing of span of bridge for deflection due to live load with platform for loading arrangements, apparatus for measurement etc. complete as per drawing and specifications (As per I.R.C.S.P.51) | 77 | tonne | 912 | 70224
30 | PMGSY 2018 | 3.4 (ii) | (ii) Construction of embankment with approved material obtained from borrow pits, transporting to site, spreading, grading to required slope and compacting to meet requirement of Tables 300.1 and 300.2 (Beyond 250m)with all leads as per Technical Specification Clause 301.5(Having CBR more than 5) | 532.39 | cum | 211 | 112334.29
31 | PMGSY 2018 | 3.12 (a) | Construction of Subgrade and Earthen Shoulders Construction of subgrade and earthen shoulders with approved material (Granular material having CBR more than 7) obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacted to meet requirement of Table 300.2 as per Technical Specification Clause 303.1. | 241.875 | cum | 216 | 52245
32 | PMGSY 2018 | 4.1 (a) | Granular Sub-base as per Table:- 400-1 Construction of granular sub-base by providing close graded Material, , carriage of mixed Material to work site, spreading in uniform layers with motor grader on prepared surface watering, rolling and compacting with vibratory power roller at OMC to achieve the desired density, complete as per clause 401.A Plant mix method (with Mechanically crushed stone only) (ii) for grading- II Material | 120.9375 | cum | 780 | 94331.25
33 | PMGSY 2018 | 4.8 | Wet Mix Macadam Providing, laying, spreading and compacting graded stone aggregate to wet mix macadam specification including premixing the material with water at OMC in mechanical mixer (Pug Mill), carriage of mixed material by tipper to site, laying in uniform layers in sub-base/base course on a well prepared sub-base and compacting with smooth wheel roller of 80 to 100kN weight to achieve the desired density including lighting, barricading and maintenance of diversion, etc as per Tables 400.11 & 400.12 and Technical Specification Clause 406. | 80.625 | cum | 1774 | 143028.75
34 | PMGSY 2018 | 3.12 (a) | Construction of Subgrade and Earthen Shoulders Construction of subgrade and earthen shoulders with approved material (Granular material having CBR more than 7) obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacted to meet requirement of Table 300.2 as per Technical Specification Clause 303.1. | 107.55 | cu.m. | 216 | 23230.8
35 | PMGSY 2018 | 6.1 (ii) | Construction of un-reinforced, jointed at expansion and construction joint only, plain cement concrete pavement, thickness as per design, over a prepared sub base, with 43 grade cement or any other type as per Clause 1501.2.2 M30 (Grade), coarse and fine aggregates conforming to IS:383, maximum size of coarse aggregate not exceeding 25 mm, mixed in a concrete mixer of not less than 0.2 cum capacity and appropriate weigh batcher using approved mix design, laid in approved fixed side formwork (steel channel, laying and fixing of 125 micron thick polythene film, wedges, steel plates including leveling the formwork as per drawing), spreading the concrete with shovels, rakes, compacted using needle, screed and plate vibrators and finished in continuous operation including provision of contraction and expansion, construction joints, applying, primer, sealant, using curing compound (where specified) and water finishing to lines and grade as per drawing and Technical Specification Clause 1501. | 161.25 | cu.m. | 6116 | 986205
36 | PMGSY 2018 | 10.5 (II) | Providing and laying pitching on slopes laid over prepared filter media as per drawing and technical specifications Clause 1302 Cement concrete blocks of size as per Table 1300.2 cast in Cement concrete of grade M 15 | 79.6425 | cu.m. | 5227 | 416291.3119
37 | PMGSY 2018 | 10.6 | Providing and laying Filter material underneath pitching in slopes complete as per drawing and Technical Clause 1302 | 39.8212 | cu.m. | 1992 | 79323.9232
38 | PMGSY 2018 | 10.11 | Construction of toe walls for protection of slopes as per drawing and technical specifications Clause 1302.5Cement concrete grade M 10 in case of concrete block P.C.C grade M 10 (Nominal mix 1:3:6) | 0 | cum | 4378 | 0
39 | PMGSY 2018 | 9.2 (A) | Cautionary, mandatory, informatory direction and place Semi-Reflective Traffic signs upto 0.90 sqm identification sign boards. Direction and place identification signs up to 0.9 sqm size board Providing and erecting direction and place identifications of semi reflective sign boards as per IRC:67 made of 2 mm thick M.S. Sheet duly stove enameled paint in white colour in front and grey colour on back with red reflective border of 70 mm width and required message, letters, figures with reflective engineering grade tape as per MORD specifications of required shade and colour. Supported and welded on 47 mm x 47mm of 12 SWG Square tube of 3050 mm height duly strengthened by 25 mm x 5 mm M/s flat iron on edges on back firmly fixed to the ground by means of properly designed foundations with M-15 grade cement concrete 450 mm x 450 mm x 600 mm, 600 mm below ground level as per approved drawing and Technical Specification Clause 1701 | 0.72 | Sqm | 5675 | 4086
40 | PMGSY 2018 | 9.14 B | Providing and Fixing Informatory and Logo Board of PMGSY Project (B) Providing and fixing of typical PMGSY informatory sign board with Logo as per MORD specifications and drawing. Three MS Plates of 1.6 mm thick, top and middle plate duly welded with MS flat iron 25mm x 5m size on back on edges. The lower plate will be welded with MS angle iron frame of 25mm x 25mm x 5mm. The angle iron frame of the lower most plate and flat iron frame of middle plate will be welded to 2 nos. 75mm x 75 mm of 12 SWG sheet tubes posts duly embedded in cement concrete M-15 grade blocks of 450mm x 450mm x 600mm, 600mm below ground level. The top most diamond plate will be welded to middle plate by 47mm x 47mm of 12 SWG steel plate tube. All M.S. will be stove enameled on both sides. Lettering and printing arrows, border etc. will be painted with ready mixed synthetic enamel paint of superior quality in required shade and colour. All sections of framed posts and steel tube will be painted with primer and two coats of epoxy paint as per drawing Clause 1701 and Annexure 1700.1 be painted with ready mixed synthetic enamel paint of superior quality in required shade and colour. All sections of framed posts and steel tube will be painted with primer and two coats of epoxy paint as per drawing Clause 1701 and Annexure 1700.1 | 1 | each | 16499 | 16499 | #REF! | #REF!
41 | PMGSY 2018 | 9.15(A) | Providing and fixing 'Citizen Information Board' of PMGSY Project (A) Providing and fixing of typical " PMGSY Citizen Information Board" with Logo as per MoRD specifications & drawings, made of 75 mm square or 75 mm dia circular steel tube of 12 SWG 3.2 m height and cross member 2 nos 1m long, fixed with angle iron 50x50x5 mm MS angle on the back | 1 | each | 16818 | 16818
42 | PMGSY 2018 | 9.16 | Providing & Fixing of PMGSY 'Logo' board Providing and fixing of typical PMGSY logo board as per MoRD specifications and drawings. | 1 | each | 7951 | 7951
43 | PMGSY 2018 | 9.17 | Reinforced cement concrete M15 grade Guard Stone of size 200 mm x 200mm x 800 mm fixing in position including painting and printing etc. as per drawing, Technical Specification and as per direction of Engineer in Charge. | 88 | Nos | 566 | 49808
44 | PMGSY 2018 | 7.19 | HYSD steel bars Supplying, fitting and placing HYSD bar reinforcement (Fe 415) in substructrue complete as per drawings and technical specification Clauses 1002, 1005, 1010 & 1202 | 1.2096 | T | 64348 | 77835.3408
45 | PMGSY 2018 | 11.13 | Painting on Concrete Surfaces White washing two coats on parapet walls of CD and tree trunks including preparation of surface by cleaning scraping etc. as per technical specifications Clause 1915 | 39.6 | sqm | 20 | 792 |  | 95954
|  |  | TOTAL AMOUNT |  |  |  | 30455803.7841
|  |  | ADD 18% GST |  |  |  | 35937848.4652 | -35937804.5327 | 43.9325
|  |  | Maintenance Cost |  |  |  |  | 761395.0946
|  |  | 1st Year |  |  |  | 114209.2642 | 898446.2116
|  |  | 2nd Year |  |  |  | 114209.2642
|  |  | 3rd Year |  |  |  | 152279.0189
|  |  | 4th Year |  |  |  | 190348.7737
|  |  | 5th Year |  |  |  | 190348.7737
|  |  | Total Maintencnce Cost |  |  |  | 761395.0946
|  |  | Add 18% GST |  |  |  | 898446.2116
|  |  | G-Total |  |  |  | 36836294.6769
|  |  | Say Rs. In Lacs |  |  |  | 368.3629
| Sub Engineer CGRRDA, PIU 01 Bastar |  | Assistant Engineer CGRRDA, PIU 01 Bastar |  | Executive Engineer CGRRDA, PIU 01 Bastar

## COMPRATIVE (hidden)
Comperative Statement
ISSUED BY ENGINEER IN-CHIEF C.G.P.W.D RAIPUR
INFORCE FORM 01.01.2016
COMPRETIVE STATEMENT FOR HIGH LEVEL BRIDGE ACROSS
REVISED ESTIMATE FOR HIGH LEVEL BRIDGE ACROSS GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.(CG05077)
7 SPAN @ 21.43 M = 150 M., ABUTMENT 2 x 5.0 = 10 M. WALL TYPE PIER & R.C.C. BOX TYPE ABUTMENT
ISSUED BY CHIEF ENGINEER C.G.R.R.D.A. RAIPUR
INFORCE FORM 01.09.2014
Parsodikala Side =250.00 M. & Sukhari Side = 100.00 m.
Sr. no. | Item Id | BOQ Description | Unit | As Per DPR |  |  | As per Revised/Actual |  |  | Saving |  |  | Excess |  |  | Reason
|  |  |  | Qty | Rate | Amount | Qty | Rate | Amount | Qty | Rate | Amount | Qty | Rate | Amount
1 | 2.1 | Excavation for Structures (Earth work in excavation of foundation of structures as per drawing and technical specification, including setting out, construction of shoring and bracing, removal of stumps and other deleterious matter, dressing of sides and bottom and backfilling with approved material.)
| A | Ordinary soil
| (i) | Up to 3m depth | cum | 3726 | 131.4 | 489596.4 | #REF! | #REF! | #REF! | #REF! | 131.4 | #REF! | 0 | 131.4 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | 3m to 6 depth | cum | 1046 | 150.3 | 157213.8 | 0 | 150.3 | 0 | 1046 | 150.3 | 157213.8 | 0 | 150.3 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | Above 6 m depth | cum | 51 | 184.5 | 9409.5 | 0 | 184.5 | 0 | 51 | 184.5 | 9409.5 | 0 | 184.5 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| C | Hard rock (requiring blasting) | cum | 552 | 721.8 | 398433.6 | 0 | 721.8 | 0 | 552 | 721.8 | 398433.6 | 0 | 721.8 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
Add extra 20% in the rates of above items for dewatering (Assessment of dewatering shall be made as per site condition )
| (i) | Up to 3m depth | cum | 1104 | 26.28 | 29013.12 | #REF! | #REF! | #REF! | #REF! | 26.28 | #REF! | 0 | 26.28 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | 3m to 6 depth | cum | 784 | 30.06 | 23567.04 | 0 | 30.06 | 0 | 784 | 30.06 | 23567.04 | 0 | 30.06 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | Above 6 m depth | cum | 51 | 36.9 | 1881.9 | 0 | 36.9 | 0 | 51 | 36.9 | 1881.9 | 0 | 36.9 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
| C | Hard rock (requiring blasting) | cum | 552 | 144.36 | 79686.72 | 0 | 144.36 | 0 | 552 | 144.36 | 79686.72 | 0 | 144.36 | 0 | कार्य स्थल पर OPEN FOUNDATION से PILE FOUNDATION कार्य होने के कारण मात्रा कम हो रही है।
2 | 2.3 | Sand Filling in Foundation Trenches as per Drawing & Technical Specifications. | cum | 0 | 1110.6 | 0 | #REF! | 1110.6 | #REF! | 0 | 1110.6 | 0 | #REF! | 1110.6 | #REF! | दोनो अबटमेन्ट बाक्स टाईप होने के FILTER Media की जगह sand Filling लेने के कारण मात्रा बढ़ रही है।
3 | 2.6 A(i) | Plain/Reinforced cement concrete in open foundation complete as per drawing and technical specifications. and technical specifications. A Using concrete mixer PCC Grade M15 | cum | 483.75 | 4151.7 | 2008384.875 | #REF! | #REF! | #REF! | #REF! | 4151.7 | #REF! | 0 | 4151.7 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा कम हो रही है।
4 | 2.6 B(III) | Plain cement concrete in sub-structure complete as per drawing and Technical Specifications (iii) RCC Grade M- 30 | cum | 623.84 | 5417.1 | 3379403.664 | #REF! | #REF! | #REF! | #REF! | 5392.8 | #REF! | 0 | 5392.8 | 0 | कार्य स्थल पर आवश्यकतानुसार RETAINING WALL कार्य होने के कारण मात्रा कम हो रही है।
5 | 2.16 | Providing steel liner 10 mm thick for curbs and 6mm thick for steining of wells including fabricating and setting out as per detailed drawing and specifications as per section 1200 and 1900. | MT | 0 | 65286 | 0 | #REF! | 65286 | #REF! | 0 | 65286 | 0 | #REF! | 65286 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से Pile Foundation देने के कारण मात्रा बढ़ रही है।
6 | 2.17 (iii) | Bored cast-in-situ M35 grade R.C.C. pile excluding reinforcement complete as per drawing and technical specifications and removal of excavated earth with all lifts and lead upto 1000 m as per section 1100 and 1700. | cum | 0 | 14123.7 | 0 | #REF! | 14123.7 | #REF! | 0 | 14123.7 | 0 | #REF! | 14123.7 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से PILE FOUNDATION देने के कारण मात्रा बढ़ रही है।
7 | L.S. | SAFE BEARING CAPACITY TEST | Nos | 0 | 3000 | 0 | 9 | 3000 | 27000 | 0 | 3000 | 0 | 9 | 3000 | 27000 | निर्माण स्थल में हार्ड राँक नही मिलने से SAFE BEARING CAPACITY TEST की आवश्यकता होने के कारण मात्रा बढ़ रही है।
8 | 2.21 | Pile Load Test on single Vertical Pile in accordance with IS:2911(Part-IV) in static load method only Lateral load test | Each Test | 0 | 67500 | 0 | #REF! | 67500 | #REF! | 0 | 67500 | 0 | #REF! | 67500 | #REF! | PILE FOUNDATION देने के कारण एक Dynomic Test होना आवश्यक है, जिस कारण मात्रा बढ़ रही है।
9 | 2.22 A (iii) | Cement concrete for reinforced concrete in pile cap complete as per drawing and Technical Specifications per clause 1100,1500 and 1700. RCC Grade M35 | cum | 0 | 5297.4 | 0 | #REF! | 5297.4 | #REF! | 0 | 5297.4 | 0 | #REF! | 5297.4 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से PILE FOUNDATION देने के कारण मात्रा बढ़ रही है।
10 | 2.23 | Levelling course for Pile cap (Providing and laying of P.C.C.M-15 levelling course 100mm thick below the pile cap.) | cum | 0 | 4067.1 | 0 | #REF! | 4067.1 | #REF! | 0 | 4067.1 | 0 | #REF! | 4067.1 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से PILE FOUNDATION देने के कारण मात्रा बढ़ रही है।
11 | 2.24 | Supplying, fitting and placing HSD (High Strength Deformed Steel) bar reinforcement in foundation complete as per drawing and technical specifications as per section 1600. | MT | 0 | 61823.7 | 0 | #REF! | 61823.7 | #REF! | 0 | 61823.7 | 0 | #REF! | 61823.7 | #REF! | निर्माण स्थल में DESIGN LEVEL नीचे जाने से PILE FOUNDATION देने के कारण मात्रा बढ़ रही है।
12 | 2.25 | Taking exploratory boring 100 mm dia. at the location of piers and abutments or for high embankments in approaches in all types of strata as per I.R.C. 78-2014 and section 2400 of specifications for collection of samples at different depth (rock sample and undisturbed soil sample) and test including preserving core samples as per specifications.
| (i) | Upto 1.0 m below bed level | each | 12 | 5355.9 | 64270.8 | #REF! | 5355.9 | #REF! | #REF! | 5355.9 | #REF! | 0 | 5355.9 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा कम हो रही है।
| (ii) | Beyond 1.0 m upto 5.0 m depth | meter | 60 | 1170 | 70200 | #REF! | 1170 | #REF! | #REF! | 1170 | #REF! | 0 | 1170 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा कम हो रही है।
| (iii) | Beyond 5.0 m depth | meter | 28.99 | 1327.5 | 38484.225 | #REF! | 1327.5 | #REF! | 0 | 1327.5 | 0 | #REF! | 1327.5 | #REF! | निर्माण स्थल में HARD ROCK नही मिलने के कारण मात्रा बढ़ रही है।
13 | 3.6 | Providing and laying Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications section 1500, 1700 and 2200
| D(a)(iii) | Height upto 5m (RCC Grade M30) | cum | 674 | 5733 | 3864042 | #REF! | 5733 | #REF! | #REF! | 5733 | #REF! | 0 | 5733 | 0 | PILE FOUNDATION देने के कारण के कारण मात्रा कम हो रही है।
| E(a)(iii) | Height upto 5m (RCC Grade M30) | cum | 373 | 5894.1 | 2198499.3 | #REF! | 5894.1 | #REF! | #REF! | 5894.1 | #REF! | 0 | 5894.1 | 0 | PILE FOUNDATION देने के कारण के कारण मात्रा कम हो रही है।
| F(a)(iii) | Height upto 10m (RCC Grade M30) | cum | 132 | 6175.8 | 815205.6 | #REF! | 6175.8 | #REF! | #REF! | 6175.8 | #REF! | 0 | 6175.8 | 0 | PILE FOUNDATION देने के कारण के कारण मात्रा कम हो रही है।
14 | 3.7 | Supplying, fitting and placing HYSD bar reinforcement in sub-structure complete as per drawing and technical specifications section 1600 and 2200 | tonne | 121 | 62101.8 | 7514317.8 | #REF! | 62101.8 | #REF! | #REF! | 62101.8 | #REF! | 0 | 62101.8 | 0 | BRIDGE की HIGHT बढ़ने के कारण मात्रा बढ़ हो रही है।
15 | 3.8 | Providing weep holes in Brick masonry/ Plain/ Reinforced concrete abutment, wing wall/return wall with 100 mm dia AC pipe, extending through the full width of the structure with slope of 1V :20H towards drawing foce. Complete as per drawing and Technical specifications section 2706 and 2200 | meter | 122 | 288.9 | 35245.8 | #REF! | 288.9 | #REF! | 0 | 288.9 | 0 | #REF! | 288.9 | #REF! | कार्य स्थल पर आवश्यकतानुसार RETAINING WALL कार्य होने के कारण मात्रा बढ़ रही है।
16 | 3.9 | Back filling behind abutment, wing wall and return wall complete as per drawing and Technical specification 710.1.4 of I.R.C. 78 and 2200 (i) Granular material | cum | 224 | 814.5 | 182448 | #REF! | 814.5 | #REF! | 0 | 814.5 | 0 | #REF! | 814.5 | #REF! | BRIDGE की HIGHT बढ़ने के कारण मात्रा बढ़ हो रही है।
17 | 3.1 | Providing and laying of Filter media with granular materials/stone crushed aggregates satisfying the requirements laid down in clause 2504.2.2. of MoRTH specifications to a thickness of not less than 600 mm with smaller size towards the soil and bigger size towards the wall and provided over the entire surface behind abutment, wing wall and return wall to the full height compacted to a firm condition complete as per drawing and technical specifications 710.1.4 of I.R.C. 78 and 2200 | cum | 879 | 1733.4 | 1523658.6 | #REF! | 1733.4 | #REF! | #REF! | 1733.4 | #REF! | 0 | 1733.4 | 0 | कार्य स्थल पर आवश्यकतानुसार RETAINING WALL पे ही Filter media उपयोग होने के कारण मात्रा कम हो रही है।
18 | 3.14 | Supplying, fitting and fixing in position true to line and level elastomeric bearing conforming to IRC: 83 (Part-II) section IX and clause 2005 of MoRTH specifications complete including all accessories as per drawing and Technical Specifications section 2000 and 2200 | cum | 234000 | 0.9 | 210600 | #REF! | 0.9 | #REF! | #REF! | 0.9 | #REF! | 0 | 0.9 | 0 | स्लैब की संख्या कम होने के कारण मात्रा कम हो रही है।
19 | 4.1 B | Furnishing and Placing Rein forced / Pressse Cement Concrete in Super Structure as per drawing and Technical RCC Grade M30 (i) Height upto 5m
| c | RCC GRADE M 30
|  | (i) Height upto 5m. | cum | 1026 | 6301.8 | 6465646.8 | 0 | 6301.8 | 0 | 1026 | 6301.8 | 6465646.8 | 0 | 6301.8 | 0 | SOLID SLAB की जगह T-BEAM & SLAB होने के कारण मात्रा कम हो रही है।
20 | 4.1 B | SUPER STRUCURE Furnishing and Placing Reinforced/Prestressed cement concrete in super-structure as per drawing and Technical Specification sections 1500, 1600 and 1700 B. RCC Grade M 30 (II)SUPER - STRUCTURE II For T-beam & slab (a) Using Concrete Mixer (Iii)Height above 10m | cum | #REF! | 7059.6 | #REF! | #REF! | 7059.6 | #REF! | 0 | 7059.6 | 0 | #REF! | 7059.6 | #REF! | SOLID SLAB की जगह T-BEAM & SLAB होने के कारण मात्रा बढ़ रही है।
21 | 4.2 | Supplying Fitting and placing un-coated HYSD bar reinforcement in foundation complete as per drawing and technical as per section 1600 | tonne | 86.81 | 63090.9 | 5476921.029 | #REF! | 63090.9 | #REF! | 0 | 63090.9 | 0 | #REF! | 63090.9 | #REF! | SOLID SLAB की जगह T-BEAM & SLAB होने के कारण मात्रा बढ़ रही है।
22 | 4.4 | Providing and laying Cement concrete wearing coat M-30 grade including reinforcement complete as per drawing and Technical Specification | cum | 91 | 10662.3 | 970269.3 | #REF! | 10662.3 | #REF! | #REF! | 10662.3 | #REF! | 0 | 10662.3 | 0 | ABUTMENT TOP SLAB की लम्बाई कम होने के कारण मात्रा कम हो रही है।
23 | 4.6 | Construction of RCC railing of M30 Grade in-situ with 20 mm nominal size aggregate, true to line and grade, tolerance of vertical RCC post not to exceed 1 in 500, centre to centre spacing between vertical post not to exceed 2000 mm, leaving adequate space between vertical post for expansion, complete as per approved drawings and technical specifications. (vide drawing No. SD/201, SD/304) | meter | 322 | 1637.1 | 527146.2 | #REF! | 1637.1 | #REF! | #REF! | 1637.1 | #REF! | 0 | 1637.1 | 0 | ABUTMENT TOP SLAB की लम्बाई कम होने के कारण मात्रा कम हो रही है।
24 | 4.9 | Drainage Spouts complete as per drawing and Technical specifications of section 2705 | each | 60 | 1806.3 | 108378 | #REF! | 1806.3 | #REF! | 0 | 1806.3 | 0 | #REF! | 1806.3 | #REF! | T-BEAM & SLAB की लम्बाई बढ़ने के कारण मात्रा बढ़ रही है।
25 | 4.1 | PCC M15 Grade leveling course below approach slab complete as per drawing and Technical specification and as per relevant section 2700 | cum | 9 | 3993.3 | 35939.7 | #REF! | 3993.3 | #REF! | #REF! | 3993.3 | #REF! | 0 | 3993.3 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
26 | 4.11 | Providing and laying M-30 grade Reinforced cement concrete approach slab including reinforcement and formwork complete as per drawing and Technical specification and as per relevant sections 1500, 1600, 1700 and 2704 | cum | 18 | 8520.3 | 153365.4 | #REF! | 8520.3 | #REF! | #REF! | 8520.3 | #REF! | 0 | 8520.3 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
27 | 4.14 | Filler joint (A)Providing & fixing 2 mm thick corrugated copper plate ( 12 m long x 25 cm wide ) in expansion joint complete as per drawing & Technical Specification.
| A | (A) Providing & fixing 20 mm thick Corrugated copper plate ( 12 m long x 25 cm deep ) in expansion joint complete as per drawing & Technical Specification. | sqm | 23.1 | 19674 | 454469.4 | 0 | 19674 | 0 | 23.1 | 19674 | 454469.4 | 0 | 19674 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
| B | (B) Providing & fixing 20 mm thick compressible fiber board ( 12 m long x 25 cm deep ) in expansion joint complete as per drawing & Technical Specification. | sqm | 75.02 | 1083.6 | 81291.672 | #REF! | 1083.6 | #REF! | #REF! | 1083.6 | #REF! | 0 | 1083.6 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
| D | (D)Providing and filling joint sealing compound ( 12 m long x 100 mm wide x 10 mm deep recess) as per drawings and technical specifications with coarse sand and 6% bitumen by weight | sqm | 9.24 | 198 | 1829.52 | #REF! | 198 | #REF! | 0 | 198 | 0 | #REF! | 198 | #REF! | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
28 | 4.18 | Strip Seal Expansion Joint (Providing and laying of a strip seal expansion joint catering to maximum horizontal movement upto 70 mm, complete as per approved drawings and standard specifi cations to be installed by the manufacturer/supplier or their authorized representative ensuring compliance to the manufacturer's instructions for installation.) | meter | 0 | 10011.6 | 0 | #REF! | 10011.6 | #REF! | 0 | 10011.6 | 0 | #REF! | 10011.6 | #REF! | T-BEAM & SLAB होने के कारण मात्रा बढ़ रही है।
29 | 4.21 | Painting on concrete surface of R.C.C. Railing (Providing and applying 2 coats of water based cement paint to unplastered concrete surface after cleaning the surface of dirt, dust, oil, grease, efflorescence and applying paint @ of 1 litre for 2 Sq.m. ) | sqm | 0 | 135.9 | 0 | #REF! | 135.9 | #REF! | 0 | 135.9 | 0 | #REF! | 135.9 | #REF! | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
30 | 4.22 | Providing and Fixing of Av. 20mm thick marble plate i/c cutting and polishing and inscribed details as per approved drawing i/c engraving the matter as desired. | Nos | 2 | 4500 | 9000 | #REF! | 4500 | #REF! | #REF! | 4500 | #REF! | #REF! | 4500 | #REF! | इस आयटम मे कोई विचलन नही आ रहा है।
31 | 4.24 | Testing of span of bridge for deflection due to live load with platform for loading arrangements, apparatus for measurement etc. complete as per drawing and specifications (As per I.R.C.S.P.51) | tonne | 77 | 765 | 58905 | #REF! | 765 | #REF! | #REF! | 765 | #REF! | #REF! | 765 | #REF! | इस आयटम मे कोई विचलन नही आ रहा है।
32 | 5.1 | Providing and laying boulders apron on river bed for protection against scour with stone boulders weighing not less than 40 kg each complete as per drawing and Technical specification as per relevant clauses of section 2503 | cum | 276.49 | 2171.7 | 600453.333 | 0 | 2171.7 | 0 | 276.49 | 2171.7 | 600453.333 | 0 | 2171.7 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
33 | 5.4 A | Providing and laying Pitching on slopes laid over prepared filter media including boulder apron laid dry in front of toe of embankment complete as per drawing and Technical specifications. | cum | 20 | 2171.7 | 43434 | 0 | 2171.7 | 0 | 20 | 2171.7 | 43434 | 0 | 2171.7 | 0 | Approch Road का RATE लगने के कारण मात्रा बच रही है।
34 | 5.5 | Providing and laying Filter material underneath pitching in slopes complete as per drawing and Technical specification. | cum | 10 | 1871.1 | 18711 | 0 | 1871.1 | 0 | 10 | 1871.1 | 18711 | 0 | 1871.1 | 0 | Approch Road का RATE लगने के कारण मात्रा बच रही है।
|  | PART-A GRAND TOTAL |  | G.Total | #REF! |  | G.Total | #REF! |  | G.Total | #REF! |  | G.Total | #REF!
| PART-B | [5 empty] | Excess | #REF! |  |  |  |  | Excess | #REF!
35 | 3.4 (ii) | Construction of subgrade and earthen shoulders with approved material (Granular material having CBR more than 7) obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacted to meet requirement of Table 300.2 as per Technical Specification Clause 303.1.For Item No.3.12(a) & (b) | cum | 4523 | 176 | 796048 | #REF! | 176 | #REF! | 0 | 176 | 0 | #REF! | 176 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
36 | 3.5 | Excavation in Cutting in Soil by manual means Excavation for roadway in soil for carrying of cut earth to embankment site with a lift upto 1.5 m and lead upto 50 m as per Technical Specification Clause 302.3 | cum | 0 | 76 | 0 | #REF! | 76 | #REF! | 0 | 76 | 0 | #REF! | 76 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
37 | 3.4(i) | 3.4 Construction of Embankment with Material Obtained from Pits (i) Construction of embankment with approved material obtained form borrow pits, transported to site, spreading, grading to required slopes and compacting to meet requirement of Tables 300.1 & 300.2 with a lead up to 250 m as per technical specifications clause 301.5 | cum | 483 | 118 | 56994 | #REF! | 152 | #REF! | 0 | 152 | 0 | #REF! | 152 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
38 | 3.12 (b) | Construction of Subgrade and Earthen Shoulders Construction of subgrade and earthen shoulders with approved material (Granular material having CBR more than 7) obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacted to meet requirement of Table 300.2 as per Technical Specification Clause 303.1. | cum | 0 | 176 | 0 | #REF! | 176 | #REF! | 0 | 176 | 0 | #REF! | 176 | #REF! | Approch Road में Earthen Shoulders की मात्रा नहीं होने के कारण मात्रा बढ़ रही है।
39 | 4.1 B | Granular Sub-base with Well Graded Material (CBR 20 or more) (Table 400.1) Construction of granular sub-base by providing well graded material having CBR 20 or more, spreading in uniform layers with motor grader on prepared surface, mixing by mix in place method with rotavator at OMC, and compacting with vibratory rollers of 80 to 100KN static weight to achieve the desired density, complete as per Technical Specification Clause 401. For Grading mentioned in table 400.1 (Grading III) Disintegrated rock i.e. mourum having CBR value not less then 15% and PI & LL not more then 6 and 25 respectively (with prior permission of Chief Engineer) | cum | 173 | 450 | 77850 | #REF! | 450 | #REF! | 0 | 450 | 0 | #REF! | 450 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
40 | 4.7 (ii) | Water Bound Macadam with Crushable Screenings WBM Grading 2 Providing, laying, spreading and compacting mechanically crushed stone aggregates of specific sizes to water bound macadam specification including spreading in uniform thickness, hand packing, rolling with three wheel 80-100 kN static roller in stages to proper grade and camber, applying and brooming, crushable screening to fill-up the interstices of coarse aggregate, watering and compacting to the required density Grading 3 as per Technical Specification Clause 405. | cum | 80 | 1583 | 126640 | #REF! | 1583 | #REF! | 0 | 1583 | 0 | #REF! | 1583 | #REF! | Approch Road की लम्बाई बढ़ने के मात्रा बढ़ रही है।
41 | 4.7 (iii) | Water Bound Macadam with Crushable Screenings WBM Grading 3 Providing, laying, spreading and compacting mechanically crushed stone aggregates of specific sizes to water bound macadam specification including spreading in uniform thickness, hand packing, rolling with three wheel 80-100 kN static roller in stages to proper grade and camber, applying and brooming, crushable screening to fill-up the interstices of coarse aggregate, watering and compacting to the required density Grading 3 as per Technical Specification Clause 405. | cum | 80 | 1694 | 135520 | 0 | 1694 | 0 | 80 | 1694 | 135520 | 0 | 1694 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
42 | 4.12 | Construction of hard shoulders as per Technical Specification Clause 407.Construction of hard shoulder with granular material having CBR value not less than 15 including all leads & lift, watering & compaction with smooth wheeled roller to achieve the desired density as per technical specification clause 407 & 401. | cum | 161 | 358 | 57638 | #REF! | 358 | #REF! | 0 | 358 | 0 | #REF! | 358 | #REF! | कार्य स्थल पर आवश्यकतानुसार कार्य होने के कारण मात्रा बढ़ रही है।
43 | 5.1 | Prime Coat Providing and applying primer coat with bitumen emulsion (SS-1) on prepared surface of granular base including cleaning of road surface and spraying primer at the rate of 0.70-1.0 kg/sqm using mechanical means as per Technical Specification Clause 502 | sqm | 1071 | 53 | 56763 | 0 | 53 | 0 | 1071 | 53 | 56763 | 0 | 53 | 0 | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बच रही है।
44 | 5.2 | Tack coat Providing and applying tack coat with Bitumen emulsion (RS-1) using emulsion distributor at the rate of 0.20 to 0.25 kg per sqm on the prepared bituminous surface cleaned with Hydraulic broom as per Technical Specification Clause 503 | sqm | 1071 | 15 | 16065 | 0 | 15 | 0 | 1071 | 15 | 16065 | 0 | 15 | 0 | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बच रही है।
45 | 5.3(ii) | 20mm thick Open-Graded Premix Carpet using Bituminous (VG/modified bitumen) Binder Providing, laying and rolling of open-graded premix carpet of 20 mm thickness composed of aggregate 13.2mm size (passing 22.4mm size sieve & retained on 11.2mm sieve and 11.2mm size (passing 13.2mm sieve and retained on 5.6mm sieve) either using penetration grade/ VG bitumen or emulsion to required line, grade and level to serve as wearing course on a previously prepared base, including mixing in a suitable plant, laying and rolling with a three wheel 80-100 kN static roller capacity, finished to required level and grades to be followed by seal coat of either Type A or Type B or Type C as per Technical Specification Clause 508., Viscocity grade (VG) Bitumen specification as per IS 73:2006 (ii) Bitumen (VG-30) | sqm | 1071 | 155 | 166005 | 0 | 155 | 0 | 1071 | 155 | 166005 | 0 | 155 | 0 | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बच रही है।
46 | 5.5 Case-(II) Type -B (II) | Seal Coat Providing and laying seal coat sealing the voids in a bituminous surface laid to the specified levels, grade and cross fall using Type A, Type B and Type C as per Technical Specification Clause 510, Viscocity grade (VG) Bitumen specification as per IS 73:2006 Bitumen (VG-30) | sqm | 1071 | 56 | 59976 | 0 | 56 | 0 | 1071 | 56 | 59976 | 0 | 56 | 0 | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बच रही है।
47 | 6.1 (ii) | Cement Concrete Pavement Construction of un-reinforced, jointed at expansion and construction joint only, plain cement concrete pavement, thickness as per design, over a prepared sub base, with 43 grade cement or any other type as per Clause 1501.2.2 M30 (Grade), coarse and fine aggregates conforming to IS:383, maximum size of coarse aggregate not exceeding 25 mm, mixed in a concrete mixer of not less than 0.2 cum capacity and appropriate weigh batcher using approved mix design, laid in approved fixed side formwork (steel channel, laying and fixing of 125 micron thick polythene film, wedges, steel plates including leveling the formwork as per drawing), spreading the concrete with shovels, rakes, compacted using needle, screed and plate vibrators and finished in continuous operation including provision of contraction and expansion, construction joints, applying, primer, sealant, using curing compound (where specified) and water finishing to lines and grade as per drawing and Technical Specification Clause 1501. | cum | 0 | 5097 | 0 | #REF! | 5097 | #REF! | 0 | 5097 | 0 | #REF! | 5097 | #REF! | Approch Road मे cement concrete का कार्य होने के कारण मात्रा बढ़ रही है।
48 | 7.1 (I) | Excavation for Structure as per drawing and technical specifications Clause 305.1 including setting out, construction of shoring and bracing, removal of stumps and other deleterious material and disposal upto a lead of 50 m, dressing of sides and bottom and backfilling in trenches with excavated suitable material. (I) Ordinary soil( i). Upto 3 m depth | cum | 0 | 161 | 0 | #REF! | 161 | #REF! | 0 | 161 | 0 | #REF! | 161 | #REF! | Toe Wall कार्य होने के कारण मात्रा बढ़ रही है।
49 | 7.7 | Plain Cement Concrete M10 (1:3:6 nominal mix) in levelling course below open foundation of Head walls as per drawings & Technical Specification Clause 1109 Nominal Mix 1:3:6(with 40mm Graded metal | cum | 0 | 3963 | 0 | #REF! | 3963 | #REF! | 0 | 3963 | 0 | #REF! | 3963 | #REF! | Toe Wall कार्य होने के कारण मात्रा बढ़ रही है।
50 | 7.10(II) | Providing concrete for plain/reinforced concrete in open foundation complete as per drawings and technical specifications Clause 802, 803, 1202 & 1203 II. P.C.C grade M 15(Nominal mix (1:2.5:5) | cum | 0 | 3899 | 0 | #REF! | 3899 | #REF! | 0 | 3899 | 0 | #REF! | 3899 | #REF! | Toe Wall कार्य होने के कारण मात्रा बढ़ रही है।
51 | 10.5 | Providing and laying pitching on slopes laid over prepared filter media as per drawing and technical specifications Clause 1302 I. Stone/Boulder | cum | 0 | 1430 | 0 | #REF! | 1430 | #REF! | 0 | 1430 | 0 | #REF! | 1430 | #REF! | Pitching कार्य होने के कारण मात्रा बढ़ रही है।
52 | 10.6 | Providing and laying filter material underneath pitching in slopes complete as per drawing and technical specifications Clause 1302 | cum | 0 | 1337 | 0 | #REF! | 1657 | #REF! | 0 | 1337 | 0 | #REF! | 1337 | #REF! | Pitching कार्य होने के कारण मात्रा बढ़ रही है।
53 | 7.6 (C) | Laying Reinforced Cement Concrete Pipe NP3 as per drawing and technical specification Clause 1402.6 Providing and laying reinforced cement concrete pipe NP3 for culverts on first Class bedding in single row including fixing with cement mortar 1:2 but excluding excavation, bedding protection works, backfilling, concrete and masonry works in head walls and parapets Clause 1106. (C) 450 mm dia | meter | 0 | 1961 | 0 | #REF! | 1961 | #REF! | 0 | 5177 | 0 | #REF! | 5177 | #REF! | 450 mm dia Pipe कार्य होने के कारण मात्रा बढ़ रही है।
54 | 9.2 (B) | Cautionary, mandatory, informatory direction and place identification sign boards. (B)Semi-Reflective Traffic signs more than 0.90 sqm sign board Providing and erecting direction and place identification of semi reflective sign boards as per IRC-67 made of 2 mm thick M.S. Sheet duly stove enameled paint white colour in front and grey colour on back with reflective border of 70 mm width and required message, letters, figures with reflective tape of engineering grade as per MORD specifications of required shade and colour. Supported and welded on two nos. 47 mm x 47 mm of 12 SWG square tube of 3050 mm height duly strengthened by 25 mm x 5 mm MS flat iron on edges on back firmly fixed to the ground by means of properly designed foundations with M-15 grade cement concrete 450 mm x 450 mm x 600 mm, 600 mm below ground level as per approved drawing and Technical Specification Clause 1701 | Sqm | 0 | 4667 | 0 | #REF! | 4667 | #REF! | 0 | 4667 | 0 | #REF! | 4667 | #REF! | Semi-Reflective Traffic signs कार्य होने के कारण मात्रा बढ़ रही है।
55 | 9.9 | Boundary Pillar Reinforced cement concrete M15 grade boundary pillars/local stone of standard design as per IRC:25, fixed in position including finishing and lettering but excluding painting as per drawing and Technical Specification Clause 1704. | each | 102 | 489 | 49878 | #REF! | 489 | #REF! | 0 | 489 | 0 | #REF! | 489 | #REF! | Boundary Pillar कार्य होने के कारण मात्रा बढ़ रही है।
56 | 9.14 B | Providing and Fixing Informatory and Logo Board of PMGSY Project (B) Providing and fixing of typical PMGSY informatory sign board with Logo as per MORD specifications and drawing. Three MS Plates of 1.6 mm thick, top and middle plate duly welded with MS flat iron 25mm x 5m size on back on edges. The lower plate will be welded with MS angle iron frame of 25mm x 25mm x 5mm. The angle iron frame of the lower most plate and flat iron frame of middle plate will be welded to 2 nos. 75mm x 75 mm of 12 SWG sheet tubes posts duly embedded in cement concrete M-15 grade blocks of 450mm x 450mm x 600mm, 600mm below ground level. The top most diamond plate will be welded to middle plate by 47mm x 47mm of 12 SWG steel plate tube. All M.S. will be stove enameled on both sides. Lettering and printing arrows, border etc. will be painted with ready mixed synthetic enamel paint of superior quality in required shade and colour. All sections of framed posts and steel tube will be painted with primer and two coats of epoxy paint as per drawing Clause 1701 and Annexure 1700.1 be painted with ready mixed synthetic enamel paint of superior quality in required shade and colour. All sections of framed posts and steel tube will be painted with primer and two coats of epoxy paint as per drawing Clause 1701 and Annexure 1700.1 | each | 0 | 14930 | 0 | #REF! | 14930 | #REF! | 0 | 14930 | 0 | #REF! | 14930 | #REF! | Informatory and Logo Board कार्य होने के कारण मात्रा बढ़ रही है।
57 | 9.15(A) | Providing and fixing 'Citizen Information Board' of PMGSY Project (A) Providing and fixing of typical " PMGSY Citizen Information Board" with Logo as per MoRD specifications & drawings, made of 75 mm square or 75 mm dia circular steel tube of 12 SWG 3.2 m height and cross member 2 nos 1m long, fixed with angle iron 50x50x5 mm MS angle on the back | each | 0 | 14015 | 0 | #REF! | 14015 | #REF! | 0 | 14015 | 0 | #REF! | 14015 | #REF! | Citizen Information Board कार्य होने के कारण मात्रा बढ़ रही है।
58 | 9.16 | Providing & Fixing of PMGSY 'Logo' board Providing and fixing of typical PMGSY logo board as per MoRD specifications and drawings. | each | 2 | 6626 | 13252 | 1 | 6626 | 6626 | 1 | 6626 | 6626 | 0 | 6626 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
59 | 11.13 | Painting on Concrete Surfaces White washing two coats on parapet walls of CD and tree trunks including preparation of surface by cleaning scraping etc. as per technical specifications Clause 1915 | sqm | 383 | 15 | 5745 | #REF! | 15 | #REF! | #REF! | 15 | #REF! | 0 | 15 | 0 | कार्य स्थल पर आवश्यकतानुसार कार्य नही होने पर मात्रा बच रही है।
60 | 9.5 | Providing and laying Reinforced Cement Concrete pipe NP 3 / prestressed concrete pipe on first class bedding. (Laying Reinforced cement concrete pipe NP3 /prestressed concrete pipe for culverts on first class bedding of granular material including fixing collar with cement mortar 1:2 but excluding excavation, protection works, backfilling, concrete and masonry works in head walls and parapets . ) (D) 1000 mm dia | meter | 20 | 4833 | 96660 | 0 | 4833 | 0 | 20 | 4833 | 96660 | 0 | 4833 | 0 | गलत आयटम नं॰ होने के कारण मात्रा बच रही है।
[6 empty] | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF!
[8 empty] | Excess | #REF! |  |  |  |  | Excess | #REF!
|  | Sub Engineer |  | Assistant Engineer |  |  |  | Executive Engineer |  |  |  |  | Superintending Engineer
|  | CGRRDA, PIU - 01, Ambikapur |  | CGRRDA, PIU - 01, Ambikapur |  |  | CGRRDA, PIU - 01, Ambikapur | [5 empty] | CGRRDA,Project Circle No. -01,Ambikapur
|  | Distt. - Surguja |  | Distt. - Surguja |  |  |  | Distt. - Surguja |  |  |  |  | Distt. - Surguja ( C.G.)

## LEVEL (hidden)
LEVEL BOOK
Name Of Bridge:-GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
PACKAGE NO.:-CGLSB16-21
CH. | RL
| L3 | L2 | L1 | C | R1 | R2 | R3
0 | 101.215 | 101.215 | 101.215 | 100.58 | 100.285 | 99.415 | 98.905
20 | 100.915 | 100.165 | 99.755 | 100.035 | 99.565 | 98.265 | 98.165
40 | 101.015 | 99.815 | 99.075 | 99.355 | 98.915 | 98.165 | 97.965
60 | 100.215 | 99.115 | 98.285 | 98.705 | 98.585 | 97.915 | 97.925
80 | 99.585 | 99.075 | 97.795 | 98.065 | 97.665 | 96.965 | 96.715
100 | 99.715 | 99.015 | 97.495 | 97.635 | 97.535 | 97.245 | 97.315
120 | 99.415 | 98.815 | 97.265 | 97.495 | 97.815 | 97.425 | 96.815
140 | 99.415 | 98.715 | 97.075 | 97.365 | 97.615 | 96.865 | 96.715
160 | 95.755 | 96.155 | 97.005 | 97.125 | 96.975 | 97.075 | 96.705
180 | 96.155 | 96.905 | 96.375 | 96.365 | 96.245 | 95.985 | 95.825
200 | 96.295 | 95.945 | 95.735 | 95.945 | 96.005 | 95.935 | 95.755
220 | 95.935 | 95.445 | 95.415 | 95.575 | 95.805 | 95.305 | 95.005
240 | 95.015 | 95.115 | 95.215 | 95.225 | 95.235 | 95.435 | 95.725
260 | 95.675 | 95.355 | 95.015 | 94.855 | 94.835 | 94.155 | 93.905
270 | 94.795 | 94.795 | 94.315 | 93.355 | 93.935 | 94.795 | 94.795
280 | 94.395 | 93.295 | 91.695 | 92.675 | 92.795 | 92.995 | 94.195
290 | 94.795 | 94.795 | 94.795 | 90.815 | 94.795 | 94.795 | 94.795
300 | 94.795 | 94.795 | 94.795 | 91.195 | 94.795 | 94.795 | 94.795
310 | 94.795 | 94.795 | 94.795 | 91.535 | 94.795 | 94.795 | 94.795
320 | 94.795 | 94.795 | 94.795 | 91.585 | 94.795 | 94.795 | 94.795
330 | 94.795 | 94.795 | 94.795 | 91.815 | 94.795 | 94.795 | 94.795
340 | 94.795 | 94.795 | 94.795 | 91.905 | 94.795 | 94.795 | 94.795
350 | 94.795 | 94.795 | 94.795 | 91.905 | 94.795 | 94.795 | 94.795
360 | 94.795 | 94.795 | 94.795 | 91.805 | 94.795 | 94.795 | 94.795
370 | 94.795 | 94.795 | 94.795 | 91.825 | 94.795 | 94.795 | 94.795
380 | 94.795 | 94.795 | 94.795 | 92.095 | 94.795 | 94.795 | 94.795
390 | 94.795 | 94.795 | 94.795 | 92.495 | 94.795 | 94.795 | 94.795
400 | 94.795 | 94.795 | 94.795 | 93.145 | 94.795 | 94.795 | 94.795
410 | 96.785 | 96.585 | 96.285 | 96.175 | 95.885 | 96.085 | 95.185
420 | 97.245 | 97.075 | 96.935 | 97.055 | 96.885 | 96.585 | 96.285
430 | 98.965 | 99.005 | 99.665 | 99.915 | 99.095 | 98.345 | 98.265
440 | 100.865 | 100.965 | 101.035 | 100.705 | 100.485 | 100.385 | 100.445
450 | 101.145 | 101.215 | 101.285 | 101.345 | 101.205 | 101.015 | 100.715
470 | 100.115 | 100.375 | 100.465 | 100.525 | 100.535 | 100.565 | 100.655
490 | 100.495 | 100.965 | 101.315 | 101.215 | 101.225 | 100.875 | 100.665
510 | 101.085 | 101.215 | 101.545 | 101.885 | 101.565 | 101.285 | 101.105
530 | 101.165 | 101.265 | 101.375 | 101.575 | 101.415 | 101.165 | 101.045
550 | 100.885 | 101.165 | 101.405 | 101.685 | 101.625 | 101.185 | 100.515
Sub Engieer | [5 empty] | Assistant Engieer
CGRRDA, PIU -01, Ambikapur | [5 empty] | CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.) | [5 empty] | Distt- Surguja ( C.G.)
Executive Engineer
CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.)

## APPROCH ROAD (hidden)
FOR APPROCH ROAD CALCULATION SHEET
Name Of Bridge:-GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
PACKAGE NO.:-CGLSB16-21
S. No. | Chainage | Ground R.L. | Formation R.L. | Area |  | Comulative Area |  |  | Volume
|  |  |  | Cutting | Filling | Cutting | Filling | Length | Cutting | Filling
1 | 0 | 100.58 |  | 3.4202 | 0 | 1.7101 | 0 | 0 | 0 | 0
2 | 20 | 100.035 |  |  | 7.336 | 1.7101 | 3.668 | 20 | 34.202 | 73.36
3 | 40 | 99.355 |  |  | 20.2099 | 0 | 13.773 | 20 | 0 | 275.459
4 | 60 | 98.705 |  |  | 36.6888 | 0 | 28.4494 | 20 | 0 | 568.987
5 | 80 | 98.065 |  |  | 54.7186 | 0 | 45.7037 | 20 | 0 | 914.074
6 | 100 | 97.635 |  |  | 64.2053 | 0 | 59.462 | 20 | 0 | 1189.239
7 | 120 | 97.495 |  |  | 69.7632 | 0 | 66.9843 | 20 | 0 | 1339.685
8 | 140 | 97.365 |  |  | 82.1357 | 0 | 75.9494 | 20 | 0 | 1518.989
9 | 160 | 97.125 |  |  | 109.276 | 0 | 95.7058 | 20 | 0 | 1914.117
10 | 180 | 96.365 |  |  | 127.444 | 0 | 118.36 | 20 | 0 | 2367.2
11 | 200 | 95.945 |  |  | 136.112 | 0 | 131.778 | 20 | 0 | 2635.56
12 | 220 | 95.575 |  |  | 137.58 | 0 | 136.846 | 20 | 0 | 2736.92
13 | 240 | 95.225 |  |  | 174.204 | 0 | 155.892 | 20 | 0 | 3117.84
14 | 255 | 95.855 |  |  | 186.196 | 0 | 180.2 | 15 | 0 | 2703
15 | 260 | 94.855 |  |  | 0 | 0 | 93.098 | 5 | 0 | 465.49
16 | 270 | 93.355 |  |  | 0 | 0 | 0 | 10 | 0 | 0
17 | 280 | 92.675 |  |  | 0 | 0 | 0 | 10 | 0 | 0
18 | 290 | 90.815 |  |  | 0 | 0 | 0 | 10 | 0 | 0
19 | 300 | 91.195 |  |  | 0 | 0 | 0 | 10 | 0 | 0
20 | 310 | 91.535 |  |  | 0 | 0 | 0 | 10 | 0 | 0
21 | 320 | 91.585 |  |  | 0 | 0 | 0 | 10 | 0 | 0
22 | 330 | 91.815 |  |  | 0 | 0 | 0 | 10 | 0 | 0
23 | 340 | 91.905 |  |  | 0 | 0 | 0 | 10 | 0 | 0
24 | 350 | 91.905 |  |  | 0 | 0 | 0 | 10 | 0 | 0
25 | 360 | 91.805 |  |  | 0 | 0 | 0 | 10 | 0 | 0
26 | 370 | 91.825 |  |  | 0 | 0 | 0 | 10 | 0 | 0
27 | 380 | 92.095 |  |  | 0 | 0 | 0 | 10 | 0 | 0
28 | 390 | 92.495 |  |  | 0 | 0 | 0 | 10 | 0 | 0
29 | 400 | 93.145 |  |  | 0 | 0 | 0 | 10 | 0 | 0
30 | 410 | 96.175 |  |  | 0 | 0 | 0 | 10 | 0 | 0
31 | 415 | 97.055 |  |  | 150.048 | 0 | 75.024 | 5 | 0 | 375.12
32 | 420 | 97.055 |  |  | 140.344 | 0 | 145.196 | 5 | 0 | 725.98
33 | 430 | 99.915 |  |  | 81.416 | 0 | 110.88 | 10 | 0 | 1108.8
34 | 440 | 100.705 |  |  | 42.0758 | 0 | 61.7459 | 10 | 0 | 617.459
35 | 450 | 101.345 |  |  | 25.75 | 0 | 33.9129 | 10 | 0 | 339.129
52 | 470 | 103.155 |  |  | 30.402 | 0 | 28.076 | 20 | 0 | 561.52
53 | 490 | 101.655 |  |  | 12.1445 | 0 | 21.2733 | 20 | 0 | 425.465
54 | 510 | 100.835 |  |  | 1.4792 | 0 | 6.8119 | 20 | 0 | 136.237
[9 empty] | 34.202 | 26109.63
[9 empty] | Cutting | Filling
[9 empty] | 34.202 | 26109.63
DEDUCTION FOR RETAINING WALL EXCAVATION QTY. | [7 empty] | #REF! | 80% | #REF!
DEDUCTION FOR RETAINING WALL FILTER MEDIA QTY. | [7 empty] | #REF! | 100% | #REF!
DEDUCTION FOR TOE WALL EXCAVATION QTY. | [7 empty] | #REF! | 80% | #REF!
DEDUCTION FOR BACK FILLING QTY. | [7 empty] | #REF! | 100% | #REF!
[9 empty] | G.Total | #REF!
Sub Engieer | [8 empty] | Assistant Engineer
CGRRDA, PIU -01, Ambikapur | [8 empty] | CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.) | [8 empty] | Distt- Surguja ( C.G.)
Executive Engineer
CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.)

## DIVERSION ROAD (hidden)
FOR COFFER DAM CALCULATION SHEET
Name Of Bridge:-GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
S. No. | Chainage | Ground R.L. | Formation R.L. | Area |  | Comulative Area |  |  | Volume
|  |  |  | Cutting | Filling | Cutting | Filling | Length | Cutting | Filling
15 | 250 | 94.855 | 94 | 2.489 | 0 | 1.2445 | 0 | 0 | 0 | 0
16 | 270 | 93.355 | 94 |  | 3.7345 | 1.2445 | 1.8673 | 20 | 24.89 | 37.3455
17 | 280 | 92.675 | 94 |  | 9.4737 | 0 | 6.6041 | 10 | 0 | 66.0415
18 | 290 | 90.815 | 94 |  | 34.6209 | 0 | 22.0473 | 10 | 0 | 220.4735
19 | 300 | 91.195 | 94 |  | 28.3585 | 0 | 31.4897 | 10 | 0 | 314.8975
20 | 310 | 91.535 | 94 |  | 23.2449 | 0 | 25.8017 | 10 | 0 | 258.0175
21 | 320 | 91.585 | 94 |  | 22.5319 | 0 | 22.8884 | 10 | 0 | 228.8845
22 | 330 | 91.815 | 94 |  | 19.3809 | 0 | 20.9564 | 10 | 0 | 209.5645
23 | 340 | 91.905 | 94 |  | 18.2055 | 0 | 18.7932 | 10 | 0 | 187.9325
24 | 350 | 91.905 | 94 |  | 18.2055 | 0 | 18.2055 | 10 | 0 | 182.0555
25 | 360 | 91.805 | 94 |  | 19.5135 | 0 | 18.8595 | 10 | 0 | 188.5955
26 | 370 | 91.825 | 94 |  | 19.2487 | 0 | 19.3811 | 10 | 0 | 193.8115
27 | 380 | 92.095 | 94 |  | 15.8305 | 0 | 17.5396 | 10 | 0 | 175.3965
28 | 390 | 92.495 | 94 |  | 11.3025 | 0 | 13.5665 | 10 | 0 | 135.6655
29 | 400 | 93.145 | 94 |  | 5.3095 | 0 | 8.306 | 10 | 0 | 83.0605
30 | 420 | 95.185 | 94 | 2.108 | 0 | 1.054 | 2.6548 | 20 | 21.08 | 53.0955
Total Length | 170 | [7 empty] | 45.97 | 2534.8375
[9 empty] | Cutting | Filling
Sub Engieer | [8 empty] | Assistant Engineer
CGRRDA, PIU -01, Ambikapur | [8 empty] | CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.) | [8 empty] | Distt- Surguja ( C.G.)
Executive Engineer
CGRRDA, PIU -01, Ambikapur
Distt- Surguja ( C.G.)

## V.S. Phy. (hidden)
Abstract Variation Statement Financial
CONSTRUCTION OF LONG SPAN BRIDGE ACROSS GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
PACKAGE No. CGLSB - 16-21
S.No. |  | Length of Bridge (In M) | Length of Approch (In M) | Cost of Bridge (Rs. In Lakh) | Cost of Approach Road ( Rs. In Lakh) | Total Cost (Rs. In Lakh) | Cost of Maintenance (Rs. In Lakh) | Total cost (Bridge + Approcah) - Rs. In Lakh | Add Above Tender 7.20 % | Total Tender Amount (Rs. In Lakh)
Particulars
1 | As per Agreement | 150 | 255 | 380.99 | 17.15 | 398.14 | 9.95 | 408.09 | 28.6661 | 436.7561
2 | As per Actual/Recvised | 150 | 350 | #REF! | #REF! | #REF! | 9.95 | #REF! | #REF! | #REF!
3 | Variation in amount | 0.00 M. | 95 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF!
4 | % of variation | 0% | 37.25% | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF!
|  | ZERO | EXCESS | EXCESS | EXCESS | EXCESS |  | EXCESS | EXCESS | EXCESS
| Sub Engineer |  | Assistant Engineer |  |  | Executive Engineer |  |  | Superintending Engineer
| CGRRDA, PIU - 01, Ambikapur |  | CGRRDA, PIU - 01, Ambikapur |  |  | CGRRDA, PIU - 01, Ambikapur |  |  | CGRRDA,Project Circle No. -01,Ambikapur
| Distt. - Surguja |  | Distt. - Surguja |  |  | Distt. - Surguja |  |  | Distt. - Surguja ( C.G.)

## approch road+ (hidden)
Name Of Bridge:-GHUNGHUTA RIVER BRIDGE ON LAKHANPUR TO PARSODIKALA AT. CH.- 4550 M.
S. No. | Chainage | Ground R.L. | Formation R.L. | Area |  | Comulative Area |  |  | Volume
|  |  |  | Cutting | Filling | Cutting | Filling | Length | Cutting | Filling
1 | 0 | 100.58 |  |  | 0.923 | 0 | 0.4615 | 0 | 0 | 0
2 | 20 | 100.035 |  |  | 4.765 | 0 | 2.844 | 20 | 0 | 56.88
3 | 40 | 99.355 |  |  | 30.35 | 0 | 17.5575 | 20 | 0 | 351.15
4 | 60 | 98.705 |  |  | 43.944 | 0 | 37.147 | 20 | 0 | 742.94
5 | 80 | 98.065 |  |  | 45.38 | 0 | 44.662 | 20 | 0 | 893.24
6 | 100 | 97.635 |  |  | 50.225 | 0 | 47.8025 | 20 | 0 | 956.05
7 | 120 | 97.495 |  |  | 56.645 | 0 | 53.435 | 20 | 0 | 1068.7
8 | 140 | 97.365 |  |  | 66.073 | 0 | 61.359 | 20 | 0 | 1227.18
9 | 160 | 97.125 |  |  | 89.596 | 0 | 77.8345 | 20 | 0 | 1556.69
10 | 180 | 96.365 |  |  | 106.22 | 0 | 97.908 | 20 | 0 | 1958.16
11 | 200 | 95.945 |  |  | 112.088 | 0 | 109.154 | 20 | 0 | 2183.08
12 | 220 | 95.575 |  |  | 135.396 | 0 | 123.742 | 20 | 0 | 2474.84
13 | 240 | 95.225 |  |  | 145.86 | 0 | 140.628 | 20 | 0 | 2812.56
14 | 255 | 95.855 |  |  | 157.828 | 0 | 151.844 | 15 | 0 | 2277.66
15 | 260 | 94.855 |  |  | 0 | 0 | 78.914 | 5 | 0 | 394.57
16 | 270 | 93.355 |  |  | 0 | 0 | 0 | 10 | 0 | 0
17 | 280 | 92.675 |  |  | 0 | 0 | 0 | 10 | 0 | 0
18 | 290 | 90.815 |  |  | 0 | 0 | 0 | 10 | 0 | 0
19 | 300 | 91.195 |  |  | 0 | 0 | 0 | 10 | 0 | 0
20 | 310 | 91.535 |  |  | 0 | 0 | 0 | 10 | 0 | 0
21 | 320 | 91.585 |  |  | 0 | 0 | 0 | 10 | 0 | 0
22 | 330 | 91.815 |  |  | 0 | 0 | 0 | 10 | 0 | 0
23 | 340 | 91.905 |  |  | 0 | 0 | 0 | 10 | 0 | 0
24 | 350 | 91.905 |  |  | 0 | 0 | 0 | 10 | 0 | 0
25 | 360 | 91.805 |  |  | 0 | 0 | 0 | 10 | 0 | 0
26 | 370 | 91.825 |  |  | 0 | 0 | 0 | 10 | 0 | 0
27 | 380 | 92.095 |  |  | 0 | 0 | 0 | 10 | 0 | 0
28 | 390 | 92.495 |  |  | 0 | 0 | 0 | 10 | 0 | 0
29 | 400 | 93.145 |  |  | 0 | 0 | 0 | 10 | 0 | 0
30 | 410 | 96.175 |  |  | 0 | 0 | 0 | 10 | 0 | 0
31 | 415 | 97.055 |  |  | 117.36 | 0 | 58.68 | 5 | 0 | 293.4
32 | 420 | 97.055 |  |  | 106.576 | 0 | 111.968 | 5 | 0 | 559.84
33 | 430 | 99.915 |  |  | 51.49 | 0 | 79.033 | 10 | 0 | 790.33
34 | 440 | 100.705 |  |  | 20.104 | 0 | 35.797 | 10 | 0 | 357.97
35 | 450 | 101.345 |  |  | 11.316 | 0 | 15.71 | 10 | 0 | 157.1
36 | 470 | 100.525 |  |  | 19.93 | 0 | 15.623 | 20 | 0 | 312.46
37 | 490 | 101.225 |  |  | 8.04 | 0 | 13.985 | 20 | 0 | 279.7
38 | 510 | 101.885 |  |  | 6.57 | 0 | 7.305 | 20 | 0 | 146.1
39 | 530 | 101.575 |  |  | 5.69 | 0 | 6.13 | 20 | 0 | 122.6
[9 empty] | 0 | 21973.2
[9 empty] | Cutting | Filling

## Sheet2 (hidden)
2578.25
1089.58
850.29
305.5
205.58
26.19
155.57
85.51
183.71
226.252
191.5
132.71
319.37
189.37
439.12
322
121.53
111.4
905.02
905.02
663.65
250.47
229.6
305.02
156.86
98.51
196.93
324.31
875.69
34.73
217.34
108.66
796.55
1975.44
887.33
375.41
557.2
1154.38
274.92
84.83
147.84
1269.95
528.69
288.04
21145.822
1057.2911
22200