## B.O.Q.
Bill of Quantity
योजना का नाम:- नगर निगम मोतिहारी क्षेत्रांतर्गत वार्ड संख्या 24 में धर्मेंद्र यादव के घर से राजा ठाकुर के घर तक एवं बबलू सिंह के घर से गोपाल जी के घर तक एवं सीमा देवी के घर से सुदामा प्रसाद के घर तक नाला एवं पीसीसी सड़क का निर्माण कार्य
|  | Estimated Cost:- |  | Rs.
|  | E/M to be Deposited:- |  | Rs.
|  | Cost of BOQ:- |  | Rs.
Time of completion:-
Date of Tender:-
E-Tendering Fee
Sl No. | SOR | Item of Works | Unit | Quantity | Rate | Amount
1 | BCD/2.25(A) | Providing E/W filling in roadside embankment including dressing of sides and ramming of bottoms with all complete job | m3 | 124.8 | 411.7 | 51380.16
2 | BCD/ 15.7.4 | Dismantling of brickwork in Old drain including stacking of serviceable materials and disposal of unserviceable materials do do all complete job | m3 | 44.82 | 823.7 | 36918.23
3 | BCD/ 15.2.1 | Demolishing cement concrete including disposal of unserviceable materials within 50m lead 1:3:6 or richer mix | m3 | 23.96 | 970.9 | 23262.76
4 | BCD/ 2.8.1 | Earth work in excavation infoundation trenches or drains (not excluding 1.5m in width or 10spen or plain) including dressing of sides and raiming of bottoms liftup to 1.5m including gating out the excavated soil and disposal of surplus excavated soil dorected with in of 50m. | m3 | 175.6 | 360.7 | 63338.92
5 | BCD/ 2.28 | Supply and filling inplinth with local sand under floor including watering ramming can soil dating and dressing comp. | m3 | 66.75 | 287.3 | 19177.28
6 | BCD/ 11.72 | Providing designation 100A one brick flat soling joint filled with local sand including cost of watering taxes royality all complete as per building specification and direction E/I. | m2 | 563.2 | 283.3 | 159554.56
7 | BCD/16.42 | Providing cement concrete 1:2:4 (1 cement:2 coarse sand :4 graded stone aggregates 40mm nominal size) in pavements ,laid to required slope and camber in panels as required including consolidation, finishing tamping all complete job and direction of E/I | m3 | 139.4 | 4649 | 648070.6
8 | BCD/5.9.2 | Providing shuttering and centring including strutting ,propping etc. and removal of form for walls including attached pilasters ,buttrusses ,plinth and string courses with all complete jobs and direction of E/I. | m2 | 302.43 | 375.1 | 113441.49
9 | BCD/5.1.2 | Providing and laying RCC in Drain (1:1.5:3) 1 cement 1.5course sand 4 graded stone agregate 20mm nominal size. | m3 | 50.17 | 4688.3 | 235212.01
10 | BCD/5.22.7B | Reinforcement for R.C.C. work including straigheining, cutting, bending placing inposition and binding all complete TMTC 500 - 10mm dia | kg | 4425 | 92.6 | 409755
11 | BCD/6.1.12/1 | Providing designation 100A brickwork in CM (1:4) all complete as per specification and direction E/I. | m3 | 125.38 | 5017.9 | 629144.3
12 | BCD/13.17.2 | Providing 12mm th. cement plaster in CM (1:4) with neat cement punning | m2 | 639.35 | 192.2 | 122883.07
13 | BCD/2.25 | Pumping out water caused by tidal seepage etc dodo all complete job | KL | 26.9 | 107.2 | 2883.68
| TOTAL RS. |  |  |  |  | 2515022.06
14 |  | Add extra cost of materials:
A |  | bricks | Nos | 75670 | 359.04 | 27168.56
B |  | cement | MT | 81.51 | 231.56 | 18874.46
|  | TOTAL RS. |  |  |  | 46043.02
15 |  | Add carriage cost of materials:
A |  | bricks. | Nos | 75670 | 919.21 | 69556.62
B |  | local sand | m3 | 75.2 | 310.47 | 23347.34
C |  | coarse sand | m3 | 128 | 2941.19 | 376472.32
D |  | stone aggregates | m3 | 161.14 | 2547.88 | 410565.38
|  | Sub Total: |  |  |  | 3441006.74
|  | Add 5.36% for 18% GST |  |  |  | 184437.96
17 |  | deduction 20% for old bricks of old drain | nos. | 4428 | 5128 | 22706.784
|  | Total (1) |  |  |  | 3602737.916
18 |  | Add S. Fee cost of material:
A |  | Bricks | Nos | 75670 | 512.8 | 38803.58
B |  | Local Sand | m3 | 75.2 | 14.2 | 1067.84
C |  | Coorse Sand | m3 | 128 | 17.6 | 2252.8
D |  | Stone Chips | m3 | 161.14 | 59.5 | 9587.83
E |  | E/Work | m3 | 0 | 3.3 | 0
|  | SUB TOTAL RS. |  |  |  | 51712.05
|  | Add 18% GST |  |  |  | 9308.169
|  | TOTAL(2) RS |  |  |  | 61020.219
|  | TOTAL (1+2) RS |  |  |  | 3663758.135
|  | say |  |  |  | 3663759