K / W –3

# BANGALORE UNIVERSITY

Office of the University Engineer,JnanaBharathi Campus,Bangalore-560 056

(Telephone No.080-22961106/07, 080-23218768

e-mail: universityengineerbub@gmail.com)

TENDER FOR THE WORK OF

REPLACEMENT OF WORN OUT HT AND LT POWER TRANSMISSION LINES, RCC POLES, PIN & DISC INSULATORS AT JNANABHARATHI CAMPUS, BANGALORE UNIVERSITY, BANGALORE.

ST Reserved work

| TENDER REFERENCE | : | Notification no: No: UE/DM/TENDER-NOT/JBC/BUB/ 01/2026-27 dated: 06.05.2026 (Indent- 66) |
| --- | --- | --- |
| PERIOD OF SALE OF TENDER DOCUMENT | : | Please refer Karnataka Public Procurement Portal , URL: https://kppp.karnataka.gov.in/ |
| LAST DATE FOR SALE OF TENDER DOCUMENT & DATE OF PRE BID MEETING | : | Please refer Karnataka Public Procurement Portal , URL: https://kppp.karnataka.gov.in/ |
| LAST DATE AND TIME FOR RECEIPT OF TENDERS | : | Please refer Karnataka Public Procurement Portal , URL: https://kppp.karnataka.gov.in/ |
| TIME AND DATE OF OPENING OF COVER ONE OF TENDERS | : | Please refer Karnataka Public Procurement Portal , URL: https://kppp.karnataka.gov.in/ |
| PLACE OF OPENING OF COVER ONE OF TENDERS | : | ON-LINE |
| ADDRESS FOR COMMUNICATION | : | Office of the University Engineer, Bangalore University, JnanaBharathi Campus, Bangalore - 560056 |

:

:

| Section | Description | Page No. |
| --- | --- | --- |
| 1 | INVITATION FOR TENDERS (IFT) | 3 |
| 2 | INSTRUCTIONS TO TENDERERS (ITT) | 4 |
| 3 | QUALIFICATION INFORMATION | 18 |
| 4 | FORM OF TENDER, LETTER OF ACCEPTANCE, NOTICE TO 21 PROCEED WITH THE WORK AND AGREEMENT FORM | 21 |
| 5 | CONDITIONS OF CONTRACT (CC) | 24 |
| 6 | CONTRACT DATA | 37 |
| 7 | SPECIFICATIONS | 42 |
| 8 | DRAWINGS | 43 |
| 9 | BILL OF QUANTITIES | 44 |
| 10 | FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT | 45 |

SECTION 1: INVITATION FOR TENDERS (IFT)

Notification no: No: UE/DM/TENDER-NOT/JBC/BUB/ 01/2026-27 dated: 06.05.2026 (Indent- 66)

- The  University Engineer, Bangalore University, Bangalore invites tenders from eligible tenderers, in two cover system for the works detailed in the table through Karnataka Public Procurement Portal, URL: https://kppp.karnataka.gov.in/  of the Government of Karnataka).  The Tenderers are advised to note the minimum qualification criteria specified in Clause 3 of the Instructions to Tenderers to qualify for award of the contract.

- Tender documents  may be downloaded from the Karnataka Public Procurement Portal of Karnataka as per specified time and date in the portal

- Tenders must be accompanied by the earnest money deposit specified for the work in the table below.  Earnest money deposit will have to be in any of the forms as per the instructions in the Karnataka Public Procurement Portal, URL: https://kppp.karnataka.gov.in/ and shall have to be valid for 45 days beyond the validity of the tender.

- Tenders must be submitted online through https://kppp.karnataka.gov.in/as per time and date specified in the portal  and the opening of the tenders will be as per the Karnataka Public Procurement Portal , URL: https://kppp.karnataka.gov.in/ guidelines.

5.	Other details and conditions can be seen in the tender documents.

TABLE

| # Sl.No | # Name of work | # Form No. | # Estimated amount (Excluding GST@18%) # (Rs) | # Earnest money deposit at 1% | # Period of completion | # Contractor eligibility | # Category |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # 1 | # 2 | # 3 | # 4 | # 5 | # 6 | # 7 | # 8 |
| 1. | REPLACEMENT OF WORN OUT HT AND LT POWER TRANSMISSION LINES, RCC POLES, PIN & DISC INSULATORS AT JNANABHARATHI CAMPUS, BANGALORE UNIVERSITY, BANGALORE | # K/W-3 | Rs. 64,56,039.76 | Rs. 64,600.00 | 6 months | Class-III & above Electical | ST |

# Sd/-

University Engineer

Bangalore  University,

Bangalore

SECTION 2:  INSTRUCTIONS TO TENDERERS (ITT) 
Table of Clauses

A.	General	Page No.

1.	Scope of Tender	7

2.	Eligible Tenderers	7

3.	Qualification of the Tenderer	7

4.	One Tender per Tenderer	8

5.	Cost of Tendering	8

6.	Site Visit	8

B.	Tender Documents

7.	Content of Tender documents	9

8.	Clarification of Tender Document	9

9.	Amendment of Tender documents	9

C.	Preparation of Tenders

10.	Documents comprising the Tender	9

11.	Tender prices	10

12.	Tender validity	10

13.	Earnest money deposit	10

14.	Format and signing of Tender	13

D.	Submission of Tenders

15.    Sealing and marking of Tenders	13

16.    Deadline for submission of Tenders	13

17.    Late Tenders	13

18.    Modification and Withdrawal of Tenders	13

E.	Tender opening and evaluation

19.    Opening of First Cover of all Tenders and evaluation to determine

qualified Tenderers	13

20.    Opening of Second Cover Tenders of qualified Tenders and evaluation	14

21.    Process to be confidential	14

22.    Clarification of Tenders	14

23.    Examination of Tenders and determination of responsiveness	15

24.    Correction of errors	15

25.    Evaluation and comparison of Tenders	15

F.	Award of contract

26.    Award criteria	16

27.    Employer’s right to accept any Tender and to reject any or all Tenders	16

28.    Notification of award and signing of Agreement	16

29.    Security deposit	16

30.    Advance payment and Security	17

31    Corrupt or Fraudulent Practices	17

A. General

1.	Scope of Tender

  - The University Engineer, Bangalore University, Bangalore (Referred to as Employer in these documents) invites tenders following Two Cover tender procedure, from eligible class III and above Electrical contractors who have been registered with KPWD, Tenderers, for the construction of works (as defined in these documents and referred to as "the works") detailed in the Table given in the Invitation for Tenders (IFT). The Tenderers may submit tenders for any or all of the works detailed in the table given in IFT.

2.	Eligible Tenderers

2.1	Tenderers shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued by the Government of Karnataka

2.2	Tenders from Joint ventures are not acceptable.

3.	Qualification of the Tenderer:

3.1	All Tenderers shall provide the requested information accurately and in sufficient detail in Section 3:

Qualification information.

3.2	To qualify for award of this contract, each Tenderer in his name should have in the last five years i.e.

  - to 2025-26).

(a)  A minimum financial turnover of Rs. 64.57 Lakhs should be achieved in any one year during the last five   years, attested copy of the certificate issued by the Charted Accountant should be enclosed.

(b) The tenderer should have completed satisfactorily any Electrical HT work within the stipulated period of value not less than Rs.16.15 Lakhs during last Five years, attested copy of the certificate issued by the rank not less than Executive Engineer should be enclosed.

  - Each Tenderer should further demonstrate:

- Availability by owning at least 50% of the required/specified key and critical equipment for this work and the remaining 50% can be deployed on lease/hire basis for all works provided, the relevant documents (commitment agreements etc.,) for availability for this work are furnished. -NA.-

  - To qualify for a package of contracts made up of this and other contracts for which tenders are 
invited in this IFT, the Tenderer must demonstrate having experience and resources to meet the 
aggregate of the qualifying criteria for the individual contracts. – NA –

  - Liquid assets and / or availability of credit facilities of not less than Rs. 19.40 Lakhs (Credit lines/letter of credit/ certificates from banks for meeting the fund requirement) from nationalized banks issued after the date of notification for this work

3.5	Sub-contractors’ experience and resources shall not be taken into account in determining the Tenderer’s compliance with the qualifying criteria except to the extent stated in 3.2 (d) and (e) above.

3.6 	Tenderers who meet the above specified minimum qualifying criteria, will only be qualified, if their 	available tender capacity is more than the total tender value. The available tender capacity will be 	calculated as under:

Assessed available tender capacity = (A*N*5 - B )

where

A = Maximum value of civil engineering works executed in any one year during the last five years updated to 2026-27 price level) taking into account  the completed as well as works in progress.

N = Number of years prescribed for completion of the works for which tenders are invited.

B = Value, at 2026-27price level, of existing commitments and on-going works to be completed during the next 0.5 years.

Note:	The statements showing the value of existing commitments and on-going works as well as the

stipulated period of completion remaining for each of the works listed should be countersigned by

the Employer in charge, not below the rank of an Executive Engineer or equivalent.

3.7	Even though the Tenderers meet the above criteria, they are subject to be disqualified if they have:

-	made misleading or false representations in the forms, statements and attachments submitted in

proof of the qualification requirements; and/or

-	record of poor performance such as abandoning the works, not properly completing the contract,

inordinate delays in completion, litigation history, or financial failures etc.; and/or

-	participated in the previous Tender for the same work and had quoted unreasonably high tender

prices and could not furnish rational justification.

3.8. Site visit:The Tenderer at his own responsibility and risk is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the Tender and entering into a contract for construction of the Works. The cost of visiting the Site shall be at the Tenderer’s own expense.

B.  Tender documents

4.	Content of Tender documents

4.1	The set of tender documents shall have all the Sections given in Page 2:

4.2	Both the sets of Tender documents should be filled and submitted through Karnataka Public Procurement Portal , URL: https://kppp.karnataka.gov.in/.

5.	Amendment of Tender documents

5.1	Before the deadline for submission of tenders, the Employer may modify the tender documents by

issuing addenda.

5.2	Any addendum thus issued shall be part of the tender documents and shall be through Karnataka Public Procurement Portal , URL: https://kppp.karnataka.gov.in/.

5.3	To give prospective Tenderers reasonable time in which to take an addendum into account in preparing

their tenders, the Employer shall extend as necessary the deadline for submission of tenders, in

accordance with Sub-Clause 12.2 below.

C.  Preparation of Tenders

6.     Documents comprising the Tender

6.1	The tender submitted by the Tenderer shall be in two covers and shall contain the documents        as follows.

    - First Cover :

(a)	Earnest Money Deposit; (refer Karnataka Public Procurement Portal ,URL: https://kppp.karnataka.gov.in/)

(b)	Qualification Information as per formats given in Section 3; (Refer Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/)

6.1.2 Second Cover:

(a)	The Tender (in the format indicated in Section 4)

(b)	Priced Bill of Quantities (Section 9);

and any other materials required to be completed and submitted by Tenderers in accordance with theseinstructions. The documents listed under Sections 3, 4, 6 and 9 shall be filled in without exception.

6.2	Tenderers submitting tenders together with other contracts stated in the IFT to form a package will so

Indicate in the tender together with any discounts offered  for the award of more than one contract.

7.     Tender prices

7.1	The contract shall be for the whole works as described in Sub-Clause 1.1, based on the priced  
Bill of Quantities submitted by the Tenderer.

7.2 	The Tenderer shall fill in rates and prices and line item total (both in figures and words) for all items of the Works described in the Bill of Quantities along with total tender price (both in figures and 
 words). Items for which no rate or price is entered by the Tenderer will not be paid for by the  
Employer when executed and shall be deemed covered by the other rates and prices in the Bill of 
 Quantities.  Corrections, if any, shall be made by crossing out, initialing, dating and rewriting.

7.3 	All duties, taxes, and other levies payable by the contractor under the contract, or for any other cause, 
shall be included in the rates, prices and total Tender Price submitted by the Tenderer. (However, GST at 12% of the Contract amount will be paid separately).

7.4	The rates and prices quoted by the Tenderer shall be subject to adjustment during the performance of

the Contract    in accordance with the provisions of Clause of the Conditions of Contract

8.	Tender validity

8.1	Tenders shall remain valid for a period not less than ninety days after the deadline date for tender

submission specified in Clause 16.  A tender valid for a shorter period shall be rejected by the Employer as non-responsive.

8.2 	In exceptional circumstances, prior to expiry of the original time limit, the Employer may request that 
the Tenderers may extend the period of validity for a specified additional period.  The request and 
the Tenderers' responses shall be made in writing or by cable.  A Tenderer may refuse the request 
without forfeiting his earnest money deposit.  A Tenderer agreeing to the request will not be 
 required or permitted to modify his tender, but will be required to extend the validity of his earnest money deposit  for a period of the extension, and in compliance with Clause 13 in all respects.

9.	Earnest money deposit:

9.1. Tender Transaction fee and Earnest Money Deposit.

The supplier/contractor can pay the Earnest Money Deposit (EMD) in the Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/ using any of the following payment modes:

- Credit Card

- Direct Debit

- National Electronic Fund Transfer (NEFT)

- Over the Counter (OTC)

OTC payment procedure

If a contractor/supplier chooses to make payment of EMD/tender processing fees Over The Counter (OTC) in any of the designated Axis Bank branches listed in the Karnataka Public Procurement Portal web-site (www.eproc.karnataka.gov.in), the contractor/supplier will need to log into Karnataka Public Procurement Portal system, access the tender for which bid is being created and then select the OTC option under the payment section and print the Challan shown in that section. The printed challan will have the unique bid reference number and the amount to be remitted. Along with the challan, contractor can choose to make the payment either in the form of cash or in the form of Demand Draft. Cheque payments will not be accepted. The contractor is requested to specifically inform the bank officer to input the unique bid reference number printed in the challan in the banking software. Upon successful receipt of the payment, the bank will provide a 16-digit reference number acknowledging the receipt of payment. This 16-digit reference number has to be inputted by contractor in the payment section of its bid as payment confirmation before the bid is submitted (i.e.) as a pre-requisite for bid submission.

NEFT payment procedure

If a contractor/supplier chooses to make payment of EMD/tender processing fees using Reserve Bank of India's (RBI) National Electronic Fund Transfer (NEFT) system, the contractor/supplier will need to log into Karnataka Public Procurement Portal system, access the tender for which bid is being created and then select the NEFT option under the payment section and print the Challan shown in that section. The printed challan will have the unique bid reference number, account details of Government of Karnataka and the amount to be remitted. The contractor has to submit the printed challan to its bank-branch (NEFT-enabled) and request for an account-to-account transfer, wherein the money will get transferred from the contractors' bank account to GoK's bank account. The contractor should ensure that NEFT transfer instructions are executed and the funds are wired to the Government of Karnataka's principal account before the last date for bid submission and preferably 24 hours before the last date for bid submission. If the contractor's bank transfers/wires the money after the last date for bid submission, the contractor's bid will be liable for rejection. Upon executing the transfer, the contractor's bank will provide a reference number generated by NEFT software as confirmation of transfer, which has to be inputted by contractor in the payment section of its bid as payment confirmation before the bid is submitted (i.e.) as a pre-requisite for bid submission. Also, the account number from which the funds were transferred have to be inputted in the Karnataka Public Procurement Portal system as part of its bid.

The supplier/contractor’s bid will be evaluated only on confirmation of receipt of the payment (EMD) in the Government of Karnataka central pooling a/c held at Axis BankEMD amount will have to be submitted by the supplier/contractor taking into account the following conditions:

- EMD will be accepted only in the form of electronic cash (and not through Demand Draft or Bank Guarantee) and will be maintained in the Govt.’s central pooling account at Axis Bank until the contract is closed.

- The entire EMD amount for a particular tender has to be paid in a single transaction For details on e-Payment services refer to Karnataka Public Procurement Portal ,URL: https://kppp.karnataka.gov.in/ for more details on the process.

Note: In Karnataka Public Procurement Portal, URL: https://kppp.karnataka.gov.in/ Contractor has the option of withdrawing the Bid by digitally signing to withdraw/can cell bid before the bid submission time /Date.

10.	Format and signing of Tender

Tenderer shall submit the Bid electronically before the submission date and time published in KPP portal.

D.  Submission of Tenders

11.	Sealing and marking of tenders

Tenderer shall submit the Bid electronically before the submission date and time published in

Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/.

12. Deadline for submission of the Tenders

12.1 Tenders must be submitted online in the e Procurement portal to the Employer on or before the time & date specified in Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/

12.2   The Employer may extend the deadline for submission of tenders by issuing an amendment in accordance with Clause 9, in which case all rights and obligations of the Employer and the Tenderers previously subject to the original deadline will then be subject to the new deadline.

13. Late Tenders

In online e procurement system, you shall not be able to submit the bid after the bid submission time and date as the icon or the task in the e procurement portal will not be available

14. Modification and Withdrawal of Tenders

Tenderer has all the time to modify and correct or upload any relevant document in the portal till Bid submission date and time, as published in the e procurement portal

E.  Tender opening and evaluation

15.	Opening of First Cover of all Tenders and evaluation to determine qualified Tenderers:

15.1     The Employer will open the First Covers of all the Tenders received (except those received late or withdrawn), including modifications for First Cover made pursuant to  Clause 18, in the presence of the Tenderers or their representatives who choose to attend at the time,date and the place as notified in Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/.  In the event of the specified date of Tender opening being declared a holiday for the Employer, the Tenders will be opened at the appointed time and location on the next working day.

15.2KPP Portal, Contractor has the option of withdrawing the Bid by digitally   signing to withdraw / cancel the bid, before the bid submission time /Date

.

15.3 	The Tenderes names, the presence or absence of earnest money deposit (amount, format and validity), 	the submission of qualification information and such other information as the Employer may consider 	appropriate will be announced by the Employer at the opening electronically.

15.4	The Employer shall prepare minutes of the Tender opening, including the information disclosed to those present in accordance with Sub-Clause 19.3.

15.5	The Employer will evaluate and determine whether each tender (a) meets the eligibility criteria defined in ITT Clause 2; (b) is accompanied by the required earnest money deposit as per stipulations in ITT Clause and (c) meets the minimum qualification criteria stipulated in ITT Clause 3. The Employer will draw out a list of qualified Tenderers.

15.6 	The Tenderers are bound to furnish the original certified documents to the employer within five days from the day of opening of technical bid for verification, failing which the bid of tenderer will be considered as non responsive.

16.	Opening of Second Cover of qualified Tenderers and evaluation:

16.1	The Employer will inform all the Qualified Tenderers the time, date and venue fixed for   the opening of the Second Cover containing the priced Tenders. The Employer willopenwill open the Second Covers of Qualified Tenderers at the appointed time and date electronically. In the event of the specified date of Second Cover opening being declared a holiday for the Employer, the Second Covers will be opened at the appointed time and location on the next working day.

16.2	Envelopes electronically marked “MODIFICATION FOR SECOND COVER” shall be opened and thesubmissions therein will be taken into consideration during evaluation.

16.3	The Tenderers' names, the Tender prices, the total amount of each Tender, any discounts, Tender modifications and withdrawals, and such other details as the Employer may consider appropriate, will be announced by the Employer electronically.  No Tender shall be rejected at Tender opening.

16.4	The Employer shall prepare minutes of the Second Cover Tender opening, including the information

Dis closed in accordance with Sub-Clause 20.3.

17.	Process to be confidential

17.1	Information relating to the examination, clarification, evaluation, and comparison of Tenders and recommendations for the award of a contract shall not be disclosed to Tenderers or any other persons not officially concerned with such process until the award to the successful Tenderer has been announced. Any effort by a Tenderer to influence the Employer's processing of Tenders or award decisions may result in the rejection of his Tender.

18	Clarification of Tenders

18.1	To assist in the examination, evaluation, and comparison of Tenders, the Employer may, at his discretion, ask any Tenderer for clarification of his Tender, including breakdowns of unit rates. The request for clarification and the response shall be through Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/, but no change in the price or substance of the Tender shall be sought, offered, or permitted except as required to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Tenders in accordance with Clause 24.

18.2 	Subject to sub-clause 22.1, no Tenderer shall contact the Employer on any matter relating to its Tender from the time of the Tender opening to the time the contract is awarded.  If the Tenderer wishes to bring additional information to the notice of the Employer, it should do so electronically.

If they have any query or need clarifications related to Karnataka Public Procurement Portal  contact Karnataka Public Procurement Portal help desk  from  9.00 AM to 9.00 PM ( Monday to Saturday) Ph No: 080-22485867 or send query through Karnataka Public Procurement Portal ,URL: https://kppp.karnataka.gov.in/ through query option on or before specified time.

18.3	Any effort by the Tenderer to influence the Employer in the Employer’s Tender evaluation, Tender

comparison or contract award decisions may result in the rejection of the Tenderers’ Tender.

19.	Examination of Tenders and determination of responsiveness

19.1	Prior to the detailed evaluation of Tenders, the Employer will determine whether each Tender; (a) has

been properly signed; and; (b) is substantially responsive to the requirements of the Tender documents.

19.2 	A substantially responsive Tender is one which conforms to all the terms, conditions, and specifications of the Tender documents, without material deviation or reservation. A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of the Works; (b) which limits in any substantial way, inconsistent with the Tender documents, the Employer's rights or the Tenderer's obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other Tenderers presenting substantially responsive Tenders.

19.3	If a Tender is not substantially responsive, it will be rejected by the Employer, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation.

20.	Correction of errors

20.1	Tenders determined to be substantially responsive will be checked by the Employer for any arithmeticerrors. Errors will be corrected by the Employer as follows:

(a)	where there is a discrepancy between the rates in figures and in words, the lower of the two

will govern17; - Not Applicable-

(b)	where there is a discrepancy between the unit rate and the line item total resulting from

multiplying the unit rate by the quantity, the unit rate as quoted will govern. - Not Applicable-

20.2	The amount stated in the Tender will be adjusted by the Employer in accordance with the above procedure for the correction of errors and, with the concurrence of the Tenderer, shall be considered as binding upon the Tenderer. If the Tenderer does not accept the corrected amount the Tender will be rejected, and the earnest money deposit may be forfeited in accordance with Sub-Clause 13.6 (b). - Not Applicable-

21.	Evaluation and comparison of Tenders

21.1	The Employer will evaluate and compare only the Tenders determined to be substantially responsive in

accordance with Clause 23.

21.2	In evaluating the Tenders, the Employer will determine for each Tender the evaluated Tender Price byadjusting the Tender Price as follows:

(a)	making any correction for errors pursuant to Clause 24;  - Not Applicable-

(b)	making appropriate adjustments to reflect discounts or other price modifications offered inaccordance with Sub Clause 18.5- Not Applicable-.

22.3 	The Employer reserves the right to accept or reject any variation, deviation, or alternative offer. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the Tender documents or otherwise result in unsolicited benefits for the Employer shall not be taken into account in Tender evaluation.

22.4 	The estimated effect of the price adjustment conditions under Clause 41 of the Conditions of 
Contract, 	during the implementation of the Contract, will not be taken into account in tender Evaluation

22.5 	If the tender of the successful tenderer is seriously unbalanced in relation to the Employer’s estimate of the cost of the work to be performed under the contract, the Employer may require the Tenderer to produce detailed price analyses for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, the Employer may require that the amount of the performance security set forth in Clause 29 be increased at the expense of the successful Tenderer to a level sufficient to protect the Employer against financial loss in the event of default of the successful under the contract.

F.  Award of Contract

22.	Award criteria

22.1	Subject to Clause 27, the Employer will award the Contract to the Tenderer whose Tender has been determined to be substantially responsive to the Tender documents and who has offered the lowest evaluated Tender Price, provided that such Tenderer has been determined to be (a) eligible in accordance with the provisions of Clause 2, and (b) qualified in accordance with the provisions of Clause 3.

23.	Employer's right to accept any Tender and to reject any or all Tenders

23.1	Notwithstanding Clause 26, the Employer reserves the right to accept or reject any Tender, and tocancel the Tender process and reject all Tenders, at any time prior to the award of Contract, without  thereby incurring any liability to the affected Tenderer or Tenderers or any obligation to inform the affected Tenderer or Tenderers of the grounds for the Employer's action.

24.	Notification of award and signing of Agreement

24.1	The Tenderer whose Tender has been accepted will be notified of the award by the Employer prior to expiration of the Tender validity period through Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/ and registered letter. This letter (hereinafter and in the Conditions of Contract called the "Letter of Acceptance") will state   the sum that the Employer will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the "Contract Price").

24.2 	The notification of award will constitute the formation of the Contract, subject only to the furnishing of 
	Security deposit in accordance with the provisions of Clause 29.

24.3	The Agreement will incorporate all agreements between the Employer and the successful Tenderer. It will be  kept ready for signature of the successful Tenderer in the office of Employer within 30 days following the notification of award along with the Letter of Acceptance. Within 20 days of receipt, the successful Tenderer will sign the Agreement and deliver it to the Employer.

24.4	Upon the furnishing by the successful Tenderer of the Performance Security, the Employer will promptly  notify the other Tenderers that their Tenders have been unsuccessful.

25.	Security deposit

25.1	Within 20 days of receipt of the Letter of Acceptance, the successful Tenderer shall deliver to the Employer a Security deposit in any of the forms given below for an amount equivalent to 5% of the Contract price plus additional security for unbalanced tenders in accordance with Clause 24.1 of ITT and Clause 44 of the Conditions of Contract. : (NA)

[

The security deposit of 5% of the contract price payable shall be deducted in every running bill. However, in case of first and final bill the entire security deposit will be deducted from the final bill.

26.	Corrupt or Fraudulent practices

26.1	The GOK requires that the Tenderers/Suppliers/Contractors, observe the highest standard of ethics during the procurement and execution of such contracts.  In pursuance of this policy, GOK :

(a) 	will reject a proposal for award if it determines that the Tenderer recommended for award has 	engaged in corrupt or fraudulent practices in competing for the contract in question;

(b) will declare a firm ineligible, either indefinitely or for a stated period of time, to be awarded a 	GOK contract if it at any time determines that the firm has engaged in corrupt or fraudulent 	practices in competing for, or in executing, a GOK contract.

26.2	Furthermore, Tenderers shall be aware of the provision stated in sub-clause 50.2 of the Conditions of

Contract.

SECTION 3: QUALIFICATION INFORMATION

The information to be filled in by the Tenderer here under will be used for purposes of computing Tender

capacity as provided for in Clause 3 of the Instructions to Tenderers. This information will not be incorporated in the Contract.

1.1 	Constitution or legal status of Tenderer

Place of Registration

Principal place of business:

1.2 	Total value of civil engineering construction

works executed and payments received in the last five years

(inRs. Lakhs)1

[Attach copy]

(Attach Copy)

Financial year     Amount in Rs

2021 - 22______________ 
2022 - 23______________ 
2023 - 24______________ 
2024- 25______________
2025   -  26______________

1.3	Work performed as Prime Contractor (in the same name) on works of similar nature over during the

five years specified in 1.2 above.

Project	Name of   Descrip-  Contract  Value of   Date of    Specified  Actual date of	Remarks explaining reasons

Name	Employer  -tion of     Number   contract   issue of   period of  completion	for delay in completion of work

Work	Rs. Lakhs work	completion

order

1	2	3	4	5	6	7	8	9

1.4	Quantities of work executed as prime contractor (in the same name) during the last five years specified

in 1.2 above:

| Year | Name of work | Name of Employer | Quantity of work performed |  |  |  |  |  |  |  | Remarks (Indicate contractreference) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Earthwork Excavation | Concrete (PCC / RCC) | Fabrication of Steel Reinforcement | Masonry with SSM/ Concrete Block /Clay Hallow Brick / Burnt Bricks | Water proof treatment to Basement/ roof slab/ terrace/ toilets. | Flooring Vitrified / Granite / Ceramic | Dadoing with Granite / Ceramic tiles. | Painting |  |

2021 - 22______________ 
2022 - 23______________ 
2023 - 24______________ 
2024  -  25______________
2025   -            26

1.5	Information on works for which Tenders have been submitted and works which are yet to be completed as  on the date of this Tender.

(A)   Existing commitments and on-going works:

1	Attach Certificate from Chartered Accountant

2	Items of work for which data is requested should tally with that specified in ITT Clause 3

Description  Place	Contract No.   Name	Value of	Stipulated	Value of works3   Anticipated

of	&& Date	and	Contract	period of	remaining to be   date of

Work	State	Address	(Rs. lakhs)	completion   completed	completion

of Employer	(Rs. lakhs)

(1)	(2)	(3)	(4)	(5)	(6)	(7)	(8)

(B)   Works for which Tenders already submitted:

Description	Place	Name and	Estimated	Stipulated	Date when	Remarks

of	&	Address of	value of works	period of	decision is	if any

Work	State	Employer	(Rs. lakhs)	completion	expected

(1)	(2)	(3)	(4)	(5)	(6)	(7)

1.6.	The following items of equipment are considered essential for successfully carrying out the works. The

Tenderer should furnish all the information listed below.

Item of Equipment	Requirement4	Owned and available	Remarks

No.	Capacity	Owned	Number/	Age/

Capacity	Condition

1.7	Reports on the  financial standing of the tenderer, such as profit and loss statements and auditor’s

reports for the last five years;

1.8 	Qualification and experience of the key technical and management personnel in permanent

employment with the tenderer and those that are proposed to be deployed  on this contract, if awarded.

1.9. 	Name, address, and telephone, telex, and fax numbers of the Tenderers' bankers who may provide 
	references if contacted by the Employer.

1.10 	Evidence of access to financial resources to meet the qualification requirement  specified in ITT 	Clause3.3 (b): Cash in hand, Letter of Credit etc. List them below and attach certificate from the 
	Banker in the  suggested format as under

3Attach Certificates from Engineers -in- Charge

4The item of equipment, required number and capacity should match with those specified in ITT Clause 3.3 (a)

BANKER’S CERTIFICATE

This is to certify that M/s. ………………………….. is a reputed company with a good financial standing. If the contract for this work, namely ……………………………… (name of the work) is awarded to the above firm, we shall be able to provide  overdraft/credit facilities to the extent of Rs. …………… to meet the working capital requirements for executing the above contract

Sd/-

Name of the Bank, Senior Bank Manger Address:……………………………….

1.11 	Proposals for subcontracting components of works amounting to more than 20% of the contract price .

Item of Work	Value of Sub-Contract	Identified Sub-Contractor	Experience of similar work 5

(Name and address)

1.12	Information on litigations in which the Tenderer is involved:

Other Party (ies)	Employer	Details of dispute	Amount involved	Remarks showing present status

5 Attach certificates from the respective Employers

SECTION 4:   FORMS OF TENDER, LETTER OF ACEPTANCE, NOTICE TO PROCEED WITH 
	THE WORK AND AGREEMENT FORM

Form of Tender- Not Applicable

Description of the Works:   ___________________________________________________

_______________________________________________________ 6 Tender

To	:

Address :

___________________________________________________________________________ 7

GENTLEMEN,

We offer to execute the Works described above in accordance with the Conditions of Contract accompanying this Tender for the Contract Price of _________   [in figures]

(________________________________________________) [in letters].8

This Tender and your written acceptance of it shall constitute a binding contract between us. We understand that you are not bound to accept the lowest or any Tender you receive.

The advance payment required is Rs…………………………….

We undertake that, in competing for (and, if the award is made to us, in executing) the above contract, we will 
strictly observe the laws against fraud and corruption in force in India namely “Prevention of Corruption Act 
1988”.

We hereby confirm that this Tender complies with the Tender validity and Earnest money deposit required by the Tender documents.

We attach herewith our current income-tax clearance certificate. Yours faithfully,

Authorized Signature:

Name & Title of Signatory:  _________________________________________________________________

Name of Tenderer

Address:

6To be filled in by the Employer before issue of the Tender document

7	To be filled in by the Employer before issue of the Tender document

8	To be filled in by the Tenderer, together with his particulars and date of submission at the bottom of the Form of Tender

Letter of Acceptance

(Letterhead paper of the Employer)

________________________[date]

To:	_________________________________________________________________________[name and

address of the Contractor]

Dear Sir,

This is to notify you that your Tender dated ____________ for execution of the

[name of the contract and identification number, as given in the Instructions to Tenderers] for the Contract Price of Rupees ——___________________________________________________________ (_____________) [amount in words and figures], as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted by our Agency.

Yours faithfully,

Authorized Signature

Name and Title of Signatory Name of Agency

Issue of Notice to proceed with the work

(letterhead of the Employer)

————— (date)

To

—————————————— (name and address of the Contractor)

Dear Sirs:

Pursuant to your signing of the contract agreement for the construction of ——————  9a Tender Price of Rs.——————, you are hereby instructed to proceed with the execution of the said works in accordance with the contract documents.

Yours faithfully,

(Signature, name and title of signatory authorized to sign on behalf of Employer)

9 Name of the contract

Agreement Form

Agreement

This agreement, made the ___________________day of ______________20_______,

between___________________________________________________________________________________ ________________________________________[name and address of Employer]

(hereinafter called “the Employer”) of the one part and _____________________________________________

______________________________________________________[name and address of contractor] (hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor execute _____________________________

______________________________________________________________________________________[name and identification number of Contract] (hereinafter called “the Works”) and the Employer has accepted the Tender by the Contractor for the execution and completion of such Works and the remedying of any defects therein  at a contract price of Rupees...

NOW THIS AGREEMENT WITNESSETH as follows:

1. 	In this Agreement, words and expression shall have the same meanings as are respectively assigned to 
	them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read 
	and construed as part of this Agreement.

2. 	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, 
	the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any 
	defects therein in conformity in all aspects with the provisions of the Contract.

3. 	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of 
	the Works and the remedying the defects wherein the Contract Price or such other sum as may become 
	payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

4.	The following documents shall be deemed to form and be read and construed as part of this Agreement,

viz:

i)	Letter of Acceptance;

ii)	Notice to proceed with the works;

iii)	Contractor’s Tender;

iv)	Contract Data;

v)	Conditions of contract (including Special Conditions of Contract);

vi)	Specifications;

vii)	Drawings;

viii)	Bill of Quantities;  and

ix)	Any other document listed in the Contract Data as forming part of the contract.

In witness whereof the parties thereto have caused this Agreement to be executed the day and year first before written.

The Common Seal of

was hereunto affixed in the presence of:

Signed, Sealed and Delivered by the said   ___________________________________________________

in the presence of:

Binding Signature of  Employer
Binding Signature of Contractor

SECTION 5: CONDITIONS OF CONTRACT

Table of Contents

A.	General	Page No.

1.    Definitions	21

2.    Interpretation	21

3.    Law governing contract	22

4.    Employers decisions	22

5.    Delegation	22

6.    Communications	22

7.    Subcontracting	22

8.    Other Contractors	22

9.    Personnel	22

10.  Employer’s and Contractor’s risks	22

11.  Employer’s risks	22

12  Contractor’s risks	23

13.  Insurance	23

14.  Site Investigation Report	23

15  Query about Contract Data	23

16  Contractor to construct the Works	23

17.  The Works to be completed by Intended Completion Date	23

18  Approvals by the Employer	24

19.  Safety	24

20.  Discoveries	24

21.  Possession of the Site	24

22.  Access to the Site	24

23.  Instructions	24

24.  Procedure for resolution of disputes	24

B.	Time Control

25.  Program	24

26.  Extension of the Intended Completion Date	25

27.  Delays ordered by the Employer	25

28.  Management meetings	25

C.	Quality Control

29.  Identifying defects	25

30.  Tests	25

31.  Correction of defects	25

32.  Uncorrected defects	25

D.	Cost Control

33  Bill of Quantities (BOQ)	26

34  Variations	26

35.  Payment for Variations	26

36.  Submission of bills for payment	27

37  Payments	27

38.  Compensation events	27

39.  Tax	27

40  Price Adjustment	27

41.  Liquidated damages	28

42.  Advance Payments	28

43.  Securities	28

44.  Cost of repairs	29

E	Finishing of Contract

45.  Completion	29

46.  Taking Over	29

47.  Final account	29

48.  As built drawings and/or Operating and Maintenance Manuals	29

49.  Termination	29

50  Payment upon termination	30

51.  Property	30

52.  Release from performance	30

F	Special Conditions of Contract	31

Conditions of Contract

A.  General

1.	Definitions

1.1	Terms which are defined in the Contract Data are not also defined in the Conditions of Contract but

keep their defined meanings. Bold letters are used to identify defined terms.

Bill of Quantities means the priced and completed Bill of Quantities forming part of the Tender. Compensation events are those defined in Clause 38 hereunder.

The Completion Date is the date of completion of the Works as certified by the Employer in accordance with Sub Clause 46.1.

The Contract is the contract between the Employer and the Contractor to execute, complete and

maintain the Works. It consists of the documents listed in Clause 2.2 below.

The Contract Data defines the documents and other information which comprise the Contract.

The Contractor is a person or corporate body whose Tender to carry out the Works has been accepted by the Employer.

The Contractor's Tender is the completed Tender document submitted by the Contractor to the Employer.

The Contract price is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract.

Days are calendar days; months are calendar months.

A Defect is any part of the Works not completed in accordance with the Contract.

The Defects liability period is the period named in the Contract Data and calculated from the Completion Date.

The Employer is the party who will employ the Contractor to carry out the Works.

Equipment is the Contractor's machinery and vehicles brought temporarily to the Site to construct the Works.

The Initial Contract price is the Contract Price listed in the Employer's Letter of Acceptance.

The Intended Completion Date is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Contract Data. The Intended Completion Date may be revised only by the Employer by issuing an extension of time.

Materials are all supplies, including consumables, used by the contractor for incorporation in the Works.

Plant is any integral part of the Works which is to have a mechanical, electrical, electronic or chemical or biological function.

The Site is the area defined as such in the Contract Data.

Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Employer.

The Start Date is given in the Contract Data. It is the date when the Contractor shall commence

execution of the works. It does not necessarily coincide with any of the Site Possession Dates.

A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract which includes work on the Site.- Deleted.

A Variation is an instruction given by the Employer which varies the Works.

The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the Contract Data.

2.	Interpretation

2.1	In interpreting these Conditions of Contract, singular also means plural, male also means female or

neuter, and the other way around. Headings have no significance. Words have their normal meaning

under the language of the Contract unless specifically defined. The Employer will provide instructions

clarifying queries about the Conditions of  Contract.

2.2	The documents forming the Contract shall be interpreted in the following order of priority:

(1)	Agreement

(2)	Letter of Acceptance, notice to proceed with the works

(3)	Contractor’s Tender

(4)	Contract Data

(5)	Conditions of Contract

(6)	Specifications

(7)	Drawings

(8)	Bill of quantities and

(9)	any other document listed in the Contract Data as forming part of the Contract.

3.	Law governing contract

3.1	The law governing the Contract is the Laws of India supplanted by the Karnataka Local Acts.

4.	Employer's decisions

4.1	Except where otherwise specifically stated, the Employer will decide contractual matters between the

Employer and the Contractor .

5.	Delegation

5.1	The Employer may delegate any of his duties and responsibilities to other people after notifying the

Contractor and may cancel any delegation after notifying the Contractor.

6.	Communications

6.1	Communications between parties which are referred to in the conditions are effective only when in

writing. A notice shall be effective only when it is delivered (in terms of Indian Contract Act).

7.	Subcontracting

7.1	Deleted

8.	Other Contractors

8.1	The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities,

and the Employer.

9.	Personnel

9.1	The Contractor shall employ the technical personnel (of number and qualifications) as may be

stipulated by GOK from time to time during the execution of the work. The technical staff so

employed shall be available at site as may be stipulated by the Employer.

9.2	If the Employer asks the Contractor to remove a person who is a member of  the Contractor’s staff or

his work force stating the reasons, the Contractor shall ensure that the person leaves the Site within

seven days and has no further connection with the work in the Contract.

10.	Employer’s and Contractor's risks

10.1	The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor

carries the risks which this Contract states are Contractor’s risks.

11.	Employer's risks

11.1 The Employer is responsible for the excepted risks which are:

(a)    rebellion,   riot commotion or disorder unless solely restricted to employees of the Contractor or his

Sub-Contractors arising from the conduct of the Works;  or

(b)  a cause due solely to the design of the Works, other than the Contractor’s design; or

(c) any operation of the forces of nature (in so far as it occurs on the Site) which an experienced contractor:

(i)	could not have reasonably foreseen; or

(ii)	could reasonably have foreseen, but against which he could not reasonably have taken at

least one of the following measures;

(A)  prevent loss or damage to physical property from occurring by taking appropriate measures or

(B)  insure against such loss or damage

12.	Contractor’s risks

12.1	All risks of loss of or damage to physical property and of personal injury and death which arise during

and in consequence of the performance of the Contract other than the excepted risks are the

responsibility of the Contractor.

13.	Insurance:

13.1	The Contractor shall prior to commencing the works, effect and thereafter maintain insurances , in the

joint names of the Employer and the Contractor, (cover from the first working day after the Start Date to the end of Defects  Liability Period), in the amounts stated in the Contract Data : 
(a)  for loss of or damage to the Works, Plants and Materials and the Contractor’s equipment; 
(b)  for liability of both Parties for loss, damage, death and injury to third parties or their property 
	arising out of the Contractor’s performance of the  Contract including the Contractor’s 
        liability for damage to the Employer’s property other than the Works and

(c)  for liability of both Parties and of any Employer’s representative for death and injury
       to theContractor’s personnel except to the extent that liability arises from the 
       negligence of the 	Employer, any Employer’s representative or their Employees.

13.2 	Policies and certificates for insurance shall be delivered by the Contractor to the Employer for his approval before the Start Date. All such insurance shall provide for compensation to be payable to rectify the loss or damage incurred. All payments received from insurers relating to loss or damage shall be held jointly by the Parties and used for the repair of the loss or damage or as compensation for loss or damage that is not to be repaired.

13.3 	If the Contractor fails to effect or keep in force any of the insurances referred to in the previous sub-clauses or fails to provide satisfactory evidence, policies or receipts, the Employer may without prejudice to any other right or remedy, effect insurance for the cover relevant to such default and pay the premiums due and recover the same as a deduction from any other monies due to the Contractor. If no payments is due, the payment of the premiums shall be a debt due.

13.4	Alterations to the terms of an insurance shall not be made without the approval of the Employer.

13.5	Both Parties shall comply with any conditions of the insurance policies.

14.	Site Investigation Reports:

14.1	The Contractor, in preparing the tender, shall rely on any site investigation reports referred to in the

Contract data, supplemented by any information available to the Tenderer.

15.	Queries about the Contract Data

15.1	The Employer will clarify queries on the Contract Data.

16.	Contractor to construct the Works

16.1	The Contractor shall construct the Works in accordance with the Specification and Drawings.

17.	The Works to be completed by the Intended Completion Date

17.1	The Contractor may commence execution of the Works on the Start Date and shall carry out the

Works in accordance with the program submitted by the Contractor, as updated with the approval of

the Employer, and complete them by the Intended Completion Date.

18.	Approval by the Employer:

18.1	The Contractor shall submit Specification and drawings showing the proposed Temporary Works to

the Employer, who is to approve them if they comply with the Specifications and Drawings.

18.2	The Contractor shall be responsible for the design of Temporary Works

18.3	The Employer’s approval shall not alter the Contractor’s responsibility for design of the Temporary

Works.

18.4	The Contractor shall obtain approval of third parties to the design of third parties to the design of the

temporary Works where required.

18.5	All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are

subject to prior approval by the Employer before their use.

19.	Safety

19.1	The Contractor shall be responsible for the safety of all activities on the Site.

20.	Discoveries

20.1	Anything of historical or other interest or of significant value unexpectedly discovered on the Site is

the property of the Employer. The Contractor is to notify the Employer of such discoveries and carry

out the Employer's instructions for dealing with them.

21.	Possession of the Site

21.1	The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is

not given by the date stated in the Contract Data the Employer is deemed to have delayed the start of

the relevant activities and this will be Compensation Event.

22.	Access to the Site

22.1	The Contractor shall allow the Employer and any person authorized by the Employer access to the

Site, to any place where work in connection with the Contract is being carried out or is intended to be

carried out and to any place where materials or plant are being manufactured / fabricated / assembled

for the works.

23.	Instructions

23.1	The Contractor shall carry out all instructions of the Employer which comply with the applicable laws

where the Site is located.

24.	Procedure for resolution of Disputes:

24.1	If the Contractor is not satisfied with the decision taken by the Employer, the dispute shall be referred

by either party to Arbitration within 30 days of the notification of the Employer’s decision.

24.2	If neither party refers the dispute to Arbitration within the above 30 days, the Employer’s decision will

be final and binding.

24.3	The Arbitration shall be conducted in accordance with the arbitration procedure stated in the Special

Conditions of Contract.

24.3	Not applicable

B.  Time Control

25.	Program

25.1       Within the time stated in the Contract Data the Contractor shall submit to the Employer for approval a

Program showing the general methods, arrangements, order, and timing for all the activities in the

Works.

25.2	The Employer's approval of the Program shall not alter the Contractor's obligations. The Contractor

may revise the Program and submit it to the Employer again at any time. A revised Program is to show

the effect of Variations and Compensation Events.

Extension of the Intended Completion Date

26.1	The Employer shall extend the Intended Completion Date if a Compensation Event occurs or a

Variation is issued which makes it impossible for Completion to be achieved by the Intended

Completion Date.

26.2	The Employer shall decide whether and by how much to extend the Intended Completion Date within

21 days of the Contractor asking the Employer for a decision upon the effect of a Compensation Event

or Variation and submitting full supporting information.

27.	Delays ordered by the Employer

27.1	The Employer may instruct the Contractor to delay the start or progress of any activity within the

Works.

28.	Management meetings

28.1	The Employer may require the Contractor to attend a management meeting. The business of a

management meeting shall be to review the progress achieved and the plans for remaining work.

28.2	The responsibility of the parties for actions to be taken is to be decided by the Employer either at the

management meeting or after the management meeting and stated in writing to be distributed to all

who attended the meeting.

C.  Quality Control

29.	Identifying defects

29.1	The Employer shall check the Contractor's work and notify the Contractor of any Defects that are

found. Such checking shall not affect the Contractor's responsibilities. The Employer may instruct the

Contractor to search for a Defect and to uncover and test any work that the Employer considers may

have a Defect

30.	Tests

30.1	If the Employer instructs the Contractor to carry out a test not specified in the Specification to check

whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and

any samples. If there is no Defect the test shall be a Compensation Event.

31.	Correction of defects

31.1	The Employer shall give notice to the Contractor of any Defects before the end of the Defects Liability

Period, which begins at Completion and is defined in the Contract Data. The Defects Liability Period

shall be extended for as long as Defects remain to be corrected.

31.2	Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length

of time specified by the Employer’s notice.

32.	Uncorrected defects

32.1	If the Contractor has not corrected a Defect within the time specified in the Employer’s notice, the

Employer will assess the cost of having the Defect corrected, and the Contractor will pay this amount.

D.   Cost Control

33.	Bill of Quantities (BOQ)

33.1	The BOQ shall contain items for the construction, installation, testing, and commissioning work to be

done by the Contractor.

33.2	The BOQ is used to calculate the Contract Price. The Contractor is paid for the quantity of the work

done at the rate in the BOQ for each item

34.	Variations

34.1	The Employer shall have power to order the Contractor to do any or all of the following as considered

necessary or advisable  during the progress of the work by him

(a)  Increase or decrease of any item of work included in the Bill of Quantities (BOQ); (b) Omit any item of work;

(c)  Change the character or quality or kind of any item of work;

(d)  Change the levels, lines, positions and dimensions of any part of the work;

(e)  Execute additional items of work of any kind necessary for the completion of the works; and (f)   Change in any specified sequence, methods or timing of construction of any part of the work.

34.2 	The Contractor shall be bound to carry out the work in accordance with any instructions in this

connection, which may be given to him in writing by the Employer and such alteration shall not vitiate or invalidate the contract.

34.3 	Variations shall not be made by the Contractor without an order in writing by the Employer, provided 
	that no order in writing shall be required for increase or decrease in the quantity of an item appearing 
	in the BOQ so long as the work executed conforms to the approved drawings.

34.4	The contractor shall promptly request in writing to the Employer to confirm verbal orders and the officer 
issuing oral instruction shall confirm it in writing within 30 days, failing which the work shall be carried out as though there is no variation.  In case variation is approved it shall be accompanied by Bill Of Quantity, failing which the contractor shall be responsible for deviation if any.  Further, approval        has to be obtained for the variation.

35.	Payments for Variations

35.1	Payment for increase in the quantities of an item in the BOQ up to 25% of that provided in the Bill of

Quantities shall be made at the rates quoted by the Contractor.

35.2 	For quantities in excess of 125% of the tendered quantity of an item as given in the BOQ, the

Contractor shall be paid at the rate entered in or derived from in the Schedule of Rates (applicable for 
the area of the work and current at the time of award of contract) plus or minus the overall percentage 
of the original tendered rates over the current Schedule of Rates prevalent at the time of award of 
contract.

35.3 	If there is no rate for the additional, substituted or altered item of the work in the BOQ, efforts would 
	be made to derive the rates from those given in the BOQ or the Schedule of Rates (applicable for the 
	area of the work and current at the time of award of contract) and if found feasible the payment would 
	be made at the derived rate for the item plus or minus the overall percentage of the original tendered 
	rates over the current Schedule of Rates prevalent at the time of award of contract

35.4 	If the rates for additional, substituted or altered item of work cannot be determined either as at 35.1 or

35.2 or 35.3 above, the Contractor shall be requested to submit his quotation for the items supported by analysis of the rate or rates claimed, within 7 days.

35.5 	If the Contractor's quotation is determined unreasonable, the Employer may order the Variation and 
	make a change to the Contract Price which shall be based on Employer’s own forecast of the effects of 
	the Variation on the Contractor's costs.

35.6 	If the Employer decides that the urgency of varying the work would prevent a quotation being given 
	and considered without delaying the work, no quotation shall be given and the Variation shall be 
	treated as a Compensation Event.

35.7	Under no circumstances the Contractor shall suspend the work on the plea of non-settlement of rates

for items falling under this Clause.

36.	Submission of bills for payment

36.1	The Contractor shall submit to the Employer monthly bills of the value of the work completed less the

cumulative amount paid previously.

36.2 	The Employer shall check the Contractor's bill and determine the value of the work executed which 
	shall comprise of   (i) value of the quantities of the items in the BOQ completed and (ii) valuation of 
	Variations and Compensation Events.

36.3	The Employer may exclude any item paid in a previous bill or reduce the proportion of any item

previously paid in the light of later information.

37.	Payments

37.1	Payments shall be adjusted for deductions for advance payments other than recoveries in terms of contract 
 and taxes, at source as applicable under the law.  The Employer shall pay the Contractor within 60 days of 
  submission of the bill Subject available of grants.  The contractor shall be liable to pay liquidated damages for shortfall in progress.  For progress beyond the agreed programme payment it subject to availability of the grants.

37.2	Items of the Works for which no rate or price has been entered in will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract. This Project is North Eastern Council funded project. Payments are subject to funding from North Eastern Council.

38.	Compensation events

38.1	The following are Compensation events unless they are caused by the Contractor:

(a)	The Employer does not give access to a part of the Site by the Site Possession Date stated

in the Contract Data.

(b)	The Employer orders a delay or does not issue drawings, specifications or instructions

required for execution of works on time.

(c)	The Employer instructs the Contractor to uncover or to carry out additional tests upon

work which is then found to have no Defects.

(d)	The Employer gives an instruction for dealing with an unforeseen condition, caused by the

Employer, or additional work required for safety or other reasons.

(e)	The effect on the Contractor of any of the Employer’s Risks.

(f)	The Employer unreasonably delays issuing a Certificate of Completion.

(g)	Other Compensation Events listed in the Contract Data or mentioned in the Contract.

38.2	If a Compensation Event would cause additional cost or would prevent the work being completed

before the Intended Completion Date, the Contract Price shall be increased and/or the Intended

Completion Date is extended. The Employer shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended.

38.3 	As soon as information demonstrating the effect of each Compensation event upon the Contractor's 
	forecast cost has been provided by the Contractor, it is to be assessed by the Employer and the 
	Contract Price shall be  adjusted accordingly. If the Contractor's forecast is deemed unreasonable, the 
	Employer shall adjust the Contract Price based on Employer’s own forecast. The Employer will 
	assume that the Contractor will react competently and promptly to the event.

38.4	The Contractor shall not be entitled to compensation to the extent that the Employer's interests are

adversely affected by the Contractor not having given early warning or not having cooperated with the

Employer.

39.	Tax

39.1	The rates quoted by the Contractor shall be deemed to be inclusive of the sales and other taxes that the Contractor will have to pay for the performance of this Contract.  The Employer will perform such duties in regard to the deduction of such taxes at source as per applicable law. However GST at twelve percent will be paid.

40.	Price Adjustment:  - Not Applicable -

40.1   a. For all works costing more than Rs.50 lakhs, if the period of execution is more than 12 months, the price adjustment will be calculated as prescribed in Annexure to G.O. No.FD59 PRO Cell/2004 Dt:26-11-2004

b. If the period of execution is more than 6 months but less than or equal to 12 months for work costing more than Rs.50 lakshs, Star Rates  in respect of specified materials (Cement, steel and Bitumen) only shall be payable to the contractor based on the All India Average Whole Sale Price Index for the said materials. The Star Rates adjustments shall be increased or decreased in the index as applied to be said materials between the last date for receiving bids and the date of execution as per the approved Program of Works submitted by the contractor at the time of execution of agreement which shall mandatory be a part of agreement.

c.   If the period of execution is less than or equal to 6 months,  for all works irrespective of the cost of the works, Price adjustments or Start Rates shall not be applicable.

d. In works contracts where price adjustment clause is provided, the price adjustment shall be admissible from the date of opening of tenders (Original or extended).

- Price Adjustment clause shall not be included in Goods and Equipment tender documents. However, in respect of tender documents for procurement of Electric Cables, Transformers, Generators, Motors that have raw material component subject to price fluctuations, appropriate price adjustment clauses may be incorporated by the Tender Inviting Authority in the tender documents, with the specific approval of the concerned Head of the Department or Managing Director of the Public Sector Undertaking/Board.

  - The above mentioned methods of price adjustments clause are subject to the following conditions:

- The price adjustment clause or the star rates shall not be admissible if the contract period is extended due to lapse on the part of the contractor.

- For the cases (A) and (B) above, if the contract period is extended due to no fault of the contractor, the modified programme shall be approved by the competent authority and shall become a part of agreement for which price adjustment /star rates will be applicable.

- For the purpose of working out price adjustment and star rates, the price index issued from time to time by the Ministry of Commerce and Industry, Government of India should be adopted.

- The formulae for price adjustment shall be as prescribed in Annexure – 1 to the G.O No: FD 59 PRO.Cell/2004 dated:26.11.2004, which is appended.

40.3      The above instructions will only be applicable prospectively and shall not be applicable for contracts concluded in the past or being concluded presently or for tenders already invited.

40.4      The above instructions shall apply to all Procurement Entities as defined in Section 2(d) Chapter I of the Karnataka Transparency in Public Procurement Act, 1999.

41.	Liquidated damages

41.1	The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the Contract

Data for each day that the Completion Date is later than the Intended Completion Date (for the whole of the works or the milestone as stated in the Contract Data).  The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages does not affect the Contractor's liabilities.

41.2	If the Intended Completion Date is extended after liquidated damages have been paid, the Employer

shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment

of bill.

42.	Advance Payments: - Not Applicable-

42.1	The Employer shall make payment to the Contractor of the amounts stated in the Contract Data by the

date stated in the Contract Data, against provision by the Contractor of an unconditional bank

guarantee in a form acceptable to the Employer issued by a Nationalized/Scheduled Bank in amounts equal to the advance payment. The guarantee shall remain effective until the advance payment has been repaid, but the amount of the guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest will not be charged on the advance payment.

42.2 	The Contractor is to use the advance payment only to pay for Mobilization expenses required

specifically for execution of the Works. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Employer.

42.3	The advance payment shall be repaid by deducting proportionate amounts from payments otherwise

due to the Contractor, following the schedule of completed percentages of the Works on a payment

basis. No account shall be taken of the advance payment or its repayment in assessing valuation of the

work done, variations, price adjustments, compensation events or liquidated damages.

43.	Securities:

43.1	The Security deposit (including additional security for unbalanced tenders) shall be provided to the

Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount

and form and type of instrument acceptable to the Employer. The Security deposit shall be valid until a

date 30 days from the date of expiry of Defects Liability Period and the additional security for 
              unbalanced tenders shall be valid until a date 30 days from the date of issue of the certificate of 
completion.

44.	Cost of Repairs:

44.1   Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and 
	the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor's cost if 
	the loss or damage arises from the Contractor's acts or omissions.

E.  Finishing the Contract

45.	Completion

45.1	The Contractor shall request the Employer to issue a Certificate of Completion of the Works and the

Employer will do so upon deciding that the Work is completed.

46.	Taking over

46.1	The Employer shall take over the Site and the Works within seven days of   issuing a certificate of

Completion.

47.	Final account

47.1	The Contractor shall supply to the Employer a detailed account of the total amount that the Contractor

considers payable under the Contract before the end of the Defects Liability Period. The Employer

shall issue a Defect Liability Certificate and certify any final payment that is due to the Contractor

within 90 days of receiving the Contractor's account if it is correct and complete. If it is not, the

Employer shall issue within 90 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Employer shall decide on the amount payable to the Contractor and  make payment within 60 days of receiving the Contractor’s revised account.

48.	As built drawings and /or Operating and Maintenance Manuals

48.1	If “as built”* Drawings and/or operating and maintenance manuals are required, the Contractor shall

supply them by the dates stated in the Contract Data.

48.2	If the Contractor does not supply the Drawings by the dates stated in the Contract Data, or they do not

receive the Employer’s approval, the Employer shall withhold the amount stated in the Contract Data from 
               payments due to the Contractor.

49.	Termination

49.1	The Employer may terminate the contract if the other party causes a fundamental breach of the contract.

49.2	Fundamental breaches of Contract include, but shall not be limited to the following:

(a)	The Contractor stops work for 45 days when no stoppage of work is shown on the current

Program and the stoppage has not been authorized by the Employer;

(b)       Deleted

(c)		The Contractor becomes bankrupt or goes into liquidation other than for a reconstruction

or amalgamation;

(d)	Deleted

(e)      The Employer gives Notice that failure to correct a particular Defect is a fundamental

breach of Contract and the Contractor fails to correct it within a reasonable period of time

determined by the Employer;

(f)        the Contractor does not maintain a security which is required;

(g)	the Contractor has delayed the completion of works by the number of days for which the

maximum amount of liquidated damages can be paid as defined in the Contract data;

and

(h) 	if the Contractor, in the judgment of the Employer has engaged in corrupt or

fraudulentpractices in competing for or in the executing the Contract.

For the purpose of this paragraph : “corrupt practice” means the offering, giving, receiving 
or soliciting of anything of value to influence the action of a public official in the 
procurement process or in contract execution.   “Fraudulent practice” means a 
misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of the Borrower, and includes collusive practice among Tenderers 
(prior to or after Tender submission) designed to establish Tender prices at artificial non-competitive levels and to deprive the Borrower of the benefits of free and open 
competition.”

49.3	When either party to the Contract gives notice of a breach of contract to the Employer for a cause other

than those listed under Sub Clause 49.2 above, the Employer shall decide whether the breach is

fundamental or not.

49.4	Notwithstanding the above, the Employer may terminate the Contract for convenience.

49.5	If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secure

and leave the Site as soon as reasonably possible.

50.	Payment upon Termination

50.1	If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the

Employer shall prepare bill for the value of the work done less advance payments received up to the 
date of the bill, less other recoveries due in terms of the contract, less taxes due to be deducted at 
source as per applicable law and less the percentage to apply to the work not completed as indicated in the Contract Data. Additional Liquidated Damages shall not apply.  If the total amount due to the 
Employer exceeds any payment due to the Contractor the difference shall be a debt payable to the 
Employer.

50.2 	If the Contract is terminated at the Employer's convenience or because of a fundamental breach of 
	Contract by the Employer, the Employer shall prepare bill for the value of the work done, the 
	reasonable cost of removal of Equipment, repatriation of the Contractor's personnel employed solely 
	on the Works, and the Contractor's costs of protecting and securing the Works and less advance 
	payments received up to the date of the certificate, less other recoveries due in terms of the contract, 
	and less taxes due to be deducted at source as per applicable law and make payment accordingly.

51.	Property

51.1	All materials on the Site, Plant, Equipment, Temporary Works and Works are deemed to be the

property of the Employer,  if the Contract is terminated because of a Contractor’s default.

52.	Release from performance

52.1	If the Contract is frustrated   by any event entirely outside the control of either the Employer or the

Contractor the Employer shall certify that the Contract has been frustrated. The Contractor shall make 
the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for 
all work carried out before receiving it and for any work carried out afterwards to which commitment 
was made

F.    Special Conditions of Contract

- Labour :

The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for the engagement of all staff and labour, local or other, and for their payment, housing, feeding and transport.

The Contractor shall, if required by the Employer, deliver to the Employer a return in detail, in such form and at such intervals as the Employer may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the Contractor on the Site and such other information as the Employer may require.

2.	Compliance with labour regulations :

During continuance of the contract, the Contractor and his sub contractors shall abide at all times by all 
existing labour enactments and rules made there under, regulations, notifications and bye laws of the 
State or Central Government or local authority and any other labour law (including rules), regulations, 
bye laws that may be passed or notification that may be issued under any labour law in future either by 
the State or the Central Government or the local authority. The Contractor shall keep the Employer 
indemnified in case any action is taken against the Employer by the competent authority on account of 
contravention of any of the provisions of any Act or rules made there under, regulations or 
notifications including amendments. If the Employer is caused to pay or reimburse, such amounts as 
may be necessary to cause or observe, or for non-observance of the provisions stipulated in the 
notifications/bye laws/Acts/Rules/regulations including amendments, if any, on the part of the 
Contractor, Employer shall have the right to deduct any money due to the Contractor including his 
amount of security deposit.  The Employer shall also have right to recover from the Contractor any 
sum required or estimated to be required for making good the loss or damage suffered by the 
Employer.

The employees of the Contractor and the Sub-Contractor in no case shall be treated as the employees of the Employer at any point of time.

3.	Protection of Environment:

The contractor shall take all reasonable steps to protect the environment on and off the Site and to 
avoid damage or nuisance to persons or to property of the public or others resulting from pollution, 
noise or other causes arising as a consequence of his methods of operation. During continuance of the 
contract, the contractor and his sub-contractors shall abide at all times by all existing enactments on 
environmental protection and rules made there under, regulations, notifications and bye-laws of the 
State or Central Government, or local authorities and any other law, bye-law, regulations that may be 
passed or notification that may be issued in this respect in future by the State or Central Government or 
the local authority.

4.	Arbitration (Clause 24 ) Deleted

4.1	The procedure for arbitration shall be as follows:

- In case of dispute or difference arising between the Employer and the Contractor relating to any matter arising out of or connected with this agreement it shall be settled in accordance with the Arbitration and Conciliation Act 1996. The disputes or differences shall be referred to a Sole Arbitrator. The Sole Arbitrator shall be appointed by agreement between the parties; failing such agreement, by the Appointing Authority As per Karnataka Arbitration center (national & international) Rules 2012 (as Govt circular no Law 273 LAC 2012 (B) dtd:10.01.2014).

(b)  Arbitration proceedings shall be held at

(c)  The cost and expenses of arbitration proceedings will be paid as determined by the Arbitrator. 
	However the expenses incurred by each party in connection with the preparation, presentation, 
	etc.,   shall be borne by each party itself.

(d)  Performance under the contract shall continue during the arbitration proceedings and 
	payments due the Contractor by the Employer shall not be withheld, unless they are the 
	subject matter of the arbitration proceedings.

5.	Others

(a)	1% of the Tendered amount will be deducted towards “Labour Welfare Fund “.

(b) The Tenderer has to produce all the relevant Documents as indicated in the Bid Document in originals during the opening of the Technical Bid  “ Mandatorily “ . This is in addition to Uploading all the relevant Documents in the e-procurement portal. If the Originals are not submitted, the Tender will be rejected.

(c)	All other documents which are required to be submitted are to be uploaded in the e-Procurement Portal in General Documents section, while electronically submitting the bid. If any of the Documents as desired are not submitted the Tender will be rejected.

- The FSD payable at the time of executing agreement, will be refunded only after successful Completion of Defect Liability Period.

- In the case of the death of a contractor after executing the agreement / commencement of the work, his legal heir, if an eligible registered contractor and willing, can execute and complete the work at the accepted tender rates irrespective of the cost of the work.

- Estimate rates are excluding GST as per govt Circular No:FD 417 Exp-12/2024, Banglore Dtd:09.08.2024 and prevailing GST (18% of amount put to tender) amount is kept in form of Lumpsum in sanctioned estimate. Therefore amount put to tender and ECV amount are excluding GST. But the itemwise rates do not include GST. Hence GST will be paid separately for the executed amount accordingly

- The GST shall not be paid in the extended period of contract for which the Contractor alone is responsible for delay as determined by the authority while granting the extension of time. The Government and the Contractor are abide to any increase or decrease in GST during agreement period.

- The Contractor should  follow the Environmental policy

SECTION 6: CONTRACT DATA

Items marked "N/A" do not apply in this Contract.

The following documents are also part of the Contract:	Clause Reference

  The Schedule of Operating and Maintenance Manuals	[48]

  The Methodology and Program of Construction	[25]

  Site Investigation Reports	[14]

  The Schedule of Key and Critical Equipment to be deployed

on the work as per agreed program of construction.	[25]

The Employer is: University Engineer, Bangalore University, Bangalore[1.1]

Address:JnanaBharathi Campus, Bangalore - 560056

Name of authorized Representative: University Engineer, Bangalore University, Bangalore.

The name and identification number of the Contract is

No: UE/DM/TENDER-NOT/JBC/BUB/ 01/2026-27 dated: 06.05.2026 (Indent- 66)

[1.1]

The Works consist of: Replacement of Worn out HT and LT Power Transmission Lines, Rcc Poles, Pin & Disc Insulators

.

The start date shall be two weeks from the date of issue of notice to proceed with the work.	[1.1]

The Intended Completion Date for the whole of the Works is 6 months with the following milestones																									[17, 26]

Name of Work: Replacement Of Worn Out Ht And Lt Power Transmission Lines, Rcc Poles, Pin & Disc Insulators At Jnanabharathi Campus, Bangalore University, Bangalore.

The site procession date is – two weeks after issue of notice to proceed with the work[21]

The Site is located at Jnana Bharathi Campus, Bangalore University, Bangalore 560056

Defect liability period is 365 Days from date of completion															[1.1]

and is defined in drawings nos. Enclosed separately

The date by which “as-built” drawings (in scale 1:100) in 2 sets are required is within 30 days of issue

of certificate of completion of Whole or Section of the Work as the case may be.	[48]

The date by which Operating and Maintenance Manuals are required is within 30 days of issue of

certificate of completion of Whole or Section of the Work as the case may be.	[48]

The amount to be with held for failing to supply “as built” drawings or supply of Operation and

Maintenance Manuals by the date required is Rs.________                                                      [48]

The following events shall also be fundamental breach of the contract :	[49.2]

1.	The contractor has contravened Sub-clause 7.1 and Clause 9 of CC.

The percentage to apply to the value of the work not completed representing the Employer's	[50.1]

additional cost for completing the Works shall be 30 percent.

SECTION 7:SPECIFICATIONS

ENCLOSED IN Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/

SECTION 8: DRAWINGS

ENCLOSED in Karnataka Public Procurement Portal ,          URL: https://kppp.karnataka.gov.in/

SECTION 9: BILL OF QUANTITIES

|  |  |  |  | Rate (Rs) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sl. No. | Description of item (with brief specification and reference to Book of specification) | Quantity | Unit | In figures | In words | Amount (Rs) |
|  | ENCLOSED IN Karnataka Public Procurement Portal , URL: https://kppp.karnataka.gov.in/ |  |  |  |  |  |
| Total Tender Price (in figures) |  |  |  |  |  |  |
| (in words) |  |  |  |  |  |  |

Note:

(1)Item for which no rate or price   has been entered in will not be paid for by the Employer when executed

and shall be deemed   covered by the other rates and prices in the Bill of Quantities (refer: ITB Clause

11.2 and CC Clause 37.2).

(2)Unit rates and prices shall be quoted by the Tenderer in Indian Rupees.

(3)	Where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by quantity, the unit rate quoted shall govern [ITT Clause 24.1 (b)]