KARNATAKA URBAN WATER SUPPLY AND DRAINAGE BOARD

(E-Procurement Tender)

TENDER FOR “ PROVIDING DRINKING WATER SUPPLY TO PROPOSED TEXTILE PARK (UNDER PM MITRA SCHEME) NEAR NADISINOOR VILLAGE FROM PROPOSED BARRAGE ACROSS BHIMA RIVER NEAR MADRI VILLAGE  UNDER DC WORKS INCLUDING OPERATION & MAINTENANCE FOR A PERIOD OF 5 YEARS (INCLUDING 1 YEAR DLP) THROUGH  DESIGN, BUILD OPERATION AND TRANSFER (DBOT) MODE LUMPSUM - NO VARIATIONODE LUMPSUM - NO VARIATION”.

2026

TENDER DOCUMENT

OFFICE OF THE CHIEF ENGINEER,

KARNATAKA URBAN WATER SUPPLY AND DRAINAGE BOARD

KALABURAGI

TENDER FOR THE WORK OF

TENDER FOR “ PROVIDING DRINKING WATER SUPPLY TO PROPOSED TEXTILE PARK (UNDER PM MITRA SCHEME) NEAR NADISINOOR VILLAGE FROM PROPOSED BARRAGE ACROSS BHIMA RIVER NEAR MADRI VILLAGE  UNDER DC WORKS INCLUDING OPERATION & MAINTENANCE FOR A PERIOD OF 5 YEARS (INCLUDING 1 YEAR DLP) THROUGH  DESIGN, BUILD OPERATION AND TRANSFER (DBOT) MODE LUMPSUM - NO VARIATIONODE LUMPSUM - NO VARIATION”.

| Tender Reference | : | Indent No. KUWSDB/2026-27/WS/WORK_INDENT518 |
| --- | --- | --- |
| Date and time for commencement of downloading of tender document from the e-procurement portal https://kppp.karnataka.gov.in | : | As per e-procurement portal |
| Last date and time for seeking clarifications if any | : | As per e-procurement portal |
| Date, time and venue of pre-bid meeting: Venue | : | As per e-procurement portal Office of the Chief Engineer, K.U.W.S. and D. Board, Jalbhavan, Rajapur, Kalaburagi. |
| Last date and time for downloading of the tender document From the e-procurement portal https://kppp.karnataka.gov.in | : | As per e-procurement portal |
| Last date and time for submission/uploading of tender in the e-procurement portal https://kppp.karnataka.gov.in | : | As per e-procurement portal |
| Date and time for opening of the Technical tenders | : | As per e-procurement portal |
| Date and time for opening of the financial tenders | : | As per e-procurement portal |
| Place for opening of the tenders and address for communication | : | Office of the Chief Engineer, K.U.W.S. and D. Board, Jalbhavan, Rajapur, Kalaburagi.– 585105. |

DISCLAIMER

The information contained in this Tender document or subsequently provided to Tenderer(s), whether verbally or in documentary or any other form by or on behalf of the Employer or any of its employees or advisors, is provided to Tenderer(s) on the terms and conditions set out in this tender document and such other terms and conditions subject to which such information is provided.

This Tender document is not an agreement and is neither an offer nor initiation by the Employer to the prospective Tenderers or any other person. The purpose of this Tender document is to provide interested parties with information that may be useful to them in making their financial proposals pursuant to this Tender document. This Tender document includes statements, which reflect various assumptions and assessments arrived by the Employer in relation to the Project. Such assumptions, assessments and statements do not purport to contain all the information that each Tenderer may require. This Tender document may not be appropriate to all persons, and it is not possible for the Employer, its employees or advisors to consider the investment objectives, financial situation and particular needs of each party who reads or uses this Tender document. The assumptions, assessments, statements and information contained in all sections of this Tender document may not be complete, accurate, adequate or correct. Each Tenderer should, therefore, conduct its own investigations and analysis and should check the accuracy, adequacy, correctness, reliability and completeness of the assumptions, assessments, statements and information contained in this Tender document and obtain independent advice from appropriate sources.

Information provided in this Tender document to the Tenderer(s) is on a wide range of matters, some which may depend upon interpretation of law. The information given is not intended to be an exhaustive account of statutory requirements and should not be regarded as a complete or authoritative statement of law. The Employer accepts no responsibility for the accuracy or otherwise for an interpretation or opinion on law expressed herein.

The Employer, its employees and advisors make no representation or warranty and shall have no liability to any person, including any Tenderer under the law, statute, rules or regulations or tort, principles of restitution or unjust enrichment or otherwise for any loss, damages, cost or expenses which may arise from or be incurred or suffered on account of anything contained in this Tender document or otherwise, including the accuracy, adequacy, correctness, completeness or reliability of the Tender document and any assessment, assumption, statement or information contained therein or deemed to form part of this Tender document or arising in any way for participation in this Tender Stage.

The Employer also accepts no liability of any nature whether resulting from negligence or otherwise howsoever caused arising from reliance of any Tenderer upon the statements contained in this Tender document. The Employer may in its absolute discretion, but without being under any obligation to do so, update, amend or supplement the information, assessment or assumptions contained in this Tender document.

The issue of this Tender document does not imply that the Employer is bound to select a Tenderer or to appoint the selected Tenderer, as the case may be, for the Project and the Employer reserves the right to reject all or any of the Tenderers or Tenders without assigning any reason whatsoever.

The Tenderer shall bear all its costs associated with or relating to the preparation and submission of its Tender including but not limited to preparation, copying, postage, delivery, fees, expenses associated with any demonstrations or presentations which may be required by the Employer or any other costs incurred in connection with or relating to its Tender. All such costs and expenses will remain with the Tenderer and the Employer shall not be liable in any manner whatsoever for the same or for any other costs or other expenses incurred by a Tenderer in preparation or submission of the Tender, regardless of the conduct or outcome of the Tendering Process.

TABLE OF CONTENTS

SECTION 1: INVITATIONFORTENDERS (IFT)	5

SECTION 2: INSTRUCTIONS TO TENDERERS (ITT)	36

SECTION 3: QUALIFICATION INFORMATION	63

SECTION 4: FORMS OF TENDER	114

SECTION 5: CONDITIONS OF CONTRACT	121

SECTION 6: CONTRACT DATA	137

SECTION 7: TECHNICAL SPECIFICATIONS	238

SECTION 8: DRAWINGS	239

SECTION 9: BILL OF QUANTITIES (FINANCIAL PROPOSAL)	240

SECTION 10: FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT	243

# SECTION 1: INVITATION FOR TENDERS (IFT)

(Through e-Procurement Mode)

Indent No: - KUWSDB/2026-27/WS/WORK_INDENT518                            Date: 23-06-2026 .

- The Chief Engineer, KUWS&D Board, Kalaburagi, Karnataka invites tenders from eligible Tenderers, Two Cover Tender procedure as per Rule 28 of the KTPP Act shall be followed. The Tenders are required to submit two separate sealed covers, one containing the Earnest money deposit and the details of their capability to undertake the tender (as detailed in ITT Clause 3and 6), which will be opened first and the second cover containing the price tender which will be opened only if the Tenderer is found to be qualified to execute the tendered works. The Tenderers are advised to note the minimum qualification criteria specified in Clause 3 of the Instructions to Tenderers to qualify for award of the contract.

  - Technical Proposal

- Containing the Earnest Money Deposit and the details of their capability to undertake the Tender (as detailed in ITT in Clause 10) will be opened first. The Proposal includes Technical Proposal of the tenderer of not lower than the departmental proposal which will be evaluated as part of Technical Scrutiny (see Clause 3.8 for details regarding this).

- Tenderer should submit the technical proposal (concept) with the general layout of scheme, location of the scheme components and type of land and extent of area. The concept shall indicate the details of items involved, quality and make of core items. The concept will be placed before the Evaluation Committee set up by KUWSDB for evaluation. Only after acceptance of concept of the scheme, Financial Proposal will be opened.

- The Tenderer shall furnish any clarifications required by the committee within the time as indicated in the communication for seeking such additional clarification. In case of failure by the Tenderer to submit the clarifications on time, the Committee’s decision is final and binding.

- Financial Proposal will be opened only if the Tenderer is found to be technically qualified as per above conditions. The Financial Proposals of Tenderers whose Technical Proposals are rejected/disqualified shall not be opened.

- The tenders are to be submitted online through the e-procurement portal https://kppp.karnataka.gov.in only before the tender submission due date, along with a non-refundable tender processing fee in the form and manner as prescribed by e-Procurement Platform. The Chief Engineer, KUWSDB, having office at K.U.W.S. and D. Board, Jalbhavan, Kusnoor Road, Rajapur, Kalaburagi – 585105, will not be held responsible for the technical issues with the said Portal. Tenders submitted in any other manner will not be accepted. Tenderers are required to obtain Level III digital signature from designated firms (available on the e-procurement portal) and then register with the Government of Karnataka e-procurement platform and submit tenders by using their ID and digital signature. The Tenderer is required to ensure browser compatibility of the computer well in advance to the last date and time for receipt of the Tenders. It is the Tenderer’s responsibility to verify the e-procurement portal for the latest information related to the Tender. E-mail address of the helpdesk is Email to: support@eprochelpdesk.com. E-procurement portal helpdesk telephones numbers are +91 80 46010000, +91 80 68948777 who may be contacted during office hours.

- Tenders must be accompanied by Earnest Money Deposit specified for the work in the Table below. The EMD shall be deposited through e-Procurement Portal, https://kppp.karnataka.gov.in as mentioned in Instructions to Tenderers and shall have to be valid for 45 days beyond the validity of the Tender.

- A Pre-tender meeting will be held as notified in the e-procurement portal in the office of The Chief Engineer, Karnataka Urban Water Supply and Drainage Board, Kalaburagi to clarify the issues if any, and to answer questions on any matter that may be raised at that stage as stated in Clause 8.2 of ‘Instructions to Tenderers’ of the tender document.

- Tenders must be correctly and properly uploaded in e-Procurement Portal (https://kppp.karnataka.gov.in) on or before the date and time specified in e-procurement portal and Technical Proposal of the Tenders will be opened on the specified time and date, in the presence of the Tenderers who wish to attend. If the office happens to be closed on the any specified date of the Tenders, the said action shall be taken on the next working day at the same time and venue.

- Other details are available in the Tender documents.

| Sl No | Name of work | Approximate value of work (INR) Excluding GST | EMD (INR) | Tender Processing Fee | Contract Period/Period of Completion* |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |
|  | TENDER FOR “ PROVIDING DRINKING WATER SUPPLY TO PROPOSED TEXTILE PARK (UNDER PM MITRA SCHEME) NEAR NADISINOOR VILLAGE FROM PROPOSED BARRAGE ACROSS BHIMA RIVER NEAR MADRI VILLAGE UNDER DC WORKS INCLUDING OPERATION & MAINTENANCE FOR A PERIOD OF 5 YEARS (INCLUDING 1 YEAR DLP) THROUGH DESIGN, BUILD OPERATION AND TRANSFER (DBOT) MODE LUMPSUM - NO VARIATIONODE LUMPSUM - NO VARIATION”. PART-A: CAPITAL WORKS - DESIGN, CONSTRUCTION, OPERATION & MAINTENANCE OF PROVIDING WATER SUPPLY SCHEME TO TEXTILE PARK DPR Preparation & General Requirement; Detailed Scheme Report and Drawings: Cost of production of set of documents & drawings, Total Station Survey, Soil Investigations including trial pits and SBC of Soil. Construction Documents and Drawings: Cost of production of set of construction documents & drawings 1.1 Civil, Pipeline and Building Works 1.2 Mechanical Plants 1.3 Electrical Plants 1.4 Production of Progress Reports Approval of QAP Any additional items required for the production of construction documents & drawings Operation and Maintenance Manuals: Costs for the production of operation and maintenance manuals 2.1 First issue (prior to Tests on Completion) 2.2 As built O & M Manuals (Shall be read in conjunction with Section 7: Specifications, Special specifications for all the items) II Survey, Design, Drawings, Construction, Supply, Installation, Testing and Commissioning of Water Supply System - Construction of Embankment by excavating the available approved Gravel/ Murrum deposited at a place or borrow pits during or prior excavation with all lifts and lead, transportation to site, spreading, grading to required slope and compacting to meet the requirement complete as per specifications, including cost of labour, rolling, water, all materials,usage& all other appurtenaces required to complete the work etc., complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Construction of 4.5 M dia intake well in Bhima river at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Providing connecting main of 500mm dia RCC NP-3 class pipes for the length of 95mtrs from intake well to jackwell in Bhima river at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Construction of Inspection Chamber (2Nos) @ 48m for connecting main 500mm dia RCC pipe - 95m from intake well to jackwell in Bhima river at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Construction of 6 mtr. dia. RCC Jackwell cum 8 mtr. Pump House in Bhima river at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Providing 11 KV express power supply line from Fharthabad sub station to the proposed Headworks at barrage near Madri Village and WTP in textile park for a length not less than 23.50Km. etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Supply, erection, electrification and commissioning of 2 Nos. of 90HP or suitable HP (100% standby )submersible Verticle Turbine Pumpsets at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Construction of R.C.C. approach bridge for the length of 95mtrs to jackwell cum pumphouse at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Providing,laying,jointing,testing and commissioning of 300mm dia. DI K-9 class raw water rising main for the length of not less than 17.52Km from proposed jackwell cum pumphouse at barrage near Madri Village to proposed WTP in textile park. etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. - Construction of 3.63 MLD output ( in 22 Hours ) capacity water treatment plant (WTP) at proposed Textile Park near Nadishirnur village including, aerator,raw water channel,flash mixer,floculator,tube settler,filter complex,chlorine rooom,chemical house, laboratory,1.50 LL or suitable capacity back wash OHT, 2LL sump, yard lighting, electrical and electrification of WTP components,sludge disposal arrangements, barbed wire fencing to WTP,internal roads, electro-mechanical works,land scaping of WTP etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | ₹2492.44 Lakhs (CAPEX: ₹2143.17 Lakhs OPEX: ₹349.27 Lakhs) | ₹29.41 Lakhs | As per e-procurement portal. | 18 months including monsoon period for CAPEX. |
|  | PART-B: Operation & Maintenance O & M of the assets created for a period of 5 years including Defects Liability period for 12 months. |  |  |  | 60 months after successful completion of Part I including 1 year of DLP for OPEX. |

Sd/-

Chief Engineer,

KUWSDB, Kalaburagi.

Kalaburagi Zone.

SECTION 2: INSTRUCTIONS TO TENDERERS (ITT)

Table of Clauses

SECTION 1: INVITATIONFORTENDERS (IFT)	5

SECTION 2: INSTRUCTIONS TO TENDERERS (ITT)	36

A.	GENERAL	36

1.	Scope of Tender	36

2.	Eligible Tenderers:	36

3.	Qualification of the Tenderer	38

4.	One Tender per Tenderer:	44

5.	Cost of Tendering:	44

6.	Site visit:	44

B.	TENDER DOCUMENTS	44

7.	Content of Tender documents	44

8.	Clarification of Tender Documents	44

9.	Amendment of Tender documents	45

C.	PREPARATION OF TENDERS	45

10.	Documents comprising the Tender	45

11.	Tender prices	48

12.	Tender validity	49

13.	Earnest Money Deposit	49

14.	Format and signing of Tender	50

D.	SUBMISSION OF TENDERS	50

15.	Online Tender Submission	50

16.	Deadline for submission of the Tenders	51

17.	Late Tenders	51

18.	Modification and Withdrawal of Tenders	51

E.	TENDER OPENING AND EVALUATION	52

19.	Opening of Technical proposal of all Tenders and evaluation to determine technically qualified Tenderers:	52

20.	Opening of Financial Proposal of qualified Tenderers and evaluation: As per e-Portal	53

21.	Process to be confidential	53

22.	Clarification of Tenders	53

23.	Examination of Tenders and determination of responsiveness	53

24.	Correction of errors	54

25.	Evaluation and comparison of Tenders	54

F.	AWARD OF CONTRACT	55

26.	Award criteria	55

27.	Employer’s right to accept any Tender and to reject any or all Tenders	55

28.	Notification of award and signing of Agreement	55

29.	Security Deposit / Performance Security	56

30.	Advance Payment and Security:	57

31.	Corrupt or Fraudulent practices	57

SECTION 3: QUALIFICATION INFORMATION	63

SECTION 4: FORMS OF TENDER	114

SECTION 5: CONDITIONS OF CONTRACT	121

A.	General	123

1.	Definitions	123

2.	Interpretation	124

3.	Law governing contract	124

4.	Employer's decisions	124

5.	Delegation	125

6.	Communications	125

7.	Sub –Contracting: deleted	125

8.	Other Contractors	125

9.	Personnel	125

10.	Employer’s and Contractor's risks	125

11.	Employer's risks	125

12.	Contractor’s risks	125

13.	Insurance:	126

14.	Site Investigation Reports:	126

15.	Queries about the Contract Data	126

16.	Contractor to construct the Works	126

17.	The Works to be completed by the Intended Completion Date	126

18.	Approval by the Employer:	127

19.	Safety	127

20.	Discoveries	127

21.	Possession of the Site	127

22.	Access to the Site	127

23.	Instructions	127

24.	Procedure for resolution of Disputes:	128

B.	Time Control	128

25.	Program	128

26.	Extension of the Intended Completion Date	128

27.	Delays ordered by the Employer	128

28.	Management meetings	128

C.	QUALITY CONTROL	129

29.	Identifying defects	129

30.	Tests	129

31.	Correction of defects	129

32.	Uncorrected defects	129

D.	COST CONTROL	129

33.	Bill of Quantities (BOQ)	129

34.	Variations - NOT APPLICABLE	129

35.	Payments for Variations- NOT APPLICABLE	129

36.	Submission of bills for payment	129

37.	Payments	130

38.	Compensation events	130

39.	Tax	131

40.	Price Adjustment: (Applicable for civil works only& not applicable for electro-mechanical and O&M works)	131

41.	Liquidated damages	131

42.	Advance Payments:	132

43.	Securities:	132

44.	Cost of Repairs:	132

E.	FINISHING THE CONTRACT	132

45.	Completion	132

46.	Taking over	132

47.	Final account	133

48.	As built drawings and /or Operating and Maintenance Manuals	133

49.	Termination	133

50.	Payment upon Termination	134

51.	Property	134

52.	Release from performance	134

53.	Additional Clauses:	134

F.	SPECIAL CONDITIONS OF CONTRACT	136

SECTION 6: CONTRACT DATA	137

ANNEXURE-F: QUALITY ASSURANCE PLAN FOR MATERIALS	198

SCHEDULE-1: PHYSICAL AND FINANCIAL ACTIVITY PROGRESS	210

SCHEDULE 2: OPERATION AND MAINTENANCE	233

SCHEDULE 3: SCHEDULE OF PAYMENT	235

ANNEXURE-A: Construction Supervision and Contract Management	236

SECTION 7: TECHNICAL SPECIFICATIONS	238

SECTION 8: DRAWINGS	239

SECTION 9: BILL OF QUANTITIES (FINANCIAL PROPOSAL)	240

SECTION 10: FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT	243

# SECTION 2: INSTRUCTIONS TO TENDERERS (ITT)

## A.	GENERAL

### Scope of Tender

  - The CHIEF ENGINEER, KUWSDB, Kalaburagi, Karnataka (referred to as Employer in these documents invites Tender following the Two cover Document Tender procedure through e-Procurement Portal of e-Governance Department, Government of Karnataka (https://kppp.karnataka.gov.in), from eligible Tenderers, for the work (as defined in these documents and referred to as "the Works") detailed in the Table given in the Invitation for Tenderers (IFT).

  - The Project Description and KUWSBD is in process of hiring contractor / operator on Design, Built, Operate and Transfer (DBOT) basis for  PROVIDING DRINKING WATER SUPPLY TO PROPOSED TEXTILE PARK (UNDER PM MITRA SCHEME) NEAR NADISINOOR VILLAGE FROM PROPOSED BARRAGE ACROSS BHIMA RIVER NEAR MADRI VILLAGE  UNDER DC WORKS INCLUDING OPERATION & MAINTENANCE FOR A PERIOD OF 5 YEARS (INCLUDING 1 YEAR DLP) THROUGH  DESIGN, BUILD OPERATION AND TRANSFER (DBOT) MODE LUMPSUM - NO VARIATION  Technical (To be added description of each project along with its various components & project boundary)

### Eligible Tenderers:

  - Tenderers shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued by the Government of Karnataka or Government of India or any another state / central government.

  - Tenders from Joint Ventures are acceptable. Please refer “Tender Data Sheet”.

  - The Tenderers must be eligible as per the Finance Department Government Order No. FD 455 Exp-12 2020 Bengaluru Dated: 25-08-2020., who are coming from countries which are sharing the land border with India and if they are intended to participate in the Government of Karnataka Tenders.

    - Competent Authority and Procedure for Registration

- The Competent Authority for the purpose of registration of bidders under this order has been constituted in the department of Commerce & Industries, Government of Karnataka.

- The Registration Committee Shall have the following members:

- Principal Secretary/Secretary to Govt. Department of Commerce and Industries shall be the Chairman.

- An officer not below the rank of Secretary to Govt., Home Department.

- An officer not below the rank of Secretary to Govt., of those Departments whose procurements are covered by applications under consideration.

- Any other officer whose presence is deemed necessary b the Chairman of the Committee.

- Department of Commerce and /industries shall lay down the method of applicant, format etc. for such bidders as stated in para (1) of this order.

- On receipt of an application seeking registration from a bidder from a country covered by para (1) of this order, the Competent Authority shall first seek political and security clearances from the Ministry of External Affairs and Ministry of Home Affairs, Government of India as per guidelines issued from time to time. Registration shall not be given unless political and security clearance have both been received.

- The department of Commerce and Industries in consultation with Home Department may issue guidelines for internal use regarding the procedure for scrutiny of such applications by them.

- The decision of the Competent Authority to register such bidder may be for all kinds of tenders or for a specified type(s) of goods or services, and may be for a specified or unspecified duration of time, as deemed fit. The decision of the Competent Authority shall be final.

- Registration granted by the Competent Authority of the Government of Karnataka shall be valid only for procurements by the Procurement Entities as defined in the Section 2(d) of Karnataka Transparency in Public Procurements Act, 1999.

- The Competent Authority is empowered to cancel the registration already granted if it determines that there is sufficient cause. Such cancellation by itself, however, will not affect the execution of contracts already awarded. Pending cancellation, it may also suspend the registration of a bidder, and the bidder shall not be eligible to bid in any further tenders during the period of suspension.

- In transitional cases failing under para (6) of this Order, where it is felt that it will not be practicable to exclude bidders from a country which shares a land border with India, a reference seeking permission to consider such bidders shall be made by the procuring entity to the Competent Authority giving full information and detailed reasons. The competent Authority shall decide whether such bidders may be considered, and if so, shall follow the procedure laid down in the above paras.

- The Competent Authority is required to send a quarterly report to the Cabinet Secretary, Government of India regarding the cases of registration given and denied.

    - Restrictions of procurement

Any bidder from a country which shares a land with India will be eligible to bid in this tender only if the bidder is registered with the Competent Authority

- “Bidder” (including the term ‘tenderer’, ‘consultant’ or ‘service provider’ in certain contexts) means any person or firm or company, including any member of a consortium or joint venture (that is an association of several persons, or firms or companies), every artificial juridical person not falling in any of the descriptions of bidders stated hereinbefore, including any agency branch or office controlled by such person, participating in a procurement process.

- “Bidder from a country which shares a land border with India” for the purpose means:

- An entity incorporated, established or registered in such a country; or

- A subsidiary of an entity incorporated, established or registered in such a country; or

- An entity substantially controlled through entities incorporated, established or registered in such a country; or

- An entity whose beneficial owner is situated in such a country: or

- An Indian (or other) agent of such an entity; or

- A natural person who is a citizen of such a country; or

- A consortium or joint venture where any member of the consortium or joint venture falls under any of the above.

- The beneficial owner for the purpose of above clause will be as under:

- In case of a company or Limited Liability Partnership, the beneficial owner is the natural person(s), who, whether acting alone or together, or through one or more juridical person, has a controlling ownership interest or who exercises control through other means.

- “Controlling ownership interest” means ownership of or entitlement to more than twenty- five percent of shares or capital or profits of the company;

- “Control” shall include the right to appoint majority of the directors or to control the management or policy decisions including by virtue of their shareholding or management rights or shareholders agreements or voting agreements;

- In case of a partnership firm, the beneficial owner is the natural person(s) who, whether acting alone or together, or through one or more juridical person, has ownership of entitlement to more than fifteen percent of capital or profits of the partnership;

- In case of an unincorporated association or body of individuals, the beneficial owner is the natural person(s), who, whether acting alone or together, or through one or more juridical person, has ownership of or entitlement to more than fifteen percent of the property or capital or profits of such association or body of individuals;

- Where no natural person is identified under A, B & C above, the beneficial owner is the relevant natural person who holds the position of senior managing official;

- In case of a trust, the identification of beneficial owner(s) shall include identification of the author of the trust, the trustee, the beneficiaries with fifteen percent or more interest in the trust and any other natural person exercising ultimate effective control over the trust through a chain of control or ownership.

- An agent is a person employed to do any act for another, or to represent another in dealings with third person.

- A certificate for having read the above clauses is required to be submitted / uploaded by the tenderer separately in the following format:

“I have read the clause regarding restrictions on procurement from a bidder of a country which shares a land border with India; I certify that this bidder is not from such a country or, if from such a country, has been registered with the Competent Authority. I hereby certify that this bidder fulfills all requirements in this regard and is eligible to be considered. (Where applicable, evidence of valid registration by the Competent Authority shall be attached.)”

- IN CASES WHERE SUB CONTRACTING IS PROVIDED:

A certificate is required to be submitted / uploaded by the Tenderer in respect of sub-contracting separately in the following format:

“I have read the clause regarding restrictions on procurement from a bidder of a country which shares a land border with India and on sub-contracting to contractors from such countries; I certify that this bidder is not from such a country or, if from such a country, has been registered which Competent Authority and will not sub-contract any work to a contractor from such countries unless such contractor is registered with the Competent Authority. I hereby certify that this bidder fulfills all requirements in this regard and is eligible to be considered. [Where applicable, evidence of valid registration by the Competent Authority shall be attached.]”

##### In case of Joint Venture

2.4.1       One of the partners, who is responsible for performing a key function as per the Joint Venture Agreement or is executing a major component of the proposed contract, shall be nominated as being in-charge (hereinafter referred to as “Lead Partner”) for tendering period and, in the event of a successful tender, during contract execution. The Lead Partner shall be authorized to incur liabilities and receive instructions / take up all the matter related to the contract management and implementation for and on behalf of any and all partners of the joint venture; this authorization shall be evidenced by submitting a Power of Attorney signed by legally authorized signatories of all the partners. Role of parties/JV partners detailing Key functions under taken by each partner shall be provided in the JV agreement.

### Qualification of the Tenderer

  - All Tenderers shall provide the requested information accurately and in sufficient detail in Section 3: Qualification information. [Requirements as listed in Clause 3.2, 3.3 & 3.4 are minimum qualification conditions and any Tenderer failing to meet the same shall stand disqualified at the technical evaluation stage].

  - To qualify for this Tender, each Tenderer in its name should have in the last five years i.e., 2021-2022 to 2025-26.

| Si. No | Qualification criteria | Single Entity | Joint Venture |
| --- | --- | --- | --- |
| 3.2(a) | Achieved in at least two financial year a Minimum Financial turnover of INR. 39.21 Croresin the last five financial years (2021-2022 to 2025-2026) (in all classes of civil engineering construction works only). The Consolidated Annual Financial turnover certificate for the relevant financial years certified by Statutory Auditor along with UDIN number (also the audited financial statements for each of the financial years) to be submitted. | Has to meet this qualification criteria | Partners may either individually or jointly meet this qualification criterion. However, each of the Partners of the JV shall meet not less than 25% & Lead partner shall meet not less than 50% of this qualification criteria |
| 3.2 (b) | ##### Satisfactorily completed (90% of the Contract Value), as prime contractor atleast one water supply project/ lift irrigation projects of value not less than INR 12.46 Crores. Note: The value of work mentioned in the work done certificate shall be Excluding GST. | Has to meet this qualification criteria | Partners may either individually or jointly meet this qualification criterion from one of their respective projects. However, any one of the partners to meet not less than 50% of this qualification criterion. The partner meeting 50% of this qualification criteria shall be referred to as the ‘Technical Partner/Lead Partner’. |
| 3.2 (c) | ##### Executed the following minimum quantities of work, executed in any one year |  |  |
|  | ##### Providing & laying of MS/DI/ HDPE or. in combination of these pipes – 14240 m length. | Has to meet this qualification criteria | ##### Any partner or partners jointly to meet this qualification criterion. ##### However, the Lead partner shall meet not less than 50% of this qualification criteria |
| 3.2 (d) | ##### The Tenderer should have constructed Jackwell/Wetwell of min 3.0 m dia in any one year. | Has to meet this qualification criteria | ##### Any partner or partners jointly to meet this qualification criterion. |
| ##### 3.2 (e) | ##### The Tenderer should have constructed a WTP or in combination of minimum 1.82 MLD capacity in any one year. | ##### Has to meet this qualification criteria | ##### Any partner or partners jointly to meet this qualification criterion. |
| 3.2 (f) | ##### The Tenderer should have executed SEEC of DWT/ CF/ submerged CF/ non-clog sewage pumping machineries with allied accessories not less than 90 HP or in combination in any one year. | ##### Has to meet this qualification criteria | ##### Any partner or partners jointly to meet this qualification criterion. |
| ##### 3.2 (g) | ##### The Tenderer or his identified sub- contractor should possess valid Electrical licence and should have completed at least one work of Providing 11KV/33 KV express feeder main of value not less than ₹106.18 Lakhs in any one year. | ##### Has to meet this qualification criteria or his identified sub-contractor shall meet the qualification criteria. | ##### Any partner or partners jointly shall meet this qualification criteria or his identified sub-contractor shall meet the qualification criteria. |

The Maximum JV Partners are limited to Three (3). JV members shall nominate the partner who meet not less than 50% of qualification criteria under 3.2 above as Lead Member of the JV.

Note:1) The work done experience in similar Water Supply projects executed by the Tenderer in any of the Central / State Government Departments / Quasi Government Organizations and Government Undertakings shall have to be submitted along with the tender. The Work done certificate from the Executive Engineer / Employer (Government Departments/ Government Undertakings) who has executed the Agreement shall be furnished. The experience certificates issued on behalf of Executive Engineer will not be considered.

2) For the purpose for this Tender submission, the Tenderer should either have an in-house Design team or hire a reputed Design Consultant. However, NO Design Consultant/s shall work or prepare design/s or provide services or advice to more than one tenderer for this particular work. In case two or more tenderers are utilizing the same design consultant, then all such submissions by the tenderers will be Annulled. Therefore, a design consultant can provide his services to only One Tenderer for this work.

(Design Consultant shall mean a reputed person or a reputed firm/entity carrying out survey/s (topographical, geo technical, household or any other survey required for the project), hydraulic designs (including network design), electrical designs, and water supply designs calculations with drawings, designs calculations with drawings).

Design Consultant is required to submit his work experience credentials and minimum key personnel i.e Hydraulic Expert-1 No, Structural Expert-1 No, Electromechanical Expert-1 No. The credentials of the Design Consultant and CVs of key personnel (minimum) shall be evaluated along with the Conceptual Scheme Report.

  - The Tenderer should further demonstrate:

- Availability by owning/hired (50:50) key and critical equipment for this work.

| Sl. No | Critical Equipment required | Quantity |
| --- | --- | --- |
| 1 | Excavators. | 1 No. |
| 2 | Concrete / Groove cutting machine. | 1 No. |
| 3 | Electro fusion / Butt welding machine. | 1 No. |
| 4 | Concrete mixer | 1 No. |

- Liquid assets and/or availability of credit facilities of not less than Rs.16.53 Crores unconditional Credit line/ letter of credit/ certificates from banks for meeting the fund requirement etc. If the Banker Certificate is conditional, then the Tender is liable for rejection.  (Either, Partners of the JV / or Lead partner shall meet this qualification criteria.) Please refer “Tender Data Sheet”

- Technical, administrative and managerial personnel proposed to be employed for key site management in this work with their qualification details should be furnished in Annexure – III.

- Litigation details of the Tenderers with the details of the parties concerned and the amount involved should be furnished in Annexure-V.

  - To qualify for contract made up of this for which Tenders are invited in this Tender, the Tenderer must demonstrate having experience and resources to meet the aggregate of the qualifying criteria for the individual contracts.

  - Deleted.

  - Tenderer who meets the above specified minimum qualifying criteria, will only be qualified, if their available Tender capacity is more than the total Tender value.  The available Tender capacity will be calculated as under

Assessed available Tender capacity = (A*N*1.5 - B) where

A=Maximum value of civil engineering works executed in any one year during the last five years (updated to 2026-27 price level) taking into account the completed as well as works in progress.

N = Number of years prescribed for completion of the works for which Tenders are invited. (N = 1.50 years (18 months) in this Tender).

B = Value, at 2026-27 price level, of existing commitments and on-going works to be completed during the next 1.50 years.

In case of JV, values of A& B shall be the sum total of the respective figures of all the partners.

Note: The statements showing the value of existing commitments and on-going works as well as the stipulated period of completion remaining for each of the works listed should be countersigned by the Employer in Charge, not below the rank of an Executive Engineer or who has executed the Agreement.

  - Even though the Tenderers meet the above criteria, they are subject to be disqualified if they have:

- made misleading or false representations in the forms, statements and attachments submitted in proof of the qualification requirements; and/or

- Record of poor performance such as abandoning the works, not properly completing the contract, inordinate delays in completion, litigation history, or financial failures etc.

- participated in the previous Tender for the same work and had quoted unreasonably high tender prices and could not furnish rational justification.

  - Technical Proposal Details to the extent of Conceptual Scheme Report (CSR)/Design of Water Supply Scheme shall be submitted as part of technical proposal by the Tenderer.

NOTE: This is a Design, Build, Operate & Transfer (DBOT) Tender, therefore, the Tenderer are expected to propose their best design along with land requirement within the overall framework of CPHEEO Guidelines/ Standards and other prescribed National/ International standards/norms and terms & conditions of this Tender limiting the construction period to 24 months and considering the given design parameters in this Tender document for various components in the system. The Tenderer shall be responsible for the operations and Maintenance of the project facilities for a period of 60 months including 1 year of DLP, from the date of commissioning the project.

    - As a part of the technical proposal the Tenderer shall submit technical proposal/design as far as possible after actual site visit.

    - The proposed design shall be at least of the level of CSR (Conceptual Scheme Report) for Water Supply Scheme prepared by the KUWSDB.

    - Tender Evaluation Committee comprising of subject experts shall evaluate the CSR proposal/design submitted by the Tenderer. The Tenderer will have to make a detailed presentation on the proposed design to the committee during evaluation.

    - In order to have utmost transparency in technical evaluation of the design, the minimum parameters which shall be covered (in detail) for the proposed design by Tenderer as part of the technical proposal (however, the format shall not be construed to limit the design and technical proposal that the Tenderer wishes to submit).

- Proposal submitted for this water supply scheme shall consist (see format in this regard) but not limited to;

Water Supply System

  - Technical surveys (Total Station Survey, Soil Investigations including trial pits and SBC of Soil, Core log, bathometric survey as applicable and Customer survey for providing connections.

  - Ensure that the design`s incorporate the water balance and Mass balance study.

  - Hydraulic calculations for Pumping mains, based on preliminary levels.

  - Layout and hydraulic flow diagrams showing flow, pipe diameter, length, type of material etc., IS/referred code for calculations of pipe diameter, surge protection details.

  - General arrangement drawings for various units like Service reservoirs, etc.

  - Preliminary longitudinal sections for rising mains / bulk transmission mains and hydraulic flow diagrams showing flow, pipe diameter, length, type of material etc., IS/referred code for calculations of pipe diameter.

  - Electrical load calculations, transformer sizing calculations and any other major items.

  - Installation of Bulk water meter at all the outlet points in the water supply system to measure the production and supplied.

  - Type of Pump, power requirement and combined efficiency pump & motor considered.

  - Extent of area Private/Government considered and extent of land considered for each of the major items. The lands procured for the project shall be registered in the name of the Handloom and Textile Department by the Successful Tenderer.

  - Single Line Diagrams for all pumping stations and Intermediate Pumping stations.

  - Filled up formats as enclosed in the Tender document

- Location of Land, Availability / Requirement – the tentative requirement of the land for the each project / package is in accordance with the Technical Specification – Section 7

- If the land to be acquired, the Tenderer is responsible to identify and facilitate acquire the required land on behalf of Handloom and Textile Department. The land cost as per Guidance value only will be paid by the KUWSDB.

- All approvals from statutory bodies like respective NHAI, NH, Railways, GESCOM, KPTCL, PWD, KRDCL, KSHIP, ULB, MI, Forest and Revenue Department etc., is the responsibility of the Tenderer. However necessary documents required for the permissions would be provided by the KUWSDB. Necessary deposits will be paid by the KUWSDB based on the intimation received from the respective Dept.

The Consultant/technical expert who has helped/assisted the department in any form 	for preparing the proposal of this scheme cannot be a consultant for the Tenderer 	during preparation CSR/DSR/designs/ execution/ O& M or in any form which leads to 	conflict of interest of the department & fraudulent practice

- A preliminary base line schedule depicting all the major activities with their proposed duration shall also be submitted as part of the technical proposal. The duration shall not exceed the overall scheme duration of the Project.

  - The work done experience in similar Water Supply Projects executed by the Tenderer in any of the Central/State Government Departments/Quasi Government Organizations and Government Undertakings shall have to be submitted along with the tender. Work done certificates issued by the concerned officer not below the rank of Executive Engineer / Employer from Central/State Government Department/ Undertaking/ Quasi Government Organization should be submitted for each qualifying project submitted by the Tenderer as part of evaluation under Clause 3.2 of ITT. The experience certificates issued by an officer below the rank of Executive Engineer / Employer or on behalf of the Executive Engineer / Employer will not be considered.

### One Tender per Tenderer:

  - Each tenderer shall submit only one tender for one. A Tenderer who submits or participates in more than one Tender will cause all the proposals with the Tenderer’s participation to be disqualified.

### Cost of Tendering:

  - The tenderer shall bear all costs associated with the preparation and submission of his tender, and the Employer will in no case be responsible and liable for those costs.

### Site visit:

  - The Tenderer at his own cost, responsibility and risk is required to visit and examine the site (s) of works and its surroundings and obtain all information that may be necessary for preparing the Tender and entering into a contract for construction of the Works. The cost of visiting the Site shall be at the Tenderer own expense. The bidder is solely responsible to carry out diligence of projects before bidding.

## B.	TENDER DOCUMENTS

### Content of Tender documents

  - The Tender documents comprise of the following sections:

###### Section 1 – Invitation for Tenders

###### Section 2 – Instructions to Tenderers

###### Section 3 – Qualification Information

###### Section 4 – Forms of Tender, Letter of Acceptance, Notice to Proceed with the Work and Agreement Form

###### Section 5 – Conditions of Contract

###### Section 6 – Contract Data

###### Section 7 – Technical Specifications (Employer’s Requirement)

###### Section 8 – Drawings

###### Section 9 – Bill of Quantities (Financial Proposal)

###### Section 10 – Format of Bank Guarantee for Security Deposit / Advance Payment

  - The tender documents are available on line on the website http://kppp.karnataka.gov.in and can be downloaded free of cost.

### Clarification of Tender Documents

  - A prospective Tenderer requiring any clarification on the Tender documents may notify the Employer in writing or by cable (hereinafter “cable” includes telex and fax/Email) at the Employer’s address indicated in the IFT. The Employer will respond to any request for clarification which he receives up to the pre-bid meeting date and time. Description of clarification sought and the response of the Employer will be uploaded for information of all the prospective tenderers without identifying the source of request for clarification.

  - Pre-Tender Meeting:

    - The Tenderer or his authorized representative is invited to attend a pre-Tender meeting which will take place at Office of The Chief Engineer KUWS&D Board, Kalaburagi Karnataka., at the date and time mentioned in the e-procurement portal.

    - The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage.

    - The tenderer is requested to submit any questions online through the e-procurement portal not later than the day of the meeting.

    - Minutes of the meeting, including the text of the questions raised (without identifying the source of enquiry) and the responses given will be uploaded on the web site https://kppp.karnataka.gov.in for the information all the prospective tenderers without identifying the source of questions raised. Any modification of the tender documents listed in Sub-Clause 7.1 which may become necessary as a result of the pre-tender meeting shall be made by the Employer exclusively through the issue of an Addendum pursuant to Clause 9 and not through the minutes of the pre-tender meeting.

    - Non-attendance at the pre-tender meeting will not be a cause for disqualification of a tenderer.

### Amendment of Tender documents

  - Before the deadline for submission of tenders, the Employer may modify the tender documents by issuing addenda / corrigendum which shall be posted on the e-procurement portal. https:// kppp.karnataka.gov.in

  - Any addendum/corrigendum thus issued shall be part of the tender documents and shall be notified as addendum/ corrigendum in the e-procurement portal, which shall be binding on all the prospective tenderers.

  - To give tenderers reasonable time in which to take an addendum / corrigendum into account in preparing their tenders, the Employer may extend as necessary the deadline for submission/uploading of tenders, in accordance with Sub-Clause 16.2 below. This shall be notified in the e-procurement portal.

## C.	PREPARATION OF TENDERS

### Documents comprising the Tender

The Tender submitted by the Tenderer shall be in two tender documents in e-procurement and shall contain the documents as mentioned below:

  - Technical Proposal (through e-Procurement Portal (https://kppp.karnataka.gov.in ):

- The Tender Documents and its Annexures shall be duly filled and signed by the tenderer.

  - Performance of the Tenderer showing value of Civil Engineering work for the past five financial years –Annexure-I

  - Annual Turnover (Civil Engineering works) for the last five financial years –Annexure-II

  - Experience in works of similar nature and magnitude within a period of 5 financial years –Annexure-I

  - Commitment of works on hand – Annexure-I

  - Works for which Tenders are already submitted –Annexure-I

  - List of Equipment’s available with Tenderer –Annexure-I

  - Qualification/Experience of key personnel proposed for technical and administrative functions under this contract – Annexure-III

  - Sample Format for evidence of access to or availability of credit facilities –Annexure-IV.

  - Details of Litigation – Annexure-V

  - Declaration by the Tenderer about black-listing etc. –Annexure-VI

  - Letter of Declaration (Annexure VIII)

  - Format for Power of Attorney for signing of Tender (Annexure – VIIA)

  - Format for Power of Attorney for Lead Partner of Joint Venture (Annexure VIIIB)

  - Format for Joint Venture Agreement to be executed and registered (Annexure VIIIC)

  - Format for AFFIDAVIT Regarding Correctness of Information Furnished and Documents Submitted (Annexure VIII D)

  - Format for Submission of Conceptual Scheme Report (Annexure – IX)

List of Certificates.

- Signature of both the Partners/Power of Attorney attested by the Notary Public

- Registration of the JV, signature of the authorized person attested by the Notary Public

- Proof of Registration of firm/Company

- Audited Balance Sheets

- Credit line Certificate from Financial Institutions – (Format-III)

- Income Tax Clearance Certificate

- Sales Tax / GST Verification Certificate

- Certificate of performance issued by not less than the rank of Executive Engineer of the organization.

- Any other material required to be done and submitted by the Tenderers in accordance with these instructions.

- Any other material required to be completed and submitted by the Tenderers in accordance with these instructions.

- Technical proposal Details cum Conceptual Scheme Report /Design of all the Water Supply Scheme components (see minimum prescribed format at Section 7 – Technical Specifications (Employer’s Requirement)).

- Proposal submitted for this water supply scheme shall consist (see format in this regard) but not limited to;

Water Supply System

  - Hydraulic calculations for rising main, pumping stations, based on preliminary levels.

  - Ensure that the design`s incorporate the water balance and Mass balance study.

  - Layout and hydraulic flow diagrams showing flow, pipe diameter, length, type of material etc., IS/referred code for calculations of pipe diameter, surge protection details.

  - General arrangement drawings for various units including OHTs etc.

  - Preliminary longitudinal sections for rising mains / bulk transmission mains and hydraulic flow diagrams showing flow, pipe diameter, length, type of material etc., IS/referred code for calculations of pipe diameter.

  - Electrical load calculations, transformer sizing calculations and any other major items.

  - Installation of Bulk water meter at all the outlet points in the water supply system to measure the production and supplied.

  - Type of Pump, power requirement and combined efficiency pump & motor considered.

  - Extent of area Private/Government considered and extent of land considered for each of the major items. The lands procured for the project shall be registered in the name of Handloom and Textile Department as per law.

  - Single Line Diagrams for all pumping stations.

  - Billing software and hardware system requirements.

  - Filled up formats as enclosed in the Tender document

- If the land to be acquired, the Tenderer is responsible for identify and facilitate to acquire the required land on behalf of Handloom and Textile Department. The land cost as per Guidance value only will be paid by the KUWSDB.

- All approvals from statutory bodies like respective NHAI, NH, Railways GESCOM, KPTCL, PWD, KRDCL, KSHIP, ULB, Forest and Revenue Department etc., is the responsibility of the Tenderer. However necessary documents required for the permissions would be provided by the KUWSDB. Necessary deposits will be paid by the KUWSDB based on the intimation received from the respective Dept.

- Details of O&M staff considered for effective operation and management of this water supply scheme with breakup of staff provided at each unit / facility /location with their skill.

- A preliminary base line schedule depicting all the major activities with their proposed duration shall also be submitted as part of the Technical Proposal. The duration shall not exceed the overall scheme duration of the Project

NOTE: This is a Design, Build, Operate & Transfer (DBOT) Tender, therefore, the Tenderers are expected to propose their best design along with land requirement within the overall framework of CPHEEO Guidelines/Standards/Technical Specification – Section 7 and other prescribed National/International standards/norms and terms & conditions of this Tender limiting the construction period and considering the given design parameters in this Tender document for various components in the system.

    - As a part of the technical proposal the Tenderer shall submit as detailed design as possible after actual site visit.

    - The proposed design shall be at least of the level of CSR (Conceptual Scheme Report) for this Water Supply Scheme.

    - The Evaluation Committee comprising of Subject matter experts shall evaluate the submitted design of the Tenderer.

    - In order to have utmost transparency in technical evaluation of the design, the minimum parameters which shall be covered in detail for the proposed design by Tenderer as part of the technical proposal (however, the format shall not be construed to limit the design and technical proposal that the Tenderer wishes to submit).

    - The Evaluation Committee shall evaluate the technical eligibility and the Conceptual Scheme for awarding the marks to the proposed design (water supply). The proposed design must score at least 70% marks in each (i.e., 70% in water supply design) to be considered as having qualified. Further, the proposed design must score at least 70% in each Item of the design. In case the proposed design fails to score at least 70% marks in each Item and overall 70% marks then the design shall be rejected & the Tender shall be declared as technically non-responsive.

    - In case the proposed design is rejected as per 10.1.5 by the Evaluation Committee then the Tender shall be declared as having failed in the technical evaluation and the Financial Proposal of such Tenderer shall not be opened.

    - The decision of the Evaluation Committee to accept or reject a proposed design as per 10.1.5 shall be final.

  - The Financial Proposal (through e-Procurement Portal(https://kppp.karnataka.gov.in)):

  - Any other materials required to be completed and submitted by Tenderers in accordance with these instructions. The documents listed under Sections 3, 4, 6 and 9 shall be filled in without exception.

### Tender prices

  - The contract shall be for the whole works as described in Sub-Clause 1.1, based on the financial proposal submitted by the Tenderer online. The tender prices should be inclusive of the prevalent duties excluding GST applicable as per GOI notification issued from time to time.

  - The Tenderer shall make online entries to fill in rates in the financial proposal in e-procurement portal. Upon numerical entry of the rates for the various items, the amount in words would automatically appear and the total tender price would automatically be calculated by the system and would be displayed. Items for which no rate or price is entered by the Tenderer will not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Financial Proposal.

  - The tender prices should be inclusive of all applicable duties (excluding GST), and other levies payable by the contractor under the contract (such as Royalty for minor minerals, Karnataka Building and other Construction Workers Welfare Cess), or for any other cause, Insurance, shall be included in the rates, prices and total Tender Price submitted by the Tenderer. The GST will be paid as per actual separately on production of documentary evidence for having paid GST for the said work.

Note: The contractors are required to procure the minor minerals from the government licensed query lease holders only obtaining the Mineral Dispatch Permits (MDPs) and produce these permits to the bills paying authorities. In such cases the royalty charges from the bills shall not be deducted. If the contractor fails to produce the Mineral Dispatch Permits, penalty at five times the applicable royalty charges along with the royalty from the bills of the contractor will be deducted as per the proceedings of the Director Mines and Geology Department Bangalore dated: 25.03.2018 or any latest amdentments/circulars.

  - The rates and prices quoted by the Tenderer of the Contract shall be subject to adjustment during the performance of the Contract in accordance with the provisions of Clause 40 of the Conditions of Contract

### Tender validity

  - Tenders shall remain valid for a period not less than 90 (Ninety) days after the deadline date for tender submission specified in Clause 16. A tender valid for a shorter period shall be rejected by the Employer as non-responsive.

  - In exceptional circumstances, prior to expiry of the original time limit, the Employer may request the Tenderers to extend the period of validity for a specified additional period. The request and the Tenderers responses shall be made in writing or by cable. A Tenderer may refuse the request without initiating action as stated in earnest money deposit. A Tenderer agreeing to the request will not be required or permitted to modify his tender, for the period of the extension, and in compliance with Clause 13 in all respects.

### Earnest Money Deposit

  - The Tenderers shall furnish, as part of his Tender, earnest money deposit in the amount as shown in column 4 of the Table of ITT for this particular work through e-procurement only. This earnest money deposit shall be submitted in e-Procurement Portal as per prescribed form & procedure in this regard.

    - Instruments having fixed validity issued as Earnest Money Deposit for the Tender shall be valid for 45 days beyond the validity period of the Tender.

  - Any Tender not accompanied by an acceptable earnest money deposit and not secured as indicated in Sub-Clauses13.1 and 13.2 above shall be rejected by the Employer as non-responsive. The Tenders must be accompanied by Earnest Money Deposit (EMD) of 
₹29.41 Lakhs. (Rupees Twenty Nine Lakhs and Fourty one Thousand Only), out of which ₹1,00,000/- (Rupees One Lakh only) shall be paid online through e - Procurement Portal using any of the following Payment Modes viz., Credit Card, Direct Debit, National Electronic Fund Transfer (NEFT), Over the Counter (OTC) and the balance amount of ₹28.41 Lakhs. (Rupees Twenty Eight Lakhs and Fourty one Thousand Only), in the form of Banker’s Cheque/Demand Draft/ Pay Order / Fixed Deposit Receipt or Unconditional Bank Guarantee (including e-Bank Guarantee) issued only from Nationalized Bank/ Scheduled Banks meaning as per the Section 2 (e) of the RBI Act 1934, in the Name of Chief Engineer, KUWS & D Board, Kalaburagi. The scanned copy of the original Bank Guarantee (including e- Bank Guarantee) shall be uploaded in the portal during bid proposal submission and the original Bank Guarantee (including e-Bank Guarantee) should be submitted to Office of the Chief Engineer, KUWS & D Board, Kalaburagi zone within 5 days from the last date of receipt of tender.

  - The Earnest Money Deposit of unsuccessful Tenderers will be returned within 30 days of the end of the tender validity period specified in Sub-Clause 12.1

  - The Earnest Money Deposit of the successful Tenderer will be discharged when the Tenderer has signed the Agreement and furnished the required Performance Security/Additional Performance Security if applicable.

  - The Earnest Money Deposit shall be forfeited:

a.	If the Tenderer withdraws the Tender after Tender opening during the period of Tender validity

b.	If the Tenderer does not accept the correction of the Tender Price, pursuant to Clause 24

c.	in the case of a successful Tenderer, if the Tenderer fails within the specified time limit to

i.	sign the Agreement

ii.	furnish the required Security Deposit.

d.	If the Tenderer submitted any morphed / forged / fail / wrong documents with respect the claims made under tender proposals.

### Format and signing of Tender

  - The Tenderer shall prepare the documents comprising the Tender as described in Clause 10 of these Instructions to Tenderers, and upload into the e-Procurement Portal. Ordinarily, the document as uploaded in e-Procurement Portal shall form the basis to decide the Tender.

  - The documents comprising the Tender shall be typed or written in indelible ink and shall be signed by a person or persons duly authorized to sign on behalf of the Tenderer. All pages of the Tender where entries or amendments have been made shall be initiated by the person signing the Tender and uploaded onto e-Procurement Portal(https:// kppp.karnataka.gov.in ).

  - The Tender shall contain no alterations or additions, except those to comply with instructions issued by the Employer, or as necessary to correct errors made by the Tenderer, in which case such corrections shall be initiated by the person signing the Tender.

## D.	SUBMISSION OF TENDERS

### Online Tender Submission

  - The Tenderers shall upload their tenders through e-procurement platform. No other modes of submission are permitted. The tendering is through website https://kppp.karnataka.gov.in. Detailed guidelines for viewing of tenders and submission of online tenders are given in the website. The prospective tenderers can submit their tender online. However, the tenderers are required to have enrolment/registration in the web site and should have valid Digital Signature Certificate (DSC). The DSC can be obtained from any authorized certifying agencies as given in the e-procurement portal. The tenderers should register in the web site https://kppp.karnataka.gov.in. After this, the tenderers can log in the site through the secured login for submission of their proposal

(i) technical proposal and required details as per Clause 10.

(ii) Financial Proposal.

  - The tenderers are requested to go through the tender documents carefully and submit the required information and documents without exception to avoid risk of rejection of tenders

  - The financial tender shall be in the required folder. All the documents are to be signed digitally by the tenderer. After electronic online tender submission, the system generates a unique tender reference number which is time stamped. This shall be treated as acknowledgement of tender submission.

  - Process of e-Tender Submission:

    - Tender Processing Fees and Downloading of Tender Document

Tenderer can download the Tender document for free from the portal (https://kppp.karnataka.gov.in) till the due date and time for Tender submission. Tenderer shall pay the Tender processing fees prescribed in the e-Procurement portal to participate in this Tender. The Tender processing fee has to be paid through any of the four e-payment options in the portal:

•	Credit Card

•	Direct Debit

•	National Electronic Funds Transfer (NEFT)

•	Over the Counter (OTC)

Please note that payments submitted through cheque or demand draft shall not be accepted. Further details regarding e-Payment, please refer to e-Procurement portal at the above-mentioned website or call e-procurement helpline +91-8046010000 +91-8068948777.The details of Tender Processing Fee shall be filled in the FORM given in Section 4 and upload in the e- procurement portal at appropriate section.

Note: It will be in the interest of the Tenderers to familiarize themselves with the e- Procurement system to ensure smooth preparation and submission of the Tender documents.

  - Authentication of Tender

The responsive Tender shall be signed by the Tenderer or a person duly authorized to sign by the Tenderer. A letter of authorization shall be supported by a written power-of-attorney accompanying the Tender. All pages of the Tender, except for un-amended printed literature, shall be initiated and stamped by the person or persons signing the Tender.

### Deadline for submission of the Tenders

  - Tenders must be uploaded all the documents before the due date as notified in e-procurement Portal. The e-procurement platform will not accept the tenders after the stipulated date and time (as per the clock of the e-procurement platform)

  - The Employer may extend the deadline for submission of tenders by issuing an amendment in accordance with Clause 9, in which case all rights and obligations of the Employer and the Tenderers previously subject to the original deadline will then be subject to the new deadline as extended. The amendment/notification shall be notified in the e-procurement platform.

### Late Tenders

  - Tenders cannot be uploaded by the tenderers after the deadline for submission / uploading of tenders (as per the clock of the e-procurement platform) prescribed by the Employer.

### Modification and Withdrawal of Tenders

  - Tenderers may modify Tenders in e-Procurement Portal or withdraw their Tenders before the deadline prescribed in Clause 16 through Karnataka Transparency in Public Procurements Portal (https:// kppp.karnataka.gov.in).

  - Tenderers may cancel / modify their tenders before the deadline for submission of the tenders.

  - For modification of tenders, the tenderers need not make any additional payment towards the cost of tendering process. For tender modification and consequent re-submission, the tenderer is required to cancel his bid submitted earlier (only the financial is cancelled. All the uploaded documents would be there). The last modified tender submitted by the tenderer within the tender submission time shall be considered as the tender. For this purpose, modifications / withdrawal by other means will not be accepted. In online system of tender submission, the modification/cancellations is allowed any number of times. The tenderers may cancel its bid by clicking on the cancel button in the MY Bids Section before the deadline for submission of tenders, however if the tender is cancelled and not resubmitted within the stipulated time on the last date of submission of tenders, it would deemed to be withdrawn.

  - As per the system design, in case a tenderer wishes to modify his tender before the ; last date and time for submission of tenders and after submission of the tender, then the tenderer is required to withdraw his bid first. In order to provide a quick reference to his financial tender entered by the tenderer in the e-procurement system, a provision has been made in the e-procurement system wherein the tenderer can retain a copy of the financial tender in his local machine prior to his submission of tender. The values as available in the copy of the financial tender can subsequently be copied into the financial tender screen which then is made available to the tenderer on withdrawal of his tender price to last date and time of tender submission.

  - No tender may be modified/cancelled online after the deadline for submission of tenders.

  - Withdrawal or modification of a Tender between the deadline for submission of Tenders and the expiration of the original period of Tender validity specified in Clause 12.1 above or as extended pursuant to Clause 12.2 is not allowed in the e-procurement system.

## E.	TENDER OPENING AND EVALUATION

### Opening of Technical proposal of all Tenders and evaluation to determine technically qualified Tenderers:

  - The Employer will open the Technical proposal of all the Tenders received at the specified date and time mentioned in the e-Procurement Portal. The intimation regarding opening of tenders shall communicated on the through the e-procurement portal. In the event of the specified date of Tender opening being declared a holiday for the Employer, the Tenders will be opened at the appointed time and location on the next working day.

  - The Employer shall first undertake evaluation of the (I) Technical Proposal as per this Tender document and details contained hereinafter.

  - The Employer will evaluate and determine whether each Tender-

a.	meets the eligibility criteria defined in Clause 2 & 3 of ITT & is not otherwise disqualified as per this Tender;

b.	is accompanied by the required earnest money deposit as per stipulations in ITT Clause

c.	meets the minimum qualification criteria stipulated in Clause 3 of ITT.

d.	the technical proposal of the Tenderer qualifies in the evaluation by the “Evaluation Committee”

e.	Technical presentation on the CSR & Design of all the components of Water supply system by the tenderer shall be made be made to Evaluation Committee.

  - Technical Proposal Details to the extent of Conceptual Scheme Report (CSR)/Design of Water Supply Scheme submitted as part of technical proposal shall be evaluated by Evaluation Committee as part of Technical evaluation. If the Tenderers’ Technical Proposal fails to score minimum prescribed marks as defined in Annexure – IX, then such Technical proposals shall be rejected though they have qualified.

    - The Evaluation Committee shall evaluate and award marks to the proposed design. The proposed design must score more than 70% marks for technical qualification. Further, the proposed design must score at least 70%, or such other prescribed minimum marks, in each Item of the design. In case, the proposed design fails to score at least 70% marks in each Item (or such marks as may be prescribed) and overall 70% marks then the design shall be rejected & the Tender shall be declared as technically non-responsive.

    - Pursuant to Clause 19.4.1, in case the proposed design of any Tenderer is rejected by the Evaluation Committee, then such Tenderers shall be declared as having failed in the technical evaluation.

    - The decision of the Evaluation Committee to accept or reject a proposed technical proposal/design as per Clause 19.4.1 shall be final and binding.

  - The tenderer has to give detailed technical presentation on the process, methodology, material of construction of the proposed technology, confirming to tender clause & specification and with relevant details as requested by the Employer.

### Opening of Financial Proposal of qualified Tenderers and evaluation: As per                e-Portal

  - The Employer will inform all the Qualified Tenderers the time, date and venue fixed for the opening of the Financial Proposal. The Employer will open the Financial Proposal of only the technically qualified Tenderers at the specified time and date mentioned on e-procurement portal. In the event of the specified date of Financial Proposal opening being declared a public holiday, the Financial Proposal shall be opened on the next working-day.

### Process to be confidential

  - Information relating to the examination, clarification, evaluation, and comparison of Tenders and recommendations for the award of a contract shall not be disclosed to Tenderers or any other persons not officially concerned with such process until the award to the successful Tenderer has been announced. Any effort by Tenderer to influence the Employer’s processing of Tenders or award decisions may result in the rejection of his Tender.

### Clarification of Tenders

  - To assist in the examination, evaluation, and comparison of Tenders, the Employer may, at his discretion, ask any Tenderer for clarification of his Tender, including breakdowns of unit rates. The request for clarification and the response shall be in writing or by cable, but no change in the price or substance of the Tender shall be sought, offered, or permitted.

  - Subject to sub-clause 22.1, no Tenderer shall contact the Employer on any matter relating to its Tender from the time of the Tender opening to the time the contract is awarded.  If the Tenderer wishes to bring additional information to the notice of the Employer, it should do so by uploading on the e-procurement portal.

  - Any effort by the Tenderer to influence the Employer in the Employer’s Tender evaluation, Tender comparison or contract award decisions may result in the rejection of the Tenderers’ Tender.

### Examination of Tenders and determination of responsiveness

  - Prior to the detailed evaluation of Tenders, the Employer will determine whether each Tender; (a) has been properly signed; and; (b) is substantially responsive to the requirements of the Tender documents.

  - A substantially responsive Tender is one which conforms to all the terms, conditions, and specifications of the Tender documents, without material deviation or reservation. A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of the Works; (b) which limits in any substantial way, inconsistent with the Tender documents, the Employers rights or the Tenderer's obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other Tenderers presenting substantially responsive Tenders.

  - If a Tender is not substantially responsive, it will be rejected by the Employer, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation. All conditional Tenders shall summarily be rejected irrespective of their qualification.

### Correction of errors

  - Tenders which are determined to be substantially responsive will be checked by the Employer for any arithmetic errors. Errors will be corrected by the Employer as follows:

(a)	where there is a discrepancy between the rates in figures and in words, the lower of the two shall prevail/govern; and

(b)	where there is a discrepancy between the unit rate and the line-item total resulting from multiplying the unit rate by the quantity, the unit rate as quoted will govern.

  - The amount stated in the Tender will be adjusted by the Employer in accordance with the above procedure for the correction of errors and, with the concurrence of the Tenderer, shall be binding upon the Tenderer. If the Tenderer does not accept the corrected amount the Tender will be rejected, and the earnest money deposit may be forfeited in accordance with Sub-Clause 13.6(b).

### Evaluation and comparison of Tenders

The Employer will open the Financial-Tender of only the technically qualified Tenders as per Clause 3, 10, 19 & 23; and evaluate and compare the Financial-Tender as per this Tender document.

Note: The bid will be compared with the prevailing SR of Uni-SoR (Common SR) / GESCOM/ KPTCL SRs as on the last date of submission of tenders.

  - In evaluating the Tenders, the Employer will determine for each Tender the evaluated Tender Price by adjusting the Tender Price as follows.

a.	making an appropriate adjustment for acceptable variations, deviations;  and

b.	making appropriate adjustments to reflect discounts or other price modifications offered in accordance with Clause 18.

c.	Evaluate the quoted OPEX cost to the net present value by the method of discounting factor. Lowest offer would be evaluated on the basis of sum total of “Total quoted CAPEX cost” and “Total NPV of quoted OPEX cost for 5 years including defect liability for period of 1 year”. As demonstrated in the preamble of the financial proposal.

  - The Employer reserves the right to accept or reject any variation, deviation or alternative offer. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the Tender documents or otherwise result in unsolicited benefits for the Employer shall not be taken into account in Tender evaluation.

  - The estimated effect of the price adjustment conditions under Clause 40 of the Conditions of Contract, during the implementation of the Contract, will not be taken into account in tender Evaluation.

  - If the tender of the successful tenderer is seriously unbalanced in relation to the Employer’s estimate of the cost of the work to be performed under the contract, the Employer may require the Tenderer to produce detailed price analyses for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, the Employer may require that the amount of the performance security set forth in Clause 29 be increased at the expense of the successful Tenderer to a level sufficient to protect the Employer against financial loss in the event of default of the successful under the contract. The Format of the Bank Guarantee is given in Section10. The Bank Guarantee shall be valid until 28 days from the date of issue of certificate of completion of works.

*(Unbalanced Tender is defined as a tender where the tender premium is negative beyond 10%. Additional Security shall be collected for all Tenders whose Tender Premium is negative beyond 10%, and no Additional Security shall be collected for all tenders whose Tender Premium is up to Minus 10%. Additional Security shall be collected only to the extent of negative premium beyond minus 10%).

## F.	AWARD OF CONTRACT

### Award criteria

  - Subject to Clause 27, the Employer will award the Contract to the Tenderer whose Tender has been determined to be substantially responsive to the Tender documents and who has offered the lowest evaluated Tender Price, provided that such Tenderer has been determined to be (a) eligible in accordance with the provisions of Clause 2, and (b) qualified in accordance with the provisions of Clause 3.2.

### Employer’s right to accept any Tender and to reject any or all Tenders

  - Notwithstanding Clause 26, the Employer reserves the right to accept or reject any Tender, and to cancel the Tender process and reject all Tenders, at any time prior to the award of Contract, without thereby incurring any liability to the affected Tenderer or Tenderers or any obligation to inform the affected Tenderer or Tenderers of the grounds for the Employer’s action.

### Notification of award and signing of Agreement

  - The Qualified Tenderer whose Tender has been accepted will be notified of the award by the Employer prior to expiration of the Tender validity period by cable, telex, e-mail or facsimile confirmed by registered letter. This letter (hereinafter and in the Conditions of Contract called the "Letter of Acceptance") will state the sum that the Employer will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the "Contract Price").

  - The notification of award will constitute the formation of the Contract, subject only to the furnishing of Security deposit in accordance with the provisions of Clause 29.

  - The Agreement will incorporate all agreements between the Employer and the successful Tenderer. It will be kept ready for signature of the successful Tenderer in the office of Employer within 30 days following the notification of award along with the Letter of Acceptance. Within 20 days of receipt of notification of award, and upon furnishing of the Performance Security as required (including the additional performance security for unbalanced tender) the successful Tenderer will sign the Agreement.

  - Upon signing of the Agreement, the Employer will promptly notify the other Tenderers that their Tenders have been unsuccessful.

### Security Deposit / Performance Security

  - Within 20 days of receipt of Letter of Acceptance, the successful Tenderer shall deliver to the Employer the following unconditional Security Deposits in any of the forms given below in accordance with Clause 43 of the Conditions of Contract.

(i)	for an amount equivalent to 5% (or as per prevailing GO) of the Contract price for CAPEX plus Additional Security for unbalanced tenders * valid until a date 30 days beyond the date of completion of Defects Liability Period that shall be released on submission of Security Deposit (5% of OPEX applicable for the O&M Period as below and issue of town wise Completion Certificate for CAPEX by the Employer. Additional Security for unbalanced tenders in full* for OPEX portion town wise shall be submitted during concluding of agreement in the form of Demand Draft and will be released after completion of 30 days beyond the date of completion of respective O&M periods.

(ii)	for an amount equivalent to 5% of the OPEX (Operation & Maintenance) valid until a date 30 days beyond the date of completion of respective O&M period (s) that shall be released after successful handing over of scheme to Handloom and Textile Department.

Performance Security shall be submitted in the form:

-	Banker’s Cheque/Demand Draft/ Pay Order / Fixed Deposit Receipt or Unconditional Bank Guarantee (including e-Bank Guarantee) in the name of Executive Engineer, KUWS&DB, Kalaburagi.

-	In case of Additional Security for Unbalanced Tender only Demand Draft shall be acceptable for O&M part.

-	Un-conditional bank guarantee in the form given in Section-10 (Form of Bank Guarantee)

*(Unbalanced Tender is defined as a tender where the tender premium is negative beyond 10%. Additional Security shall be collected for all Tenders whose Tender Premium is negative beyond 10%, and no Additional Security shall be collected for all tenders whose Tender Premium is up to Minus 10%. Additional Security shall be collected only to the extent of negative premium beyond minus 10%).

  - If the security deposit is provided by the successful Tenderer in the form of a Bank Guarantee (including e-Bank Guarantee), it shall be issued either by a Nationalized / Scheduled Bank (Scheduled Bank shall mean a bank as defined under Section 2(e) of the Reserve Bank of India Act, 1934)

  - Deleted.

  - Failure of the successful Tenderer to comply with the requirements of Sub-Clause 29. 1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Earnest Money Deposit and will be debarred as per the procedure laid under the KTPP Rule 26, 26A, 26B and 26C.

  - The Unconditional Security deposit will be discharged by the Employer and returned to the contractor not later than 30 days following the date of issue of certificate of completion of the defect’s liability period under the Contract. The Performance Security towards CAPEX cost will be released after furnishing of the Performance Security for OPEX for 5 years if O & M is carried out with supplementary agreement between KUWS& DB and Contractor. The unconditional security deposit towards OPEX, will be released to the contractor not later than 30 days, after successful handing over of the scheme to Handloom and Textile Department.

### Advance Payment and Security:

  - The Employer will provide an advance payment (for mobilization) on the contract price (excluding operation and maintenance Charges) as stipulated in the Conditions of Contract, subject to the maximum amount as stated in the Contract Data. The advance payment shall be made on submission of the Unconditional Bank Guarantee for an equal amount in the Form as given in Section 10. The secured advance against materials brought to site of work is also payable subject to fulfilment of conditions as given in the Contract Data.

### Corrupt or Fraudulent practices

  - The KUWS & DB require that the Tenderers/Suppliers/Contractors, observe the highest standard of ethics during the procurement and execution of such contracts.  In pursuance of this policy, KUWS&DB:

(a)	will reject a proposal for award if it determines that the Tenderer recommended for award has engaged in corrupt or fraudulent practices in competing for the contract in question;

(b)	will declare a firm ineligible, either indefinitely or for a stated period of time, to be awarded a KUWS&DB contract if it at any time determines that the firm has engaged in corrupt or fraudulent practices in competing for, or in executing, a KUWS&DB contract.

  - Furthermore, Tenderers shall be aware of the provision stated in sub-clause 49.2 of the Conditions of Contract.

TENDER DATA SHEET

Contents of this Tender Data Sheet shall complement, supplement, or amend the provisions in the Instructions to Tenderers (ITT). Wherever there is a conflict, the provisions herein shall prevail over those in ITT.

| Clause Reference | Description |
| --- | --- |
| Clause 2.2 | ##### Tenders from Joint Ventures are acceptable. The number of entities forming Joint Venture shall be limited to THREE (3). Tenderer shall mean a single entity or a group of entities (the “Joint Venture”) coming together, as the case may be, to implement the Project. However, no Tenderer applying individually or as a member of a Joint Venture, as the case may be, can be a member of another Joint Venture. The term Tenderer used herein would apply to both, single entity and Joint Venture. |
| Clause 2.3 | ##### The Tenderer (Single Entity / Joint Venture) shall be a company registered under The Indian Companies Act 1956/2013 or partnership firm registered under The Indian Partnership Act 1932. |
| Clause 2.4 | ##### In case of Joint Venture ###### 2.4.1 One of the partners, who is responsible for performing a key function as per the Joint Venture Agreement or is executing a major component of the proposed contract, shall be nominated as being in-charge (hereinafter referred to as “Lead Partner”) for tendering period and, in the event of a successful tender, during contract execution. The Lead Partner shall be authorized to incur liabilities and receive instructions / take up all the matter related to the contract management and implementation for and on behalf of any and all partners of the joint venture; this authorization shall be evidenced by submitting a Power of Attorney signed by legally authorized signatories of all the partners. ###### 2.4.2 All partners of the Joint Venture shall be legally liable, jointly and severally, during the tendering process and for the execution of the contract in accordance with the contract terms, and a statement to this effect shall be included in the authorization mentioned in the above Clause. All members of the Joint Venture must have experience in execution of similar works stated in clause 3.2. ###### 2.4.3A copy of the Joint Venture Agreement (JVA) entered into by the partners with duly Notarized shall be uploaded with the Tender submission. Pursuant to Sub-Clauses 2.4.1 and 2.4.2 above, the JVA shall include among other things: the ’VA's objectives; the proposed management structure; the contribution of each partner to the joint venture operations; the commitment of the partners for joint and several liability for due performance; recourse/sanctions within the JVA in the event of default or withdrawal of any partner; and arrangements for providing the required indemnities. |
| Clause 3.3.C | Technical, administrative, and managerial personnel proposed to be employed for key site management in this work with their qualification details should be furnished in Annexure – III. |
| Clause 3.3.D | Litigation details of the Tenderers with the details of the parties concerned and the amount involved should be furnished in Annexure-V. |
| Clause 3.8 | ##### Technical Proposal Details to the extent of Conceptual Scheme Report (CSR)/Design of Water Supply Scheme shall be submitted as part of technical proposal by the Tenderer. NOTE: This is a Design, Build, Operation & Transfer (DBOT without variation) mode Lump sum tender, therefore, the Tenderer are expected to propose their best design along with land acquisition within the overall framework of CPHEEO Guidelines/Standards and other prescribed National/International standards/norms and terms & conditions of this Tender limiting the construction period to 24 months which includes 02 month for survey & design & 03 month for Trail run and commissioning and considering the given design parameters in this Tender document for various components in the system. The Tenderer shall be responsible for the operations and Maintenance of the project facilities for a period of 60 months including 1 year of DLP, from the date of commissioning the project. 3.8.1 As a part of the technical proposal the Tenderer shall submit technical proposal/design as far as possible after actual site visit. 3.8.2 The proposed design shall be at least of the level of CSR (Conceptual Scheme Report) for Water Supply Scheme prepared by the KUWSDB. 3.8.3 Tender Evaluation Committee comprising of subject experts shall evaluate the CSR proposal/design submitted by the Tenderer. The Tenderer will have to make a detailed presentation on the proposed design to the committee during evaluation. 3.8.4 In order to have utmost transparency in technical evaluation of the design, the minimum parameters which shall be covered (in detail) for the proposed design by Tenderer as part of the technical proposal (however, the format shall not be construed to limit the design and technical proposal that the Tenderer wishes to submit). Proposal submitted for this water supply scheme shall consist (see format in this regard) but not limited to; Water Supply System - Technical surveys (Total Station Survey, Soil Investigations including trial pits and SBC of Soil, Core log , bathometric survey as applicable and Customer survey for providing connections. - Hydraulic calculations for intake, Pumping mains, pumping stations, based on preliminary levels. - Layout and hydraulic flow diagrams showing flow, pipe diameter, length, type of material etc., IS/referred code for calculations of pipe diameter, surge protection details. - General arrangement drawings for various units from tapping point to Service reservoir - Preliminary longitudinal sections for rising mains / bulk transmission mains and hydraulic flow diagrams showing flow, pipe diameter, length, type of material etc., IS/referred code for calculations of pipe diameter. - Installation of Bulk water meter near tapping point in the water supply system to measure the production and supplied. - Extent of area Private/Government considered and extent of land considered for each of the major items. The lands procured for the project shall be registered in the name of the Handloom and Textile Department by the Successful Tenderer - Filled up formats as enclosed in the Tender document - Filled up formats as enclosed in the Tender document - All approvals from statutory bodies like Railways, NH ESCOM, KPTCL, KSHIP, Forest, BWSSB/KUWSDB/ULB, NHAI PWD etc., is the responsibility of the bidder. However necessary documents required for the permissions would be provided by the KUWSDB/ULB. Necessary deposits will be paid by the KUWSDB based on the intimation received from the respective Departments. - The Consultant/technical expert who has helped/assisted the department in any form for preparing the proposal of this scheme cannot be a consultant for the Tenderer during preparation CSR/DSR/designs/ execution or in any form which leads to conflict of interest of the department & fraudulent practice. - A preliminary base line schedule depicting all the major activities with their proposed duration shall also be submitted as part of the technical proposal. The duration shall not exceed the overall scheme duration of the Project. - If the land to be acquired, the Tenderer is responsible for identify and facilitate to acquire the required land on behalf of Handloom and Textile Department. The land cost as per Guidance value only will be paid by the KUWSDB/ Handloom and Textile Department. - The O&M cost shall be borne by the Handloom and Textile Department. The O&M agreement shall come into effect after completion of the construction activities after successful commissioning of the project. - The employer shall not be liable for any compensation in the event of non-Commencement of O & M due to non-receipt of O& M fund from Handloom and Textile Department. |
| Clause 3.9 | The work done experience in similar Water Supply projects executed by the Tenderer in any of the Central / State Government Departments / Quasi Government Organizations and Government Undertakings shall have to be submitted along with the tender. Work done certificates issued by the concerned officer not below the rank of Executive Engineer or Employer who has executed the agreement from Central / State Government Department / Undertaking / Quasi Government Organization should be submitted for each qualifying project submitted by the Tenderer as part of evaluation under Clause 3.2. The experience certificates issued by an officer below the rank of Executive Engineer / Employer who has executed the agreement or on behalf of Executive Engineer/ Employer who has executed the agreement will not be considered. |
| Clause 3.10 | For the experience certificates furnished by the Tenderers which are obtained from the departments outside the State, clarification will be obtained by the Employer from the concerned department whenever felt necessary as to whether the details furnished in the certificates are genuine, before finalization of evaluation. Employer reserve the right verifies the certificates / credentials submitted by the Tenderer(s). |
| Clause 3.11 | ##### If the documents of any Tenderer are not found to be genuine at any stage during or after tender process, then such Tenderer shall be disqualified and EMD/ Performance Security / Additional Security shall be forfeited as the case may be and the Tenderer shall be subject to penal action as deemed fit by the Employer. |
| Clause 19.4 | ##### Technical Proposal Details to the extent of Conceptual Scheme Report (CSR)/Design of Water Supply Scheme submitted as part of Technical Proposal shall be evaluated by TATSC as part of technical evaluation. If the Tenderers’ Technical Proposal fails to score minimum prescribed marks as defined in Annexure – IX, then such Technical Proposals shall be rejected though they have met the qualification criteria as per Clause 3.2 of ITT. ##### 19.4.1 The TATSC shall evaluate and award marks to the proposed design. The proposed design must score more than 70% marks for technical qualification. Further, the proposed design must score at least 70%, or such other prescribed minimum marks, in each module of the design. In case, the proposed design fails to score at least 70% marks in each module (or such marks as may be prescribed) and overall, 70% marks then the design shall be rejected & the Tender shall be declared as technically non-responsive. ##### 19.4.2 Pursuant to Clause 19.4, in case the proposed design of any Tenderer is rejected by the TATSC, then such Tenderers shall be declared as having failed in the technical evaluation. ##### 19.4.3 The decision of the TATSC to accept or reject a proposed Technical Proposal/design as per Clause 19.4 shall be final and binding. |

SECTION 3:

QUALIFICATION INFORMATION

ANNEXURE-I

# SECTION 3: QUALIFICATION INFORMATION

(To be submitted by Single Entity and each Partner in case of JV)

The information to be filled in by the Tenderer hereunder will be used for purposes of computing Tender capacity as provided for in Clause 3 of the Instructions to Tenderers. This information will not be incorporated in the Contract.

  - Constitution or legal status of Tenderer[Attach copy]

Place of Registration

Principal place of business:

  - Total value of civil engineering construction works executed and payments received in the last five years ………….. (in Rs. Crores)

2021-22……………….

2022-23……………….

2023-24……………….

2024-25……………….

2025-26……………….

  - Work performed as Prime Contractor (in the same name) on works of  water supply  during the five years specified in 1.2 above.

| Project Name | Name of Employer | Description of Work | Contract Number | Value of Contract ₹ (Cr) | Date of issue of work order | Specified period of completion | Actual Date of completion | Remarks explaining reason for delay/ incompletion of work |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |

  - Quantities of work executed as prime contractor (in the same name) during the last five years specified in 1.2above:

| Sl No | Year | Name of Work | Name of Employer | Quantity of work performed | Remarks (Indicate contract reference) |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Pipeline work (MS/DI/HDPE or in combination) in Km. |  |
| (1) | (2) | (3) | (4) | (5) | (6) |

  - Information on works for which Tenders have been submitted and works which are yet to be completed as on the date of this Tender.

- Existing commitments and on-going works:

| SL NO. | Description of Work | Place & State | Contract No. & Date | Name and Address of Employer | Value of Contract (₹ Cr) | Stipulated period of completion | Value of works remaining to be completed (₹ Cr) | Anticipated date of completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |

- Works for which Tenders already submitted:

| SL NO. | Description of Work | Place & State | Name and Address of Employer | Estimated value of works (₹ Cr) | Stipulated period of completion | Date when decision is expected | Remarks if any |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |

  - The following items of equipment are considered essential for successfully carrying out the works. The Tenderer should furnish all the information listed below

| Item of Equipment | Requirement |  | Availability Status |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | No. | Capacity | Owned/Leased/ to be Procured | Number/ Capacity | Age/ Condition |  |

Attach Certificates

| Item of Equipment | Requirement |  | Owned | Owned and available |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  | No | Capacity |  | Number/Capacity | Age/Condition |  |

  - Reports on the financial standing of the Tenderer, such as profit and loss statements and auditor’s reports for the last five years;

  - Qualification and experience of the key technical and management personnel in permanent employment with the Tenderer and those proposed to be deployed on this contract, if awarded.

  - Name, address, telephone, telex, and fax numbers of the Tenderers’ bankers who may provide references if contacted by the Employer.

  - Evidence of access to financial resources to meet the qualification requirement specified in ITT Clause3.3 (b): Cash in hand, Letter of Credit etc. List them below and attach certificate from the Banker in the suggested format provided at Annexure– IV.

  - The proposed methodology and program of construction, backed with equipment planning and deployment, duly supported with broad calculations and quality control procedures proposed to be adopted, justifying their capability of execution and completion of the work as per technical specifications within the stipulated period of completion as per milestones.

ANNEXURE-II

#### CERTIFICATE FROM STATUTORY AUDITOR FOR ANNUAL TURNOVER

(To be submitted by Single Entity and each Partner in case of JV )

#### (To be on the letterhead of the statutory auditor with registration number)

#### This is to certify that M/s________________ registered under _________________and having it head office at ______________________has the following Annual Turnover in the last five years.

2021-22………………. Rs Crores

2022-23………………. Rs Crores

2023-24………………. Rs Crores

2024-25………………. Rs Crores

2025-26………………. Rs Crores

#### ANNEXURE-III

Qualification/Experience of key personnel proposed for staff for site management and execution of works under this contract

| No. | Position | Number Required | Minimum Qualification | Total Work Experience [years] | Experience In Similar Works [years] |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Manager/Water Supply | 1 | Graduate in Civil Engineering with Post Graduation in Construction Management/MBA (Finance/operations) | 10 | 5 years in construction supervision of water supply projects |
| 2 | Water supply Engineer | 2 | Full time Post Graduate in Civil/ Environmental Engineering | 5 | 3 years in design/execution of water supply projects |
| 3 | Project Engineers | At least 1 per Site | Bachelor/Diploma in Civil/Electrical/Mechanical Engineering. | 5/7 | Overall, 5 years for Bachelor / 7 years for Diploma Engineering, with 2 years of relevant construction supervision experience of water supply, used water, drainage infrastructure projects. |
| 4 | Safety/ Environment Expert | At least 1 per Site | Bachelor’s Degree in Engineering/relevant field. | 7 | 7 years relevant experience in construction safety, monitoring of HSE compliance. |

Qualification/Experience of other Key Personnel proposed for the technical and administrative functions under this contract

| Sl. No | Name of the staff | Proposed Position | Qualification | Total Years of Experience | Years of Experience in the proposed position | Remarks |
| --- | --- | --- | --- | --- | --- | --- |

Seal of the firm	Signature of the Tenderer with date

#### ANNEXURE-IV

BANKER’S CERTIFICATE

(To be submitted by Single Entity and each Partner in case of JV)

The bidder should submit the Banker’s Certificate as per the Circular from Finance Department No: FD-CAM/16/2022(p-2) Dated: 22-08-2022., which is given below Format

Reference Number (SL NO) Place:

Date:

To:

[Name & Address of the beneficiary]

This is to certify that M/s. …………………………. Having his/their registered / administrative office at __________ is a customer of our Bank and is/are engaged in ___________. If the said condition is allotted/awarded with__________ [brief details of works] we may extend credit facilities up to Rs. _____ Lakh, to meet his/their working capital requirement towards the execution of the said work order as per Loan policy of the Bank.

This certificate is valid up to three months from the date of issue, that is up to dd/mm/yyyy.

Yours faithfully.

Bank Manger

NOTE: If the Banker Certificate is conditional then the bid proposal is liable for rejection.

#### ANNEXURE-V

  - Information on litigations in which the Tenderer is involved:

  - (To be submitted by Single Entity and each Partner in case of JV)

| Sl No. | Other Parties | Employer | Details of dispute | Amount involved | Remarks showing present status |
| --- | --- | --- | --- | --- | --- |

Attach certificates from the respective Employers.

#### ANNEXURE-VI

Declaration by the Tenderer for Not being Blacklisted:

(To be submitted by Single Entity and each Partner in case of JV)

It is to certify that our firm I.......................................................................... has not been black listed /banned / debarred by any Central/ State / UT Government Department or Undertaking / Organization.

Seal Tenderer

...................................... .......................................

(Signature of the Tenderer)

Note: It it is found at any stage during the bid processing or later that bidder / tenderer has submitted falsified information or misrepresented that facts , the Employer shall have right to reject the bids / terminate the agreement  as the case may be. It is further clarified that the EMD/Performance Security / Additional Performance Security or as appropriate may also be forfeited in part or ful by the Employer.

#### Annexure-VIIA

Format for Power of Attorney for signing of Tender

(Refer Clause 10.1)

(To be submitted by Single Entity and Lead Partner in case of JV)

Know all men by these presents, we, ____________________(name of the firm and address of the registered office) do hereby irrevocably constitute, nominate, appoint and authorize Mr./ Ms.________________________(name), son/daughter/wife of and presently residing at ________________, who is presently employed with us and holding the position of___________, as our true and lawful attorney (hereinafter referred to as the “Attorney”) to do in our name and on our behalf, all such acts, deeds and things as are necessary or required in connection with or incidental to submission of our Tender for ‘_________’ (the “Project’) proposed or being developed by the KUWS&DB, Bangalore  (the “Employer”) including but not limited to signing and submission of all applications, tenders and other documents and writings, participate in pre-tender and other conferences and providing information/ responses to the Employer, representing us in all matters before the Employer, signing and execution of all contracts including the agreement and undertakings consequent to acceptance of our Tender, and generally dealing with the Employer in all matters in connection with or relating to or arising out of our Tender for the said Project and/ or upon award thereof to us and/or until the entering into of the Contract with the Employer.

AND we hereby agree to ratify and confirm and do hereby ratify and confirm all acts, deeds and things done or caused to be done by our said Attorney pursuant to and in exercise of the powers conferred by this Power of Attorney and that all acts, deeds and things done by our said Attorney in exercise of the powers hereby conferred shall and shall always be deemed to have been done by us.

IN WITNESS WHEREOF WE, ____________, ___________AND______________, THE ABOVE NAMED PRINCIPAL HAVE EXECUTED THIS POWER OF ATTORNEY ON THIS I OF 20.....

For 	.

(Signature, name, designation and address)

of person authorized by Board Resolution

(In case of Firm/ Company)

Witnesses:

Accepted

(Signature)

(Name, Title and Address of the Attorney)		(Notarized)

Person identified by me/ personally appeared before me/
Attested/ Authenticated*
(*Notary to specify as applicable) 
(Signature Name and Address of the Notary)

Seal of the Notary Registration No. of the Notary Date:

Notes:

- The mode of execution of the Power of Attorney should be in accordance with the procedure, if any, laid down by the applicable law and the charter documents of the executant(s) and when it is so required, the same should be under common seal affixed in accordance with the required procedure.

- Wherever required, the Tenderer should submit for verification the extract of the charter documents and documents such as a board or shareholders’ resolution/ power of attorney in favour of the person executing this Power of Attorney for the delegation of power hereunder on behalf of the Tenderer.

ANNEXURE-VIII

Letter of Declaration

(To be submitted by Single Entity and each Partner in case of JV )

Date:

To:

_________

__________

Dear Sir / Madam,

Sub: “___________” [mention the name of Project]

This has reference to the Tender being submitted by _______ [mention the name of the Tenderer / Lead Partner of the Joint Venture), as Single Entity/ Lead Partner of the Joint Venture comprising _________ and ______ [mention name(s) of the Partners] in respect of Selection of Tenderer for ________________ [mention the Name of the Project] in response to the Tender Document issued by the Employer dated _____.

We hereby confirm the following:

- We ________ [mention the name of the Tenderer/JV Partner furnishing the Letter of Declaration], have examined in detail and have understood and satisfied ourselves regarding the contents including in respect of the following:

- For the purpose of all subsequent communications with the Employer, the Tenderer shall be represented by ________ [mention name of the authorized representative of the Tenderer/Lead Partner];

{The Joint Bidding Agreement has been signed between/among_____, ____ and ______ [mention the names of the Partners], as Partners of the Joint Venture; and the Tender is being submitted on behalf of the Joint Venture by _____ [mention the name of the Lead Partner].}

- We have satisfied ourselves regarding our role as [here give a brief description of the role] in the Project as specified in the Tender. If the Tenderer/Joint Venture is awarded the Project, we shall perform our role as outlined in the Tender to the best of our abilities. We have examined the Tender in detail and the commitments made in the same. We agree and undertake to abide by the Tender and the commitments made therein.

We authorize ____________ [mention name of the authorized representative of the Tenderer/Lead Partner], as the Authorized Representative and authorize the same to perform all tasks including, but not limited to providing information, responding to enquiries, entering into contractual commitments etc. on behalf of the Joint Venture, in respect of this Project.

{We understand that, no change in the membership in the Joint Venture, in the role and form of responsibility of any Partner shall be permitted after submission of the Tender. If any change in the membership of the Joint Venture is desired, it would be communicated to the Employer in writing for its approval. The Employer would reserve the right to reject such requests for a change of Joint Venture structure, if in its opinion; it would adversely affect the same.}

ANNEXURE-VIIIB

Form of Power of Attorney for Lead Partner of Joint Venture

(To be submitted in case of JV only)

KNOWN ALL MEN BY THESE PRESENTS THAT WE, the Partners, M/s ____________, M/s ______ and M/s__________ whose details are given hereunder have formed a Joint Venture (*)/ intend to form a Joint Venture (*) [(*) delete whichever is not applicable] and having our Registered Offices at______________, ________ and _________________ respectively (hereinafter‘called the 'Joint Venture' which expression shall unless repugnant to the context or meaning thereof, include its successors, administrators and assigns) do hereby constitute, nominate and appoint M/s_________ having its Registered/Head Office at __________ as our duly constituted lawful Attorney (hereinafter called "Attorney" or "Authorized Representative" or "Lead Partner") to exercise all or any of the powers for and on behalf of the Joint Venture in regard to work for the tender for which have been invited by _____________ (hereinafter called the “Employer”) for ______________ (hereinafter called the “Project”) to undertake the following acts:

- To sign participate in the tender process including signing and submission of tenders, participating in pre-tender and other conferences, providing information/responses to the Employer and representing us in all matters relating to the tender for the aforesaid Project of the Employer on behalf of the "Joint Venture".

- To negotiate with the Employer, the terms and conditions for award of the Contract pursuant to the aforesaid tender and to sign the Contract with the Employer for and on behalf of the Joint Venture.

For the above purpose, the person(s) authorized by the Partner In-charge shall be the person(s) authorized to act on behalf of the "Joint Venture" as per the Power of Attorney given to him/her/them by the Partner In-Charge,

It is clearly understood that all the Partners of the joint venture shall be liable jointly and severally for the execution of the Contract in accordance with the Contract terms and the Lead Partner shall ensure performance of the Contract(s) and if one or more Partner fail to perform their respective portions of the Contract(s), the same shall be deemed to be a default by all the Partners.

It is expressly understood that this Power of Attorney shall remain valid binding and irrevocable till completion of the Design, Build, Testing and Commissioning as well as the Operations and Maintenance Period in terms of the Contract.

The Joint Venture hereby agrees and undertakes to ratify and confirm all the whatsoever the said Attorney/Authorized Representatives/Lead Partner quotes in the tender, negotiates and signs the Contract with the Employer and/or proposes to act on behalf of the Joint Venture by virtue of this Power of Attorney and the same shall bind the Joint Venture as if done by itself.

IN WITNESS THEREOF WE THE PRINICPALS ABOVE NAMED HAVE EXECUTED THIS POWER OF ATTORNEY ON THIS ____ DAY OF _____ 20_____.

For and on behalf of _______

[Lead Partner]

Signature......................................................

Name..........................................................

Designation...........................................................

For and on behalf of _______

[Partner- 1]

Signature......................................................

Name..........................................................

Designation........................................................

Witness:

1. Signature......................................................

Name..........................................................

Designation........................................................

2. Signature.....................................................

Name.........................................................

Designation................................................................

Occupation..........................................................

[Notarized]

Notes:

- The mode of execution of the Power of Attorney should be in accordance with the procedure, if any, laid down by the applicable law and the charter documents of the executants and when it is so required, the same should be under common seal affixed in accordance with the required procedure.

- Wherever required, the Tenderer should submit for verification, the extract of the charter documents such as resolution/power of attorney in favour of the person executing this Power of Attorney for the delegation of power hereunder on behalf of the Partners.

- Power of Attorney executed abroad should conform to the provisions of Notaries Act, 1952 and Indian Stamp Act, 1899.

ANNEXURE-VIIIC

Format of Joint Venture Agreement

(To be submitted in case of JV only )

THIS JOINT VENTURE AGREEMENT is entered into on this the _____ day of ____ 20__.

BETWEEN

- _________, a company/partnership incorporated registered under_____ Act, _____ and having its registered office at ______ (hereinafter referred to as the “Lead Partner” or “First Part” which expression shall, unless repugnant to the context include its successors and permitted assigns)

AND

- ________, a company/partnership incorporated registered under _____ Act, _____ and having its registered office at _______ (hereinafter referred to as the “Second Partner`” or “Second Part” which expression shall, unless repugnant to the context include its successors and permitted assigns

AND

- ________, a company/partnership incorporated registered under _____ Act, _____ and having its registered office at _______ (hereinafter referred to as the “Third Partner`” or “Third Part” which expression shall, unless repugnant to the context include its successors and permitted assigns

The above-mentioned parties of the FIRST AND SECOND PART are collectively referred to as the “Parties” and each is individually referred to as a “Party.”

WHEREAS,

- ___________- (the “Employer”), having its principal office at __________ including its administrators, successors and assigns) have invited Proposals (the “Proposals”) by its Tender Document No. _____ dated __________ (the “Tender Document”) for ______________ (the “Project”).

The Parties are interested in jointly bidding for the Project as partners of a joint venture (the “Joint Venture”) and in accordance with the terms and conditions of the Tender document in respectof the Project, and

It is a necessary condition under the Tender document that the partners of the Joint Venture shall enter into a Joint Venture Agreement and furnish a copy thereof with the Tender.

NOW IT IS HEREBY AGREED as follows:

- Definitions and Interpretations

In this Agreement, the capitalized terms shall, unless the context otherwise requires, have the meaning ascribed thereto under the RFP.

- Joint Venture

The Parties do hereby irrevocably constitute a Joint Venture for the purposes of jointly participating in the selection process for the Project.

The Parties hereby undertake to participate in the selection process only through this Joint Venture and not individually and/ or through any other Joint Ventures constituted for this Project, either directly or indirectly or through any of their Associates.

- Role of the Parties

The Parties hereby undertake to perform the roles and responsibilities as described below:

- Party of the First Part shall be the Lead Partner of the Joint Venture and shall have the Power of Attorney from all Parties for conducting all business for and on behalf of the Joint Venture during the duration of the Project and shall be responsible for ______ [insert role];

- Party of the Second Part shall be responsible for _______ [insert role]

- Party of the Third Part shall be responsible for _______ [insert role]

- Joint and Several Liability

The Parties do hereby undertake to be jointly and severally responsible for all obligations and liabilities relating to the Project and in accordance with the terms of the Tender Document till the expiry of the Contract.

- Shareholding in the JV

The Parties agree that the proportion of shareholding among the Parties in the JV shall be as follows:

First Party: ____ %

Second Party: ____%

Third Party: ____%

- Representation of the Parties

Each Party represents to the other Parties as of the date of this Agreement that

- such Party is duly organized, validly existing and in good standing under the laws of its incorporation and has all requisite power and authority to enter into this Agreement;

the execution, delivery and performance by such Party of this Agreement has been authorized by all necessary and appropriate corporate or governmental action and a copy of the extract of the charter documents and board resolution/ power of attorney in favor of the person executing this Agreement for the delegation of power and authority to execute this Agreement on behalf of the Joint Venture is annexed to this Agreement, and will not, to the best of its knowledge:

- require any consent or approval not already obtained;

- violate any Applicable Law presently in effect and having applicability to it;

- violate the memorandum and articles of association, by-laws or other applicable organizational documents thereof;

- violate any clearance, permit, concession, grant, license or other governmental authorization, approval, judgment, order or decree or any mortgage agreement, indenture or any other instrument to which such Party is a party or by which such Party or any of its properties or assets are bound or that is otherwise applicable to such Party; or

- create or impose any liens, mortgages, pledges, claims, security interests, charges or encumbrances or obligations to create a lien, charge, pledge, security interest, encumbrances or mortgage in or on the property of such Party, except for encumbrances that would not, individually or in the aggregate, have a material adverse effect on the financial condition or prospects or business of such Party so as to prevent such Party from fulfilling its obligations under this Agreement;

- this Agreement is the legal and binding obligation of such Party, enforceable in accordance with its terms against it; and there is no litigation pending or, to the best of such Party's knowledge, threatened to which it or any of its Associates is a party that presently affects, or which would have a material adverse effect on the financial condition or prospects or business of such Party in the fulfilment of its obligations under this Agreement

- Termination

This Agreement shall be effective from the date hereof and shall continue in full force and effect until the completion of the Project is achieved under and in accordance with the Contract. However, in case the Joint Venture is either not qualified for the Project or does not get selected for award of the Project, the Agreement will stand terminated in case the Tenderer is not qualified or upon return of the Earnest Money Deposit by the Employer to the Tenderer, as the case may be.

- Miscellaneous

This Joint Venture Agreement shall be governed by laws of India. The Parties acknowledge and accept that this Agreement shall not be amended by the Parties without the prior written consent of the Employer.

IN WITNESS WHEREOF THE PARTIES ABOVE NAMED HAVE EXECUTED AND DELIVERED THIS AGREEMENT AS OF THE DATE FIRST ABOVE WRITTEN.

| Signed, Sealed and Delivered: | Signed, Sealed and Delivered: |
| --- | --- |
| For and on behalf of LEAD PARTNER (Signature):______________________________ (Name):_________________________________ (Designation): ___________________________ (Address):_______________________________ | For and on behalf of OTHER PARTNER (Signature):_____________________________ (Name):_______________________________ (Designation):___________________________ (Address):____________________________ |

WIESS:

1. Signature......................................................

Name..........................................................

Designation........................................................

2. Signature.....................................................

Name.........................................................

Designation................................................................

Occupation..........................................................

Notes:

  - The mode of execution of the Joint Venture Agreement should be in accordance with the procedure, if any, laid down by the applicable law and the charter documents of the executants and when it is so required, the same should be under common seal affixed in accordance with the required procedure.

  - Wherever required, the Tenderer should submit for verification, the extract of the charter documents such as resolution/power of attorney in favour of the person executing this Power of Attorney for the delegation of power hereunder on behalf of the Joint Venture.

  - JOINT VENTURE AGREEMENT SHALL BE DULY NOTARIZED AND TO BE UPLOADED ALONG WITH TECHNICAL PROPOSAL.

ANNEXURE-VIII D

AFFIDAVIT REGARDING CORRECTNESS OF INFORMATION FURNISHED AND DOCUMENTS SUBMITTED

I ……………………………………………………. Son/daughter of ………………………………………… residing at ……… …………………………………………………………………………. (Address) Authorized Signatory/ Proprietor /Partner/ Director of M/s…………………………………….. situated at …………………………………………………. …………………………………………………… (Address) hereby solemnly declare as under:

- That I have submitted my tender for the work…………………………………………………………… ………………………….. in response to Invitation to Tender No. ………………………………………… ………………issued by ……………………………………………………………………………………… on the e-procurement portal https://kppp.karnataka.gov.in

- That I have uploaded the scanned copies/copies of the following documents as required by the tender document and in support of my meeting the stipulated eligibility and qualification requirements as stipulated in the tender document:

- …………………………………………………………………………………………………..;

- …………………………………………………………………………………………………..;

- ……………………………………………………………………………………………………;

- ……………………………………………………………………………………………………;

- ……………………………………………………………………………………………………;

- …………………………………………………………………………………………………….;

- ………………………………………………………………………………………………………;

- ……………………………………………………………………………………………………..;

- ……………………………………………………………………………………………………..;

- That the information furnished by me in the format are correct to the best of my knowledge and the documents/ certificates uploaded are true to the originals;

- That I am in possession of the original documents and ready to produce the original documents and the original documents in support of the qualification information furnished for verification by the Employer or his authorized representative within 5 days of receiving the request from the Employer or his authorized representative;

- That I have not made misleading or false representation in the Forms, Statements and Attachments submitted/uploaded in proof of qualification requirements;

- That I do not have record of poor performance such as abandoning the works, not properly completing the contracts, inordinate delays in completion in completion, litigation history or financial failures etc,

- That I have not participated in the previous tenders for the same work and could not furnish rational justification for the prices quoted by me when requested by the Employer;

- I am aware of the provision of ITT Clause 3.7 and agree that I am subject to be disqualified on the above accounts and also aware that the KUWS&DB can take administrative action against me.

Deponent

VERIFICATION:

Verified at …………………………. On this ……………….. month ……………………. Year that contents of the above affidavit are true and correct to the best of my knowledge and belief and nothing is false or fabricated or has been concealed there from.

Deponent:

Note:

1) This Form has to be duly completed, signed and uploaded on the e-procurement portal in the First Folder – Techno Commercial Tender.

2) The affidavit may be submitted in the letter head of the Bidder, duly Notarised by the Notary.

ANNEXURE - IX

Format for Submission of Conceptual Scheme Report

The KUWSDB has constituted an Evaluation Committee that shall evaluate the Conceptual Scheme Report submitted by the Tenderer on the following parameters. The TATSC will evaluate each module for compliance.

PART-A: Design Consultant/Design Experience

| Sl. No. | Description | Desired Experience | Allocated Marks | Details to be filled by the tenderers | Marks Secured |
| --- | --- | --- | --- | --- | --- |
|  | Design of water supply project | At least two projects of not less than INR 50 Crore cost each. | 25 |  |  |
|  | Hydraulic Expert | - Bachelor’s Degree in Civil/Environmental/ Equivalent Engineering. - 8years’ experience in Water supply system including Treatment & water network designs and construction. - Proficiency in all advanced water related Software’s (WaterGem). | 25 |  |  |
|  | Structural Expert | - Graduate in Civil Engineering - 8 years‘ experience in the field of structural engineering, - Experience in designs of water retaining structures, Proficiency in structural design using computer programs. | 25 |  |  |
|  | Electrometrical Expert | - Graduate in Electrical/ Instrumentation Engineer or equivalent - 8years’ experience in water and sewerage field - Experience in design of equipment size, rating etc of WTP/STP, Pumping Stations &water supply equipment. - Experience in installation and O&M of equipment at WTP/STP, Pumping Stations &water supply equipment | 25 |  |  |
| Total |  |  | 100 |  |  |

PART-B: Textile Park

| ITEM – 1:- POPULATION PROJECTION OF THE PROJECT: Marks 50 (The Tenderer has to score minimum of 35 marks) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sl. No. | Description | Allocated Marks | Details to be filled by the tenderers | Marks Secured |
| 1 | Details of population along with the method of population projection adopted | 50 |  |  |
|  | -Base year |  |  |  |
|  | -Intermediate Year |  |  |  |
|  | -Ultimate year |  |  |  |
|  | Total | 50 |  |  |

| ITEM – 2:- HEAD WORKS – 110 Marks (The Tenderer has to score minimum of 77 marks) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sl. No. | Description | Allocated Marks | Details to be filled by the tenderers | Marks Secured |
| a) Coffer Dam, Intake Well, Intake Channel & connecting pipeline |  |  |  |  |
| 1 | Designed year | 5 |  |  |
| 2 | Source Sustainability Study, Location (Place) of intake well with Latitude / Longitude | 25 |  |  |
| 3 | Bed level of Proposed Barrage near Madri village (RL) |  |  |  |
| 4 | Lowest Water Level of Proposed Barrage near Madri village (RL) |  |  |  |
| 5 | High Flood Level of Proposed Barrage near Madri village (RL) |  |  |  |
| 6 | Bed Level of Intake well |  |  |  |
| 7 | Scour Depth details |  |  |  |
| 8 | Lowest discharge / flow at the proposed intake point |  |  |  |
| 9 | Details of Intake well – sizing with levels | 10 |  |  |
| 10 | Details of Connecting main – Invert level, dia, length & material of pipe | 10 |  |  |
| b) Jack well cum pump house & Pumping Machineries |  |  |  |  |
| 1 | Invert level of the connecting pipe at Jackwell/pump house structure | 10 |  |  |
| 2 | Sizing of Jackwell cum pump house (dia, depth & height) | 10 |  |  |
| 3 | Number of raw water pumps & designed year | 10 |  |  |
|  | Working + Standby (W + S) (Nos) |  |  |  |
| 4 | Type of raw water pumps proposed with duty conditions | 10 |  |  |
| 5 | Efficiency of pump, Motor Capacity & pump set duty condition (%) | 10 |  |  |
| 6 | Dedicated express power supply and electrical substation | 10 |  |  |
|  | Total | 110 |  |  |

ITEM – 3: - RAW WATER RISING MAIN: 70 Marks (The Tenderer has to score minimum of 49 marks)

| Sl. No. | Description | Allocated Marks | Details to be filled by the tenderers | Marks Secured |
| --- | --- | --- | --- | --- |
| 1 | Designed year | 5 |  |  |
| 2 | Length of the pipeline (m) | 5 |  |  |
| 3 | Diameter of pipeline OD / ID with hydraulic design (eco main) | 25 |  |  |
| 4 | Pipe material and class of pipe | 5 |  |  |
| 5 | Velocity of flow at design capacity (m / sec) | 10 |  |  |
| 6 | Numbers of sluice & Air valves | 5 |  |  |
| 7 | Surge protection | 15 |  |  |
|  | Total | 70 |  |  |

ITEM – 4: - WATER TREATMENT PLANT: Marks 200 (The Tenderer has to score minimum of 140 marks)

| Sl No. | Description | Allocated Marks | Details to be filled by the tenderers | Marks Secured |
| --- | --- | --- | --- | --- |
| 1 | Designed Year | 5 |  |  |
| 2 | Proposed Location with Latitude / Longitude | 10 |  |  |
| 3 | Design capacity (MLD) | 10 |  |  |
| 4 | Technology proposed | 15 |  |  |
| 5 | Details of Components proposed | 10 |  |  |
| 6 | Extent of Land identified | 10 |  |  |
| 7 | Pumping / working hours per day | 10 |  |  |
| 8 | Type of disinfection facility meeting CPHEEO / WHO guidelines Chlorination Dosage – mg/l | 10 |  |  |
| 9 | Guaranteed Mandatory Performance Parameters of the treated water at the Outlet of WTP | 20 |  |  |
|  | a) Turbidity (NTU) |  |  |  |
|  | b) TDS (PPM) |  |  |  |
|  | c) pH |  |  |  |
|  | d) Color (JTU) |  |  |  |
|  | e) E. Coli (MPN/100ml) |  |  |  |
|  | f) Chloride(ppm) |  |  |  |
|  | g) TSS(PPM) |  |  |  |
|  | h) Fluoride (ppm) |  |  |  |
|  | i) Total Hardness (ppm) |  |  |  |
| 10 | Type of Flow measuring devices | 10 |  |  |
| 11 | Sludge disposal | 10 |  |  |
| 12 | Backwash Methodology | 10 |  |  |
| 13 | Protection wall for WTP premises (Type & Height) | 10 |  |  |
| 14 | Details of Landscaping & Internal roads (Type of road and width) | 10 |  |  |
| 15 | Treated Water Storage Reservoir |  |  |  |
|  | Design capacity (Million Litres) | 5 |  |  |
|  | Detention Time (hrs.) | 5 |  |  |
| 16 | Treated Water Pumping Station |  |  |  |
|  | Size of Pump house ( L x B x Height) | 5 |  |  |
|  | Type of pure water pumps proposed with duty conditions | 10 |  |  |
|  | Efficiency of pump, Motor & pump set (%) | 10 |  |  |
|  | Type of suction (Positive/Negative) | 5 |  |  |
|  | Dedicated express power supply and electrical substation | 10 |  |  |
|  | Total | 200 |  |  |

ITEM – 5:- DETAILS OF LAND REQUIRED FOR PROPOSED COMPONENTS –  20 Marks (The Tenderer has to score minimum of 14 marks)

| Sl No | Item of work | Marks Allocated | Location proposed and confirmed by Tenderer with Extent in Acres (Government land/private land) | Marks secured by Tenderer | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Headworks with Approach | 10 |  |  |  |
| 2 | Water Treatment Plant and other facilities such as office, restrooms, quarters, etc. | 10 |  |  |  |
|  | Total | 20 |  |  |  |

| ITEM – 6:-Operation & Maintenance of assets built under the contract : 40 marks (The Tenderer has to score minimum of 28 marks) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Sl. No. | Description | Allocated Marks | Details to be filled by the tenderers | Marks Secured |
| 1 | Quality Parameters PH Residual Chlorine Turbidity | 25 |  |  |
| 2 | Rectification of Leakages Methodology Manpower Timeline | 15 |  |  |
|  | Total | 40 |  |  |

| Summary of Marks |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM No | Description | Marks | Minimum Marks | Marks Obtained by the Tenderer |
| 1 | POPULATION PROJECTION OF THE TOWN/CITY | 50 | 35 |  |
| 2 | HEAD WORKS | 110 | 77 |  |
| 3 | RAW WATER PUMPING MAIN | 70 | 49 |  |
| 4 | WATER TREATMENT PLANT | 200 | 140 |  |
| 5 | DETAILS OF LAND REQUIRED FOR PROPOSED COMPONENTS | 20 | 14 |  |
| 6 | OPERATION & MAINTENANCE OF ASSETS BUILT UNDER THE CONTRACT | 40 | 28 |  |
|  | Total | 490 | 343 |  |

| SUMMARY OF MARKS |  |  |  |
| --- | --- | --- | --- |
| Sl. No | Parts & Towns | Total Marks | Minimum Marks Required |
|  | PART-A: Design Consultant/ Design Experience | 100 | 70 |
|  | PART-B: Tech Park | 490 | 343 |
|  | Total | 590 | 413 |

NOTE:

- The above parameters indicated is only for evaluation purpose and performance standards shall not be limited to the above, however, the Tenderer must design and construct and operate the entire systems per the CPHEEO norms - Technical Specifications (Section 7) and system design criteria.

- It is further clarified that the evaluation of the Conceptual Scheme Report (CSR) to give marks to the proposed solution by the bidder shall be in accordance with the Technical Specifications (Section 7) and CPHEEO norms. The bidder / Tenderers are encouraged to provide most techno-economical solutions.

# SECTION 4: FORMS OF TENDER

DETAILS OF PAYMENT OF TENDER PROCESSING FEES

From: (Tenderer)

___________________

___________________

___________________

To:

The Chief Engineer

Karnataka Urban Water Supply and Drainage Board

Jalbhavan, Rajapur, Kusnoor Road,

Kalaburagi- 585105

Sir,

  - I/ We have made the payment of the tender processing fees of Rs. ………….. Rupees…………………..Only through Credit Card / Direct Debit / National Electronic Funds Transfer (NEFT)/ over the counter in ……………. branch of Nationalized bank on……………. (Strike the modes not used)

  - I/We have submitted the Earnest Money Deposit in the Prescribed format.

  - We agree that the action may be initiated as stipulated in the Earnest Money deposit by the Employer if we:

- Withdraw our bid during the period of validity specified in the bidding document;

- Do not sign the Agreement within the specified time limit in case we are successful and letter of acceptance has been communicated;

- Do not furnish the required Performance Security deposit as required in clause 29 of ITB.

……………………………………………..

(Signature and Name of Tenderer)

Date:

LETTER OF ACCEPTANCE

(On the Letterhead of the Employer)

Date:

To,

[Name and address of the Contractor]

Dear Sir,

This is to notify you that your Tender dated: _____ for the execution of the (Name of the contract and identification number, as given in the Instructions to Tenderers) for the Contract Price of Rs. _______ (amount in words and figures), as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted by our Agency

You are hereby requested to furnish Security deposit in the form detailed in Clause 29.1 of ITT for an amount of Rs. _____________ towards Design, Build, Testing& Commissioning within 20 days of the receipt of this letter of acceptance valid up to 30 days of the intended date of completion of CAPEX works plus additional security for unbalanced tenders in terms of Clause 25.5 of ITT, in the form detailed in Clause 29.1 of ITT for an amount of Rs. ___________ within 20 days of the receipt of this letter of acceptance valid up to 28 days from the date of expiry of Intended Completion Period of CAPEX and sign the contract, failing which action as stated in Para 29.4 of ITT will be taken.

Yours faithfully,

Authorized Signature

Name and Title of Signatory Name of Agency

DETAILS OF PAYMENT OF TENDER PROCESSING FEES & AND EARNEST MONEY DEPOSIT

From: (Tenderer)

____________________

____________________

____________________

To:

The Chief Engineer,

Karnataka Urban Water Supply and Drainage Board,

Jalbhavan, Rajapur, Kusnoor Road,

Kalaburagi- 585 105.

.

Sir:

- I/ We have made the payment of the tender processing fees of Rs. ______________/- Rupees ______________only(in words) through Credit Card/Direct Debit/ National Electronic Funds Transfer (NEFT)/ over the counter in ______________branch of ICICI bank on______________ (Strike the modes not used)

- I/We have made the payment of the Earnest Money of Rs______________ Rupees______________ only (in words) through Credit Card/Direct Debit/National Electronic Funds Transfer (NEFT)/ over the counter in ______________ branch of ICICI bank on ______________ (Strike the modes not used)

- I/We have made the payment of the balance of Earnest Money of Rs______________ Rupees______________Only(in words) through the following:

- Bank Guarantee No:.______________ dated ______________ issued by ______________ Valid up to ______________for an amount of Rs______________ Rupees_____________ Only (in words);

- Demand Draft No______________ dated ______________ issued by ______________ Bank______________ Branch  for an amount of Rs. ______________ Rupees ______________only (in words)

- Certified Cheque /Banker’s cheque No:______________ dated ______________issued by ______________ Bank ______________ Branch for an amount of Rs______________ Rupees ______________only (in words)

- SSI No______________ dated______________ issued by Post Office ______________ located at ______________ For Rupees______________ (in figures) Rupees ______________ (in words)

(strike the mode not used)

- We agree that the Earnest Money deposited by us as detailed above may be forfeited by the Employer if we:

- Withdraw our bid during the period of validity specified in the bidding document;

- Do not sign the Agreement within the specified time limit in case we are successful and letter of acceptance has been communicated;

- Do not furnish the required Performance Security deposit as required in Clause 29 of ITB

_______________________________

(Signature and Name of Tenderer)

Date:

FORMAT OF BANK GUARANTEE FOR EARNEST MONEY DEPOSIT

To: _____________

_____________

_____________

[name of Employer]

[address of Employer]

WHEREAS ______[name and address of Contractor] ______________[name of Work]

AND WHEREAS it has been stipulated by you in the said Work that the Contractor shall furnish you with a Bank Guarantee by a recognized Nationalized / Scheduled Commercial Bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of Rs.____________________ [amount of guarantee] Rupees__________________________ __________________________[in words], and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ____________________ [amount of guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until till the Tender validity.

Signature and seal of the guarantor

ISSUE OF NOTICE TO PROCEED WITH THE WORK

(On the Letter head of the Employer)

To

_____________________________

_____________________________

_____________________________

(name and address of the Contractor)

Dear Sirs:

Pursuant to your furnishing the requisite security deposit as stipulated in ITT Clause 29.1 and signing of the contract agreement for the construction of __________ for Tender Price of Rs_______, you are hereby instructed to proceed with the execution of the said works in accordance with the contract documents.

Yours faithfully,

(Signature, name and title of signatory authorized to sign on behalf of Employer)

AGREEMENT FORM

This agreement made on this the	day of	20	, between _____________ [Name and address of Employer] (here in after called “the Employer”) of the one part and _________ Name and address of contractor] (hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor execute ___________ [name and identification number of Contract] (hereinafter called “the Works”) and the Employer has accepted the Tender by the Contractor for the execution and completion of such Works and the remedying of any defects therein at a Contract Price of Rupees_____ [in Figures] (_____________) [in Words].

NOW THIS AGREEMENT WITNESSETH as follows:

- In this Agreement, words and expression shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

- In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all aspects with the provisions of the Contract.

- The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

- The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

  - Letter of Acceptance;

  - Notice to proceed with the works;

  - Contractor’s Tender;

  - Contract Data;

  - Conditions of contract (including Special Conditions of Contract)

  - Specifications;

  - Drawings

  - Bill of Quantities/Schedules; and

  - Any other document listed in the Contract Data as forming part of the contract.

  - Any Addendum/Corrigendum/ pre-bid meeting clarifications etc.

In witness whereof the parties thereto have caused this Agreement to be executed the day and (year first) before written.

The Common Seal of	was hereunto affixed in the presence of:

Signed, Sealed and Delivered by the said

In Presence of:

Binding signature of Employer: _____________

Binding signature of Contractor: _____________

# SECTION 5: CONDITIONS OF CONTRACT

TABLE OF CONTENTS

A.	General	123

1.	Definitions	123

2.	Interpretation	124

3.	Law governing contract	124

4.	Employer's decisions	124

5.	Delegation	125

6.	Communications	125

7.	Sub –Contracting: deleted	125

8.	Other Contractors	125

9.	Personnel	125

10.	Employer’s and Contractor's risks	125

11.	Employer's risks	125

12.	Contractor’s risks	125

13.	Insurance:	126

14.	Site Investigation Reports:	126

15.	Queries about the Contract Data	126

16.	Contractor to construct the Works	126

17.	The Works to be completed by the Intended Completion Date	126

18.	Approval by the Employer:	127

19.	Safety	127

20.	Discoveries	127

21.	Possession of the Site	127

22.	Access to the Site	127

23.	Instructions	127

24.	Procedure for resolution of Disputes:	128

B.	Time Control	128

25.	Program	128

26.	Extension of the Intended Completion Date	128

27.	Delays ordered by the Employer	128

28.	Management meetings	128

C.	QUALITY CONTROL	129

29.	Identifying defects	129

30.	Tests	129

31.	Correction of defects	129

32.	Uncorrected defects	129

D.	COST CONTROL	129

33.	Bill of Quantities (BOQ)	129

34.	Variations - NOT APPLICABLE	129

35.	Payments for Variations- NOT APPLICABLE	129

36.	Submission of bills for payment	129

37.	Payments	130

38.	Compensation events	130

39.	Tax	131

40.	Price Adjustment: (Applicable for civil works only& not applicable for electro-mechanical and O&M works)	131

41.	Liquidated damages	131

42.	Advance Payments:	132

43.	Securities:	132

44.	Cost of Repairs:	132

E.	FINISHING THE CONTRACT	132

45.	Completion	132

46.	Taking over	132

47.	Final account	133

48.	As built drawings and /or Operating and Maintenance Manuals	133

49.	Termination	133

50.	Payment upon Termination	134

51.	Property	134

52.	Release from performance	134

53.	Additional Clauses:	134

F.	Special Conditions of Contract	136

CONDITIONS OF CONTRACT

## A.	General

### Definitions

  - Terms which are defined in the Contract Data are not also defined in the Conditions of Contract but keep their defined meanings. Bold letters are used to identify defined terms.

| Bill of Quantities | means the priced and completed Bill of Quantities forming part of the Tender. |
| --- | --- |
| Compensation events | are those defined in Clause 38 hereunder. |
| The Completion Date | is the date of completion of the Works as certified by the Employer in accordance with Sub Clause 45.1 |
| The Contract | is the contract between the Employer and the Contractor to execute, complete and maintain the Works. It consists of the documents listed in Clause 2.2 below. |
| Contract Data | defines the documents and other information which comprise the Contract. |
| Commencement Date | shall be the date at which the following precedent conditions have all been fulfilled - signature of the Contract Agreement by both Parties - receipt of Performance Security - Certificates for Insurance taken (if any) |
| Contractor | is a person or corporate body who’s Tender to carry out the Works has been accepted by the Employer. |
| Contractor's Tender | is the completed Tender document submitted by the Contractor to the Employer. |
| Contract price | is the price stated in the Letter of Acceptance and Thereafter as adjusted in accordance with the provisions of the Contract. |
| Days | are calendar days; Months are calendar months. |
| Design Build Period / Construction period | shall be period as indicated by the Employer in the Contract from the date of signing of contract including testing and Trial Run Period. |
| Defect | is any part of the Works not completed in accordance with the Contract. |
| Defects liability period | is the period named in the Contract Data and calculated from the Completion Date. |
| Employer | is the party who will employ the Contractor to carry out the Works. |
| Employer Representative | is the person authorized by the Employer for the Contract |
| Force Majeure | is an event or effect that can neither be anticipated nor controlled (such as Act of God). |
| Equipment | is the Contractor's machinery and vehicles brought temporarily to the Site to construct the Works. |
| Initial Contract price | is the Contract Price listed in the Employer's Letter of Acceptance |
| Intended Completion Date | is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Contract Data. The Intended Completion Date may be revised only by the Employer by issuing an extension of time. |
| Materials | are all supplies, including consumables, usedby the contractor for incorporation in the Works. |
| Operation Service Period / Operations and maintenance Period / O&M period | shall be period as indicated by the Employer in the Contract from the date of successful completion of Design Build Period. |
| Plant | is any integral part of the Works which is to have a mechanical, electrical, electronic or chemical or biological function etc. |
| Site | is the area defined as such in the Contract Data |
| Specification | means the Specification of the Works included in the Contract and any modification or addition made or approved by the Employer. |
| Start Date | is given in the Contract Data. It is the date when the Contractor shall commence execution of the works. It does not necessarily coincide with any of the Site Possession Dates. All milestones and intended completion dates will depend on this date. |
| Sub-contractor | is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract which includes work on the Site. |
| Trial Run Period | shall be period as indicated by the Employer in the Contract before the completion of Design Build Period and commencement of O&M Period. |
| Variation | is an instruction given by the Employer which varies the scope of Works. |
| Works | what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the Contract Data. |

### Interpretation

  - In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter, and vice-versa. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Employer will provide instructions clarifying queries about the Conditions of Contract.

  - The documents forming the Contract shall be interpreted in the following order of priority:

(1)	Agreement

(2)	Letter of Acceptance, notice to proceed with the works

(3)	Contractor’s Tender

(4)	Contract Data

(5)	Conditions of Contract including Special Conditions of Contract

(6)	Specifications

(7)	Drawings

(8)	Bill of quantities/Schedules and

(9)	Any other document listed in the Contract Data as forming part of the Contract.

(10) Addendum/ Corrigendum/ pre-bid meeting clarifications etc.

### Law governing contract

  - The law governing the Contract is the Laws of India supplanted by the Karnataka Local Acts.

### Employer's decisions

  - Except where otherwise specifically stated, the Employer will decide contractual matters between the Employer and the Contractor.

### Delegation

  - The Employer may delegate any of his duties and responsibilities to other people after notifying the Contractor and may cancel any delegation after notifying the Contractor.

### Communications

  - Communications between parties which are referred to in the conditions are effective only when in writing. A notice shall be effective only when it is delivered (in terms of Indian Contract Act).

### Sub –Contracting: deleted

### Other Contractors

  - The Contractor shall co-operate and share the Site with other contractors, public authorities, utilities, and the Employer.

### Personnel

  - The Contractor shall employ the technical personnel (of number and qualifications) as may be stipulated by KUWS& D Board from time to time during the execution of the work. The technical staff so employed shall be available at site as may be stipulated by the Employer.

  - If the Employer asks the Contractor to remove a person who is a member of the Contractor’s staff or his work force stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract.

### Employer’s and Contractor's risks

  - The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks.

### Employer's risks

  - The Employer is responsible for the excepted risks which are:

(a)	rebellion, riot commotion or disorder unless solely restricted to employees of the Contractor or his Sub-Contractors arising from the conduct of the Works; or

(b)	a cause due solely to the design of the Works, other than the Contractor’s design; or

(c)	any operation of the forces of nature (in so far as it occurs on the Site) which an experienced contractor:

(i)	could not have reasonably foreseen

(ii)	could reasonably have foreseen, but against which he could not reasonably have taken at least one of the following measures;

A.	Prevent loss or damage to physical property from occurring by taking appropriate measures.

B.	insure against such loss or damage

### Contractor’s risks

  - All risks of loss of or damage to physical property and of personal injury and death which arise during and in consequence of the performance of the Contract other than the excepted risks are the responsibility of the Contractor.

### Insurance:

  - The Contractor shall prior to commencing the works, effect and thereafter maintain insurances, in the joint names of the Employer and the Contractor, (cover from the first working day after the Start Date to the end of Defects Liability Period), in the amounts stated in the Contract Data:

(a)	for loss of or damage to the Works, Plants and Materials and the Contractor’s equipment;

(b)	for liability of both Parties for loss, damage, death and injury to third parties or the property arising out of the Contractor’s performance of the Contract including the Contractor’s liability for damage to the Employer’s property other than the Works

(c)	for liability of both Parties and of any Employer’s representative for death and injury to the Contractor’s personnel except to the extent that liability arises from the negligence of the Employer, any Employer’s representative or their Employees.

  - Policies and certificates for insurance shall be delivered by the Contractor to the Employer for his approval before the Start Date. All such insurance shall provide for compensation to be payable to rectify the loss or damage incurred. All payments received from insurers relating to loss or damage shall be held jointly by the Parties and used for the repair of the loss or damage or as compensation for loss or damage that is not to be repaired.

  - If the Contractor fails to effect or keep in force any of the insurances referred to in the previous sub-clauses or fails to provide satisfactory evidence, policies or receipts, the Employer may without prejudice to any other right or remedy, effect insurance for the cover relevant to such default and pay the premiums due and recover the same as a deduction from any other monies due to the Contractor. If no payments is due, the payment of the premiums shall be a debt due.

  - Alterations to the terms of an insurance shall not be made without the approval of the Employer.

  - Both Parties shall comply with any conditions of the insurance policies.

### Site Investigation Reports:

  - The Contractor, in preparing the Tender, shall rely on any site investigation reports referred to in the Contract data, supplemented by any information available to the Tenderer.

### Queries about the Contract Data

  - The Employer will clarify queries on the Contract Data.

### Contractor to construct the Works

  - The Contractor shall construct the Works in accordance with the Specification and Drawings as approved by the Chief Engineer

### The Works to be completed by the Intended Completion Date

  - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the program submitted by the Contractor, as updated with the approval of the Employer, and complete them by the Intended Completion Date.

### Approval by the Employer:

  - The Contractor shall submit Specification and drawings showing the proposed Permanent and Temporary Works to the Employer, who will approve them if they comply with the Specifications and Drawings.

  - The Contractor shall be responsible for the design of Temporary Works

  - The Employer’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works.

  - The Contractor shall obtain approval of third parties to the design of the temporary Works where required.

  - All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Employer before their use.

### Safety

  - The Contractor shall be responsible for the safety of all personnel and activities at the Site.

### Discoveries

  - Anything of historical or other interest or of significant value unexpectedly discovered at the Site is the property of the Employer. The Contractor is to notify the Employer of such discoveries and carry out the Employer's instructions for dealing with them.

### Possession of the Site

  - The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the Contract Data the Employer is deemed to have delayed the start of the relevant activities and this will be Compensation Event.

### Access to the Site

  - The Contractor shall allow the Employer and any person authorized by the Employer to have access to the Site, to any place where work in connection with the Contract being carried out or intended to be carried out and to any place where materials or plant are being manufactured / fabricated / assembled for the works.

### Instructions

  - The Contractor shall carry out all instructions of the Employer which comply with the applicable laws where the Site is located.

### Procedure for resolution of Disputes:

Deleted as per circular of GOK vide No. LAW-LAC/198/2024 Dated 16-11-2024.

## B.	Time Control

### Program

  - Within the time stated in the Contract Data the Contractor shall submit to the Employer for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works.

  - The Employer's approval of the Program shall not alter the Contractor's obligations. The Contractor may revise the Program and submit it to the Employer again at any time. A revised Program is to show the effect of Variations and Compensation Events.

### Extension of the Intended Completion Date

  - The Employer shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date.

  - The Employer shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Employer for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information.

### Delays ordered by the Employer

  - The Employer may instruct the Contractor to delay the start or progress of any activity within the Works.

### Management meetings

  - The Employer may require the Contractor to attend a management meeting. The business of a management meeting shall be to review the progress achieved and the plans for remaining work.

  - The responsibility of the parties for actions to be taken is to be decided by the Employer either at the management meeting or after the management meeting and stated in writing to be distributed to all who attended the meeting.

## C.	QUALITY CONTROL

### Identifying defects

  - The Employer or its authorized representatives shall check the Contractor's work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor's responsibilities. The Employer may instruct the Contractor to search for a Defect and to uncover and test any work that the Employer considers may have a Defect.

### Tests

  - If the Employer instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect the test shall be a Compensation Event.

### Correction of defects

  - The Employer shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion and is defined in the Contract Data. The Defects Liability Period shall be extended for as long as Defects remain to be corrected.

  - Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Employer’s notice.

### Uncorrected defects

  - If the Contractor has not corrected a Defect within the time specified in the Employer’s notice, the Employer will assess the cost of having the Defect corrected, and the Contractor will pay this amount and any delays caused to other works due to this shall be attributed to the Contractor.

## D.	COST CONTROL

### Bill of Quantities (BOQ)

  - The BOQ shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor.

  - The BOQ issued to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the BOQ for each item.

### Variations - NOT APPLICABLE

### Payments for Variations- NOT APPLICABLE

### Submission of bills for payment

  - The Contractor shall submit to the Employer monthly bills, in the electronic spread sheet, of the value of the work completed less the cumulative amount paid previously.

  - The jurisdictional authority shall check the Contractor's bill and determine the value of the work executed which shall comprise of (i) value of the quantities of the items in the BOQ completed and (ii) valuation of Compensation Events and forward to the payment authority.

  - Deleted.

  - The Employer/ authorized representative may exclude any item paid in a previous bill or reduce the proportion of any item previously paid in the light of later information.

### Payments

  - Payments shall be adjusted for deductions for advance payments, other than recoveries in terms of the contract and taxes, at source, as applicable under the law. The Employer shall pay the Contractor the within 60 days of submission of bill. The Contractor shall be liable to pay liquidated damages for short fall in progress

  - Items of the Works for which no rate or price has been entered in will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract.

### Compensation events

  - The following are Compensation events unless they are caused by the Contractor:

(a)	deleted

(b)	The Employer orders a delay or does not issue drawings, specifications or instructions required for execution of works on time.

(c)	The Employer instructs the Contractor to uncover or to carryout additional tests upon work which is then found to have no Defects.

(d)	The Employer gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons.

(e)	The effect on the Contractor of any of the Employer’s Risks.

(f)	The Employer unreasonably delays issuing a Certificate of Completion.

(g)	Other Compensation Events listed in the Contract Data or mentioned in the Contract.

  - If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date is extended. The Employer shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended.

  - As soon as information demonstrating the effect of each Compensation event upon the Contractor's forecast cost has been provided by the Contractor, it is to be assessed by the Employer and the Contract Price shall be adjusted accordingly. If the Contractor's forecast is deemed unreasonable, the Employer shall adjust the Contract Price based on Employer’s own forecast. The Employer will assume that the Contractor will react competently and promptly to the event.

  - The Contractor shall not be entitled to compensation to the extent that the Employer's interests are adversely affected by the Contractor not having given early warning or not having cooperated with the Employer.

### Tax

  - The rates quoted by the Contractor shall be deemed to be inclusive of all other taxes excluding GST, that the Contractor will have to pay for the performance of this Contract. The Employer will perform such duties in regard to the deduction of such taxes at source as per applicable law.

### Price Adjustment: (Applicable for Part –A: civil works only & not applicable for Part A: Electrical and electro-mechanical works and Part B: O&M works)

  - Contract price shall be adjusted for increase or decrease in rates and prices of labour, materials, fuels and lubricants in accordance with the following principles and procedures and as per formulae given in the Contract Data.

(a)	The price Adjustment shall apply for the work done from the date of commencement up to the end of original period of completion or extensions granted by the Employer and shall not apply to work carried out beyond the stipulated period of completion for reasons attributable to the Contractor;

(b)	Price Adjustment shall be admissible from the date of opening of tenders (original or extended)

(c)	The price adjustment shall be determined during each quarter from the formulae given in Contract Data.

(d)	Following expressions and meanings are assigned to the work done during the quarter:

R = Total value of work done during the quarter. It will include the amount of secured advance paid for (if any) during the quarter, less the amount of the secured advance recovered during the quarter. It will exclude value for works executed under variations for which price adjustment (if any) will be worked out separately based on the terms mutually agreed. It will also exclude the value of work done during the quarter which was programmed to be done prior to this quarter as per the work schedule in the agreement.

  - To the extent that full compensation for any rise or fall in costs to the contractor is not covered by the provisions of this or other Clauses in the Contract, the unit rates included in the contract shall be deemed to include amounts to cover the contingency of such other rise or fall in costs.

Note:  If the Finance department of GoK / C.A.O of the Board issues any clarification / amendments which might affect the P.A worked out / approved, the same shall be reviewed and any excess payment shall be recovered.

### Liquidated damages

  - The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the Contract Data for each day that the Completion Date is later than the Intended Completion Date (for the whole of the works or the mile stone as stated in the Contract Data). The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages does not affect the Contractor's liabilities.

  - If the Intended Completion Date is extended after liquidated damages have been paid, the Employer shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment of bill.

### Advance Payments:

  - The Employer shall make payment to the Contractor of the amounts stated in the Contract Data by the date stated in the Contract Data, against provision by the Contractor of an unconditional bank guarantee in a form acceptable to the Employer issued by a Nationalized/ Scheduled Banking amounts equal to the advance payment. The guarantee shall remain effective until the advance payment has been repaid, but the amount of the guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest will not be charged on the advance payment.

  - The Contractor shall use the advance payment only to pay for Mobilization expenses required specifically for execution of the Works. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Employer.

  - The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuation of the work done, compensation events or liquidated damages.

### Securities:

  - The Security deposit shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued for an amount and form and type of instrument acceptable to the Employer.

### Cost of Repairs:

  - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor's cost if the loss or damage arises from the Contractor's acts or omissions.

## E.	FINISHING THE CONTRACT

### Completion

  - The Contractor shall request the Employer to issue a Certificate of Completion of the Works and the Employer will do so upon deciding that the Work is completed.

### Taking over

  - The Employer shall take over the Site and the Works within seven days of issuing a certificate of Completion.

### Final account

  - The Contractor shall supply to the Employer a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Employer shall issue a Defect Liability Certificate and certify any final payment that is due to the Contractor within 90 days of ’receiving the Contractor's account if it is correct and complete. If it is not, the Employer shall issue within 90 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Employer shall decide on the amount payable to the Contractor and make payment within 60 days of receiving the Contractor’s revised account.

### As built drawings and /or Operating and Maintenance Manuals

  - “As built” 2D Drawings and/or operating and maintenance manuals are required. The Contractor shall supply them by the dates stated in the Contract Data.

  - If the Contractor does not supply the Drawings by the dates stated in the Contract Data with the Employer’s approval, the Employer shall withhold the amount stated in the Contract Data from payments due to the Contractor.

### Termination

  - The Employer may terminate the Contract if the other party causes a fundamental breach of the Contract.

  - Fundamental breaches of Contract include, but shall not be limited to the following:

(a)	The Contractor stops work for 45days when no stoppage of work is shown on the approved Program and the stoppage has not been authorized by the Employer;

(b)	Deleted

(c)	The Employer gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Employer; is a fundamental breach of Contract.

Note***: If the Tenderer fails to perform, then the Employer shall terminate the contract as per procedures. After termination, assign the balance work to another agency at the Risk & Cost of the Original Tenderer duly following procedures as per KW-4 document.

(d)	Deleted;

(e)	the Contractor has delayed the completion of works by the number of days for which the maximum amount of liquidated damages can be levied as defined in the Contract data

(f)	if the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulent practices in competing for or in executing the Contract. For the purpose of this paragraph: “corrupt practice” means the offering, giving, receiving or soliciting of anything of value to influence the action of a public official or another party in the procurement process or in contract execution. “Fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract in detriment of the Borrower, and includes collusive practice among Tenderers (prior to, during or after Tender submission) designed to establish Tender prices at artificial non-competitive levels and to deprive the Borrower of the benefits of free and open competition.”

  - When either party to the Contract gives notice of a breach of contract to the Employer for a cause other than those listed under Sub Clause 49.2 above, the Employer shall decide whether the breach is fundamental or not.

  - Notwithstanding the above, the Employer may terminate the Contract for convenience.

  - If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secure and leave the Site as soon as reasonably possible.

### Payment upon Termination

  - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Employer shall prepare bill for the value of the work done less advance payments received up to the date of the bill, less other recoveries due in terms of the contract, less taxes due to be deducted at source as per applicable law and less the percentage to apply to the work not completed as indicated in the Contract Data. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor the difference shall be a debt payable to the Employer.

  - If the Contract is terminated at the Employer's convenience or because of a fundamental breach of Contract by the Employer, the Employer shall prepare bill for the value of the work done, the reasonable cost of removal of Equipment, repartition of the Contractor's personnel employed solely on the works, and the Contractor's costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the contract, and less taxes due to be deducted at source as per applicable law and make payment accordingly.

### Property

51.1	All materials on the Site, Plant, Equipment, Temporary Works and Works are deemed to be the property of the Employer, if the Contract is terminated because of a Contractor’s default.

### Release from performance

  - If the Contract is frustrated by any event entirely outside the control of either the Employer or the Contractor the Employer shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which commitment was made.

### Additional Clauses:

  - The Additional Clauses are added in connection with requirement of the project and contract implementation. The details of the additional clauses are given under the Contract Data.

## F.	SPECIAL CONDITIONS OF CONTRACT

C Details

#### Arbitration: The Arbitration clause is withdrawn as per circular of the GoK vide No: LAW – LAC/198 /2024 dated 16.11.2024.

# SECTION 6: CONTRACT DATA

| Clause Reference | Clause Description |
| --- | --- |
| CC 1.1 | The Employer is: The Chief Engineer, KUWSDB, Kalaburagi, Karnataka. |
|  | The start date shall be the date of issue of notice to proceed with the work |
|  | Employer Representative: Executive Engineer of the concerned area/slice as the case maybe. The Employer may nominate any other officer of the KUWS&DB as Employer’s representative for the execution of the work/contract. |
|  | - Force Majeure Event Any of the following events which is beyond the control of the party claiming to be affected thereby (“Affected Party”) and which the Affected Party has been unable to overcome or prevent despite exercise of due care and diligence, and prevents the Affected Party from performing or discharging its obligations under this Agreement, shall constitute Force Majeure Event: - act of God or - any war, hostility, acts of public enemy, civil commotion, sabotage, fires, floods, explosions, epidemics quarantine restrictions, strikes, labour disruptions, riots or any other industrial disturbances not arising on account of the acts or omissions of the Contractor, for which no offsetting compensation is payable to the Contractor/s. - acts of expropriation, compulsory takeover of the Project Site and Project Facilities by the Government or any part thereof or - Any judgment or any order of a court of competent jurisdiction or statutory authority in India made against the Contractor in any proceedings which is non-collusive and duly prosecuted by the Contractor. - Obligations of Parties - As soon as practicable and in any case within 7 (seven) days of the date of occurrence of a Force Majeure Event or the date of knowledge thereof, the Affected Party shall notify the other party of the same setting out, inter alia, the following in reasonable detail: - the nature and extent of the Force Majeure Event; - the estimated Force Majeure Period; - the nature of and the extent to which, performance of any of its obligations under this Contract is affected by the Force Majeure Event; - the measures which the Affected Party has taken or proposes to take to alleviate/mitigate the impact of the Force Majeure Event and to resume performance of such of its obligations affected thereby; and - any other relevant information concerning the Force Majeure Event, and /or the rig4hts and obligations of the parties under this Contract. - As soon as practicable and in any case within 5 (five) days of notification by the Affected party in accordance with the preceding Clause 6.2 (a), the parties shall meet and hold discussions in good faith and where necessary conduct physical inspection/survey of the project site in order to: - assess the impact of the underlying Force Majeure Event, - to determine the likely duration of Force Majeure Period and, - to formulate damage mitigation measures and steps to be undertaken by the parties for resumption of obligations, the performance of which shall have been affected by the underlying Force Majeure Event. - The Affected Party shall during the Force Majeure Period provide to the other Party with regular (not less than fortnightly) reports concerning the matters set out in the preceding Clause 6.2 (b) as also any information, details or document, which the Parties may reasonably require. - Performance of Obligations If the Affected Party is rendered wholly or partially unable to perform any of its obligations under this Contract because of a Force Majeure Event, it shall be excused from performance of such obligations to the extent it is unable to perform the same on account of such Force Majeure Event provided that: - due notice of the Force Majeure Event has been given as required by the preceding Article 6.2; - the excuse from performance shall be of no greater scope and of no longer duration than is necessitated by the Force Majeure Event; - the Affected Party has taken all reasonable efforts to avoid, prevent, mitigate and limit damage, if any, caused or is likely to be caused to the Project as a result of the Force Majeure Event and to restore the Project, in accordance with the Good Industry Practice and its relative obligations under this Contract; - when the Affected Party is able to resume performance of its obligations under this Agreement, it shall give to the other party written notice to that effect and shall promptly resume performance of its obligations hereunder, the non-issue of such notice being no excuse for any delay for resuming such performance; - the Affected Party shall continue to perform such of its obligations which are not affected by the Force Majeure Event and which are capable of being performed in accordance with this Agreement; - any insurance proceeds received shall be entirely applied to repair, replace or restore the Project Site & Project Facilities damaged on account of the Force Majeure Event, in accordance with Good Industry Practice, unless otherwise agreed to by the Employer. - Termination due to Force Majeure Event - Termination - If a Force Majeure Event, is an event described under Clause 6.1(a), (b) and (d), continues or is in the reasonable judgment of the Parties likely to continue beyond a period of 120 (one hundred and twenty) days, the parties may mutually decide to terminate this Contract or continue this Contract on mutually agreed revised terms. If the parties are unable to reach an agreement in this regard, the Affected Party shall after the expiry of the said period of 120 (one hundred and twenty) days, be entitled to terminate this Agreement. - If the Force Majeure Event is an event described in Clause 6.1 (c) and the Contractor having exhausted the remedies available to him under the Applicable Laws, has been unable to secure the remedy, the Contractor shall be entitled to terminate this Agreement. - Provided further, the Employer may at its sole discretion have the option to terminate this Contract at any time after the occurrence of any event described under Clause 6.1(c) - Termination Notice If either party, having become entitled to do so, decides to terminate this Contract pursuant to the preceding Clause 6.4 (a) (i) or 6.4 (a) (ii), it shall issue Termination Notice setting out ; - in sufficient detail the underlying Force Majeure Event; - the Termination Date which shall be a date occurring not earlier than 60 (sixty) days from the date of Termination Notice; - the estimated Termination Payment including the details of computation thereof and; - any other relevant information. - Obligation of Parties Following issue of Termination Notice by either Party, the Parties shall promptly take all such steps as may be necessary or required to ensure that; - the Termination Payment, if any, payable by the Employer in accordance with the following Clause 6.4 (d) is paid to the Contractor on the Termination Date and - the Project Site along with the Project Facilities are handed back to the Employer by the Contractor on the Termination Date free from all Encumbrance. - Payment upon Termination Upon Termination of this Contract due to a Force Majeure Event, Employer shall pay to the Contractor the appropriate amount until such Termination as per the milestone achieved by the Contractor and in accordance with the payment schedule provided at Schedules 1 and 3 respectively provided the Employer shall be entitled to deduct from this payment any amount due and recoverable by the Employer from the Contractor as on the Termination Date and release the Performance Security. - Liability for other losses, damages etc. Save and except as expressly provided in this Article, neither party hereto shall be liable in any manner whatsoever to the other party in respect of any loss, damage, cost, expense, claims, demands and proceedings relating to or arising out of occurrence or existence of any Force Majeure Event. |
| CC 13 | 13.1 Insurance requirements are as under for the tender period: Si. No; Type of Cover; Minimum cover for Insurance. (a); Works and of materials Plant and machineries; The sum stated in the Agreement plus 20%. (b); Loss or damage to equipment; Full replacement cost. Loss or damage to property of Third Party; Full replacement cost. (c); Personal injury insurance or death (i) for Third Party.; For normal works it could be Rs.20 lakhs to cover 4 persons @ Rs.5 lakhs each.. (ii) for Contractor’s employees or labour.; In accordance with the statutory requirements applicable to Karnataka.. Note: For the purpose of this Contract Clause 13 along with its sub-clauses shall also be applicable for O&M period. In addition to above the contractor is obligated to Insure all the plant & equipment’s for Fire & Any other risks during the contract period. |
| CC 14 | The Contractor shall be wholly responsible to identify the suitable sources for quarry materials required for the works, such as earth, sand, stone, murrum, etc., and to make his own arrangements for collection and transportation of the materials irrespective of the leads and lifts required. The quarry thus identified by the Contractor should have proper license from the Government of Karnataka. All materials that is quarried and transported by the Contractor shall satisfy the requirements set forth in the Specifications shall be subject to the approval of the Employer. The Contractor is deemed to have taken this into account while offering his rates and no claim whatsoever shall be entertained for extra costs on this account. The Govt. notification No. CI-MMN/202/2023 dated: 01-01-2025 and circular No. MGD/DCB/2024-25 dated: 24-01-2025 is also binding on the successful bidder and latest amendments from time to time if any is also binding on the successful bidder. |
| CC 15 | The Employer will provide the additional information if any regarding the project. |
| CC 16 | The Tenderer is required to prepare DSR including design/drawings etc., complete in accordance with the Technical Specification (Section 7) and in accordance with the terms of the Contract. The Contractor (Tenderer) is required to submit Workplan, Material supply schedule to execute the work. The same shall be reviewed & approved by the Employer. The type of Material for construction (MoC)/E&M should be strictly in accordance with Technical Specification-Section-7, no change in MoC shall be allowed without prior approval of the Employer The DSR /design/drawings etc. shall be checked by Employer. The Tenderer shall adhere to the Technical Specifications / Contract terms while submissions. It is further clarified that the DSR / Design / Drawings as prepared by the Tenderer should give the details of the quantities of various items proposed by the Tenderer in DSR. |
| CC 17 & 26 | The Intended Completion Date for the whole of the Works is 18 months with the milestones as provided in Schedule 1- Physical Activity Progress. In addition, the Intended Completion Date for each town / city shall be as under; Name of City/ Town; Construction Time Period; O&M Period*. Textile Park; 18 Months; 60 Months. Note: After completion of capital works and before commencement of O&M the supplementary agreement shall be entered between KUWS&DB and Contractor for taking up of O&M. The O&M agreement shall come into effect after completion of the construction activities and comprehensive commissioning of the project. The O&M cost will be borne by Handloom & Textile Department, but not by KUWS & D Board/ GoK/GoI. |
| CC 21.1 | Possession of the site – Please refer Securing the land in Section 7: Technical Specifications (Employer’s Requirement) |
| CC 25 | Program: The Contractor shall submit a detailed time program to the Employer within 28 days after receiving the notice to commence the Works. The Contractor shall also submit a revised program whenever the previous program is inconsistent with actual progress or with the Contractor’s obligation. Each program shall include: - The order in which the Contractor intends to carry out the Works, including the anticipated timing of each stage of design, Contractor’s Documents, procurement, manufacture, inspection, delivery to Site, construction, erection, testing, commissioning and trial operations; - The periods of reviews and for any other submissions, approvals and consents specified in the Employer’s Requirements; - The sequence and timing of inspections and tests specified in the Contract; - A supporting report which includes: - A general description of the methods which the Contractor intends to adopt and of the major stages in the execution of the works; and’ - Details showing the Contractor’s reasonable estimate of the number of each class of Contractor’s personnel and of each type of Contractor’s equipment required on the Site for each major stage If at any time, the Employer gives notice to the Contractor that a program fails (to the extent stated) to comply with the Contract or to be inconsistent with the actual progress and the Contractor’s stated intentions, the Contractor shall submit a revised program to the Employer. Progress Reports: Monthly progress reports shall be prepared by the Contractor and submitted to the Employer in six copies. The first report shall cover the period up to the end of the first calendar month following the Commencement Date. Reports shall be submitted thereafter each within 7 days after the last day of the period to which it relates. Reporting shall continue until the Contractor has completed all work which is known to be outstanding at the completion date stated in the Taking Over Certificate for the Works. Each Report should include: - Charts and detailed descriptions of progress, including each stage of design, Contractor’s Documents, procurement, manufacture, delivery to Site, construction, erection, testing, commissioning and trail operation; - Photographs showing the status of manufacture and of progress at the Site; - For the manufacture of main items of Plant and Materials, the name of the manufacturer, manufacture location, percentage progress, and the actual and expected dates of: - Commencement of manufacture; - Contractor’s inspections; - Tests; and - Shipment and arrival at the Site; - Details of Contractor’s personnel and equipment; - Copies of quality assurance documents; - List of variations, including details of any hazardous incidents and activities relating to environmental aspects and public relations; and - Comparisons of actual and planned progress, with details of any events or circumstances which may jeopardize the completion in accordance with the Contract, and the measures being (or to be) adopted to overcome delays; |
| CC 29 | The Employer will engage a Third Party for inspection at manufacturer’s works and also the work site activities. The fee for the third-party inspection shall be paid by the Employer. The items for Third Party Inspection and the stages of Inspection are given in ANNEXURE D. The list is illustrative and not exhaustive. The Employer’s personnel shall at all times: - Have full access to all parts of the Site and to all places from which natural materials are being obtained; and - During production, manufacture and construction (at the Site and elsewhere) be entitled to examine, inspect measure and test the materials and workmanship and to check the progress of manufacture of Plant and production and manufacture of materials. The Contractor shall give the Employer’s personnel full opportunity to carry out these activities, including providing access, facilities, permissions and safety equipment. No such activity shall relieve the Contractor from any obligation or responsibility. The Contractor shall give notice to the Employer whenever any work is ready and before it is covered up, put out of sight, or packaged for storage or transport. The Employer shall then either carry out the examination, inspection, measurement or testing without unreasonable delay, or promptly give notice to the Contractor the Employer does not required to do so. If the Contractor fails to give the notice, he shall, if and when required by the Employer, uncover the work and thereafter reinstate and make good, all at the Contractor’s cost. #### Procurement of materials and equipment: The Contractor shall procure and use ISI marked materials and equipment or those conforming to relevant Bureau of Indian Standards or any applicable standards. The Contractor shall obtain approval to the drawings and the Quality Assurance Plan (QAP) of the materials to be used in the project by the competent authority before execution. |
| CC 31 | The Defects liability Period is One Year (365 days) for CAPEX Works. |
| CC 33 | Bill of Quantities: The Tenderer shall quote for the activities / components involved for completion of work on DBT basis and the tenderer should get approval for the break up schedule for payment from Employer based on which payment will be made for each item. The contractor is responsible for submitting of bills duly supported by hard copy of detailed measurement of works using Electronic Spread Sheet and making computation there off. The contractor shall submit diskette or CD-ROM in addition to the hard copy in the format as per ANNEXURE-E. Royalties: The Employer shall deduct Royalties on materials used in the works from progress payments to the Contractor at the rates specified in the “Karnataka Minor Minerals Concession Rules 2003” as published by the Commerce and Industries Department (Mines) and as amended from time to time. The latest amendments issued by the Mines and Geology Department will be followed. The contractors are required to procure the minor minerals from the government licenced query lease holders only obtaining the Mineral Dispatch Permits (MDPs) and produce these permits to the bills paying authorities. In such cases the royalty charges from the bills shall not be deducted. If the contractor fails to produce the Mineral Dispatch Permits, penalty at five times the applicable royalty charges along with the royalty from the bills of the contractor will be deducted as per the Govt. notification No. CI-MMN/202/2023 dated: 01-01-2025 and circular No. MGD/DCB/2024-25 dated: 24-01-2025 and latest amendment. Karnataka Building and other Construction Worker’s Welfare Cess: The Employer shall deduct Cess from the bills of the Contractor at the rates as may be notified from time to time under the building and other Construction Workers Welfare Cess Act 1996. The current rate is 1% of the tender amount. In addition GO No.LD/300/LET/2006, dated 18-01-2007 and addendum GO No.LD/95/ LET/2013, dated 01-04-2013 with latest amendments shall be part of the documents. O&M Payment: (a) The O&M cost shall be borne by the Handloom and Textile Department. The O&M agreement shall come into effect after completion of the construction activities after successful commissioning of the project. b) The employer shall not be liable for any compensation in the event of non-Commencement of O & M due to non-receipt of O& M fund from Handloom and Textile Department. |
| CC 34 | Variation: No variations are applicable in this contract. However, variation will arise only in case the Employer intends to add any additional scope of work apart from the original scope defined proposed to be taken up under this contract. The variation applicable shall be as per the scope of work envisaged for such additional scope or work and as mutually agreed between the Parties and at the discretion of the Employer. Value Engineering: The Contractor may at any time submit to the Employer a written proposal which in the Contractor’s opinion will, if adopted, (i) accelerate completion, (ii) reduce the cost to the Employer of executing, maintaining or operating the Works, (iii) improve the efficiency or value to the Employer of the completed Works, or (iv) otherwise be of benefit to the Employer. The proposal shall be prepared at the cost of the Contractor and shall include the items as specified in the variation procedure. |
| CC 35 | No payments for variations are applicable in this contract. Payment for variation shall be applicable only in case of any variation arising due to addition new scope of work by the Employer apart from the scope of work which is already proposed under this contract and the corresponding scope of work and payment for such additional scope of work and at the discretion of the Employer as mutually agreed. |
| CC 36 | Minimum amount of each bill to be submitted by the Contractor for claim shall not be less 5% of the Total Contract Price. |
| CC 37.1 | The time limit for payment to the contractor is 60 days from the date of submission of the bills. |
| CC 37.3 | i) Supply payment for Materials shall be paid only for the requirement of materials for the next 3 months only, as per the approved work plan and Material supply schedule as per Contract condition. ii) Before making RA (Running account) Bill payment, the corresponding permanent assets/works executed should be mapped in GIS portal, a mechanism shall be placed. |
| CC 37.4 | The payment shall be as per the SCHEDULE 3: Schedule of Payment |
| CC 39.1 | Taxes shall mean all taxes and duties applicable for execution of this Contract except GST. The GST shall be paid by the Employer to the Contract after statutory deduction as per the prevailing rates during payment. Note: The increase in GST shall not be paid in the extended period of contract for which the contactor alone is responsible for delay as determined by the authority while granting the extension of time |
| CC 40 | Price Adjustment Formula: R= Total value of work done during the quarter of Bill of Quantities. It will include the amount of secured advance paid for (if any) during the quarter, less the amount of the secured advance recovered during the quarter. It will exclude value for works executed under variations for which price adjustment (if any) will be worked out separately based on the terms mutually agreed. For Part-A Electro-mechanical works and Part – B (O&M Work) Price Adjustment is not applicable. - Adjustment for labour component: Price adjustment for increase or decrease in the cost due to labour shall be paid in accordance with the following formula: VL = 0.85 X PL /100 X R X(Li - Lo ) /Lo where, VL = Increase or decrease in the cost of work during the quarter under consideration due to changes in rates for local labour; Lo = The average Consumer Price Index* for industrial workers for Hubli-Dharwad Centre for the quarter preceding the date of opening of tenders as published by the Labour Bureau, Ministry of Labour, Government of India; Li = The average Consumer Price Index* for industrial workers for Hubli-Dharwad Centre for the quarter under consideration as published by Labour Bureau, Ministry of Labour, Government of India PL = Percentage of labour component of the work *The Index numbers are available in the web site, http://labourbureau.nic.in/indtab.html. - Adjustment for Cement Component: Price adjustment for increase or decrease in the cost of cement component procured by the contractor shall be paid in accordance with the following formula. VC = 0.85 X PC /100 X R X (Ci - Co ) /Co where, VC = Increase or decrease in the cost of the work during the quarter under consideration due to changes in the rates for cement; Co = The All-India average Wholesale Price Index** for cement (Ordinary Portland Cement) for the quarter preceding the date of opening of the tenders as published by the Office of Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi; Ci = The All-India average Wholesale Price Index** for cement (Ordinary Portland Cement) for the quarter under consideration as published by the Office of Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi PC = Percentage of cement component of the work Note: For the application of this clause index of Ordinary Portland Cement has been chosen to represent Cement Group **The index number are available in the web site http://eaindustry.nic.in - Adjustment for Reinforcement Steel component: Price adjustment for increase or decrease in the cost of Reinforcement Steel procured by the contractor shall be paid in accordance with the following formula. Vms = 0.85 X Pms/100 X R X (Si – So)/So where, Vms = Increase or decrease in the cost of work during the quarter under consideration due to changes in the rates for Reinforced Steel; So = The all-India average Wholesale Price Index for Mild Steel-Long products for the quarter preceding the date of opening of Bids as published by the Office of Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi Si = The all-India average Wholesale Price Index for Mild Steel-Long products for the quarter under consideration as published by the Office of Economic Advisor, Ministry of Commerce and Industry, New Delhi PmS = Percentage of steel component of the work Note: For the application of this clause, index of Mild Steel-Long products have been chosen to represent mild steel group. - Adjustment for DI component: Price adjustment for increase or decrease in the cost of DI Pipe procured by the contractor shall be paid in accordance with the following formula. Vd = 0.85 X Pd /100 X R X (Si – So)/So where, Vd = Increase or decrease in the cost of work during the quarter under consideration due to changes in the rates for pig iron; So = The all-India average Wholesale Price Index for pig iron for the quarter preceding the date of opening of Bids as published by the Office of Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi Si = The all-India average Wholesale Price Index for pig iron for the quarter under consideration as published by the Office of Economic Advisor, Ministry of Commerce and Industry, New Delhi PS = Percentage of DI component of the work Note: For the application of this clause, index of pig iron has been chosen to represent steel group. - Adjustment for MS Pipe component: Price adjustment for increase or decrease in the cost of MS Pipes procured by the contractor shall be paid in accordance with the following formula. Vms = 0.85 X Pms/100 X R X (Si – So)/So where, Vms = Increase or decrease in the cost of work during the quarter under consideration due to changes in the rates for MS Pipes; So = The all-India average Wholesale Price Index** for Mild Steel-Steel Pipes and Tubes for the quarter preceding the date of opening of Bids as published by the Office of Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi Si = The all-India average Wholesale Price Index** for Mild Steel-Steel Pipes and Tubes for the quarter under consideration as published by the Office of Economic Advisor, Ministry of Commerce and Industry, New Delhi. PmS = Percentage of steel component of the work. **The index number are available in the web site https://eaindustry.nic.in Note: For the application of this clause, index of “Mild Steel-Steel Pipes Tubes and poles” has been chosen to represent mild steel group - Adjustment of Bitumen Component: Price adjustment for increase or decrease in the cost of bitumen shall be paid in accordance with the following formula: VB = 0.85 x PB/100 x R x (Bi – Bo)/Bo, Where VB = Increase or decrease in the cost of work during the quarter under consideration due to changes in the rate for bitumen. Bo = The official retail price of bitumen at the IOC /HPCL/BPL or any other depot at Kalaburgi city on the day 30 days prior to the date of opening of Bids. Bi = The official retail price of bitumen at the IOC/HPCL/BPL or any other depot at Kalaburgi city for the 15th day of the middle calendar month of the quarter under consideration. PB = Percentage of bitumen component of the work. - Adjustment for Fuel and Lubricants: Price adjustment for increase or decrease in the cost of Fuel and Lubricants shall be paid in accordance with the following formula: VF = 0.85 X PF/100 X R X (Fi – Fo)/Fo , where, VF = Increase or decrease in the cost of work during the quarter under consideration due to changes in the rates for Fuel and Lubricants. Fo= The official rate of High-Speed Diesel (HSD) at the IOC/HPCL/BPL or other consumer pump at Kalaburgi city on the day 30 days prior to the opening of bids. Fi = The official rate of HSD at the IOC/HPCL/BPL or other consumer pump at Kalaburgi city on the 15th day of the middle of the calendar month of the quarter under consideration. FB = Percentage of Fuel and Lubricant component of the work. Note: For the application of this the price of HSD has been chosen to represent Fuel and Lubricant Group. - Adjustment for Plant and Machinery Spares Component: Price adjustment for increase or decrease in the cost of plant and machinery spares procured by the contractor shall be paid in accordance with the following formula: VP = 0.85 X PP/100 X R X (Pi – Po)/Po , where, VP = Increase or decrease in the cost of work during the quarter under consideration due to changes in the rates for plant and machinery spares. Po = The all-India average Wholesale Price Index for mining, quarrying and construction for the quarter preceding the date of opening of bids, as published by the Office of the Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi Pi = The all-India average Wholesale Price Index for mining, quarrying and construction for the quarter under consideration as published by the Office of the Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi PP = Percentage of Plant and Machinery Spares component of the work. Note: For the application of this Clause index of mining, quarrying and construction has been chosen to represent the Plant and Machinery Spares Group. - Adjustment for Other materials: Price adjustment for increase or decrease in the cost of other materials other than cement, steel, bitumen and Fuel and Lubricants, procured by the contractor shall be paid in accordance with the following formula: VM = 0.85 X PM/100 X R X (Mi – Mo)/Mo , where, VM = Increase or decrease in the cost of work during the quarter under consideration due to changes in the rates for local materials other than cement, steel, bitumen and Fuel and Lubricants. Mo = The All-India average wholesale price index for all commodities for the quarter preceding the date of opening of bids, as published by the Office of the Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi Mi = The All-India average wholesale price index for all commodities for the quarter under consideration as published by the Office of the Economic Advisor, Ministry of Commerce and Industry, Government of India, New Delhi PM = Percentage of other material component (Other than cement, steel, bitumen and Fuel and Lubricants) of the work. The following percentages will govern the price adjustment for Works items of the contract: Sl. No.; Description; Percentage. 1; Cement; 2%. 2; Reinforcement Steel; 7%. 3; MS pipes and Tubes; 0.5%. 4; D.I. Pipes and Specials; 42%. 5; Labour; 17.0%. 6; Plant and machinery spares; 9%. 7; Bitumen; 0.5%. 8; POL - Fuel and lubricants; 4%. 9; Other materials - Pm; 18%. Total; 100%. #### Transportation: The Contractor shall at its own risk and expense transport all the Plant and Equipment and the Contractor’s Equipment to the Site by the mode of transport that the Contractor judges most suitable under all the circumstances. Unless otherwise provided in the Contract, the Contractor shall be entitled to select any safe mode of transport operated by any person to carry the Plant and Equipment and the Contractor’s Equipment. Upon dispatch of each shipment of the Plant and Equipment and the Contractor’s Equipment, the Contractor shall notify the Employer by telex, cable, facsimile or Electronic Data Interchange (EDI) of the description of the Plant and Equipment and of the Contractor’s Equipment, the point and means of dispatch, arrival at the Site. The Contractor shall be responsible for obtaining, if necessary, approvals from the authorities for transportation of the Plant and Equipment and the Contractor’s Equipment to the Site. The Employer shall use its best endeavors in a timely and expeditious manner to assist the Contractor in obtaining such approvals, if requested by the Contractor. The Contractor shall indemnify and hold harmless the Employer from and against any claim for damage to roads, bridges or any other traffic facilities that may be caused by the transport of the Plant and Equipment and the Contractor’s Equipment to the Site. |
| CC 40.1 | Price Adjustment is applicable only for Part – A as per G.O. No. FD 3 PCL 2008, dtd:21.11.2008 and No. 791 EXP – 12 / 2015, Dtd: 26.02.2016. Price Adjustment is not applicable for Pumping Machinery / Electro-Mechanical works and for O&M works (Part-B). |
| CC 41 | The maximum liquidated damages for the whole of the works can be levied up to 10% (ten percent) of final contract price. The applicable liquidated damages are provided in SCHEDULE-2. |
| CC 42 | Mobilization; 5% of the Contract price for PART A (Design, Build, Testing & Commissioning); On submission of unconditional Bank Guarantee (to be drawn before end of 20% of Contract period) as per the format provided at Section – 11.. Recovery of advance payment for mobilization: The advance payment shall be recovered with percentage deductions from the interim payments certified by the Engineer under the Contract. Deductions shall commence in the next Interim Payment Certificate following that in which the total of all such payments to the Contractor has reached not less than 15 percent of the Contract Price or 4 months from the date of payment of first instalment of advance, whichever period concludes earlier, and shall be made at the rate of 7.5% percent of the amounts of all Interim Payment Certificates until such time as the loan has been repaid, always provided that the loan shall be completely repaid prior to the expiry of the original time for completion pursuant to Clauses 17 and 26. |
| CC 43 | The following securities to be provided by the Contractor shall form part of the Contract. - Security Deposit for an amount equivalent to 5% of the Contract price for PART A (Design, Build, Testing & Commissioning) valid until a date 30 days beyond the date of completion of Defects Liability Period that shall be released after Defect Liability Period is completed for PART A by the Employer. - Security Deposit for an amount equivalent to 5% of the Contract Price for PART B (Operation & Maintenance) valid until a date 60 days beyond the date of completion of O&M period that shall be released 30 days after issue of Completion Certificate for PART B by the Employer. |
| CC 45 | #### Tests on Completion: The Contractor shall carry out the tests on Completion in accordance with this Clause after providing the documents (as built drawings as well as Operation and Maintenance Manuals. The Contractor shall give to the Employer not less than 21 days’ notice of the date after which the Contractor will be ready to carry out each of the Tests on Completion. Unless otherwise agreed, Tests on Completion shall be carried out within 14 days after this date, on such day or days as the Employer may instruct. The Tests on Completion shall be carried out in the following sequence: - Pre-commissioning tests, which shall include the appropriate inspections and functional tests to demonstrate that each item of Plant can safely undertake the next stage; - Commissioning tests, which shall include the specified operational tests to demonstrate that the Works or Section can be operated safely and as specified under all available operating conditions; and - Trial operation, which shall demonstrate that the Works perform reliably and in accordance with the Contract. During trial operation, when the Works are operating under stable conditions, the Contractor shall give notice to the Employer that the Works are ready for any other Tests on Completion, including performance tests to demonstrate whether the Works conform with criteria specified in the Employer’s Requirements and with the Schedules of Guarantees. Trial operation shall not constitute a taking over under Clause. Unless otherwise stated elsewhere any product produced by the Works during trial operation shall be the property of the Employer. In considering the results of the tests on Completion, the Employer shall make allowances for the effect of any use of the Works by the Employer on the performance or other characteristics of the Works. As soon as the Works have passed each of the Tests on Completion, the Contractor shall submit a certified report of the results of these Tests to the Employer. #### Delayed Tests If the Tests on Completion are being unduly delayed by the Employer it shall be a compensation event. If the Tests on Completion are being unduly delayed by the Contractor, The Employer may by notice require the Contractor to carry out the Tests within 21 days after receiving the notice. The Contractor shall carry out the Tests on such day or days within that period as the Contractor may fix and of which he shall give notice to the Employer. If the Contractor fails to fails to carry out the Tests on Completion within the period of 21 days, the Employer’s personnel may proceed with the Tests at the risk and cost of the Contractor. The Tests on Completion shall then be deemed to have been carried out in the presence of the Contractor and the results of the Tests shall be accepted as accurate. #### Re-Testing If the Works, or a component of the Work, fail to pass the tests on completion, Rejection Clause shall apply, and the Employer or the Contractor may require such failed tests, and the Tests on Completion to be repeated under the same terms and conditions. #### Failure to Pass Tests on Completion If the Works or a component of the Work fails to pass the tests on completion repeated under Sub-Clause 14.3, the engineer shall be entitled to: a) Require the contractor to make good the defects or ensure that the materials or plant comply with the contract and order further repetition of tests on completion under Sub-Clause 14.3; or b) If the failure deprives the Employer of substantially the whole benefit of the Works or component, reject the Works or component of the Works (as the case may be), in which event the employer shall have the same remedies against the contractor as are provided under Clause 19; or In the event that the performance of any item of plant or equipment tests out to be marginally less than stipulated under the contract, then the Employer, at his sole discretion, may authorize to issue Taking Over Certificate for said component as an alternative to the other remedies under this Sub-Clause. In such case, the Employer shall determine an appropriate reduction in the contract price with due regard to the circumstances, the actual performance of the item of plant or equipment compared to the specified performance, and the impact of the reduction in performance on the overall performance of the facility as a whole. Such reduction in the contract price shall be binding on the Contractor, and the Contractor shall then proceed in accordance with his other obligations under the contract. |
| CC 46 | #### Taking over the Works and components of the works: The Employer shall take over the Works when all the Works are completed by the Contractor. The Contractor may apply by notice to the Employer for an initial taking Over Certificate not earlier than 14 days before all the Works in the Contractor’s opinion, be complete and ready for taking over. The Employer shall within 21 days after receiving the Contractor’s application: - Issue the initial Taking Over certificate to the Contractor, stating the date on which all the Works are completed in accordance with the Contract, except for any minor outstanding work and defects which will not substantially affect the use of the Works or component for their intended purpose (either until or whilst this work is completed and these defects are remedied); or - Reject the application, giving reasons and specifying the work required to be done by the Contractor to enable the initial Taking over Certificate to be issued. The Contractor shall then complete this work before issuing further notice under this Clause. If the Employer fails either to issue the initial taking Over Certificate or to reject the Contractor’s application within the period of 21 days, and the Works are substantially in accordance with the Contract, the initial Taking over Certificate shall be deemed to have been issued on the last day of that period. Upon the issue of an initial Taking over Certificate, the Contractor shall clear away and remove, from and Works to which the initial Taking over Certificate refers, all Contractor’s equipment, surplus material, wreckage, rubbish and temporary works. The Contractor shall leave the Site and the Works in a clean and safe condition. However, the Contractor may retain on Site, during the Defect Liability Period, such goods and equipment as are required for the Contractor to fulfill obligations under the Contract. #### Performance Certificate Performance of the Contractor’s obligations shall not be considered to have been completed until the Employer has issued the Performance certificate to the Contractor stating the date on which the Contractor completed the obligations under the Contract. The Employer shall issue the Performance Certificate within 28 days after the latest of the expiry dates of the Defect Liability Period. #### Clearance of Site: Upon receiving the Performance Certificate, the Contractor shall remove any remaining Contractor’s equipment, surplus material, wreckage, rubbish and temporary works from the Site. If these items have not been removed within 28 days of issue of the Performance, The Employer may get the site cleared at the cost of the Contractor and deduct the expenditure from the amounts due to the Contractor. |
| CC 48 | The date by which “as-built” drawings (in scale 1:500) in 5 sets and soft copy to the employer in appropriate format are required is within 30 days of issue of certificate of completion of Whole or Section of the Work as the case may be. As built drawings shall be submitted zone-wise for all pipeline including associated structures. |
|  | The date by which Operating and Maintenance Manuals 5 sets and soft copy to the employer in appropriate format are required is within 30 days of issue of certificate of completion of Whole or Section of the Work as the case may be. |
|  | The amount to be withheld for failing to supply “as built” drawings or supply of Operation and Maintenance Manuals by the date required is 1% of CP (Contract Price) |
|  | #### Operation and Maintenance Manual: Before commencement of the trial run of the plant, the Contractor shall submit 6 (six) copies of the operation and maintenance manual in English and Kannada languages containing descriptions, illustrations, sketches, drawings, sectional drawings, sectional arrangement view and manufacturer’s part numbers (as may be instructed by the Employer) to enable the connections, functions, operation and maintenance of all components of the complete plant to be easily followed and for all parts to be easily identified to facilitate ordering of the replacement parts. Exploded views where appropriate shall be used to clarify. The Manuals shall also include the following: - Technical data of each equipment and their performance; - Instructions for servicing and overhauling; - Particulars of lubricating oils and grease to be used, also alternative indigenous commercial Lubricating oils suitable for use; - Performance curves for all units regarding efficiency loading and output; - Performance curves for the motors; - List of tools mounted on wall panels; - List of spares provided in the spares box; - Spare parts list (Fast moving and slow moving separately) with manufacturer’s part numbers; - List of photographs of the plant and machinery as fabricated by the manufacturers; - Dos and Don’ts’s; - Safety precautions to be taken etc. #### Replacement Guarantee - The supplier guarantees that the all Goods & equipment’s supplied under this Contract are new, unused, of the most recent or current models and that they incorporate all recent improvements in design and materials unless provided otherwise in the Contract. The supplier further Guarantees that all Goods supplied under this contract shall have no defect arising from design, materials, or workmanship or from any act or omission of the Supplier that may develop under normal use of the supplied Goods in the conditions prevailing in the country of final destination. - The replacement guarantee for all Goods &equipment’s shall remain valid for one year after the Goods or any portions thereof as the case may be, have been commissioned. The supplier shall, in addition, comply with the performance and / or consumption guarantees specified under the Contract. - Upon receipt of such notice, the Supplier shall, with all reasonable speed replace the defective Goods &equipment or parts thereof, free of cost at the ultimate destination. The supplier shall take over the replaced parts / Goods & equipment’s at the time of their replacement. No claim whatsoever shall lie on the Purchaser for the replaced parts / Goods &equipment thereafter. - If the supplier, having been notified, fails to remedy the defect(s) within fifteen days, the Purchaser may proceed to take such remedial action as may be necessary, at the Supplier’s risk and expense and without prejudice to any other rights which the Purchaser may have against the Supplier under the Contract. Until such replacement is done, the agency shall take necessary action so that the plant efficiency will not be affected. |
| CC 49.2 | The following events shall also be fundamental breach of the contract The contractor has contravened Sub-clause 7.1 and Clause 9 of CC. |
| CC 50.1 | The percentage to apply to the value of the work not completed representing the Employer's additional cost for completing the Works shall be 30 percent |
| CC 53 | #### Installation - Setting Out/Supervision/Labour - Bench Mark: The Contractor shall be responsible for the true and proper setting-out of the Facilities in relation to bench marks, reference marks and lines provided to it in writing by or on behalf of the Employer. If, at any time during the progress of installation of the Facilities, any error shall appear in the position, level or alignment of the Facilities, the Contractor shall forthwith notify the Project Manager of such error and, at its own expense, immediately rectify such error to the reasonable satisfaction of the Employer’s Representative. If such error is based on incorrect data provided in writing by or on behalf of the Employer, the expense of rectifying the same shall be borne by the Employer. - Contractor’s Supervision: The Contractor shall give or provide all necessary superintendence during the installation of the Facilities, and the Construction Manager or its deputy shall be constantly on the Site to provide full-time superintendence of the installation. The Contractor shall provide and employ only technical personnel who are skilled and experienced in their respective callings and supervisory staff who are competent to adequately supervise the work at hand. #### Design, Drawings and Documents - General Design Obligations: The Contractor shall carry out, and be responsible for, the design of the Works. Design shall be prepared by the qualified designers who are Engineers or other professionals who comply with the criteria (if any) stated in the Employer’s Requirements. Unless otherwise stated in the Contract, the Contractor shall submit to the Employer for consent the name and particulars of each proposed designer and design sub-contractor. The Contractor warrants that he, his designers and design sub-contractors have the experience and capability necessary for the design. The Contractor undertakes that the designers shall be available to attend discussions with the Employer at all reasonable times, until the expiry date of the Defect Liability Period. The Board reserves rights to get the designs vetted by the third party at the Employer’s cost for which the contractor shall provide the source/ raw data which are required for vetting of the designs submitted by the agency. The Employer does not undertake to construct or make available any approach road to the proposed worksite if not mentioned in the Bill of Quantities and the bidder shall get acquainted with available means of approaches to the proposed site and quote for various items. The Employer shall not be liable for any claim raised later on the plea of non-availability or non-access to the site. - Contractor’s Documents & obligations: The Contractor’s Documents shall comprise the technical documents specified in the Employer’s Requirements, documents required to satisfy all regulatory approvals, as built drawings and Operation and maintenance manuals. The documents shall be in English language. The Contractor shall prepare all Contractors’ Documents and shall also prepare any other documents necessary to instruct the Contractor’s personnel. The Employer’s personnel shall have the right to inspect the preparation of all these documents, whenever they are being prepared. If the Employer’s Requirements describe the Contractor’s Documents which are to be submitted to the Employer for review and/or approval, they shall be submitted accordingly. Contractor’s Documents exclude any documents which are not specified as being required to be submitted for review and/or for approval. The Employer shall review the documents and give his comments if any or approve the document failing which it would be presumed that the Contractor’s Document is approved. The execution of such part of the Works shall not commence till the approval of the document or expiry of 21 days of submission. Execution of such part of the Works shall be in accordance with the reviewed and approved Contractor’s Documents. If the Contractor wishes to modify any design or drawing which has been submitted for review previously, the Contractor shall give notice to the Employer. Thereafter the Contractor shall submit revised documents to the Employer in accordance with the above procedure. If the Employer instructs that further Contractor’s Documents are required, the Contractor shall prepare then promptly. If errors, omissions, ambiguities, inconsistencies, inadequacies or other defects are found in the Contractor’s Documents, they and the Works shall be corrected at the Contractor’s cost notwithstanding any consent or approval given earlier. Any such approval or consent or any review (under this Clause or otherwise) shall not relieve the Contractor from any obligation or responsibility under this Contract. #### Technical Standards and Regulations: The design, the Contractor’s Documents, the execution and the completed Works shall comply with Bureau of Indian Standards, building, construction, and environmental laws applicable to the product being produced from the Works and other standards specified in the Employer’s Requirements, applicable to the Works, or defined by the applicable laws. If changed or new applicable standards come into force in India after the date of commencement of Works, the Contractor shall give notice to the Employer and (if appropriate) submit proposals for compliance. In the event that: - The Employer determines that compliance is required; - The proposals for compliance constitute a variation; then the Employer shall initiate a variation in accordance with Clause Variations and Adjustments. #### Training: The Contractor shall carry out the training of Employer’s personnel / the new O&M operator for the operation and maintenance of Works to the extent specified in the Employer’s Requirements. If the Contract specifies training which is to be carried out before taking over, the Works shall not be considered to be completed for the purposes of taking over under Clause [Taking Over of the Works] until this training has been completed. #### Care and Supply of Documents Each of the Contractor’s Documents shall be in the custody and care of the Contractor, unless and until taken over by the Employer. Unless otherwise stated in the Contract, the Contractor shall supply to the Employer six copies of each of the Contractor’s Documents. The Contractor shall keep, on the Site, a copy of the Contract, publications named in the Employer’s Requirements, the Contractor’s Documents, and variations and other communications given under the Contract. The Employer’s Personnel shall have the right of access to all these documents at all reasonable times. If a Party becomes aware of an error or defect of a technical nature in a document which was prepared for use in executing the Works, the Party shall promptly give notice to the other Party of such error or defect. If the Contractor suffers delay and/or incurs Cost as a result of an error in the Employer’s Requirements, and an experienced contractor exercising due care would not have discovered the error when scrutinizing the Employer’s Requirements, the Contractor shall give notice to the Employer and shall be entitled subject to GCC Clause 26 to: - An extension of time for any such delay, if completion is or will be delayed; - Payment of any such cost-plus reasonable profit which shall be included in the Contract Price After receiving this notice, the Employer shall proceed in accordance with Clause 26 to agree or determine (i) whether and (if so) to what extent the error could not reasonably have been so discovered, and (ii) the matters described in sub-paragraphs (a) and (b) above related to this extent. #### Contractor’s use of Employer’s Documents: As between the Parties, The Employer shall retain the copyright and other intellectual property rights in the Specification, the Drawings and other documents made by (or on behalf of) the Employer. The Contractor may at his cost, copy, use and obtain communication of these documents for the purposes of the Contract. They shall not, without the Employer’s consent, be copied, used or communicated to a third party by the Contractor, except as necessary for the purposes of the Contract. #### Transportation of Goods: The Contractor shall give the Employer not less than 21 days’ notice of the date on which any Plant or a major item of other Goods will be delivered to the Site. The Contractor shall be responsible for packing, loading, transporting, receiving, unloading, storing and protecting the Goods and other things required for the Works; The Contractor shall indemnify and hold the Employer harmless against and from all damages, losses and expenses (including legal fees and expenses) resulting from the transport of Goods and shall negotiate and pay all claims arising from their transport. #### Contractor’s Equipment The Contractor shall be responsible for all Contractors’ Equipment. When brought on to the Site, Contractors’ equipment shall be deemed exclusively intended for the execution of the Works. The Contractor shall not remove from the Site any major items of Contractor’s Equipment without the consent of the Employer. However, consent shall not be required for vehicles transporting Goods or Contractor’s personnel to the Site. #### Electricity and Water: The Contractor shall be responsible for the provision of all power, water and other services he may require. #### Execution of the Contract - Manner of Execution: The Contractor shall carry out the manufacture of Plant, the production and manufacture of materials and all other execution of the Works: - In the manner (if any) specified in the Contract; - In a proper workmanlike and careful manner, in accordance with recognized good practices; and - With properly equipped facilities and non-hazardous materials, except as otherwise specified in the Contract; - Contractor’s Superintendence: Throughout the design and execution of the Works and as long thereafter as is necessary to fulfill the Contractor’s Obligations, the Contractor shall provide all necessary superintendence to plan arrange, direct, manage, inspect and test the work. Superintendence shall be given by a sufficient number of persons having adequate knowledge of the language for communications and of the operations to be carried out (including the methods and techniques required, the hazards likely to be encountered and methods of preventing accidents for the satisfactory and safe execution of the Works. - Contractor’s Operation on Site: The Contractor shall confine his operations to the Site and to any additional areas which may be obtained by the Contractor and agreed by the Employer as working areas. The Contractor shall take all necessary precautions to keep Contractor’s equipment and personnel within the Site and these additional areas and to keep them off adjacent land. During the execution of the Works, the Contractor shall keep the Site free from all unnecessary obstruction, and shall store or dispose of any Contractor’s equipment or surplus materials. The Contractor shall clear away and remove from the Site any wreckage, rubbish and temporary works which are no longer required. #### Emergency Work: If by reason of any emergency arising in connection with and during the execution of the contract, any protective or remedial work is necessary as a matter of urgency to prevent the damage to the facilities, the Contractor shall immediately carryout such of work. If the contractor is unable or unwilling to do such work immediately, the Employer may do or cause such work to be done as the Employer may determine is necessary in order to prevent damage to the Facilities. In such event the Employer shall, as soon as practicable after the occurrence of any such emergency, notify the contractor in writing of such emergency, the work done and the reasons therefore. #### License / Use of Technical Information: For the operation and maintenance of the Facilities, the Contractor hereby grants a non-exclusive and non-transferable license (without the right to sub-license) to the Employer under the patents, utility models or other industrial property rights owned by the Contractor or by a third Party from whom the Contractor has received the right to grant licenses there under, and shall also grant to the Employer a non-exclusive and non-transferable right (without right to sub-license) to use the know-how and other technical information disclosed to the Employer under the Contract. Nothing herein shall be construed as transferring ownership of any patent, utility model, trademark, design, copyright, know-how or other intellectual property right from the Contractor to any third Party to the Employer. The copyright in all drawings, documents and other materials containing data and information furnished to the Employer by the Contractor herein shall remain vested in the Contractor or, if they are furnished to the Employer directly or through the Contractor by any third party, including suppliers of materials, the copyright in such materials shall remain vested in such third party. #### Confidential Information: - The Employer and the Contractor shall keep confidential and shall not, without the written consent of the other party hereto, divulge to any third party any documents, data or other information furnished directly or indirectly by the other party hereto in connection with the Contract, whether such information has been furnished prior to, during or following termination of the Contract. Notwithstanding the above, the Contractor may furnish to its Subcontractor(s) such documents, data and other information it receives from the Employer to the extent required for the Subcontractor(s) to perform its work under the Contract, in which event the Contractor shall obtain from such Subcontractor(s) an undertaking of confidentiality similar to that imposed on the Contractor. - The Employer shall not use such documents, data and other information received from the Contractor for any purpose other than the operation and maintenance of the Facilities. Similarly, the Contractor shall not use such documents, data and other information received from the Employer for any purpose other than the design, procurement of Plant and Equipment, construction or such other work and services as are required for the performance of the Contract. The obligation of a party, however, shall not apply to that information which - now or hereafter enters the public domain through no fault of that party - can be proven to have been possessed by that party at the time of disclosure and which was not previously obtained, directly or indirectly, from the other party hereto I otherwise lawfully become available to that party from a third party that has no obligation of confidentiality. The above provisions shall not in any way modify any undertaking of confidentiality given by either of the parties hereto prior to the date of the Contract in respect of the Facilities or any part thereof. The provisions of this Clause shall survive termination, for whatever reason, of the Contract. #### Guarantee Test The Guarantee Test (and repeats thereof) shall be conducted by the Contractor during Commissioning of the Facilities or the relevant part thereof to ascertain whether the Facilities or the relevant part can attain the Functional Guarantees specified in the Technical Specifications. The Employer shall promptly provide the Contractor with such information as the Contractor may reasonably require in relation to the conduct and results of the Guarantee Test (and any repeats thereof). #### Functional Guarantees: - The Contractor guarantees that during the Guarantee Test, the Facilities and all parts thereof shall attain the Functional Guarantees specified in the corresponding (Functional Guarantees) Contract Agreement, subject to and upon the conditions therein specified. - If, for reasons attributable to the Contractor, the minimum level of the Functional Guarantees specified in the corresponding to the Contract Agreement are not met either in whole or in part, the Contractor shall at its cost and expense make such changes, modifications and/or additions to the Plant or any part thereof as may be necessary to meet at least the minimum level of such Guarantees. The Contractor shall notify the Employer upon completion of the necessary changes, modifications and/or additions, and shall request the Employer to repeat the Guarantee Test until the minimum level of the Guarantees has been met. If the Contractor eventually fails to meet the minimum level of Functional Guarantees, the Employer may consider termination of the Contract. - If, for reasons attributable to the Contractor, the Functional Guarantees specified in the Contract Agreement are not attained either in whole or in part, but the minimum level of the Functional Guarantees specified in the Contract Agreement is met, the Contractor shall: - make such changes, modifications and/or additions to the Facilities or any part thereof that are necessary to attain the Functional Guarantees at its cost and expense, and shall request the Employer to repeat the Guarantee Test; The Guarantee Test of the Facilities shall be successfully completed within 30 (Thirty days) from the date of Completion. #### Patent Identity The Contractor shall, subject to the Employer’s compliance with, indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Employer may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract by reason of the installation of the Facilities by the Contractor or the use of the Facilities in India /Karnataka where the Site is located. Such indemnity shall not cover any use of the Facilities or any part thereof other than for the purpose indicated by or to be reasonably inferred from the Contract, any infringement resulting from the use of the Facilities or any part thereof, or any products produced thereby in association or combination with any other equipment, plant or materials not supplied by the Contractor, pursuant to the Contract Agreement. If any proceedings are brought or any claim is made against the Employer arising out of the matters referred to, the Employer shall promptly give the Contractor a notice thereof, and the Contractor may at its own expense and in the Employer’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Contractor fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing. The Employer shall indemnify and hold harmless the Contractor and its employees, officers and Subcontractors from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Contractor may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright or other intellectual property right registered or otherwise existing at the date of the Contract arising out of or in connection with any design, data, drawing, specification, or other documents or materials provided or designed by or on behalf of the Employer. #### Debarment of Tenderers by Procurement Entity: - The Procurement Entity may proceed with debarring such tenderer or contractor or supplier or any of the successor of the tenderer or contractor or supplier who has engaged directly or through an agent in a corrupt or fraudulent practices in participating or competing or executing the contract including misleading the Procurement Entity at any stage of procurement and executing activity. - The Procurement Entity may, by order, appoint a committee consisting of such officers not below the rank of Tender Inviting Authority to be the Debarment Committee to consider the proposals for debarring bidder or contractor or supplier and to take a decision thereof. - On the receipt of information, Debarment Committee shall provide a reasonable opportunity, including an oral hearing, to the concerned for making representations before taking a decision. - For consideration of debarment, Tender Inviting Authority or any other officer authorized by Tender Accepting Authority shall furnish the details of such bidders or contractors or suppliers who have engaged in corrupt practice and fraudulent practices to the Debarment Committee constituted under sub rule (2) above. - The Debarment Committee may make recommendations with reasoning in writing, within thirty days from date of receipt of information. Provided that, the said period may be extended by another fifteen days by Procurement Entity for the reasons to be recorded in writing. - On the recommendations of the Debarment Committee, the Procurement Entity shall by notification debar any of tenderer or contractor or supplier and publish the same on its website and Karnataka Public Procurement Portal and also maintain the list of such tenderer or contractor or the supplier or any of its successors. - The debarred tenderer or contractor or supplier shall be removed from the list of registered contractors or vendors. - The order of debarment shall be deemed to have been automatically revoked on the expiry of the period specified in the debarment order. Q.1 Debarment by the Government - The Government may debar a tenderer or contractor or supplier, in the public interest and the grounds specified in the act. - There shall be a State Level Debarment committee consisting of such officers as may be notified by the State Government to consider the proposal for debarring bidder or contractor or supplier and to take a decision thereof - On the receipt of the information, the State Level Debarment committee shall provide a reasonable opportunity, including an oral hearing, to the concerned for making representations before taking a decision on the debarment - For consideration of Debarment of the bidders or contractors or suppliers, the officer authorized by the procurement entity shall furnish the details of such bidders or contractors or suppliers to the State Level Debarment Committee constituted under sub rule (2) above; - The State Level Debarment Committee may make recommendation to the State Government to such an effect, within thirty days, from the date of receipt of the information; Provided that, the said period may be extended by another fifteen days for the reasons to be recorded in writing by the Debarment Committee. - On the recommendation of the State Level Debarment Committee, the Government shall debar by notification such tenderer or Karnataka Public Procurement Portal and shall maintain the list of such bidder or contractor or the supplier or any of its successor. - The debarred tenderer or contractor or supplier shall be removed from the list of registered contractors or vendors. - The order of debarment shall be deemed to have been automatically revoked on the expiry of the specified period in the debarment order. #### Q.2Measures to be taken after Debarment: The Procurement Entity may take appropriate measures in respect of debarred tenderer or contractor or supplier including one or more of the following, namely: - - Reject the bid and forfeit or encash Bid Security; - Terminate the contract; forfeit or encash the performance guarantee; recover the compensation of loss incurred by Procurement Entity; - Forfeit or encash any other security or guarantee or bond provided by such tenderer or contractor or supplier in relation to the such procurement; and - Recover payments including advance payments, if any, made by the Procurement Entity along with the interest thereon at the prevailing rate of Nationalized Bank. #### Contract Management: - The Procurement entity, as may be notified by the Government from time to time, shall undertake Contract Execution Management from the date of such notification on the Karnataka Public Procurement Portal in respect of works, goods and services exceeding the value of the contract as may be notified by the Government from time to time. - All the activities and processes relating to the Contract Management shall be created, entered, managed and monitored on the Karnataka Public Procurement Portal.” #### Trail run period is 3 months, wherein the Contractor would have to train the Employer/ Authority or the agency taking over the Operations and Maintenance period. The training shall have to include hands on operations training along with the manual of operations for a period of 3 months. In addition to the training in the trail run period the Contractor will be responsible for 1 year Defect Liability Period & 4 years of O & M period, wherein, the new operator will be responsible for the operations and incase of any issues the Contractor will have to rectify the same. #### If the land to be acquired, the Tenderer is responsible for identify and acquire the required land on behalf of Handloom and Textile Department. The land cost as per Guidance value only will be paid by the KUWSDB. #### All approvals from statutory bodies like respective GESCOM, KPTCL, PWD, KRDCL, KSHIP, ULB, NH, Railways, Forest and Revenue Department etc., is the responsibility of the Tenderer. However necessary documents required for the permissions would be provided by the KUWSDB. Necessary deposits will be paid by the KUWSDB based on the intimation received from the respective Dept. #### After completion of capital works and before commencement of O&M, the Supplementary agreement shall be entered between KUWS&DB and Contractor for taking up of O&M. The O&M agreement shall come into effect after completion of the construction activities and comprehensive commissioning of the project. The O&M cost will be borne by Handloom and Textile Department, but not by KUWS & D Board/ GoK/GoI. - As per the approved work plan and contract condition, the Supply payment for Materials shall be paid only for the requirement of materials for the next 3 months only. - Before making RA (Running Account) Bill payment, the corresponding permanent assets/works executed should be mapped in GIS portal. Without the mapping of GIS portal of permanent assets/works executed, the Corresponding RA Bill payment shall not be made. - To arrive the precise Price Adjustment (PA) amount, the measurement of works executed at site for month should be recorded without fail. |

All work shall be done as per the specifications and approved design. The works shall include providing all materials, equipment’s, labour, tools, plants, transport etc., and all other services necessary for the complete construction including necessary sub-soil investigations.

All work shall be done as per the specifications and approved design. The scope of the works shall not be limited to.

    - Carrying out survey using total station, establishing sufficient bench marks, design of network and all components using the latest version & licensed software approved by employer, preparation of working drawings and obtaining pre-construction approval from competent authority.

    - Earth work excavation, laying of bedding wherever specified laying of pipes laying, jointing, testing and commissioning, back filling the trenches and restoring and making good all surfaces which are damaged during excavation.

    - Fixing and connecting all pipe line fixtures such as valves, bends, tees, blank flanges, tail pieces, flow meter etc., and air vessel tee with a blank flange at the start of the rising main.

    - Construction of all appurtenant structures such as pipe supports, valve chambers, thrust blocks/anchor blocks etc.

    - Dismantling and reconstruction of structures such as culverts, storm water drains, roads, etc., and utility lines such as water supply pipe lines, sewer lines coming in the way of the pipeline alignment.

    - The O&M shall be for a period of 60 months from the date of successful commissioning. During this period the contractor has to set right the defects of any kind in the manufacture, laying and jointing of all pipelines and in the other works in scope of the tender.

    - All work shall be done as per the specifications. The work shall include the earth work excavation, providing all materials, equipments, labour, tools, plants, transport etc., and all other services necessary for the complete construction including necessary sub-soil investigations.

    - The alignment of the pipeline and valve chambers, thrust blocks, pipe supports and the general arrangements are furnished in Section 8- Drawings. Further details shall be furnished in the construction drawings during the construction stage.

    - The components and allied works executed by the Contractor and the other works within the scope of the Contract shall achieve service level bench mark and performance targets for a period of 60 months including defect liability period from the date of successful commissioning of the work under the scope of tender. During the O&M period of 60 months, any defects of any kind in manufacture, laying, jointing and constructions etc., shall be rectified by the Contractor as per the same specification as that of the item of work done.  If there are any damages to the materials supplied by the Bidder the same is to be replaced by the bidders.

    - Any other works which are not specifically mentioned in the contract, but are essential for completion and commissioning of works and achieving the required parameters set forth by the KSPCB/NGT/CPHEEO shall be taken up by the contractor without any extra financial implications.

ANNEXURE A

Extracts of Contract Labour (Regulation and Abolition) Act 1970

- The Contractor shall, at all times during the continuance of the Contract, comply fully with all existing Acts, regulations and byelaws including all statutory amendments and re-enactment of State or Central Government and other local authorities and any other enactments, notifications and acts that may be passed in future either by the State or the Central Government or local authority, including Indian Workmen’s Compensation Act, Contract Labour (Regulation and Abolition) Act 1970 and Equal Remuneration Act 1976, Factories Act, Minimum Wages Act, Provident Fund Regulations, Employees Provident Fund Act, schemes made under the same Act and also Labour Regulations mentioned in Annexure A to Section IV, Health and Sanitary Arrangement for Workmen, Insurance and other benefits and shall keep Employer indemnified in case any action is commenced by competent authorities for contravention by the Contractor. If the Employer is caused to pay or reimburse, such amounts as may be necessary to cause or observe, or for non-observance of the provisions stipulated henceforth on the part of the Contractor, the Engineer shall have the right to deduct from any moneys due to the Contractor, his amount of performance security or recover from the Contractor personally any sum required or estimated to be required for making good the loss or damage suffered by the Employer, responsibility in connection with the employees of the Contractor, who shall, in no case, be treated as the employees of the Employer at any point of time.

- Fair Wages

  - The Contractor shall pay the labourers engaged by him on the work not less than fair wage which expression shall mean, whether for time or piecework, the respective rates of wages fixed by the Public Works Department as fair wages for the area payable to the different categories of labourers or those notified under the Minimum Wages Act for corresponding employees of the Employer, whichever may be higher.

  - The Contractor shall, notwithstanding the provisions of a contract to the contrary, cause to be paid a fair wage to labourers indirectly engaged on the Works, including any labour engaged by sub/ contractors in connection with the sand works as if the labourer had been directly employed by him.

- NOTICES

  - The Contractor shall, before he commences the work, display, and correctly maintain, in a clean and legible condition at a conspicuous place on the Site, notices in English and in a language spoken by the majority of the workers, stating therein the rate of wages which have been fixed as fair wages and the hours of work for which such wages are earned and send a copy of such notices to the Engineer.

- Wages Records

  - The contractor shall maintain records of wages and other remuneration paid to his employees in such form as may be convenient and as per the requirements of the Employer/Engineer and the Conciliation Officer (Central), Ministry of Labour, Government of India, or such other authorized person appointed by the Central or State Government and the same shall include the following particulars of each worker:

- Name, worker’s number and grade;

- Rate of daily or monthly wage;

- Nature of work on which employed;

- Total number of days worked during each wage period;

- Total, amount payable for the work during each wage period;

- All deduction made from the wage with details in each case of the ground for which the deduction is made;

- Wage actually paid for each wage period.

  - The Contractor shall provide a Wage Slip for each worker employed on the Works.

  - The Wage records and Wage Slips shall be preserved for a least 36 months after last entry;

- Inspection of Wage Records

  - The Contractor shall allow inspection of the aforesaid Wage Records and Wage Slips to the Engineer and to any of his workers or to his agent at a convenient time and place after due notice is received or to the Employer or any other person authorized by him on his behalf.

  - The Employer, the Engineer or any other person authorized by them on their behalf shall have power to make enquiries with a view to ascertaining and enforcing due and proper observance of the Fair Wages Clause. He shall also have the Power to investigate into any complaint regarding any default made by the Contractor or sub-contractor in regard to such provision.

  - The Employer shall have the right to deduct from the money’s due to the Contractor any sum required or estimated to be required for making good the loss suffered by a worker or workers by reason of non-payment of the aforesaid fair wage, except on account of any deductions that may be permissible under any law for the time being in force.

  - A workman shall be entitled to be represented in any investigation or enquiry under this Clause by:

- An officer of a registered Trade Union of which he is a member.

- An officer of a federation of Trade Unions to which the Trade Union referred to in previous sub-clause is affiliated.

- Where the worker is not a member of any registered Trade Union, by an officer of a registered Trade Union connected with or by any other workmen employed in the industry in the worker is employed.

  - The Contractor or sub-contractor shall be entitled to be represented in any investigation or inquiry under this Clause by an office of an Association of Employ which he is a member.

  - No party shall be represented by a legal practitioner in any investigation or inquiry under this Clause, unless all parties agree otherwise.

- Safety Provisions

  - The Contractor shall comply with all the precautions as required for the safety of the workmen by the I.L.O. Convention No. 62 as far as they are applicable to the contract. The Contractor shall provide all necessary safety appliances, gears like goggles, helmets, masks, etc., to the workmen and the staff.

  - Suitable scaffolds shall be provided for workmen for all work that cannot safely be done from the ground, or from solid construction except for such short period work as can be done safely from ladders, When a ladder is used, an extra labour shall be engaged for holding the ladder  and if the ladder is used for carrying materials as well, suitable foot-holds and hand-holds shall be provided on the ladder, which shall be given an inclination not steeper than 1/4 to (1/4) horizontal in 1 vertical).

  - Scaffolding or staging more than 3.25 metres above the ground or floor, swing or suspended from an overhead support or erected with stationary support shall have guard rail properly attached bolted, braced and otherwise secured 1 metre high above the floor or platform of such scaffolding or staging and extending along the entire length may be necessary for the delivery of materials. Such scaffolding or staging shall be so fastened as to prevent it from swaying from the support for structure.

  - Working platform, gangways, and stairways shall be so constructed that they do not sag unduly or unequally and if a height of a platform or gangway or stairway is more 3.25 metres above ground level or floor level, it shall have closely spaced Boards, have adequate width and be suitably provided with guard rails as described in (ii) above.

  - Every opening in floor of a structure or in a working platform shall be provided with suitable means to prevent fall of persons or materials by providing suitable fencing or railing with a minimum height of one metre.

  - Safe means of access shall be provided to all working platforms and other working places. Every ladder shall be securely fixed. No portable single ladder shall be over 9 metres in length. Width between side rails in a rung ladder shall in no case be less than 30 cm for ladders up to and including 3 metres in length. For longer ladders the width shall be increased at least 6mm for each additional 30cm of length. Spacing of steps shall be uniform and shall not exceed 30cm.

  - Adequate precautions shall be taken to prevent danger from electrical equipment. No materials on any of the sites shall be so stacked or placed as to cause danger or inconvenience to any person or the public. The Contractor shall provide all necessary fencing and lights to protect public from accidents and shall be bound to bear expenses of defending every suit, action or other proceedings at law that may be brought by any person for injury sustained owing to neglect of the above precautions and to pay any damages and cost which may be awarded in any such suit, action or proceeding to any such person or which may with the consent of the Contractor be paid to compromise any claim by any such person.

  - Excavation and Trenching: All trenches, 1.5 metres or more in depth shall at all times be supplied with at least one ladder for each 20 metres in length or fraction thereof. Ladder shall be extended from bottom of trench to at least 1 metres above surface of the ground. Sides of trench which is 1.5 metres or more in depth shall be stepped back to give suitable slope or securely held by timber bracing, so as to avoid the danger of collapsing of sides. Excavated material shall not be placed within 1.5 metres of edge of trench or half the depth of trench, whichever is more. Cutting shall be done from top to bottom. Under no circumstances, undermining or undercutting shall be done.

  - Demolition: Before any demolition work is commenced and also during the process of the work:

A. 	All roads and open areas adjacent to the work site shall either be closed or suitably protected.

B. 	No electric cable or apparatus which is liable to be a source of danger over a cable or apparatus used by operator shall remain electrically charged.

C.	All practical steps shall be taken to prevent danger to persons employed by the Employer, from risk of fire or explosion, or flooding. No floor, roof or other part of a building shall be so overloaded with debris or materials as to render it unsafe.

  - All necessary personal safety equipment as considered adequate by the Engineer shall be available for use of persons employed on the Site and maintained in a condition suitable for immediate use and the Contractor shall take adequate steps to ensure proper use of the equipment by those concerned.

A. 	Workers employed on mixing asphaltic materials, cement, lime mortars/concrete shall be provided with protective footwear and protective goggles.

B.	Those engaged in handling any material which is injurious to eyes shall be provided with protective goggles.

C.	Those engaged in welding works shall be provided with welder’s protective eye-shield.

D. 	Stone breakers shall be provided with protective goggles and protective clothing and seated at sufficiently safe intervals.

E. 	When workers are employed in sewers and machine-holes, which is in use, the Contractor shall ensure that machine-hole covers are open and machine-holes are ventilated at least for an hour before the work are taken up. Machine-holes so open shall be cordoned off with suitable railing and provide warning signals or Boards to prevent accident to public.

The Contractor shall not employ men below the age of 18 years and women on the work of painting with products containing lead in any form. Whenever men above the age of 18 years are employed on the work of lead painting, the following precautions shall be taken.

No paint containing lead or lead products shall be used except in the form of paste or readymade paint.

Suitable face masks shall be supplied for use by workers when paint is applied in the form of spray or a surface having lead paint dry rubbed and scrapped.

Overalls shall be supplied by the Contractor to workmen and adequate facilities shall be provided to enable workers to wash during and on close of day’s work.

  - When work is done near any place where there is risk of drowning all necessary equipment shall be provided and kept ready for use and all necessary steps taken for prompt rescue of any person in danger and adequate provision made for prompt first aid treatment of all injuries likely to be sustained during the course of the work.

  - Use of hoisting machines and tackle including their attachments, anchorage and supports conform to the following:

- These shall be of good mechanical construction, sound material and adequate strength and free from patent defects and shall be kept in good adequate strength and free from patent defects and shall be kept in good working order and properly maintained.

- Every rope used in hoisting or lowering materials or as a means of suspension shall be of durable quality and adequate strength, and free from defects.

- Every crane driver or hoisting appliance operator shall be properly qualified and no person under the age of 21 shall be in charge of any hoisting machine including scaffold or of signals to operator.

- In case of every hoisting machine and of every chain hook, shackle swivel and pulley block used in hoisting, lowering or as means of suspension, safe working load shall be ascertained by adequate means. Every hoisting machine and all gear referred to above shall be plainly marked with safe working load. In case of a hoisting machine or a variable safe working load each safe working load and conditions under which it is applicable shall be clearly indicated. No part of any machine or any gear referred to above in the paragraph shall be loaded beyond safe working load except for the purpose of testing.

- In case of the Employer’s machine, safe working load shall be notified by the Engineer or his representative. As regards Contractor’s machines, the Contractor shall notify safe working load of each machine to Engineer or his representative whenever he brings it to site of work and get it verified by him.

  - Motors, gearing, transmission, electric wiring and other dangerous parts of hoisting appliance shall be provided with efficient safeguards hoisting appliances shall be provided with such means as will reduce the risk of accident during descent of load to the minimum. Adequate precautions shall be taken to reduce to the minimum risk of any part of a suspended load becoming accidentally displaced. When workers are employed on electrical installations which are already rècheed, insulating mats, working apparel such as gloves, sleeves and boots, as may be necessary, shall be provided, workers shall not wear any rings, watches and carry keys or other material which are good conductors of electricity. All scaffolds, ladders and other safety devices mentioned or described herein shall be maintained in safe condition and no scaffold, ladder or equipment shall be altered or removed while it is in use. Adequate washing facilities shall be provided at or near places of work.

  - These safety provisions shall be brought to the notice of all concerned by display on a notice Board at a prominent place at the work spot. Persons responsible for ensuring compliance with the safety code shall be named therein by the Contractor.

  - To ensure effective enforcement of the rules and regulations relating to safety precautions, arrangements made by the Contractor shall be open to inspection by the Engineer or his representative and the Inspecting Officer as defined in the Contractor’s Labour Regulation mentioned in thereafter these Documents as Annexure A of Section IV.

  - Notwithstanding anything contained in conditions (i) to (xiv) above, the Contractor shall remain liable to comply with the provisions of all Acts, rules, regulations and byelaws for the time being in force in India and applicable in this matter.

  - The Contractor shall be responsible for observance, by his sub/contractors, of the forgoing provisions.

  - For work carried out in the vicinity of any wharf or quay, the Contractor shall abide by all the provisions of the Dock Workers (Safety, Health and Welfare) Scheme, 1961.

- Footwear

  - The contractor shall at his own expense provide footwear for all labour engaged on concrete mixing work and other types of work involving the use of tar, cement, etc., to the satisfaction of the Engineer or his Representative, and on his failure to do so, the Employer shall be entitled to provide the same and recover the cost from the Contractor.

- Local Labour

  - The Contractor is encouraged as far as possible to employ, in the execution of the Contract, 	qualified Indian citizens as workmen. Employment of expatriate personnel is subject to the 	Indian Laws and Regulations. In case the contractor wishes to employ expatriate personnel in 	any particular trade or skill required to execute the contract, the Employer will assist the 	Contractor in obtaining permission for which the Contractor shall submit requisite data.

- Model Rules for Labour Welfare

- Definitions:

  - Workplace means a place at which, on an average, twenty or more workers are employed.

  - Large workplace means a site at which, on an average, 250 or more workers are employed.

- First Aid:

- At every workplace, there shall be maintained in a readily accessible place first aid appliances including an adequate supply of sterilized dressings and sterilized cotton wool as prescribed in the Factory Rules of the State in which the work is carried on. The appliances shall be kept in good order and, in large work places, they shall be placed under the charge of a responsible person who shall be readily available during working hours.

- At large workplaces, where hospital facilities are not available within easy distance of the Works, First Aid Posts shall be established and be run by a trained compounder.

- Where large workplaces are remotely situated and far away from regular hospitals, an indoor ward shall be provided with one bed for every 250 employees.

- Where large workplace are situated in cities, towns or in their suburbs and no beds are considered necessary owing to proximity of city or town hospitals, suitable transport shall be provided to facilitate removal of urgent cases to these hospitals. At other workplaces, some conveyance facilities shall be kept readily available to take injured person on persons suddenly taken seriously ill, to the nearest hospital.

- At large workplaces, there shall be provided and maintained an ambulance room containing the prescribed equipment and in the charge of such medical and nursing staff as may be prescribed. For this purpose, the relevant provisions of the Factory Rules of the State government of the area where the work is carried on, may be taken as the prescribed standard.

- Accommodation for Labour:

- The Contractor shall during the progress of the Work provide, erect and maintain necessary temporary living accommodation and ancillary for labour at his own expenses to the standards and scales as approved by the Engineer.

- Drinking Water:

- In every workplace, there shall be provided and maintained at suitable places, easily accessible to labour, a sufficient supply of cold water fit for drinking.

- Where drinking water is obtained from an intermittent public water supply, each workplace shall be provided with storage of cold water fit for drinking.

- Ever water supply storage shall be at a distance of not less than 15 metres from any latrine, drain or other source of pollution. Where water has to be drawn from an existing well, which is within such proximity of latrine, drain or any other source of pollution, well shall be properly chlorinated before water is drawn from it for drinking. All such wells shall be entirely closed in and be provided with a trap door which shall be dust-proof and water-proof.

- A reliable pump shall be fitted to each covered well. The trap door shall be kept locked and opened only for cleaning or inspection which shall be done at least once a month.

- Washing and Bathing Places:

- Adequate washing and bathing places shall be provided separately for men and women. Such places shall be kept in clean and drained condition.

- Scale of Accommodation in Latrines and Urinals:

- There shall be provided within the precincts of every workplace, latrines and urinals in an accessible place, and the accommodation, separately for each of these, shall not be less than at the following scale:-

| Si no | Particulars | No. of Seats |
| --- | --- | --- |
|  | Where number of persons does not exceed 50 | 2 |
|  | Where number persons exceed 50 but does not exceed 100 | 3 |
|  | For additional persons per 100 or part thereof | 3 |

In particular cases, the Engineer shall have the power to increase the requirement, wherever necessary.

- Latrines and Urinals:

    - Except in workplaces provided with water/flushed latrines connected with a water borne sewage system, all latrines shall be provided with receptacles on dry-earth system which shall be cleaned at least four times daily and at least twice during working hours and kept in a strictly sanitary condition. Receptacles shall be tarred inside and outside at least once a year.

    - If women are employed, separate latrine and urinals, screened from those for men and marked in the vernacular in conspicuous letters. “For Women Only” shall be provided on the scale laid down in rule (vi). Those for men shall be similarly marked “For Men Only”. A poster showing the figures of a man and a woman shall also be exhibited at the entrance to latrines for each sex. There shall be adequate supply of water, close to latrines and urinals.

- Construction of Latrines:

- Inside walls shall be constructed of masonry or other non-absorbent material and shall be cement washed inside and outside at least once a year. The dates of cement washing shall be noted in a register maintained for the purpose and kept available for inspection. Latrines shall have at least thatched roof.

- Disposal of Excreta:

- Unless otherwise arranged for by the local sanitary authority, arrangement for proper disposal of excreta by incineration at the workplace shall be made by means of suitable incinerator approved by the local medical, health and municipal or cantonment authorities. Alternatively, excreta may be disposed off by putting a layer or night soils at the bottom of a pucca tank prepared for that purpose and covering it with a 15 cm layer of waste or refuse and then covering it with a layer of earth for a fortnight (when it will turn into manure).

- The Contractor shall, at his own expense, carry out all instructions issued to him by the Engineer to effect proper disposal of soil and other conservancy work in respect of Contractor’s work-purpose or employees on the site. The Contractor shall be responsible for payment of any charges which may be levied by municipal or cantonment authority for execution of such work on his behalf.

- Provisions of shelters during rest:

- At every workplace, there shall be provided, free of cost, four suitable sheds, two for meals and two others for rest, separately for use of men and women labour. Height of each shelter shall not be less than 3 metres from floor-level to lowest part of roof. Sheds shall be kept clean and the space provided shall be on the basis of at least 0.5 sqm per head.

- Creches:

- At a place at which 20 or more women are ordinarily employed, there shall be provided at least one hut for use of children under the age of 6 years belonging to such women. Huts shall not be constructed to a standard lower than that of thatched roof, mud floor and wall with wooden planks spread over mud floor and covered with matting Huts shall be provided with suitable and sufficient openings, for light and ventilation. There shall be adequate provision of sweepers to keep the places clean. There shall be two maid-servants in attendance. Sanitary utensils shall be provided to the satisfaction of local medical, health and municipal or cantonment authorities. Use of huts shall be restricted to children, their attendants and mothers of children.

- Where the number of women workers is more than 25 but less than 50, the Contractor shall provide at least one hut and one maid-servant to look after children of women workers.

- Creche(s) shall be properly maintained and necessary equipment like toys, etc., provided.

- Canteen:

  - A cooked food canteen on a moderate scale shall be provided for the benefit of workers 	wherever it is considered necessary.

  - Planning, setting and erection of the above-mentioned structures shall be approved by the Engineer or his representative and the whole of such temporary accommodation shall at all times during the progress of the work be kept tidy and in a clean and sanitary condition to the satisfaction of the Engineer or his representative and at the Contractor’s expense. The Contractor shall conform generally to sanitary requirements of local medical, health and municipal or cantonment authorities and at all times adopt such precautions as may be necessary to prevent soil pollution of the site. On completion of the Works, the whole of such temporary structures shall be cleared away, all rubbish burnt, excreta or other disposal pits or trenches filled in and effectively sealed off and the whole of site left clean and tidy at the contractor’s expense to the entire satisfaction of the Engineer.

- Anti-malarial precautions:

  - The Contractor shall, at his own expense, conform to all anti-malarial instructions given to 	him by the Engineer, including filling up any borrow pits which may have been dug by him.

- Enforcement:

  - Inspecting Officer mentioned in the Contractor’s Labour Regulations or any other Officer 	nominated on his behalf by the Engineer shall report to the Engineer all cases of failure on the 	part of the Contractor and/or his sub-contractor to comply with the provisions of these Rules 	either wholly or in part and the Engineer shall impose such fines and other penalties as are 	prescribed conditions of contract.

- Interpretations, etc.:

  - On any question as to the application, interpretation or effect of these Rules, the decision of 	the Chief Labour Commissioner or Deputy Chief Labour Commissioner (Central be final and 	binding.

- Amendments:

  - The Employer may, from time to time, add to, or amend these Rules and issue such directions 	as it may be considered necessary for the proper implementation of these Rules or for the 	purpose of removing any difficulty which may arise in the administration thereof.

Extracts of Contract Labour (Regulation and Abolition) Act 1970

ANNEXURE – A – 1

CONTRACTOR’S LABOUR REGULATIONS

Regulation 1 – Definition

In these regulations, unless otherwise expressed or indicated, the following words and expression shall have the meaning hereby assigned to them:

- “Labour” mean workers employed by a contractor directly, or indirectly, through a sub-contractor, or by an agent on his behalf on a payment not exceeding Rs. 1.600/- per month.

- “Wages” means wages, which shall include wages for weekly day of rest and other allowance, whether for time or piece work, after taking into consideration prevailing market rates for similar employments in the neighbourhood but shall not be less than the minimum rates of wages fixed under the

- Payment of minimum Wages Act.

- “Contractor” for the purpose of these regulations shall include an agent or sub-contractor employing labour o

- n the work taken on contract.

- “Inspecting Officer” means any Labour Enforcement Officer, or Assistant Labour Commissioner of the chief labour

- Commissioner’s Organization.

- “Form” means a form appended to these Regulations.

Regulation 2 – Notice of Commencement

The Contractor shall within SEVEN days of commencement of the Work, furnish in writing to the Inspecting Officer of the area concerned the following information:

- Name and situation of the work

- Contractor’s name and address

- Particular of the Department for which the work is undertaken

- Name and address of sub-contractors as and when they are appointed

- Commencement and probable duration of the work

- Number of workers employed and likely to be employed

- Fair wages for different categories of workers

Regulations 3 – Hours of Work and Weekly Day of Rest

- Number of hours of work which shall constitute normal working day: The number of hours which shall constitute a normal working day for an adult shall be NINE hours. The working day of an adult worker shall be so arranged that, inclusive of intervals, if any, for rest, it shall not spread over more than Twelve hours on a day. When an adult worker is made to work for more than nine hours on any day or for more than FORTY EIGHT hours in a week, he shall in respect of overtime work, be paid wages at double the ordinary rate of wages.

Weekly day of Rest: Every worker shall be given a weekly day of rest which shall be fixed and notified at least TEN days in advance. A worker shall not be required or allowed to work on the weekly rest day unless he has or will have a substituted rest day, one of the five days immediately before or after the rest day. Provided no substitution shall be made which will result in the worker working for more than ten days consecutively without a rest day for a whole day.

Where in accordance with the foregoing provisions, a worker works on the rest day and has been given a substituted rest day, he shall be paid wages for the work done on the weekly rest day at the overtime rate of wages.

NOTE: The expression “ordinary rate of wages” means the fair wage the worker is entitled to.

Regulations 4 – Display of Notice Regarding wages, Weekly day of Rest, etc.,

The Contractor shall before he commences his work on contract, display and correctly maintain and continue to display and correctly maintain in a clean and legible condition in conspicuous places on the works, notice in English and in the local language spoken by majority of workers, giving the rate of fair wages, the hours of work for which such wages are payable, the weekly rest days workers are entitled to and name and address of the Inspecting Officer. The Contractor shall send a copy of each of such notice to the Inspecting Officer.

Regulation 5 – Fixation of Wage periods

The Contractor shall fix wage periods in respects of which wages shall be payable. No wage period shall normally exceed one week.

Regulation 6 – Payment of wages

- Wages due to every worker shall be paid to him direct. All wages should be paid in current coins or currency or in both.

- Wages of every worker employed on the Contract shall be paid where the wage period is one week, within THREE days from the end of the wage period; and in any other case before the expiry of the 7th day or 10th day from the end of the wage period according as the number of workers does not exceed 1,000 or exceeds 1,000.

- When employment of any worker is terminated by or on behalf of the Contractor, the wages earned by him shall be paid before expiry of the day succeeding the one on whichhis employment is terminated.

- Payment of wages shall be made at the Work Site on a working day except when the work is completed before expiry of the wage period in which case final payment shall be made at the Work Site within 48 hours of the last working day and during normal time.

Note: The term “Working Day” means a day on which the work on which the labour is employed is in progress.

Regulation 7 – Register of Workmen

A register of workmen shall be maintained in the Form appended to the regulations and kept at the work site or as near to it as possible and relevant particulars of every workman shall be entered therein within THREE days of his employment.

Regulation 8 – Employment Card

The Contractor shall issue an Employment card in the Form appended to these regulations to each worker on the day of work or entry into his employment. If a worker already has any such card with him issued by the previous employer, the Contractor shall merely endorse that Employment Card with relevant entries. On termination of employment, the Employment Card shall again be endorsed by the Contractor and returned to the worker.

Regulation 9 – Register of Wages etc.

- A Register of Wages cum Muster Roll in the Form appended to these regulations shall be maintained and kept at the Work Site or as near to it as possible.

- A wage slip in the form appended to these regulations shall be issued to every worker employed by the Contractor at least a day prior to disbursement of wages.

Regulation 10 – Fines and Deductions which may be made from Wages

- Wages of a worker shall be paid to him without any deductions of any kind except the following:

- Fines

- Deductions for absence from duty; i.e. from the place of his employment where he is required to work. The amount of deduction shall be in proportion to the period for which he was absent;

- Deduction for damage to or loss of goods expressly entrusted to the employed person for custody, or for loss of money which is required to be accounted for, where such damage or loss is directly attributable to his neglect or default.

- Deductions for recovery of advances or for adjustment of overpayment of wages, advance granted being entered in a register; and

- Any other deductions which the Employer may from time to time allows.

- No fines shall be imposed on any worker save in respect of such acts and omissions on his part as have been approved by the Chief Labour commissioner.

- No fine shall be imposed on a worker and no deductions for damage or loss shall be made from his wages until the worker has been given an opportunity of showing cause against such fines or deductions.

- The total amount of fines which may be imposed in any one wage period of a worker shall not exceed an amount equal to 0.3% of the wages payable to him in respect of that wage period.

- No fine imposed on a worker shall be recovered from him on instalments, or after expiry of sixty days from the date on which it was imposed. Every fine shall be deemed to have been imposed on the day of the act or omission in respect of which it was imposed.

- The Contractor shall maintain both in English and the local language a list, approved by the Chief Labour Commissioner, clearly stating the acts and omissions for which penalty or fine may be imposed on a workman and display it in good condition in a conspicuous place on the Work Site.

- The Contractor shall maintain a register of fines and the register of deductions for damage or loss in the forms appended to these regulations which should be kept at the place of work.

Regulation 11 – Register of Accidents

The Contractor shall maintain a register of accidents in such form as may be convenient at the work place but the same shall include the following particulars:

- Full particulars of the labourers who met with accident.

- Rate of wages

- Sex

- Age

- Nature of accident and cause of accident

- Time and date of accident

- Date of Time when admitted to hospital

- Date of discharge from the hospital

- Percentage of loss of earning capacity and disability as assessed by the medical Officer.

- Claim required to be paid under Workmen’s Compensation Act.

- Date of payment of compensation.

- Amount paid with details of the person to whom the same was paid

- Authority by whom the compensation was assessed

- Remarks

Regulation 12 – Preservation of Register

The Register of workmen and the Register of wages cum Muster Roll required to be maintained under these Regulations shall be preserved for One year after the date on which the last entry is made therein.

Regulation 13 – Enforcement

The Inspecting Officer shall either on his own motion or on a complaint received by him carry out investigations and send a report to the Engineer specifying the amounts representing Workers Dues and amount of penalty to be imposed on the Contractor for breach of these regulations, that have to be recovered from the Contractor, indicating full details of the recoveries proposed and the reason therefore. It shall be obligatory on the part of the Engineer on receipt of such a report to deduct such amounts from payments due to the Contractor.

Regulation 14 – Disposal of Amounts Recovered from the Contractor

The Engineer shall arrange payment to workers concerned within FORTY-FIVE days of receipt of a report from the Inspecting Officer except in cases where the Contractor had made an appeal under Regulation 16 of these regulations. In cases where there is an appeal, payment of workers dues would be arranged by the Engineer wherever such payment arise, within THIRTY days from the date of receipt of the decision of the Regional Labour Commissioner (RLC).

Regulation 15 – Welfare Fund

All moneys that are recovered by the Engineer by way of worker’s dues which could not be disbursed to workers within the time limit prescribed above, due to reasons such as whereabouts of workers not being known, death of workers, etc., and also amounts recovered as penalty, shall be credited to a Fund to be kept under the custody of the Employer for such benefit and welfare of workmen employed by Contractors as the Engineer may deem fit.

Regulation 16 – Appeal against decision of Inspecting Officer

Any person aggrieved by a decision of the Inspecting Officer may appeal, against such decision of the Regional Labour Commissioner concerned with THIRTY days from the date of the decision forwarding simultaneously a copy of this appeal of the Engineer.

The decision of the Regional Labour Commissioner shall be final and binding upon the Contractor and the Workmen.

Regulation 17 – Representation of Parties

- Workmen shall be entitled to be represented in any investigation of enquiry under these Regulations by an officer of a registered trade union of which he is a member or by an officer of a Federation of Trade Unions to which the said trade union is affiliated or where the workman is not a member of any registered trade union by an officer of a registered trade union, connected with, or by any other workmen employed in the industry in which the worker is employed.

- A contractor shall be entitled to be represented in any investigation or enquiry under these Regulations by an officer of an association of Contractors of which he is a member or by an officer of a Federation of associations of Contractors to which the said association is affiliated or by an officer of association of employees connected with or by any other employer engaged in the industry in which the Contractor is engaged.

- No party shall be entitled to be represented by a legal practitioner in any investigation or enquiry under these Regulations.

Regulation 18 – Inspecting of Books and Other Documents

The Contractor shall allow inspection of the Registers and other documents prescribed under these Regulations by Inspecting Officers and the Engineer or his authorized representative at any time and by the worker or his agent on receipt of due notice at a convenient time.

Regulation 19 – Interpretation etc.:

On any question as to the application, interpretation or effect of these regulations, the decision of the Chief Labour Commissioner or Deputy Chief Labour Commissioner (Central) as the case may be, shall be final and binding.

Regulation 20 – Amendments:

The Employer may, from time to time, add to or amend these Regulations and issue such directions as it may consider necessary for the purpose of removing any difficulty which may arise in the demonstration thereof.

REGISTRATION OF WORKMEN

SHEET NO. A-11

SECTION IV

(Regulation 7)

- Name and address of the Contractor ____________________________________

- Number and date of Contract _________________________________________

- Name and address of the Department awarding the Contract _________________

- Nature of the Contract and location of the work ____________________________

- Duration of the Contract _________________________

| Sl. No. | Name and Surname | Age & Sex | Father’s/ Husband’s name | Nature of Employment Designation | Permanent Home Address of Employee (Village, Dist: Thana) | Present Address | Date of Commencement of employment | Date of termination or leaving of employment | Signature or thumb impression of the employee | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

SECTION IV

SHEET NO. A-14

A – 13

EMPLOYMENT CARD

(Regulation 8)

- Name and Sex of the Worker _________________________________________

- Father’s / Husband’s Name ____________________________________________

- Address ___________________________________________________________

- Age or Date of Birth _________________________________________________

- Identification marks __________________________________________________

Particulars of next kin (wife/husband and children, if any, or of dependent next of kin in case the worker has no wife/husband or child).

Name _____________________

Full address of Dependents

(Specify Village, Dist and State _________________________________________)

| Sl. No. | Name and address of Employer (specify whether a contractor or a subcontractor) | Particulars of location of work site and description of work done | Total period for which the worker is employed (from ----- to -----) |  | Actual number of days worked | Leave taken (No. Of days should be specified) |  | Nature of work done by the worker |  | Wage period |  | Wage rate with particulars of unit in case of piece | Total wages earned by the worker the period shown under |  |  | Remarks | Signature of the employer |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

N.B. For a worker employed at one time on piece work basis and at another on daily wages, relevant extra in respect of each type of employment should be made separately.

WAGE SLIP

(Regulation 9)

SHEET NO. A-9

Name of Contractor

Place

|  | Name of the Worker with father/husband’s name |  |
| --- | --- | --- |
|  | Nature of Employment |  |
|  | Wage Period |  |
|  | Rate of Wages Payable |  |
|  | Total attendance/Unit of work done |  |
|  | Date(s) on which overtime worked |  |
|  | Overtime Wages |  |
|  | Gross Wages Payable |  |
|  | Total Deductions (including nature of deductions) |  |
|  | Net Wages Payable |  |

Signature/Thumb Impression	Signature/Thumb Impression

of Contractor	of employee

REGISTER OF FINES

(Regulation No. 10 (vii))

| Sl. No. | Name | Father’s/ Husband’s name | Sex | Department |  | Nature and date of the offense for which fine imposed | Whether workman showed cause against fine or not, if so, enter date | Rate of wages | Date & amount of fine imposed | Date on which fine realized | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

ANNEXURE: B

LIST OF ORGANIZATIONS WHO ARE CONSIDERED AS APPOINTING AUTHORITY FOR APPOINTMENT OF ARBITRATORS

Deleted

ANNEXURE C

SUB: THE KARNATAKA MINOR MINERALS CONCESSION (AMENDMENT) RULES, 2003.

COMMERCE AND INDUSTRIAL SECRETARIAT

NOTIFICATION NO. CI  81, MMN 2014, BANGALORE, DATED: 18th February, 2014

SCHEDULE – I

(See Sub. Rule (1) of Rule 36)

“DEAD RENT”

| SL. No. | Name of the Minor Mineral | Rate per Unit/quantity |
| --- | --- | --- |
| 1. | ORNAMENTAL AND DECORATIVE BUILDING STONES- as defined under clause (m) of rule 2. | 37500 |
| 2 | Felsite and its varieties suitable for use as Ornamental Stores. | 37500 |
| 3 | Quartzite and Sand stone and their varieties suitable for use as Ornamental Stones. | 37500 |
| 4 | Marble or crystalline lime stone as Ornamental Stone | 37500 |
| 5 | Bentonite | 27500 |
| 6 | Fullers Earth | 27500 |
| 7 | Lime Stone under title “ Shahabab stone” | 16500 |
| 8 | Lime Stone (Non Cement) | 16500 |
| 9. | Ordinary building stones – Entire state as defined under clause (g) of rule 2 |  |
| a | Bangalore, Kolar, Mysore, Mandya and Tumkur | 18750 |
| b | Other Districts | 11000 |
| 10. | Lime Shell | 16500 |
| 11. | Lime Kankar. | 16500 |
| 12. | Agate and Chalcedony. | 16500 |
| 13. | Ordinary sand | 11000 |
| 14 | Brick and Tile clays | 5500 |
| 15 | Steatite and sand stone used for making household utensils/articles – Entire state | 11000 |
| 16 | Sand stone used for making house hold articles | 11000 |
| 17 | Murram. | 4000 |
| 18 | All other minor minerals – Entire state | 5500 |

SCHEDULE – II

(See Sub. Rule (1) of Rule 36)

ROYALTY

ANNEXURE D

| Sl. No. | Items | Stages of Inspection |
| --- | --- | --- |
| 1 | Pumps | - Review of material test certificate for pump casing, bowls, shaft, impeller bearings, columns pipe etc., - Review of heat treatment certificate if any - Dynamic balancing or rotating parts/impeller. - Examination of the shaft - Hydro test of casing - Performance test at 49 Hz frequency including vibrating measurement covering following test. - Capacity in LPM/LPS - Delivery Head in mtrs. - Efficiency at the specified duty - Power absorbed by the pump at the specified duty - N.P.S.H required - Maximum power required by the pump - Shut off Head of the pump - Discharge of the pump when only on pump is operated in the system - Delivery pressure when only on pump is operated in the system - Power absorbed by the pump when only one pump is operated in the system - Efficiency of the pump when only one pump is operated in the system - Visual and dimensional check - Strip test - Speed test at 49 Hz and 50 Hz frequency. |
| 2 | MOTORS | - Dynamic balancing of rotor and visual examination of rotor assembly. - Visual inspection and testing of starter assembly. - Review of Test Certificate for conductor, Starter coils, shaft Bearings etc., - Routine tests no load x load test vibration measurement as per IS - Verification of type test report 6.Visual and dimensional check. |
| 3 | Switch gear and Electrical Panels | - Visual and dimensional check - Verification of bill of materials - Functional Test - HV/IR Test - Verification of type test reports - Voltage ratio, burden class, induced high voltage, applied high voltage test for potential transformers - Current ratio, burden, class of accuracy, test for current transformers - Rate symmetrical breaking capacity, rated making capacity, rated short time current, auxiliary voltage for release coils, impulse with standard voltage test for Switch Gear panels. - Test results of Relay provided. |
| 4 | Transformer | - Visual inspection, dimensional check and verification of bill of materials - Iron losses and Copper losses test at 90% of the rated voltage, 100% rated voltage and 110% of the rated voltage - Resistance voltage test at HV side and L.V. side - Routine tests as per IS 2026 - Verification of type results, temperature rise test, Impulse test, Insulting oil test. Etc., |
| 5 | Capacitor | All routine and type test as per IS:2834 such as sealing test, test for output/capacitance, Insulation resistance test between terminals. Containers and loss angle measurements, test for efficiency of discharge divide, test for dielectric loss angle, thermal stability test, self healing test, voltage test between terminals. |
| 6 | Cables | - Visual Inspection and Dimensional check - Routine test as per IS: 1554 - Insulation test, resistance test, current rating test, star reactance test, star capacitance test, short circuit current test, voltage drop test. |
| 7 | Valves | 1. Visual and dimension check. 2. Review of material test certificate for valve body and internals. 3. Operational smoothness. - Hydraulic test/Leakage test as per applicable codes. - Any other direction given by the Board to the inspecting agency to carryout the third party inspection. |
| 8 | Pipes | - visual and dimensional check - Review of chemical and physical test certificates as per the relevant Indian standard specifications - Hydrostatic pressure test as per the relevant Indian Standard specifications. - Hydraulic proof testing Standards factory - Ultrasonic testing of welded joints for MS pipes - Checking the integrity of epoxy lining for MS pipes at joints after laying and jointing pipes. |
| 9 | 11KV Power supply materials | As per TAQC of Gescom |

ANNEXURE –E

PROCEEDINGS OF THE GOVERNMENT OF KARNATAKA

Subject: Procurement Reforms- Measurement of Works and Supplies- Use of Measurement Books.

* * *

Preamble:

Paragraphs 208 & 209 of the Karnataka Public Works (KPW) Accounts Code Volume I, Paragraphs 300 & 301 of the Karnataka Public Works Departmental (KPWD) Code Volume I and Appendix VII of the KPWD Code Volume II detail the instructions regarding issue of measurement books, recording of measurements and storage of measurement books. The salient instructions are:

- Payments for all work done otherwise than by daily labour and for all supplies, are made on the basis of measurements recorded in measurement books. Form PWG-27 in accordance with the rules in paragraph 209;

- The measurement should be considered as a very important initial account record since it is the basis of all accounts of quantities of work done, whether by daily labour or by piece work or by contract and of materials received which have to be counted or measured;

- All measurements should be neatly taken down in the measurement book issued for the purpose and nowhere else;

- The entries should be recorded in the measurement book at the work spot indelibly in ink so as to render it difficult to tamper with or to make unauthorized additions or alterations in entries once made;

- As all payments for works or supplies are based on the quantities recorded in the measurement books, it is incumbent upon the person taking the measurement to record the measurements clearly and accurately. He will also work out and enter in the measurement book the figures for the contents or area column;

- Measurements for all works and repairs should in the first instance be taken by subordinates in charge and checked by Sub-Divisional Officers and Divisional Officers. (Assistant Executive Engineer (AEE) is to check 75% in case of works costing Rs.5000 or more and 50% in case of other works and repairs, at least 50% of the works are to be checked. Executive Engineer (EE) is to check 25% of items);

- All final measurements irrespective of value to be recorded by Assistant Engineer (AE) and AEE should check-measure 100% for all works estimated to cost Rs.5000 and more if it is a departmental work and ₹25,000 and more if it is a contract work. EE should check 25% of the total value of work done if the works cost more than Rs.25,000;

- No erasures of any kind should be permitted; mistakes should be corrected by drawing the pen through the incorrect entry, and inserting the correct figures or words between the lines. A reliable record is the object to be aimed at, as the measurement book may have to be produced as evidence in a court of law;

- Apart from measurements, the description of the item as per tender has to be written in the hand of the AE.

- Paragraph 5 of Appendix IV-A of the KPWD Code Volume II- Rules for Registration of Contractors in PWD, lays down that Class I and II Contractors should engage at least one Engineering Graduate for every work costing Rs.15 lakhs and above and Class III Contractor should engage one Engineering Graduate for every work costing Rs.10 to 15 lakhs and at least one Diploma Holder on every work or group of works together costing more than Rs.2 lakhs but less than Rs.10 lakhs.

- Clauses 7(a) and 7(b) of PWG-65 Form, the approved tender document for works, state:

- A bill shall be submitted by the Contractor on or before the 15th of each month for all items of work executed in the previous month;

- The details furnished by the Contractor in the bill should be measured by the subordinate in the presence of the Contractor or his duly authorized agent. The countersignature of the Contractor or the said agent in the measurement book shall be sufficient proof to the correctness of the measurements, which shall be binding on the Contractor in all respects;

- If the Contractor does not submit the bills within the prescribed time, the EE may depute within seven days of the prescribed date, a sub-ordinate to measure up the said work. The countersignature of the Contractor shall be obtained in the measurement book concerned with reference to which, the Department may prepare the bill.

- It is observed that the measurement books are not being used in most of the Government Departments, Public Sector Undertakings, Boards, Societies and Local Bodies for recording the receipt of goods and equipment and payments of invoices are being made on the basis of verification of receipt of materials. However, most of the Government Departments, Public Sector Undertakings, Boards, Societies and Local bodies are using the measurement books for recording the measurements as per provisions of KPWD Code. However, the compliance to the provisions of the Manual is resulting in lot of clerical work by the technical officers whose primary duty is supervision of work in the field. Also there are no consistent practices followed by various procurement entities of the State.

- The Sub-Committee constituted under the Chairmanship of Secretary, Public Works Department by Government in GO No.PWD 122 SO/FC 2003 dated 8.5.2003 to look into certain technical issues like measurement books, from the Procurement Reforms Action Plan on the recommendations of the Country Procurement Assessment Report (CPAR) and make recommendations to the Standing Committee, has examined the issue, felt that the present provisions in the Codes and manuals regarding measurement of works and supplies are archaic, time and effort consuming, do not use the currently available information Technology and has made recommendations for improvement of the system. The Working Group constituted in G.O. No.PWD 1359 SO/FC 2001 dated 14.8.2002 for implementation of the said Action Plan reviewed and endorsed the recommendations of Sub-Committee. The Standing Committee constituted in GO No. PWD 1359 SO/FC 2001 dated 5.8.2002 for implementation of the said Action Plan on the recommendations of CPAR, examined the recommendations of the Sub-Committee in detail.

Government Order No. FD 56 Pro. Cell 2004, Bangalore, 18th January 2005

Based on the recommendations of the Standing Committee this order is issued for recording of measurement of Works and Supplies. This order shall supersede the current instructions contained in the Codes and Manuals.

- A uniform procedure for recording of measurements for works and supplies should be enforced in all the Organizations coming under the purview of the Karnataka Transparency in Public Procurements Act 1999.

- The current provisions of the KPW Accounts and Departmental Codes shall continue to be applicable for all Works Contracts of value Rs.25 lakhs and less;

- In respect of Works Contracts of value more than Rs.25 lakhs, the Contractors shall be made responsible for submitting bills duly supported by hard copy of detailed measurements of work using electronic spreadsheets and making computations thereof. The Contractor shall submit diskette or CD ROM in addition to the hard copy;

- The Assistant Engineer in direct charge of the work shall take independent measurements of the work and enter the same in the electronic spreadsheets and make computations thereof. The Assistant Engineer can make use of the detailed measurements as given by the Contractor in the diskette or CD ROM. In any case the responsibility for the correctness of the measurements shall be entirely of the Assistant Engineer, as prescribed in the Codes and Manuals;

- The measurements would be checked by the officers from the hard copy of the spreadsheet as per present stipulations and computations would be made accordingly;

- The countersignature of the Contractor or his authorized Agent shall be obtained on each page in the hard copy of the detailed measurement spreadsheets prepared by the Assistant Engineer, which shall be binding on the Contractor in all respects;

- The hard copies of the detailed measurement spreadsheets shall be bound, numbered and stores, which shall be considered as the measurement books, as referred to in the Manuals and Codes. An index shall be prepared for each Contract or Work, which shall show the details of the bills, reference to measurement books and vouchers. Similarly, the diskettes or CD ROMs shall be indexed and stored.

- In respect of supplies – goods equipment, the invoices detailing the items supplied with specifications, quantity, rate and amount would be sufficient. This shall be checked and inspected by the receiving authority and accounted as per normal accounting procedure prescribed by Government or Corporation or Board or Society or Local body from time to time. Entry in measurement books need not be insisted upon.

- This order will apply prospectively and shall not be applicable for contracts concluded in the past.

- This order shall apply to all Procurement Entities as defined in Section 2(d) Chapter 1 of the Karnataka Transparency in Public Procurements Act, 1999.

- This order shall be appropriately incorporated in the Conditions of Contract of Tender Documents.

- The contents of this order shall be appropriately incorporated in the Karnataka Public Works Accounts and Departmental Codes and other Manuals.

By order and in the name of

Governor of Karnataka,

Sd/-

(Sudhakar Rao)

Principal Secretary to Government,

Finance Department.

KARNATAKA URBAN WATER SUPPLY & DRAINAGE BOARD

No.KWB/TEC/SR-2008-09/Vol-II/3899/2008-09 	Dt: 04.03.2009

CIRCULAR

Sub: Adoption of Electronic Spread Sheets In lieu of Measurement Books for recording measurements for water supply and sewerage works.

Ref: G.O. No. FD/56/Pro.Cell / 2004 Bangalore Dtd: 18.01.2005.

The Government of Karnataka has issued an order to adopt Electronic Spread Sheets In lieu of Measurement Books for recording measurement of works vide G.O cited under reference. A copy of the G.O. is enclosed for reference.  The recording of measurements of works and Running bills (both water supply) using Electronic Spread Sheets instead of Measurement Books shall be implemented in to for all the tenders to be invited in future where the amount put to tender is more than Rs.25.00 lakhs as per G.O.  In order to facilitate uniform procedure, sample Electronic Spread Sheets for measurement and running bills are enclosed to this Circular as Annexure – I & II. The Contractors shall submit the bills duly supported by hard copy of detailed measurements of work using electronic spread sheets and making computations thereof. The Contractor shall submit diskette or CD ROM in addition to the hard copy. The hard copies of the detailed measurement spreadsheets shall be bound, numbered and stores, which shall be considered as the measurement books, as referred to in the Manuals and Codes. An index shall be prepared for each Contract or Work, which shall show the details of the bills, reference to measurement books and vouchers. Similarly, the diskettes or CD ROMs shall be indexed and stored.

The necessary original Electronic Spread Sheets will be supplied by the HRD Section in the same manner as that of Measurement Books Necessary backups shall be maintained both in Executive Engineer’s and Chief Accounts Officer’s Office for records. All the instructions as stipulated in G.O. should be followed strictly.

Sd/-

Managing Director

KUWS & D Board

Bengaluru

Electronic Spread Sheet for Water Supply Works

For Measurement Sheet

Name of work:							Bill No:

Agency:							Division Code:

Authority or Agreement No. & Date: 			Book No.

Date of Measurement:						Sheet No.

| Sl.No. | Description of Item | No | Measurement |  |  | Unit | Present Qty. | Previously paid Qty. | Qty. up to date | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | L | B | D |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
|  |  |  |  | Water Mark of Board Emblem |  |  |  |  |  |  |

| Signature of Contractor with Seal | Signature of Assistant Engineer | Signature of Assistant Executive Engineer |
| --- | --- | --- |

## ANNEXURE-F: QUALITY ASSURANCE PLAN FOR MATERIALS

- MS Pipes.

- DI Pipes.

- Valves. (Sluice & Air valves)

- V-wire under drain system

| QAPs for Reference |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PRODUCT NAME:M.S. PIPES |  |  |  |  |  |  |  |  |  |  |  |  |
| Sl. No. | Component / Material | Characteristics Check | Category | Type of Check | Quantum of Check | Reference Documents | Acceptance Norms | Format of Record | Agency |  |  | Remarks |
|  |  |  |  |  |  |  |  |  | M | TPI | B |  |
| 1.0 RAW MATERIAL CONTROL |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Steel Pipes/Coils | a. Chemical | Critical | Chemical Analysis | 1/section / lot | IS 3589 - 2001 | IS 3589-2001 | MTC | R | R | R |  |
|  |  | b. Physical |  |  |  |  |  |  |  |  |  |  |
|  |  | 1. Tensile | Critical | UTM | One –ample for every 40 T | IS 3589 - 2001 | IS 3589-2001 | Lab report | W | R | R |  |
|  |  | 2. Bend Test | Critical | UTM | –ne Sample per Batch | IS 3589 - 2001 | IS 3589-2001 | Lab report | W | R | R |  |
|  |  | c. Dimension | Major | Meas–ring Instrument | 100% | IS 3589 - 2001and customer –specification, if any | IS 3589 - 2001and customer specification, if any | Manufacturer's Register / Report | W | R | R |  |
|  |  | d. Surface Defect | Major | Visual– | 100% | IS 3589 - 20’1 | IS 3589 - 2001 | Manufacturer's Register / Report | W | R | R |  |
| 2.0 PROCESS CONTROL |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Cutting the plate to size | Dimension | Minor | Measuring’ Instrument | 100% | Manufacturer’s Drawing | Manufacturer's Drawing | - | W | R | R |  |
| 2.2 | Edge preparation to size | Dimension | Minor | Measuring’ Instrument | 100% | Manufacturer’s Drawing | Manufacturer's Drawing | - | W | R | R |  |
| 2.3 | Rolling and bending to cylindrical shape | Dimension | Minor | Measuring’ Instrument | 100% | Manufacturer’s Drawing | Manufacturer's Drawing | - | W | R | R |  |
| 2.4 | Tack welding for welding | Alignment, root gap etc.,‘Major | Gauges | Manufacturer’s Drawing | 50% | Manufacturer's Drawing |  |  | W | R | R |  |
| 2.5 | Welding Procedure | Current, Voltage & Speed | Critical | Indicating’ Instruments | 50% | Manufacturer's welding procedure | Manufacturer's welding procedure | - | W | R | R |  |
| 3.0FINAL INSPECTION & TESTING |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Inspection of welded Pipes | a. Dimension | Critical | Measuring Instrument | 100% | Manufacturers Drawing / Purchaser's Specification | Manufacturers Drawing / Purchaser's Specification | Inspection Report | W | W | R |  |
|  |  | b. Welding | Critical | Visual | 100% | As per standard welding practice (IS 816 & IS 822) | As per standard welding practice (IS 816 & IS 822) | Inspection Report | W | W | R |  |
|  |  | c. Soundness of Weld | Critical | Ultrasonic | 5% | IS 4258 | IS 4258 | Ultrasonic Test Report | W | W | R |  |
|  |  | d. Mechanical Test | Critical | Root & Face Bend test | Sampling as per IS 4711 | IS 3589 | IS 3589 | Inspection Report | W | W | R |  |
|  |  | e. Hydraulic Pressure Test | Critical | Hydraulic Pressure at manufacturer's works | 100% | IS 3589 | IS 3589 | Inspection Report | W | W | R |  |
| 4.0 INNER LINING & OUTER COATING |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Physical | 1. Dimension | Major | Measuring Instrument | 100% | IS 3589/’001 | IS 3589/2001 | Manufacturer's Register/ Report | W | R | R |  |
|  |  | 2. Surface Defect | Major | Visual | 100% | IS 3589/’001 | IS 3589/2001 | Manufacturer's Register/ Report | W | R | R |  |
| 4.2 | Cement | a. Chemical | Critical | Chemical Analysis | One sample for every 200 bags | IS 269 / IS 8112/ IS 12330 | IS 269 / IS 8112/ IS 12330 | Suppliers TC | W | R | R |  |
|  |  | b. Physical |  |  |  |  |  |  |  |  |  |  |
|  |  | 1. Fineness | -do- | By Sieve | -do- | -do- | -do- | Lab report | W | R | R |  |
|  |  | 2. Standard Consistency | -do- | Lab test | -do- | -do- | -do- | Lab report | W | R | R |  |
|  |  | 3. Setting time Initial, Final | -do- | Lab test | -do- | -do- | -do- | Lab report | W | R | R |  |
|  |  | 4. Soundness | -do- | Lab test | -do- | -do- | -do- | Lab report | W | R | R |  |
|  |  | 5. Compressive Strength | -do- | Lab test | -do- | -do- | -do- | Lab report | W | R | R |  |
| 4.3 | Aggregate | a. Deleterious Material | Major | Lab test | 1’lot | IS 383 | IS 383 | 1. Supplier's TC2. Lab report. | W | R | R |  |
|  |  | b. Soundness | -do- | -do- | -do- | -do- | -do- | -do- | W | R | R |  |
|  |  | c. Specific Gravity | -do- | -do- | -do- | -do- | -do- | -do- | W | R | R |  |
|  |  | d. Grading & Size | -do- | -do- | -do- | -do- | -do- | -do- | W | R | R |  |
| 4.4 | Weld Mesh for outer Coating | Dimension | Minor | Measuring Instrument | AQL 4.0 I.L.II D.S.P of IS 2500 | As per customer specification | Manufacturer's Register/ Inspection/ Record | Manufacturer/ TPI | W | R | R |  |
| 4.5 | Water | Suitability of water for concrete works | Major | Lab test | Once in a year | IS 456 | IS 456 | Lab TC | W | R | R |  |
| 4.6 | Outer Coating Mix | a. Mix design | Major | Measurement | 1/Batch | Manufacturer’s own standard | Manufacturer's own standard | -do- | W | W | R |  |
|  |  | b. Cube Strength | Critical | Compressive strength’ | 3/Batch | IS 784 and purchaser's specification | IS 784 and purchase’s specification | Manufacturer's Register | W | R | R |  |
| 4.7 | Outside Coating | Coating thickness | Major | Spike gauges | 5% | Purchaser’s specification | Purchaser's specification | -do- | W | W | R |  |
| 4.80 | Curing | Proper curing | Critical | 1. Visual2. Co-relating wit’ cube strength | 100% | Purchaser’s specification | Purchaser's specification | -do- | W | W | R |  |
| 5.0 | FINAL INSPECTION AND TESTING |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Fabricated, lined and coated pipe | a. Surface defect’s | Major | Visual | 100% | Purchaser's specification/ ’IS 1916 | Purchaser's specification/IS 1916 | Test Reports | W | W | R |  |
|  |  | b. Dimension | Major | Measuring Instrument and Gauges | 100% | Purchaser's specification/ ’IS 1916 | Purchaser's specification/IS 1916 | -do- | W | W | R |  |
|  |  | c. Marking | Major | Visual | 100% | Purchaser's specification/ ’IS 1916 | Purchaser's specification/IS 1916 | -do- | W | W | R |  |
| 6.0 | SEALING AND STAMPING |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Stencilling IA stamp | Legibility of Stamp | Major | Visual | 100% | --- | --- | Test Reports | W | W | R | Samples inspected by TPI are double stamped |
| 7.0 | PACKING AND DESPATCH |  |  |  |  |  |  |  |  |  |  |  |
|  | Each pipes is handled only by flat canvas belt to avoid damages during handling and properly stacked to avoid damages during transport and unloading. |  |  |  |  |  |  |  |  |  |  |  |
|  | R= Review |  |  |  | MTC = Manufacturer test certificate |  |  |  |  |  |  |  |
|  | W= Witness |  |  |  | Lab TC = Laboratory test certificate |  |  |  |  |  |  |  |
|  | M =Manufacturer |  |  |  |  |  |  |  |  |  |  |  |
|  | B = Board |  |  |  |  |  |  |  |  |  |  |  |
|  | TPI = Third Party Inspection agency |  |  |  |  |  |  |  |  |  |  |  |

| QUAILTY ASSURANCE PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOR MANUFACTURE OF DUCTILE IRON PIPES, INSPECTION AND TESTING PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SL NO. | Component / Material |  | Characteristics Check |  | Category |  | Type of Check |  | Quantum of Check |  | Reference Documents | Acceptance Norms |  | Format of Record |  | Agency |  |  |  |  |
| I | Raw Material |  |  |  |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |
| 1. | BF Liquid Metal or Pig Iron |  | %C, %SI, %MN, %S, %P |  | Major |  | Chemical |  | One Per Lot or Batch |  | As per Manufacturers standard | As per Manufacturers standard |  | MTC |  | W |  |  |  |  |
| 2. | Ferro Silicon |  | %SI, %AL |  | Major |  | Chemical |  | One Per Lot or Batch |  | As per Manufacturers standard | As per Manufacturers standard |  | MTC |  | W |  |  |  |  |
| 3. | Silica Sand / River Sand |  | Sieve Analysis Compaction |  | Major |  | Chemical |  | One Per Lot or Batch |  | As per IS 8329 -2000/IS 383 | As per IS 8329 -2000 |  | MTC |  | W |  |  |  |  |
| 4. | Magnesium |  | Purity of Mg |  | Major |  | Chemical |  | One Per Lot or Batch |  | As per IS 8329 -2000 | As per IS 8329 -2000 |  | MTC |  | W |  |  |  |  |
| 5. | Zinc |  | Purity of Zn |  | Major |  | Chemical |  | One Per Lot or Batch |  | As per Manufacturers standard | As per Manufacturers standard |  | MTC |  | W |  |  |  |  |
| 6. | Cement |  | Material Conformation |  | Major |  | Physical and Chemical |  | One Per Lot or Batch |  | As per IS 8112 | As per IS 8112/ IS 12330 |  | MTC |  | W |  |  |  |  |
| 7. | Bitumen Paint |  | Specific Gravity |  | Major |  | Specific Gravity |  | One Per Lot or Batch |  | As per Manufacturers standard | As per Manufacturers standard |  | MTC |  | W |  |  |  |  |
| II | Process Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. | Heat Treatment |  | Temperature Recording Time Cycle |  | Major |  | - |  | 100% |  | As per Manufacturers standard | As per Manufacturers standard |  | Heat Treatment Chart |  | W |  |  |  |  |
| 2. | Zinc Coating |  | Deposit of Zn |  | –ajor |  | - |  | One Per Batch |  | IS 8329 - 2000 | IS 8329 – 2000 |  | Manufacturers internal Record |  | W |  |  |  |  |
| III | Inspection & Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Visual |  | As per IS - 8329 – 2000 |  | Major |  | Visual |  | 100% |  | As per IS 8329- 2000 | As per IS 8329- 2000 |  | Manufacturer Report |  | W |  |  |  |  |
| 2 | Dimensional |  | As per IS - 8329 – 2000 |  | Major |  | Measurement |  | 100% |  | As per IS 8329- 2000 | As per IS 8329- 2000 |  | Manufacturer Report |  | W |  |  |  |  |
| 3 | Lining Thickness |  | As per IS - 8329 – 2000 |  | Major |  | Physical |  | Random Check |  | As per IS 8329- 2000 / IS 11606 | As per IS 8329- 2000 |  | Manufacturer Report |  | W |  |  |  |  |
| 4 | Bitumen Coating Thickness |  | As per IS - 8329 – 2000 |  | Major |  | Physical |  | Random Check |  | As per IS 8329- 2000 / IS 11606 | As per IS 8329- 2000 |  | Manufacturer Report |  | W |  |  |  |  |
| 5 | Compression test of Cubes |  | As per IS - 8329 – 2000 |  | Major |  | Physical |  | One test per lot or batch |  | As per IS 8329- 2000 / IS 11606 | As per IS 8329- 2000 |  | Manufacturer Report |  | W |  |  |  |  |
| 6 | Gasket Fitment and Feak tightness test |  | As per IS - 8329 – 2000 |  | Major |  | Physical |  | One Per Lot or Batch |  | As per IS 8329- 2000 / IS 11606 | As per IS 8329- 2000 |  | Manufacturer Report |  | W |  |  |  |  |
| 7 | Marking on Pipes |  | As per IS - 8329 – 2000 |  | Major |  | Physical |  | Random Check |  | As per IS 8329- 2000 / IS 11606 | As per IS 8329- 2000 |  | Manufacturer Report |  | W |  |  |  |  |
| Note: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Manufacturer shall carryout 100% inspection on final product |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. All measuring instruments should be calibrated. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Cement used for lining shall conform to IS 8112 or IS 12330 depending on the usage of pipeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. The rubber gasket shall conform to IS 5382 / 1985 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Legend : M: Manufacturer, B: KUWS & DB , TPI: Third Party Inspection, R: Review, W: Witness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reviewed items may be randomly witnessed by the concerned if necessary. All measuring instruments and testing equipment shall be calibrated periodically and put up for verification to Third Party Inspection agency. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| QUALITY ASSURANCE PLAN for DI AIR VALVE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SL NO | Item & Component |  |  | Characteristics Checked |  | Category |  | Type of Check |  | Quantum of check |  | Materials Specification |  |  | Acceptance Document |  | Reference Document |  | Agency |  |  | Remarks |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | P | W | V |  |  |
| 1 | RAW MATERIAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) | (DUCTILE IRON)BODY, BONNET, WEDGE DISC, TOP HOUSING, HAND WHEEL ETC. |  |  | Physical properties |  | Major |  | Physical testa) UTSb)% Elongation |  | One Test piece Per Heat |  | Ductile Iron DIN:1693,Gr. GGG-40 or S.G.I., IS:1865 Gr.400/15 |  |  | IS:3896-1985 (DIN:1693, Gr. GGG-40 or IS:1865 Gr.400/15) |  | JEC Test Certificate |  | 1 | 1 | 3 | T.C. review by Inspection Agency |  |
| b) | (STAINLESS STEEL)STEM |  |  | Physical properties & Chemical Analysis |  | Major |  | Physical test:a) UTSb)Yield stressc)% Elongation Chemical Analysis |  | One Test piece Per Lot |  | S.SAISI:410/!S:6603 Gr.12 Cr.12 |  |  | S.SAISI:410/!S:6603 Gr.12 Cr.13 |  | JEC Test Certificate |  | 1 | 1 | 3 |  |  |
| c) | (L T. Bronze)STEM NUT |  |  | Physical properties & Chemical Analysis |  | Major |  | Physical test:a) UTSb)% Elongation Chemical Analysis |  | One Test piece Per Heat |  | L.T.BIS:318Gr.LTB-2 |  |  | L.T.BIS:318-1981Gr.LTB-3 |  | JEC Test Certificate |  | 1 | 1 | 3 |  |  |
| d) | STAINLESS STEEL bolts & nuts |  |  | Free from defects |  | Major |  | Visual |  | One Test piece Per Lot |  | As per Drawing |  |  | As per Drawing |  | JEC Test Certificate |  | 1 | 1 | 3 |  |  |
| 2 | IN PROCESS INSPECTION Machining , Drilling as per Drg& Std., Finishing |  |  | a. Surface defects |  | Major |  | Visual |  | 100% |  | As per Mfg. Std./GA Drawing |  |  | No Harmful Defects |  | Internal Inspection Report (IR) |  | 1 | 1 | 3 | Internal record |  |
|  |  |  |  | b. Dimensions |  | Major |  | Measurement |  | 100% |  | Mfg.Drg. / IS:1538 (for flanges), IS: 14846 (for face to face) |  |  | Mfg. Drg. / IS:1538-Table-6/ IS: 14846 |  |  |  |  |  |  |  |  |
| 3 | VALVES ASSEMBLY |  |  | Dimensions |  | Major |  | Measurement |  | 100% |  | Mfg.Drg. / IS:1538 (for flanges), IS: 14846 (for face to face) |  |  | Mfg. Drg. / IS:1538-Table-6/ IS: 14847 |  | Internal Inspection Report (IR) |  | 1 | 1 | 3 | Internal Inspection Report (IR) |  |
|  |  |  |  | Operativility/Performance (opening & closing) |  | Major |  | Operational Check(Close to open & vice versa) |  | 100% |  | As per Drawing |  |  | Smooth Operation (opening & closing) |  |  |  |  |  |  |  |  |
| 4 | TESTING |  |  | Hydrostatic Pressure test |  | Critical |  | Pressure test(Hyd) Body at 15 Kg/cm2 for 5 min & Seat at 10 Kg/cm2 for 2 min for PN-10 |  | 100% |  | As per IS:14846/2000 |  |  | No Leakage |  | Internal Inspection Report (IR) |  | 1 | 3 | 2 |  |  |
| 5 | FINAL INSPECTION |  |  | a. Surface defects & appearance |  | Major |  | Visual |  | 100% |  | Mfg. Std./Drg. |  |  | No Harmful surface Defects |  | Inspection Certificate |  | 1 | 3 | 2 | All Valves should be offer for inspection in painted condition &’after final inspection client's inspector will issue inspection certificates and release the valves for despatch |  |
|  |  |  |  | b. Overall Dimensions |  | Major |  | Measurement |  | 100% |  | As per IS: 14846 & IS:1538/ As per Drawing |  |  | As per GA Drawing |  | ----DO---- |  | 1 | 3 | 2 |  |  |
|  |  |  |  | c. Pressure test (Hydrostatic) |  | Critical |  | Leakage test |  | 100% |  | As per IS: 14846/2000 |  |  | IS:14846/2001IS:780/IS:2906 |  | ----DO---- |  | 1 | 3 | 2 |  |  |
|  |  |  |  | d. Performance |  | Major |  | Operational (Close to open & vice versa) |  | Random |  | Mfg. Std./ As per IS: 14846/2001 |  |  | Smooth opening & closing |  | ----DO---- |  | 1 | 3 | 2 |  |  |
|  |  |  |  | e. Painting |  | Major |  | Visual |  | 100% |  | As per Drawing/specification |  |  | As per Drawing/specification IS:780/IS:2906 |  | Internal Inspection Report (IR) |  | 1 | 1 | 2 |  |  |
|  |  |  |  | f. Marking |  | Major |  | Visual |  | 100% |  | As per Drawing |  |  | As per Drawing |  |  |  | 1 | 3 | 2 |  |  |
|  |  |  |  | 1. Manufacturer |  |  |  |  |  | P- Performed byIR- Inspection Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 2. Purchaser |  |  |  |  |  | W- Witnessed by |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 3. Inspection Agency |  |  |  |  |  | P- Verified |  |  |  |  |  |  |  |  |  |  |  |  |  |

| QUALITY ASSURANCE PLAN for DI SLUICE VALVE |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SL NO | Item & Component | Characteristics Checked | Category | Type of Check | Quantum of check | Materials Specification | Acceptance Document | Reference Document | Agency |  |  | Remarks |
|  |  |  |  |  |  |  |  |  | P | W | V |  |
| 1a) | RAW MATERIAL(DUCTILE IRON)BODY, COVER | Physical properties | Major | Physical test a) UTS b)%Elongation c) Hardness | One Test piece Per Heat | Ductile Iron DIN:1693,Gr. GGG-40 or S.G.I., IS:1865 Gr.400/15 | IS:3896-1985 (DIN:1693, Gr. GGG-40 or IS:1865 Gr.400/15) | JEC Test Certificate | 1 | 1 | 3 | T.C. review by Inspection Agency |
| b) | (Stainless steel)Float, belts/ studs & nuts | Chemical Analysis | Major | Chemical Analysis | One Test piece Per Lot | S.SAISI-304 | S.SAISI-305 | JEC Test Certificate | 1 | 1 | 3 | T.C. review by Inspection Agency |
| 2 | IN PROCESS INSPECTION Machining , Drilling as per Drg& Std., Assembling & Finishing | a. Surface defects | Major | Visual | 100% | As per Mfg. Std./GA Drawing | No Harmful Defects | Internal Inspection Report (IR) | 1 | 1 | 3 | Internal record |
|  |  | b. Dimensions | Major | Measurement | 100% | As per Mfg.Drg. / IS:1538 | As per Mfg. Drg. / IS:1538-Tab 6 |  |  |  |  |  |
|  |  | c. Lapping | Major | Blue matching | 100% | As per Mfg. Std./GA Drawing | Uniform contact b/w Seat & Contact |  |  |  |  |  |
| 3 | VALVES ASSEMBLY | Dimensions | Major | Measurement | 100% | As per Mfg.Drg. / IS:1538 | As per AWWA C-512/ GA Drawing | Internal Inspection Report (IR) | 1 | 1 | 3 | The Hydrastatic Test shall be done with water Duration of Tests: Body- 5 minutes, Seat- 2 minutes |
|  |  | Performance | Major | Floating of Ball | 100% | ----DO---- | Seating between Ball & Orifice |  |  |  |  |  |
| 4 | TESTING | Hydrostatic Pressure test | Critical | Pressure test (Hyd) PN-10 Body at 15 Kg/cm2 & Seat at 10 Kg/cm2 | 100% | As per Drawing | No Leakage | Internal Inspection Report (IR) | 1 | 3 | 2 |  |
| 5 | FINAL INSPECTION | a. Surface defects & appearance | Major | Visual | 100% | As per Drawing | No Harmful Defects | Inspection Certificate | 1 | 3 | 2 | All Valves should be offer for inspection in painted condition &’after final inspection client's inspector will issue inspection certificates and release the valves for despatch |
|  |  | b. Overall Dimensions | Major | Measurement | 100% | As per Mfg.Drg. / IS:1539 | As per AWWA C-512/ GA Drawing | ----DO---- | 1 | 3 | 2 |  |
|  |  | c. Leakage test | Critical | Pressure test (Hydrostatic) | 100% | As per Drawing specification | As per Drawing | ----DO---- | 1 | 3 | 2 |  |
|  |  | d. Performance | Major | Visual | Random | As per Drawing / Standards | Seating between Ball & Orifice | ----DO---- | 1 | 3 | 2 |  |
|  |  | e. Painting | Major | Visual | 100% | As per specification | As per Drawing/specification | Internal Inspection Report (IR) | 1 | 1 | 2 |  |
|  |  | f. Marking | Major | Visual | 100% | As per Drawing | As per Drawing |  | 1 | 3 |  |  |
|  |  | 1. Manufacturer |  |  | P- Performed byIR- Inspection Report |  |  |  |  |  |  |  |
|  |  | 2. Purchaser |  |  | W- Witnessed by |  |  |  |  |  |  |  |
|  |  | 3. Inspection Agency |  |  | P- Verified |  |  |  |  |  |  |  |

|  | Reviewed items may be randomly witnessed by the concerned if necessary. All measuring instruments and testing equipment shall be calibrated periodically and put up for verification to Third Party Inspection agency. |  |
| --- | --- | --- |

QUALITY ASSURANCE PLAN for HDPE Pipes

| Sl. No. | Stages | Characteristics | Type & Quantum of Check | Reference Document | Acceptance Norms | Format of Records | Inspection by |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | M | TPI | B |  |
| 1 | Inspection of HDPE Raw material | Base Density Melt Flow index Carbon Black content carbon Black dispersion | Random Sampling, Single sampling, general inspection II level of ISO 2859-1 | Clause 5.2.1.1 of IS 7328-92 Clause 7 of IS 2530-63 Clause 10 of IS 2530-63 Clause 5.5 of IS 7328-92 | Designation A45 of Clause 3.1.1 of IS 7328-74 Designation T006 or T012 of IS 7328-92. Clause 5.4 of IS 7328-92 Clause 5.5 of IS 7328-92 Clause 10 of IS 2530-63 Clause 16 of IS 2530-63 | MTC | T | R | R |  |
| 2 | In process inspection of HDPE Pipes | Visual & Dimensional (IS Pipe) | 100% Check | Table 3 of IS“4984 | “Clause 6 of IS:4984 and "GO BY" for visual acceptance and table 1 of IS:4984 for dimensional req. | MTC | T | R | R |  |
| 3 | Final Inspection of HDPE Pipe | 1) Visual & Dimensional (IS Pipe) | Random Sampling Table 7 of IS:4984 | Table 3 of IS“4984 | “Clause 6 of IS:4984 and "GO BY" for visual acceptance and table 1 of IS:4984 for dimensional req. | MTC | T | W | R |  |
|  |  | 2) Reversion | Random Sampling Table 8 of IS:4984 | Annex C of IS:4984-95 | Clause 8.2 of IS 4984-95 | MTC | T | W | R |  |
|  |  | 3) Hydraulic |  |  |  |  |  |  |  |  |
|  |  | a) Type Test (once in two years) | Random Sampling Table 8 of IS:4984 | Annex B, Clause 9.1 of IS:4984 and Table 6 of IS:4984 | Clause 8.1 of IS:4984 | MTC | T | R | R |  |
|  |  | b) Acceptance Test | Random Sampling Table 8 of IS:4984 | Annex B, Clause 9.1 of IS:4984 and Table 6 of IS:4984 | Clause 8.1 of IS:4984 | MTC | T | W | R |  |
|  |  | 4) Overall Migration | Clause 8.3 of IS:4984-95/ 9845-86 | Clause 8.3 of IS:4984-95/ 9845-86 | Clause 9.2.4.2 & Table 8 of IS 4984-95 / 9845-86 | MTC | T | W | R |  |
|  |  | 5) Density | Clause 8.4 of IS:4984-95/ 7328-92 | Clause 5.2.1 of IS 4984-95 / 7328-92 | Clause 9.2.4.2 & Table 8 of IS 4984-95 / 7328-92 | MTC | T | W | R |  |
|  |  | 6) Melt flow rate | Clause 8.5 of IS:4984-95 | Clause 8.5 of IS:4984-95 / 2530-63 | Clause 9.2.4.2 & Table 8 of IS 4984-95 / 2530-63 | MTC | T | W | R |  |
|  |  | 7) Carbon black content & dispersion | Clause 8.6 of IS 4984-95/ 2530-63 | Clause 8.6 of IS 4984-95/ 2530-63 | Clause 9.2.4.2 & Table 8 of IS:4984-95 / 2530-63 | MTC | T | W | R |  |
|  |  | 8) Marking | Clause 10 of IS 4984-95, Inspected with visual requirements | Clause 10 of IS 4984-95 | Clause 10 of IS 4984-95 | MTC | T | W | R |  |
| MTC - Manufacturer's Test Certificate |  |  |  |  |  |  |  |  |  |  |
| M - Manufacturer |  |  |  |  |  |  |  |  |  |  |
| TPI - Third Party Inspection Agency |  |  |  |  |  |  |  |  |  |  |
| B - KUWS & DB |  |  |  |  |  |  |  |  |  |  |
| T- Testing |  |  |  |  |  |  |  |  |  |  |
| W - Witness |  |  |  |  |  |  |  |  |  |  |
| R- Review |  |  |  |  |  |  |  |  |  |  |
| Note: 1) The measuring instruments & test shall be calibrated periodically and put up to TPI for verification. 2) The manufacturer shall give a copy of type test for TPI for scrutiny and for validity 3) The manufacturer should give a copy of internal lab report to TPI. |  |  |  |  |  |  |  |  |  |  |

## SCHEDULE-1: PHYSICAL AND FINANCIAL ACTIVITY PROGRESS

| Particulars | Physical and Financial works to be completed | Period from the date of issue of Notice to proceed with the work |
| --- | --- | --- |
| Milestone-1 | ₹10.72 Lakhs Detailed Scheme Report and Drawings: Submission of documents & drawings Civil, Pipeline and Building Works., Mechanical Plants, Electrical Plants, Instrumentation and Control System, Approval of QAP, any additional items required for the production of construction documents & drawings – 100%, Total Station Survey, Soil Investigations including trial pits and SBC of Soil – 100% Coffer dam – 0.5 % Intake well - 0.5 % Connecting main – 0.5 % Inspection Chamber 0.5% Jack well cum pumphouse – 0.5% 11 KV express feeder main from WTP to jack well – 0.5 % Raw water pumping machinery – 0.5 % Approach bridge – 0.5 % Raw water rising main – 0.5 % WTP (3.63 MLD) - 0.5 % | Two months from the date of agreement. |
| Milestone- 2 | ₹801.02 Lakhs All the quantities up to milestone-1 and Coffer dam – 75 % Intake well - 43 % Connecting main – 87 % Inspection Chamber - 60% Jack well cum pumphouse – 20% 11 KV express feeder main from WTP to jack well – 0 % Raw water pumping machinery – 0 % Approach bridge – 44.5 % Raw water rising main – 45 % WTP (3.63 ML) - 37.5 % | Eight months from the date of agreement. |
| Milestone-3 | ₹1068.66 Lakhs All the quantities up to milestone-2 and Coffer dam – 0 % Intake well - 56.5 % Connecting main – 12.5 % Inspection Chamber – 39.5 % Jack well cum pumphouse – 53% 11 KV express feeder main from WTP to jack well – 85 % Raw water pumping machinery – 81 % Approach bridge – 47 % Raw water rising main – 48.5 % WTP (3.63 MLD) - 37 % | Fourteen months from the date of agreement. |
| Milestone-4 | ₹262.77 Lakhs All the quantities upto milestone-3 and Coffer dam – 24.5 % Intake well - 0 % Connecting main – 0 % Inspection Chamber – 0 % Jack well cum pumphouse – 26.5% 11 KV express feeder main from WTP to jack well – 14.5 % Raw water pumping machinery – 12.5 % Approach bridge – 8 % Raw water rising main – 6 % WTP (3.63 MLD) - 25 % | Eighteen months from the date of agreement. |

Textile Park

Physical and Financial Activity Progress

| Sl No | Activities to be undertaken from the date of issue of notice to proceed |
| --- | --- |
|  |  | Mile stone 1 | Mile stone 2 | Mile stone 3 | Mile stone 4 |
|  |  | end of 2nd month | end of 8th month | end of 14th month | end of 18th month |
| 1 | Detailed Scheme Report and Drawings: Cost of production of set of documents & drawings | 100% |  |  |  |  |
|  | Total Station Survey, Soil Investigations including trial pits and SBC of Soil |  |  |  |  |  |
| 2 | Construction Documents and Drawings: Cost of production of set of construction documents & drawings. | 100% |  |  |  |
|  | 2.1 Civil, Pipeline and Building Works. |  |  |  |  |
|  | 2.2 Mechanical Plants. |  |  |  |  |
|  | 2.3 Electrical Plants. |  |  |  |  |
|  | 2.4 Instrumentation and Control System |  |  |  |  |
|  | Approval of QAP |  |  |  |  |
|  | Any additional items required for the production of construction documents & drawings |  |  |  |  |
| 3 | Operation and Maintenance Manuals: Costs for the production of operation and maintenance manuals |  |  |  | 100% |
|  | 3.1 First issue (prior to Tests on Completion) |  |  |  |  |
|  | 3.2 As built O & M Manuals |  |  |  |  |
| 4 | Construction of Embankment by excavating the available approved Gravel/ Murrum deposited at a place or borrow pits during or prior excavation with all lifts and lead, transportation to site, spreading, grading to required slope and compacting to meet the requirement complete as per specifications, including cost of labour, rolling, water, all materials,usage& all other appurtenaces required to complete the work etc., complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | 0.5% | 75% |  | 24.5% |
| 5 | Construction of 4.5 M dia intake well in Bhima river at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | 0.5% | 43% | 56.5% |  |
| 6 | Providing connecting main of 500mm dia RCC NP-3 class pipes for the length of 95mtrs from intake well to jackwell in Bhima river at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | 0.5% | 87% | 12.5% |  |
| 7 | Construction of Inspection Chamber (2Nos) @ 48m for connecting main 500mm dia RCC pipe - 95m from intake well to jackwell in Bhima river at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | 0.5% | 60% | 39.5% | 0 |
| 8 | Construction of 6 mtr. dia. RCC Jackwell cum 8 mtr. Pump House in Bhima river at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items | 0.5% | 20% | 53% | 26.5% |
| 9 | 11 KV express feeder main: Providing 11KV Express feeder line from substation to WTP for Yadrami WSS - 5KM as directed by the Engineer Incharge (Shall be read in conjunction with Section 7 Specifications Special specifications for all the items) | 0.5% |  | 85% | 14.5% |
| 10 | Supply, erection, electrification and commissioning of 2 Nos. of 90HP or suitable HP (100% standby )submersible Verticle Turbine Pumpsets at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | 0.5% |  | 81% | 18.5% |
| 11 | Construction of R.C.C. approach bridge for the length of 95mtrs to jackwell cum pumphouse at proposed barrage near Madri Village etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | 0.5% | 44.5% | 47% | 8% |
| 12 | Providing,laying,jointing,testing and commissioning of 300mm dia. DI K-9 class raw water rising main for the length of not less than 17.52Km from proposed jackwell cum pumphouse at barrage near Madri Village to proposed WTP in textile park. etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | 0.5% | 45% | 48.5% | 6% |
| 13 | Construction of 3.63 MLD output ( in 22 Hours ) capacity water treatment plant (WTP) at proposed Textile Park near Nadishirnur village including, aerator,raw water channel,flash mixer,floculator,tube settler,filter complex,chlorine rooom,chemical house, laboratory,1.50 LL or suitable capacity back wash OHT, 2LL sump, yard lighting, electrical and electrification of WTP components,sludge disposal arrangements, barbed wire fencing to WTP,internal roads, electro-mechanical works,land scaping of WTP etc.,complete including all lead and lifts and as directed by engineer in charge and Shall be read in conjunction with Section 7 Specifications Special specifications for all the items. | 0.5% | 37.5% | 37% | 25% |

Liquidated Damages

PART-A

The liquidated damages for the whole of the works for Part A subject to maximum of 10% of the total cost quoted by the Contractor towards Part I and that for the milestone are as under.

| Sl. No. | Milestones | LD |
| --- | --- | --- |
| 1 | Milestone 1 | ₹2,000/- per day |
| 2 | Milestone 2 | ₹1,35,000 /- per day |
| 3 | Milestone 3 | ₹3,13,000 /- per day |
| 4 | Milestone 4 | ₹3,57,000 /- per day |

| ## SCHEDULE 2: OPERATION AND MAINTENANCE PART B (Operation & Maintenance) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Operation and maintenance of the water supply scheme –Key Performance Indicators | 60 months after Completion of Part-I |  |  |  |
| Deficiency in Services during Operations and Maintenance will be levied as below for non- compliance with the agreed supply of treated water particularly in the following four parameters and corresponding weightages— Quality and Pressure (40% of variable O&M payment), Quantity/NRW (30% of variable O&M payment), Maximum Power Guarantee (20% of variable O&M payment) and Grievance Redressal (10% of variable O&M payment) |  |  |  |  |
| Event triggering the recovery of Deficiency of Services | During the O & M Period |  |  |  |
|  | Amount |  |  | Frequency |
| Quality & Pressure | • Water supplied to the scheme should be tested at Water Treatment plant with all the 17 no. water quality parameters. If not tested & report not furnished, penalty % is 10 of 40 |  |  | Monthly |
|  | • If 4 parameters are not in acceptable range the penalty % is as follows |  |  |  |
|  | Parameter | Penalty (%) Against non-compliance |  |  |
|  | Colour (Hazen) | 5 of 40 |  |  |
|  | Residual free chlorine, mg/l | 10 of 40 |  |  |
|  | Turbidity (NTU) | 5 of 40 |  |  |
|  | pH | 5 of 40 |  |  |
|  | Residual Pressure kg/m2 | 5 of 40 |  |  |
| Quantity / NRW | Illustration |  |  | Monthly |
|  | Assumed Quantity of water supplied per month | Penalty | Remarks |  |
|  | Demand | 0 | Total amount to be paid to operator against supply of demand per month (Inclusive of losses as per CPHEEO) of water is assumed as = Rs. X. The penalty will be calculated by adding for each day separately for every OHT in the project. |  |
|  | 90% of Demand | X into 10% |  |  |
|  | 80% of Demand | X into 20% |  |  |
|  | 70% of Demand | X into 30% |  |  |
|  | Less than 70% of Demand | Forfeiture of Performance Security |  |  |
| Maximum Power Guarantee | All charges towards excess power consumption of the equipment beyond the Maximum Power Guarantee by the Contractor and penalty levied by ESCOM towards lower power factor subject to 20% of 50% beyond which the Performance Security shall be forfeited. |  |  | Monthly |
| Grievance Redressal | Category of Complaints |  |  | Monthly |
|  | • Complaints that are resolvable within 12 hours |  |  |  |
|  | • Complaints that are resolvable within 24 hours |  |  |  |
|  | • Complaints that are resolvable within 48 hours |  |  |  |
|  | Type of Complaints | Time allowed for resolution of complaints without penalty | Penalty for Delay in resolving complaints (%) |  |
|  | Minor | 12 Hours | 5 of 10 |  |
|  | Medium | 24 Hours | 3 of 10 |  |
|  | Major | 48 Hours | 2 of 10 |  |

## SCHEDULE 3: SCHEDULE OF PAYMENT

Part-I:	The Tenderer has to submit a detail breakup schedule which will be approved by the Competent Authority (Employer).

Note: The detailed payment breakup schedule should be prepared based on the work program, as per the typical breakup schedule as under based on FD Note No. FD 702 Exp-9/ 2023(E) dated:18-11-2023;

(i)	Upon Satisfactory supply of Material at the work Site - 55% may be released as payment.

(ii)	Upon successful completion of earthwork, laying, jointing, testing and refilling of these items etc. 35% release can be made.

(iii)	Upon successful trial run and commissioning the remaining amount 10% may be made.

PART-II :  The payment during O & M period of five (5) years shall be made on quarterly basis.

The payment during the Phase O&M would comprise of two components, namely Fixed Payment and Variable payment, as follows:

- Fixed Payment shall be 50% of the O&M Cost.

- Variable Payment shall be 50% of the O&M Cost.

- Fixed Payment

  - The Fixed Payment shall be paid on quarterly basis during the O&M period, subject to fulfillment of the following conditions:

- Maintaining minimum number of personnel as specified in contract throughout the contract period.

- Compliance with all the obligations under the Contract.

- Variable Payment

  - The Variable Payment shall be based on the Key Performance Indicators mentioned in Schedule – 2.

  - The Variable Payment shall be paid on quarterly basis.

  - The Technical Auditor shall certify the achievement of the performance targets, based on which Employer shall make payment towards for Performance Remuneration.

# SECTION 7: TECHNICAL SPECIFICATIONS

Enclosed Separately

# SECTION 8: DRAWINGS

Enclosed Separately

# SECTION 9: BILL OF QUANTITIES (FINANCIAL PROPOSAL)

Enclosed Separately

SECTION 9: BILL OF QUANTITIES

(BoQ) -FINANCIAL PROPOSAL

Preamble:

      - The BoQ is provided for illustration purpose only. The BoQ value shall have to be directly filled and submitted on the e-procurement portal by the Tenderers. Scanned copies of Section 9: Bill of Quantities (Financial Proposal) shall not be submitted with the Technical proposal. Any tender with scanned copies of the BoQ (Financial Proposal) along with the Technical Proposal shall be summarily rejected and such Tenderers shall be disqualified from further evaluation.

      - The BoQ do not generally give a full description of the Construction Details, Plant and Materials to be supplied and the services to be performed under each item.  The entered rates and prices shall be deemed to include for the full compliance with all provisions of the Contract.

      - The Contractor shall quote for each items indicated in the Financial Proposal. The Contractor shall be responsible for making suitable assumptions for any item not indicated in the BoQ and shall include the cost of such item/s while quoting the price.

      - The Contractor shall own the designs and is wholly responsible for guaranteeing the treated water quality and supply quantity to Textile Park etc, pressure at OHTs and other discharge points etc. failing which liquidated damages shall be applicable as detailed in the contract document

      - The Contractor shall make his own arrangements and include in the costs towards disposing off of surplus excavated earth, debris etc., without causing any infringements.

      - The spares, tools and test equipment required during testing and commissioning and three (3) year operation and maintenance period is deemed to be included in the total amount quoted by the Tenderer. No additional claim whatsoever from the Contractor will not be entertained by KUWSDB for any plant, equipment, machinery, spares, parts, tools, test equipment etc. procured by the Contractor during testing and commissioning and One (1) year operation and maintenance period.

      - At the end of six months, during the O & M period/ Defect Liability Period, Employer will assess the condition of all the equipment, machinery, plant, pipeline works, civil, mechanical, electrical, I & C, works etc. and all the damaged, non performing equipment, machinery, plant etc. shall be replaced by the Contractor before handing over the plant to the Employer. The Contractor shall demonstrate satisfactory working of all the equipment, machinery, plant etc. during handing over of the facility to the Employer

      - Rates for all the items in BoQ shall be filled up.  Items left blank or missed are deemed to have been included in other items quoted.

      - The taxes and duties referred in the “Price Schedules” shall cover all the taxes and duties applicable except GST that shall be paid by the Employer at then prevailing rates

      - Although the Tenderer shall have to quote both CAPEX and OPEX. The Lowest or successful tenderer shall be selected based on the basis of sum total of “Total quoted CAPEX cost” and “Total NPV of quoted OPEX cost for 5 years including defect liability for period of 1 year.

Evaluate the quoted OPEX cost to the net present value by the method of discounting factor. Lowest offer would be evaluated on the basis of sum total of “Total quoted CAPEX cost” and “Total NPV of quoted OPEX cost for 5 years including defect liability for period of 1 year”. The method of calculation of NPV for OPEX cost is as below:

| (column 1) | OPEX rates quoted inclusive of taxes (column 2) | Discount factor for OPEX charges (DF) (column 3) | Net present value (NPV) of OPEX charges = (DF x Q OPEX) = column 3 x column 2 (column 4) |
| --- | --- | --- | --- |
| OPEX cost for 1st year |  | 1_ = 0.909 (1+rd)1 |  |
| OPEX cost for 2nd year |  | 1___ = 0.826 (1+rd)2 |  |
| OPEX cost for 3rd year |  | 1___ = 0.751 (1+rd)3 |  |
| OPEX cost for 4th year |  | 1___ = 0.683 (1+rd)4 |  |
| OPEX cost for 5th year |  | 1___ = 0.621 (1+rd)5 |  |
| Total NPV of OPEX charges (for purpose of evaluation of lowest offer) |  |  | = Sum of column 4 |

* rd= rate of discounting is taken as 10%

# SECTION 10: FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT

To,

_________________

_________________

WHEREAS		[name and address of Contractor] (hereinafter called "the Contractor") has undertaken, in pursuance of Contract No. dated	 to execute [name of Contract and brief description of Works] (herein after called "the Contract");

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOWTHEREFORE where by affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of Rs.	[amount of guarantee]Rupees			[in words],and we undertake to pay you, upon your first written demand and without caveat or argument, any sum or sums within the limits of		[amount of guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until 30 days from the date of expiry of the Defects Liability Period.

Signature and seal of the guarantor

Name of Bank

Address

Date

PERFORMANCE BANK GUARANTEE (for unbalanced items)

To:	______________________________________________ [name of Employer]

_________________________________________ [address of Employer]

WHEREAS _________________________ [name and address of Contractor] (hereinafter called "the Contractor") has undertaken, in pursuance of Contract No. _____ dated ________________ to execute _________ _________________ [name of Contract and brief description of Works] (hereinafter called "the Contract");

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of ________________[amount of guarantee]1___________________________ [in words], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ____________________ [amount of guarantee]1 as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until …….. (i.e.) 28 days from the date of issue of the certificate of completion of works.

Signature and seal of the guarantor _____________________________

Name of Bank ____________________________________________

Address ____________________________________________

Date ____________________________________________

SECTION 11:BANK GUARANTEE FOR ADVANCE PAYMENT

To:	__________________________________________ [name of Employer]

__________________________________________ [address of Employer]

___________________________________________[name of Contract]

Gentlemen:

In accordance with the provisions of the Conditions of Contract, sub-clause 51.1 ("Advance Payment") of the above-mentioned Contract, ________________________________ [name and address of Contractor] (hereinafter called "the Contractor") shall deposit with ______________________________________________________________________  [name of Employer] a bank guarantee to guarantee his proper and faithful performance under the said Clause of the Contract in an amount of _____________ [amount of guarantee]1_________________________________ [in words].

We, the ____________________ [bank or financial institution], as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligator and not as Surety merely, the payment to ____________________ [name of Employer] on his first demand without whatsoever right of objection on our part and without his first claim to the Contractor, in the amount not exceeding ____________________ [amount of guarantee]1 __________________________________ [in words].

We further agree that no change or addition to or other modification of the terms of the Contract or of Works to be performed thereunder or of any of the Contract documents which may be made between _____________________ [name of Employer] and the Contractor, shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall remain valid and in full effect from the date of the advance payment under the Contract until _________________________ [name of Employer] receives full repayment of the same amount from the Contractor.

Yours truly,

Signature and seal: _____________________________

Name of Bank/Financial Institution:  _______________

Address:  ___________________________

Date:  ____________________

- An amount shall be inserted by the bank representing the amount of the Advance Payment, and denominated in Indian Rupees.

INDENTURE FOR SECURED ADVANCES

THIS INDENTURE made the……………. day of ………….. 2016 BETWEEN …………………….……………………………… (herein after called the Contractor which expression shall where the context so admits or implies be deemed to include his executors, administrators and assigns) of the one part and the Chief Engineer (North), Karnataka Urban Water Supply and Drainage Board or his authorized representative,( herein after called the Employer, which expression shall where the context so admits or implies be deemed to include his successors in office and assigns) of the other part.

WHEREAS by an agreement dated ……………………………. (herein after called the said agreement) the Contractor has agreed AND WHEREAS the Contractor has applied to the Employer that he may be allowed advances on the security of materials absolutely belonging to him and brought by him to the site of Works the subject of the said agreement for use in the construction of such of the works as he has undertaken to execute at rates fixed for the finished work (inclusive of the cost of materials, labour, plant, equipment and other charges) AND WHEREAS the Employer has agreed to advance to the Contractor the sum of Rupees. ……………………………………………………. on the security of materials, the quantities and other particulars of which are detailed in the accounts of Secured Advances attached to the Running Account Bill for the said works signed by the Contractor on ………………………………….. and the Employer has reserved to himself the option of making any further advance or advances on the security of other materials( such materials to include materials, plant, equipment etc) brought by the Contractor to the site of the said works.

NOW THIS INDENTURE WITNESSETH that in pursuance of the said agreement and in consideration of the sum of Rupees. ……………………………..  on or before the execution of these presents paid to the Contractor by the Employer (the receipt whereof the Contractor doth hereby acknowledge) and of such further advances (if any) as may be made to him as aforesaid the Contractor doth hereby covenant and agree with the Employer and declare as follows:

- That the said sum of Rupees……………………………………… so advanced by the Employer to the Contractor as aforesaid and all or any further sum or sums advanced as aforesaid shall be employed by the Contractor in or towards expediting the execution of the said works and for no other purpose whatsoever;

- That the materials detailed in the said Account of Secured Advances which have been offered to and accepted by the Employer as security are absolutely the Contractor’s own property and free from encumbrances of any kind and the Contractor will not make any application for or receive a further advance on the security of materials  which are not absolutely his own property and free from encumbrances of any kind and the Contractor indemnifies the Employer against all claims to any materials in respect of which an advance has been made to him as aforesaid;

- That the materials detailed in the said Account of Secured Advances and all other materials on the security of which any further advance or advances may hereafter be made as aforesaid(herein after called the said materials) shall be used by the Contractor solely in the execution of the said works in accordance with the directions of the Employer and in the terms of the said agreement;

- That the Contractor shall make at his own cost all necessary and adequate arrangements for the proper watch, safe custody and protection against all risks of the said materials and that until used in construction as aforesaid the said materials shall remain at the site of the said works in the Contractor’s custody and on his own responsibility and shall at all times be open to inspection by the Employer or his authorized representatives. In the event of the said materials or any part thereof being stolen, destroyed or damaged or becoming deteriorated in a greater degree than is due to reasonable use and wear thereof the Contractor will forthwith replace the same with other materials of like quality or repair and make good the same as required by the Employer or his authorized representative;

- That the said materials shall not on any account be removed from the site of the said works except with the permission of the Employer or his authorized representative on that behalf;

- That the advances shall be repayable in full when or before the Contractor receives payment from the Employer of the price payable to him for the said works under the terms and provisions of the said agreement, provided that if any intermediate payments are made to the Contractor on account of the work done than on the occasion of each such payment the Employer will be at liberty to make a recovery from the Contractor’s bill for such payment by deducting there from the value of the said materials then actually used in the construction n and in respect of which recovery has not been made previously, the value for this purpose being determined in respect of each description of materials at the rates at which the amounts of the advances made under these presents were calculated;

- That if the Contractor shall at any time make any default in the performance or observance in any respect of any of the terms and provisions of the said agreement or of these presents the total amount of the advance or advances that may still be owing to the Employer shall immediately on the happening of such default be repayable by the Contractor to the Employer together with interest thereon at twelve percent per annum from the date or respective dates of such advance or advances to the date of repayment and with all costs, charges, damages and expenses incurred by the Employer in or for the recovery thereof or the enforcement of this security or otherwise by the reason of the default of the Contractor and the Contractor hereby covenants and agrees with the Employer to repay and pay the same respectively to him accordingly;

- That the Contractor hereby charges all the said materials with the repayment to the Employer of the said sum of Rupees ……………………………. and any further sum or sums advanced as aforesaid and all costs, charges, damages and expenses payable under these presents PROVIDED ALWAYS and it is hereby agreed and declared that notwithstanding anything in the said agreement and without prejudice to the powers contained therein if and whenever the covenant for payment and repayment herein before contained shall become enforceable and the money owing shall not be paid in accordance therewith the Employer may at any time thereafter adopt all or any of the following courses as he may deem fit:-

- Seize and utilize the said materials or any part thereof in the completion of the said works on behalf of the Contractor in accordance with the provisions in that a behalf contained in the said agreement debiting the Contractor with the actual cost of effecting such completion and the amount due in respect of advances under these presents and crediting the Contractor with the value of work done as if he had carried it out in accordance with the said agreement and at the rates thereby provided. If the balance is against the Contractor he is to pay same to the Employer on demand;

- Remove and sell by public auction the seized materials or any part thereof and out of the moneys arising from the sale retain all the aforesaid repayable or payable to the Employer under these presents and pay over the surplus (if any) to the Contractor;

- Deduct all or any part of the moneys owing out of the security deposit or any sum due to the Contractor under the said agreement.

- That except in the event of such default on the part of the Contractor as aforesaid interest on the said advance shall not be payable;

- That in the event of any conflict between the provision of these presents and the said agreement, the provisions of these presents shall prevail and in the event of any dispute or differences arising over the construction or effect of these presents, the settlement of which has not been herein before expressly provided for the same shall be referred to the Managing Director KUWS&DB whose decision shall be final and provisions of the Indian Arbitration Act, 1996 shall apply to any such reference.

In witness whereof the said………… and ……………… by the order and under direction of the Employer have hereunto set their respective hands the day and year first above written.

Signed, sealed and delivered by…………………………………………………

The said Contractor in the presence of:

Witness:  Signature: ……………………………………….

Name: ………………………………………..

Address:………………………………………

Signed by the order and direction of the Employer in the presence of :

Witness:Signature: ……………………………………….

Name: ……………………………………………

Address:…………………………………………….

To bring to the FY in which the tenders are invited, financial turnover of previous years shall be given a weight of 10% per year.

To bring to the FY in which the tenders are invited, value of works completed in previous years shall be given a weight of 10% per year

Applicable only in case of Joint Venture

Applicable only in case of Joint Venture

Add, delete or change depending on the nature of work.