##### KW-3

##### GOVERNMENT OF KARNATAKA

Karnataka Public Works Department.

Dharwad Division, Dharwad.                                                                                                                                                            Opposite All India Radio, Near K.C.D. Circle Dharwad.

Telephones: 0836 – 2747944                                                                                      Fax:  0836-2747944

TENDERS FOR THE WORK OF Improvements and Resurfacing of Tabbakaddahonalli to Bendalgatti via Beeeravalli Major District Road from km 0.00 to km 2.00 in Kalaghatagi taluk of Dharwad District CAT-1PWD/2025-26/RD/WORK_INDENT33455/CALL-3

TENDER REFERENCE	: PWD/2025-26/RD/WORK_INDENT33455/CALL-3

Contents

Section 					Description

No.

1		Invitation for Tenders (IFT)

2		Instructions to Tenderers (ITT)

3.		qualification information

4.		FORM OF TENDER, LETTER OF ACCEPTANCE, notice to

PROCEED WITH THE WORK AND agreement form

5.		Conditions of Contract (CC)

6.		CONTRACT DATA

7		Specifications

8		Drawings

9.		Bill of Quantities (Schedule `B')

10.		FormAT OF BANK GUARANTEE FOR SECURITY DEPOSIT

SECTION 1: INVITATION FOR TENDERS (IFT)

Date:IFT No: PWD/2025-26/RD/WORK_INDENT33455/CALL-3

1.	The Executive Engineer,Public Works Department, DharwadDivision, Dharwadinvites tenders from eligible tenderers, for the work detailed in the Table below.  Two Cover Tender procedure as per Rule28 of the KTPP Act shall be followed. The Tenders are required to submit two separate sealed covers, one containing the Earnest money deposit and the details of their capability to undertake the tender (as detailed in ITT Clause 3and 6), which will be opened first and the second cover containing the price tender which will be opened only if the Tenderer is found to be qualified to execute the tendered works. The Tenderers are advised to note the minimum qualification criteria specified in Clause 3 of the Instructions to Tenderers to qualify for award of the contract.

2.	Tender documents may be downloaded from Government of Karnataka e-Procurement website https://eproc.karnataka.gov.in/eportal/index.seam   under login for Contractors:

After login to Contractors, Please scroll down to the right side bottom to see List of Tenders, Please click there to find the details of NIT and download copy of the tender.   The tender can be downloaded in the portal as per prescribed date and time published in the portal. Only Interested   Contractors who wish to participate should remit online tender processing fee, after registering in the portal. The tender processing fee /transaction fee is non-refundable.

3.	Tenders must be accompanied by earnest money deposit which will be paid online through e-Procurement portal and shall have validity of 45 days beyond the validity of the Tender.

4.	Tenders must be electronically submitted (on-line through internet) with in the date and time published in e-procurement portal. First Cover of the Tenders will be opened after prescribed time and date in the e-procurement portal, in the presence of the Tenderers who wish to attend at the Office of the Executive Engineer, PW,P & IWT Department, Dharwad Division, Dharwad.

5.	A Pre-tender meeting will be held on at 11.00 hoursat the office of the

Executive Engineer, PWD, Dharwad Division, Dharwad.

. It is also published in the e-Procurement portal to clarify the issues if any, and to answer questions on any matter that may be raised at that stage as stated in Clause 8.2 of ‘Instructions to Tenderers’ of the tender document.

6.	Other details can be seen in the tender documents.

| # TABLE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # Sl No | Name of work | Approximate value of work (Rs.) | Earnest Money Deposit (Rs.) | Tender Processing Fee (Rs.) | # Period of completion # (Including Monsoon) |
| # 1 | # 2 | # 3 | # 4 | # 5 | # 6 |
| # 1 | Improvements and Resurfacing of Tabbakaddahonalli to Bendalgatti via Beeeravalli Major District Road from km 0.00 to km 2.00 in Kalaghatagi taluk of Dharwad District CAT-1PWD/2025-26/RD/WORK_INDENT33455/CALL-3 | # Rs. # 6404545.26 | The EMD of Rs. 128100/-, the Earnest Money Deposit shall be in two parts. Part (1) Rs.50000 /- by e-payment and Part (2) Rs. 78100/- shall be in favour of Executive Engineer PWD, Dharwad Division, Dharwad, and may be in the form of Bank Guarantee issued by Nationalized/Scheduled Bank / in favor of Executive Engineer, PWD, Dharwad Division, Dharwad | # Ase-proc Defines it. | # 6 months (Including Monsoon) |

# Executive Engineer,

# PUBLIC WORKS Department,

# Dharwaddivision, Dharwad.

# Section 2:  Instructions to Tenderers (ITT)

# Table of Clauses

A.	General

1.	Scope of Tender

2.	Eligible Tenderers

3.	Qualification of the Tenderer

- One Tender per Tenderer

- Cost of Tendering

- Site Visit

B.	Tender Documents

- Content of Tender documents

- Clarification of Tender Document

9.	Amendment of Tender documents

C.	Preparation of Tenders

10.	Documents comprising the Tender

11.	Tender prices

12.	Tender validity

13.	Earnest money deposit

14.	Format and signing of Tender

D.	Submission of Tenders

# 15.	Sealing and marking of Tenders

# 16.	Deadline for submission of Tenders

- Late Tenders

# 18.	Modification and Withdrawal of Tenders

E.	Tender opening and evaluation

- Opening of First Cover of all Tenders and evaluation to determine

# qualified Tenderers

# 20.	Opening of Second Cover Tenders of qualified Tenders and evaluation

# 21.	Process to be confidential

# 22.	Clarification of Tenders

# 23.	Examination of Tenders and determination of responsiveness

# 24.	Correction of errors

# 25.	Evaluation and comparison of Tenders

# 26.	Award criteria

# 27.	Employer’s right to accept any Tender and to reject any or all Tenders

# 28.	Notification of award and signing of Agreement

# 29.	Security deposit

# 30.	Advance payment and Security

# 31	Corrupt or Fraudulent Practices

# A. General

1.	Scope of Tender

1.1	The Executive Engineer, PWD, Dharwad Division, Dharwad invites tenders following Two Cover tender procedure, from eligible Tenderers, for the work (as defined in these documents and referred to as "the works") detailed in the Table given in the Invitation for Tenders (IFT).

2.	Eligible Tenderers

2.1	Tenderers shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued by the Government of India or any State Government of Union of India

2.2	Tenders from Joint ventures are not acceptable.

3.	Qualification of the Tenderer:

  - All Tenderers shall provide the requested information accurately and in sufficient detail in Section 3:  Qualification information.

3.2  To qualify for award of this contract, each Tenderer in its name should have in the last five years i.e 2021-22, 2022-23, 2023-24, 2024-25, 2025-26

(a) Achieved in at least Two Financial years an average annual financial turnover (in all classes of civil engineering construction works only) of Rs. 64.04  Lakhs.

(b) Satisfactorily completed (at least 50% of the contract value), as prime contractor, at least one similar nature of work such as Improvement to Road work of value not less than Rs. 32.03 Lakhs.

(c)  Qty executed in any one year, the following minimum quantities of work:in the last five years i.e 2021-22, 2022-23, 2023-24, 2024-25, 2025-26

| S.No | Item | Quantity | Unit |
| --- | --- | --- | --- |
| 1 | Earthwork/ Embankment/subgrade | 502.06 | Cum |
| 2 | GSB | 533.58 | Cum |
| 3 | WMM/WBM | 342.25 | Cum |
| 4 | Asphalt Work (BM/DBM/BC/SDBC) | 185.18 | Cum |

3.3)Each Tenderer should further demonstrate:

(a) As per this note, each tenderer should demonstrate availability of few key equipments / machinery for execution of the work. However as per Govt circular no GO-FD/AE 263/EXP12-2022  dt 11-05-2022, this clause for  owning key equipments for works costing up to Rs.3.00 crores is exempted. However it is obligatory for the contractor to use the following machineries for various activities involved in construction as per Morth specification.

The following is the list of Plant & Equipment to be deployed on project

- Excavator like JCB/Hitachi etc

- Tippers / Trucks

- Road Roller (vibrator)

- PRR Roller

- Hot mix with plant (minimum capacity of 40/60 TPH)

- Paver finisher

- Vehicle Mounted (tank) Mechanical sprayer

- Pug Mill (suitable Capacity)

(b) Liquid assets and/or availability of credit facilities of not less than Rs. 19.22 Lakhs. (Credit lines/letter of credit/ certificates from the banks for meeting the fund requirement etc. The banker's certificate /LOC letter shall be in prescribed format-02, without which tender will be rejected)

  - Tenderers who meet the above specified minimum qualifying criteria, will only be qualified, if their available tender capacity is more than the total tender value. The available tender capacity will be calculated as under:

# Assessed available tender capacity = ( A*N*2.50- B )

where

A =Maximum value of civil engineering works executed in any one year during the last five years (updated to2026-27level) taking into account  the completed as well as works in progress.

N =Number of years prescribed for completion of the works for which enders are invited = 06/12. (i.e 06 months)

B =	Value, at 2026-27 price level, of existing commitments and on-going works to be completed during the next 06/12 (i.e 06 months) form the probable date of Award of this contract.

Note:		The statements showing the value of existing commitments and on-going works as well as the stipulated period of completion remaining for each of the works listed should be countersigned by the Employer in charge, not below the rank of an Executive Engineer or equivalent.

Financial turnover of previous years indicated in clause 3.2 and 3.4 above shall be given a weight of 10% per year to bring them to the price level of 2026-27

3.5	Even though the Tenderers meet the above criteria, they are subject to be disqualified if they have:

-	made misleading or false representations in the forms, statements and attachments submitted in proof of the qualification requirements; and/or

-	record of poor performance such as abandoning the works, not properly completing the contract, inordinate delays in completion, litigation history, or financial failures etc.; and/or

-	participated in the previous Tender for the same work and had quoted unreasonably high tender prices and could not furnish rational justification.

# 4.	One Tender per Tenderer:

  - Each tenderer shall submit only one tender for one work.  A tenderer who submits or participates in more than one Tender for the same work will cause all the proposals with the Tenderer’s participation to be disqualified.

5.	Cost of Tendering:

5.1	The tenderer shall bear all costs associated with the preparation and submission of his tender, and the Employer will in no case be responsible and liable for those costs.

# 6.	Site visit:

# The Tenderer at his own responsibility and risk is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the Tender and entering into a contract for construction of the Works. The cost of visiting the Site shall be at the Tenderer’s own expense.

# B.  Tender documents

7.	Content of Tender documents

7.1	The set of tender documents shall have all the Sections given in Page 2:

7.2	Both the  sets should be completed and returned with the tender.

8.	Clarification of Tender Documents

8.1	A prospective tenderer requiring any clarification of the tender documents may notify the Employer by rising  query online or in writing or by cable (hereinafter “cable” includes telex and facsimile) at the Employer’s address indicated in the invitation to tender. The Employer will respond to any request for clarification which he receives upto the date of pre-tender meeting.

8.2	Pre-tender meeting:

8.2.1	The tenderer or his authorized representative is invited to attend a pre-tender meeting which will take place at office of the Executive Engineer, PWD, Dharwad Division, Dharwad on the notified in the ITT.

8.2.2	The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage

8.2.3	The tenderer is requested to submit any questions online through query or in writing or by cable to reach the Employer not later than the date of pre-tender meeting.

8.2.4	The Employer answers all queries online to the tenderers who have raised the queries online, and through letter to those who have sought clarification in writing or by cable. Any modification of the tender documents listed in Sub-Clause 7.1 which may become necessary as a result of the pre-tender meeting shall be made by the Employer exclusively through the issue of an Addendum pursuant to Clause 9 and not through the minutes of the pre-tender meeting.

8.2.5	Non-attendance at the pre-tender meeting will not be a cause for disqualification of a

tenderer.

9.	Amendment of Tender documents

9.1	Before the deadline for submission of tenders, the Employer may modify the tender documents by issuing addenda.

9.2	Any addendum thus issued shall be part of the tender documents and shall be published on line in e-Procurement portal.

9.3	To give prospective Tenderers reasonable time in which to take an addendum into account in preparing their tenders, the Employer shall extend as necessary the deadline for submission of tenders, in accordance with Sub-Clause 16.2 below.

Star rates are not applicable

# C.  Preparation of Tenders

10.	Documents comprising the Tender

10.1	The tender submitted by the Tenderer shall be in two covers and shall contain the documents as follows::

10.1.1	First Cover:

- Earnest Money Deposit& tender Processing fee; on line payment through e-Procurement platform.

- Qualification Information as per formats 1 to 10 uploaded separately and to comply the task created in the e-Procurement Portal under General terms and Conditions and Technical parameters and Documents required from Tenderer.

    - Second Cover:

- The Tender (in the format indicated in Section 4)

- Priced Bill of Quantities (Section 9); online through e-procurement portal, no hardcopy of commercials should be attached or disclosed.

And any other materials required be completing and submitting by Tenderers in accordance with these instructions. The documents listed under Sections 3, 4, 6 and 9 shall be filled in without exception.

11.	Tender prices

11.1	The contract shall be for the whole works as described in Sub-Clause 1.1, based on the priced Bill of Quantities submitted by the Tenderer.

11.2	The Tenderer shall fill in rates and prices and line item total (both in figures and words) for all items of the Works described in the Bill of Quantities along with total tender price (both in figures and words).  Items for which no rate or price is entered by the Tenderer will not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities.  Corrections, if any, shall be made by crossing out, initialing, dating and rewriting.

11.3	All duties, taxes, and other levies payable by the contractor under the contract, or for any other cause, shall be included in the rates, prices and total Tender Price submitted by the Tenderer.

11.4	The rates and prices quoted by the Tenderer shall be subject to adjustment during the performance of the Contract   in accordance with the provisions of Clause of the Conditions of Contract

12.	Tender validity

12.1	Tenders shall remain valid for a period not less than ninety days after the deadline date for tender submission specified in Clause 16.  A tender valid for a shorter period shall be rejected by the Employer as non-responsive.

12.2	In exceptional circumstances, prior to expiry of the original time limit, the Employer may request that the Tenderers may extend the period of validity for a specified additional period.  The request and the Tenderers' responses shall be made in writing or by cable.  A Tenderer may refuse the request without forfeiting his earnest money deposit.  A Tenderer agreeing to the request will not be required or permitted to modify his tender, but will be required to extend the validity of his earnest money deposit for a period of the extension, and in compliance with Clause 13 in all respects.

13.	Earnest money deposit

13.1	EarnestMoneyDeposit

The Tenderer shall furnish, as part of his tender, earnest money deposit in the amount

as shown in column 4 of the Table of the IFT for this particular work. The Earnest Money Deposit 1,28,100 shall be in two parts. Part (1) Rs.50,000/- by e-payment and Part (2)                    Rs. 78100/- EMD shall be in favor of Executive Engineer, Public Works Department, Dharwad Division, Dharwad, and may be in the form of Bank Guarantee issued by Nationalized/Scheduled Bank in favor of Executive Engineer, PWD, Dharwad Division, Dharwad. (Contractor should upload the scanned Copy of Bank Guarantee issued by Nationalized/Scheduled Bank. Original Bank Guarantee should be handed over by the bidders TO THE EXECUTIVE ENGINEER., PWD, DHARWAD DIVISION, DHARWAD)

The supplier/contractor can pay the Earnest Money Deposit (EMD) in the e-Procurement portal using any of the following payment modes:

- Credit Card

- Direct Debit

- National Electronic Fund Transfer (NEFT)

- Over the Counter (OTC)

OTC payment procedure: If a contractor/supplier chooses to make payment of EMD/tender processing fees Over The Counter (OTC) in any of the designated ICICI Bank branches listed in the e-Procurement web-site (www.kppp.karnataka.gov.in), the contractor/supplier will need to log into e-Procurement system, access the tender for which bid is being created and then select the OTC option under the payment section and print the Challan shown in that section. The printed challan will have the unique bid reference number and the amount to be remitted. Along with the challan, contractor can choose to make the payment either in the form of cash or in the form of Demand Draft. Cheque payments will not be accepted. The contractor is requested to specifically inform the bank officer to input the unique bid reference number printed in the challan in the banking software. Upon successful receipt of the payment, the bank will provide a 16-digit reference number acknowledging the receipt of payment. This 16-digit reference number has to be entered by contractor in the payment section of its bid as payment confirmation before the bid is submitted (i.e.) as a pre-requisite for bid submission.

NEFT payment procedure: If a contractor/supplier chooses to make payment of EMD/tender processing fees using Reserve Bank of India's (RBI) National Electronic Fund Transfer (NEFT) system, the contractor/supplier will need to log into e-Procurement system, access the tender for which bid is being created and then select the NEFT option under the payment section and print the Challan shown in that section. The printed challan will have the unique bid reference number, account details of Government of Karnataka and the amount to be remitted. The contractor has to submit the printed challan to its bank-branch (NEFT-enabled) and request for an account-to-account transfer, wherein the money will get transferred from the contractors' bank account to GoK's bank account. The contractor should ensure that NEFT transfer instructions are executed and the funds are wired to the Government of Karnataka's principal account before the last date for bid submission and preferably 24 hours before the last date for bid submission. If the contractor's bank transfers/wires the money after the last date for bid submission, the contractor's bid will be liable for rejection. Upon executing the transfer, the contractor's bank will provide a reference number generated by NEFT software as confirmation of transfer, which has to be entered by contractor in the payment section of its bid as payment confirmation before the bid is submitted (i.e.) as a pre-requisite for bid submission. Also, the account number from which the funds were transferred has to be entered in the e-Procurement system as part of its bid.  
The tenderer who wish to make Earnest Money Deposit and Tender processing fee payment through Internet Banking facility may do so. The Department is in no way responsible in case the money is not deposited in the notified central pooling account held at ICICIBank, within the stipulated period. The name of the account and the account number and other details are displayed in the generated challan for the information of the tenderer.

The supplier/contractor’s bid will be evaluated only on confirmation of receipt of the payment (EMD) in the Government of Karnataka central pooling a/c held at ICICI Bank

EMD amount will have to be submitted by the supplier/contractor taking into account the following conditions:

EMD will be accepted only in the form of electronic cash (and not through Demand Draft or Bank Guarantee) and will be maintained in the Govt.’s central pooling account at ICICI Bank until the finalization of the Tender.

- The entire EMD amount for a particular tender has to be paid in a single transaction

- For details on e-Payment services refer to e-procurement portal for more details on the process.

13.2 	The Earnest Money Deposit shall have validity of 45 days beyond the validity of the tender.

13.3	Any tender not accompanied by an acceptable earnest money deposit and not secured as indicated in Sub-Clauses 13.1 above shall be rejected by the Employer as non-responsive.

13.4	The earnest money deposit of unsuccessful Tenderers will be returned within 30 days of the end of the tender validity period specified in Sub-Clause 12.1.

13.5	The earnest money deposit of the successful Tenderer will be discharged when the Tenderer has signed the Agreement and furnished the required Performance Security.

13.6	The earnest money deposit may be forfeited:

(a)	if the Tenderer withdraws the Tender after tender opening during the period of tender validity;

(b)	in the case of a successful Tenderer, if the Tenderer fails within the specified time limit to

(i)	Sign the Agreement; or

(ii)	Furnish the required Security deposit

14.	Format and signing of Tender

Tenderer shall submit the Bid electronically before the submission date and time published in e-procurement portal.

D.  Submission of Tenders

15.	Sealing and marking of tenders

Tenderer shall submit the Bid electronically before the submission date and time published.

16.	Deadline for submission of the Tenders

  - Tenders must be submitted on line in the e-Procurement portal by the Employer before the notified date and time.

  - The Employer may extend the deadline for submission of tenders by issuing an amendment in accordance with Clause 9, in which case all rights and obligations of the Employer and the Tenderers previously subject to the original deadline will then be subject to the new deadline.

17.	Late Tenders

17.1	  In online e-procurement system,tenderer shall not be able to submit the bid after the bid submission time and date as the icon or the task in the e-procurement portal will not be available.

18.	Modification and Withdrawal of Tenders

# 18.1	Tender has all the time to modify and correct or upload any relevant document in the portal till Bid submission date and time, as published in the e-procurement portal.

# 18.2	The Tenderer may withdraw his tender before the notified last date and time of tender submission

# E.  Tender opening and evaluation

19.	Opening of First Cover of all Tenders and evaluation to determine qualified Tenderers:

  - The Employer will open the First Covers of all the Tenders received in the presence of the Tenderers or their representatives who choose to attend at time specified in e-procurementportal on the date and the place specified in Clause 16. In the event of the specified date of Tender opening being declared a holiday for the Employer, the Tenders will be opened at the appointed time and location on the next working day.

  - The Employer will evaluate and determine whether each tender (a) meets the eligibility criteria defined in ITT Clause 2; (b) is accompanied by the required earnest money deposit as per stipulations in ITT Clause and (c) meets the minimum qualification criteria stipulated in ITT Clause 3. The Employer will draw out a list of qualified Tenderers.

19.3 Deleted.

  - Opening of Second Cover of qualified Tenderers and evaluation:

  - The Employer will open the Second Covers of Qualified Tenderers at the appointed time and date in the presence of the Tenders or their representatives who choose to attend. In the event of the specified date of Second Cover opening being declared a holiday for the Employer, the Second Covers will be opened at the appointed time and location on the next working day.

20.2	The Tenderers' names, the Tender prices, the total amount of each Tender, any discounts, Tender modifications and withdrawals, and such other details as the Employer may consider appropriate, will be announced by the Employer at the opening.

20.4	The Employer shall prepare minutes of the Second Cover Tender opening, including the information disclosed to those present in accordance with Sub-Clause 20.3.

21.	Process to be confidential

21.1	Information relating to the examination, clarification, evaluation, and comparison of Tenders and recommendations for the award of a contract shall not be disclosed to Tenderers or any other persons not officially concerned with such process until the award to the successful Tenderer has been announced. Any effort by a Tenderer to influence the Employer's processing of Tenders or award decisions may result in the rejection of his Tender.

22	Clarification of Tenders

22.1	To assist in the examination, evaluation, and comparison of Tenders, the Employer may, at his discretion, ask any Tenderer for clarification of his Tender, including breakdowns of unit rates. The request for clarification and the response shall be in writing or by cable, but no change in the price or substance of the Tender shall be sought, offered, or permitted.

22.2	Subject to sub-clause 22.1, no Tenderer shall contact the Employer on any matter relating to its Tender from the time of the Tender opening to the time the contract is awarded.  If the Tenderer wishes to bring additional information to the notice of the Employer, it should do so in writing.Tenderer also can submit online clarification thorughe-Procurement portal through query option.

If they have any clarification related to e-Procurement contact e-Procurement Help desk from 9 AM to 9 PM. (Monday to Saturday)

Ph. No.   – 080 –25501216, 25201227

22.3	Any effort by the Tenderer to influence the Employer in the Employer’s Tender evaluation, Tender comparison or contract award decisions may result in the rejection of the Tenderers’ Tender.

23.	Examination of Tenders and determination of responsiveness

23.1	Prior to the detailed evaluation of Tenders, the Employer will determine whether each Tender; (a) has been properly signed; and; (b) is substantially responsive to the requirements of the Tender documents.

23.2	A substantially responsive Tender is one which conforms to all the terms, conditions, and specifications of the Tender documents, without material deviation or reservation. A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of the Works; (b) which limits in any substantial way, inconsistent with the Tender documents, the Employer's rights or the Tenderer's obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other Tenderers presenting substantially responsive Tenders.

23.3	If a Tender is not substantially responsive, it will be rejected by the Employer, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation.

24. 	 Correction of errors

24.1 Tenders determined to be substantially responsive will be checked by the Employer for any arithmetic errors. Errors will be corrected by the Employer as follows:

(a) where there is a discrepancy between the rates in figures and in words, the lower of the two will govern17; and

(b) where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by the quantity, the unit rate as quoted will govern.

24.2     The amount stated in the Tender will be adjusted by the Employer in accordance with the above procedure for the correction of errors and, with the concurrence of the Tenderer, shall be considered as binding upon the Tenderer. If the Tenderer does not accept the corrected amount the Tender will be rejected, and the earnest money deposit may be forfeited in accordance with Sub-Clause 13.6 (b).

25.	Evaluation and comparison of Tenders

25.1	The Employer will evaluate and compare only the Tenders determined to be substantially responsive in accordance with Clause 23.

25.2	deleted

25.3	The Employer reserves the right to accept or reject any variation, deviation, or alternative offer. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the Tender documents or otherwise result in unsolicited benefits for the Employer shall not be taken into account in Tender evaluation.

25.4	The estimated effect of the price adjustment conditions under Clause 41 of the Conditions of Contract, during the implementation of the Contract, will not be taken into account in tender Evaluation

# 25.5	If the tender of the successful tenderer is seriously unbalanced in relation to the Employer’s estimate of the cost of the work to be performed under the contract, the Employer may require the Tenderer to produce detailed price analyses for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, the Employer may require that the amount of the performance security set forth in Clause 29 be increased at the expense of the successful Tenderer to a level sufficient to protect the Employer against financial loss in the event of default of the successful under the contract.

# F.  Award of Contract

26.	Award criteria

26.1	Subject to Clause 27, the Employer will award the Contract to the Tenderer whose Tender has been determined to be substantially responsive to the Tender documents and who has offered the lowest evaluated Tender Price, provided that such Tenderer has been determined to be (a) eligible in accordance with the provisions of Clause 2, and (b) qualified in accordance with the provisions of Clause 3.

27.	Employer's right to accept any Tender and to reject any or all Tenders

27.1	Notwithstanding Clause 26, the Employer reserves the right to accept or reject any Tender, and to cancel the Tender process and reject all Tenders, at any time prior to the award of Contract, without thereby incurring any liability to the affected Tenderer or Tenderers or any obligation to inform the affected Tenderer or Tenderers of the grounds for the Employer's action.

28.	Notification of award and signing of Agreement

28.1	The Tenderer whose Tender has been accepted will be notified of the award by the Employer prior to expiration of the Tender validity period by cable, telex, e-mail or facsimile confirmed by registered letter. This letter (hereinafter and in the Conditions of Contract called the "Letter of Acceptance") will state the sum that the Employer will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the "Contract Price").

28.2	The notification of award will constitute the formation of the Contract, subject only to the furnishing of Security deposit in accordance with the provisions of Clause 29.

28.3	The Agreement will incorporate all agreements between the Employer and the successful Tenderer. It will be kept ready for signature of the successful Tenderer in the office of Employer within 30 days following the notification of award along with the Letter of Acceptance. Within 20 days of receipt, the successful Tenderer will sign the Agreement and deliver it to the Employer.

28.4	Upon the furnishing by the successful Tenderer of the Performance Security, the Employer will promptly notify the other Tenderers that their Tenders have been unsuccessful.

29.	Security deposit

29.1	Within 20 days of receipt of the Letter of Acceptance, the successful Tenderer shall deliver to the Employer a Security depositin any of the forms given below for an amount equivalent to 5% of the Contract price plus difference amount for below quoted tenders as additional security for tenders in accordance with Clause 25.5 of ITT and Clause 44 of the Conditions of Contract.:

  - Banker’s Bank Guarantee/FDR in favour of  Executive Engineer, Public Works Department, Dharwad Division, Dharwad Payable at. Dharwad or

  - A bank guarantee (Bank Guarantee issued by Nationalized/Scheduled Bank ) in the form given in Section 10; or

-	Specified Small Savings Instruments pledged to Executive Engineer, PWD, Dharwad Division, Dharwad

29.2	If the security deposit is provided by the successful Tenderer in the form of a Bank Guarantee, it shall be issued either by a Nationalized or Scheduled bank.

29.3	The security deposit if furnished in demand draft can, if requested, be converted to interest bearing securities at the cost of the contractor.

29.4	Failure of the successful Tenderer to comply with the requirements of Sub-Clause 29.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the Earnest money deposit.

30	deleted

31.	Corrupt or Fraudulent practices

31.1	The GOK requires that the Tenderers/Suppliers/Contractors, observe the highest standard of ethics during the procurement and execution of such contracts.  In pursuance of this policy, GOK:

(a)	will reject a proposal for award if it determines that the Tenderer recommended for award has engaged in corrupt or fraudulent practices in competing for the contract in question;

(b)	will declare a firm ineligible, either indefinitely or for a stated period of time, to be awarded a GOK contract if it at any time determines that the firm has engaged in corrupt or fraudulent practices in competing for, or in executing, a GOK contract.

31.2	Furthermore, Tenderers shall be aware of the provision stated in sub-clause 50.2 of the Conditions of Contract.

SECTION 3: QUALIFICATION INFORMATION

The information required from the  tenderer is indicated in the Formats 1 to 10,which are uploaded seperately.

# SECTION 4:	FORMS OF TENDER, LETTER OF ACEPTANCE, NOTICE TO PROCEED WITH THE WORK AND AGREEMENT FORM

# Form of Tender

Description of the Works: Improvements and Resurfacing of Tabbakaddahonalli to Bendalgatti via Beeeravalli Major District Road from km 0.00 to km 2.00 in Kalaghatagi taluk of Dharwad District CAT-1PWD/2025-26/RD/WORK_INDENT33455/CALL-3

Tender

To		:   The Executive Engineer, Public Works Department, Dharwad Division,

Dharwad.

Address	:

# GENTLEMEN,

We offer to execute the Works described above in accordance with the Conditions of Contract accompanying this Tender for the Contract Price of _________  [in figures] (________________________________________________) [in letters].

This Tender and your written acceptance of it shall constitute a binding contract between us. We understand that you are not bound to accept the lowest or any tender you receive.

The advance payment required is Rs…………………………….

We undertake that, in competing for (and, if the award is made to us, in executing) the above contract, we will strictly observe the laws against fraud and corruption in force in India namely “Prevention of Corruption Act 1988”.

We hereby confirm that this Tender complies with the Tender validity, Earnest money deposit and Tender processing fee as required by the Tender documents.

# We attach herewith our current income-tax clearance certificate.

# Yours faithfully,

Authorized Signature:

# Name & Title of Signatory: __________________________________________________

Name of Tenderer     ______________________________________________

Address:	--------------------------------------------------------------------

---------------------------------------------------------------------

# Letter of Acceptance

(letterhead paper of the Employer)

________________________[date]

To:	_________________________________________________________________________[name and address of the Contractor]

# Dear Sirs,

This is to notify you that your Tender dated ____________ for execution of the Improvements and Resurfacing of Tabbakaddahonalli to Bendalgatti via Beeeravalli Major District Road from km 0.00 to km 2.00 in Kalaghatagi taluk of Dharwad District CAT-1PWD/2025-26/RD/WORK_INDENT33455/CALL-3

[Name of the contract and identification number, as given in the Instructions to Tenderers] for the Contract Price of Rupees___________________________________________________________ (_____________) [amount in words and figures], as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted by our Agency.

You are hereby requested to furnish Security deposit plus additional security for unbalanced tenders in terms of Clause 25.5 of ITT, in the form detailed in Clause 29.1 of ITT for an amount of  Rs.————— within 20 days of the receipt of this letter of acceptance valid up to 30 days from the date of expiry of Defects Liability Period i.e. up to ............ and sign the contract, failing which action as stated in Para 29.4 of ITT will be taken.

# Yours faithfully,

# Authorized Signature

# Name and Title of Signatory

# Name of Agency

---------------------------------------------------------------------------------------------------------------

# Issue of Notice to proceed with the work

(letterhead of the Employer)

————— (date)

To

—————————————— (name and address of the Contractor)

——————————————

——————————————

Dear Sirs:

| Pursuant to your furnishing the requisite security deposit as stipulated in ITT Clause 29.1 and signing of the contract agreement for the Improvements and Resurfacing of Tabbakaddahonalli to Bendalgatti via Beeeravalli Major District Road from km 0.00 to km 2.00 in Kalaghatagi taluk of Dharwad District CAT-1PWD/2025-26/RD/WORK_INDENT33455/CALL-3 |  |
| --- | --- |

Tender Price of Rs.——————, you are hereby instructed to proceed with the execution of the said works in accordance with the contract documents.

# Yours faithfully,

(Signature, name and title of signatory authorized to sign on behalf of Employer)

# Agreement Form

# Agreement

This agreement, made the ___________________day of ______________20_______, between___________________________________________________________________________________________________________________________[name and address of Employer]

(hereinafter called “the Employer”) of the one part and _____________________________________________ ________________________________________________________________________________________________________________________________________________[name and address of contractor] (hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor Improvements and Resurfacing of Tabbakaddahonalli to Bendalgatti via Beeeravalli Major District Road from km 0.00 to km 2.00 in Kalaghatagi taluk of Dharwad District CAT-1PWD/2025-26/RD/WORK_INDENT33455/CALL-3

name and identification number of Contract] (hereinafter called “the Works”) and the Employer has accepted the Tender by the Contractor for the execution and completion of such Works and the remedying of any defects therein at a contract price of Rupees...............................

NOW THIS AGREEMENT WITNESSETH as follows:

1.	In this Agreement, words and expression shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

2.	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all aspects with the provisions of the Contract.

3.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying the defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

4.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

i)	Letter of Acceptance;

ii)	Notice to proceed with the works;

iii)	Contractor’s Tender;

iv)	Contract Data;

v)	Conditions of contract (including Special Conditions of Contract);

vi)	Specifications;

vii)	Drawings;

viii)	Bill of Quantities; and

ix)	Any other document listed in the Contract Data as forming part of the contract.

In witness whereof the parties thereto have caused this Agreement to be executed the day and year first before written.

The Common Seal of ________________________________________________________

was hereunto affixed in the presence of:

# Signed, Sealed and Delivered by the said  ________________________________________

__________________________________________________________________________

in the presence of:

Binding Signature of  Employer________________________________________________

Binding Signature of Contractor________________________________________________

FORMAT No. 2

ON BANKS LETTER HEAD

FORMAT OF BANKER’S CERTIFICATE/LINE OF CREDIT LETTER [TO BE ISSUED IN THE LETTER HEAD OF THE BANK BRANCH]

Reference Number (SL.No) Place: Date: To: [Name & Address of the beneficiary] This is to certify that Mr./ M/s. ………………………….. [name of the customer] having his /their ragistered / adminstrative office at ------------------------------------ is a coustomer of our bank and is/ are engaged in -------------------------------------------------------- [nature of activity]. If the said customer is alloted / awarded with ---------------------------------------------------------------------[brief details of works], we may extend credit facilities uptoRs ---------------------lakh, to meet his/ their working capital requirement towards the execution of the said work order as per the Loan Policy of the Bank. This Certificate is valid upto Three months from date of ISSUE, i.euptodd/mm/yyyy Your’s Faithfully, BRANCH MANAGER

SECTION 5: CONDITIONS OF CONTRACT

# Table of Contents

A.	General						Page No.

1.	Definitions

2.	Interpretation

3.	Law governing contract

4.	Employers decisions

5.	Delegation

6.	Communications

7.	Subcontracting

8.	Other Contractors

9.	Personnel

10.	Employer’s and Contractor’s risks

11.	Employer’s risks

12	Contractor’s risks

13.	Insurance

14.	Site Investigation Report

15	Querry about Contract Data

16	Contractor to construct the Works

17.	The Works to be completed by Intended Completion Date

18	Approvals by the Employer

19.	Safety

20.	Discoveries

21.	Possession of the Site

22.	Access to the Site

23.	Instructions

24.	Procedure for resolution of disputes

B.	Time Control

25.	Program

26.	Extension of the Intended Completion Date

27.	Delays ordered by the Employer

28.	Management meetings

C.	Quality Control

29.	Identifying defects

30.	Tests

31.	Correction of defects

32.	Uncorrected defects

D.	Cost Control

33	Bill of Quantities (BOQ)

34	Variations

35.	Payment for Variations

36.	Submission of bills for payment

37	Payments

38.	Compensation events

39.	Tax

40	Price Adjustment

41.	Liquidated damages

42.	Advance Payments

43.	Securities

44.	Cost of repairs

E	Finishing of Contract

45.	Completion

46.	Taking Over

47.	Final account

48.	As built drawings and/or Operating and Maintenance Manuals

49.	Termination

50	Payment upon termination

51.	Property

52.	Release from performance

F	Special Conditions of Contract

Conditions of Contract

A.  General

# 1.	Definitions

1.1	Terms which are defined in the Contract Data are not also defined in the Conditions of Contract but keep their defined meanings. Bold letters are used to identify defined terms.

Bill of Quantities means the priced and completed Bill of Quantities forming part of the Tender.

Compensation events are those defined in Clause 38 hereunder.

The Completion Date is the date of completion of the Works as certified by the Employer in accordance with Sub Clause 46.1.

The Contract is the contract between the Employer and the Contractor to execute, complete and maintain the Works. It consists of the documents listed in Clause 2.2 below.

The Contract Data defines the documents and other information which comprise the Contract.

The Contractor is a person or corporate body whose Tender to carry out the Works has been accepted by the Employer.

The Contractor's Tender is the completed Tender document submitted by the Contractor to the Employer.

The Contract price is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract.

Days are calendar days; months are calendar months.

A Defect is any part of the Works not completed in accordance with the Contract.

The Defects liability period is the period named in the Contract Data and calculated from the Completion Date.

The Employer is the party who will employ the Contractor to carry out the Works.

Equipment is the Contractor's machinery and vehicles brought temporarily to the Site to construct the Works.

The Initial Contract price is the Contract Price listed in the Employer's Letter of Acceptance.

The Intended Completion Date is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Contract Data. The Intended Completion Date may be revised only by the Employer by issuing an extension of time.

Materials are all supplies, including consumables, used by the contractor for incorporation in the Works.

Plant is any integral part of the Works which is to have a mechanical, electrical, electronic or chemical or biological function.

The Site is the area defined as such in the Contract Data.

Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Employer.

The Start Date is given in the Contract Data. It is the date when the Contractor shall commence execution of the works. It does not necessarily coincide with any of the Site Possession Dates.

A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract which includes work on the Site.

A Variation is an instruction given by the Employer which varies the Works.

The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the Contract Data.

2.	Interpretation

2.1	In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter, and the other way around. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Employer will provide instructions clarifying queries about the Conditions of Contract.

2.2		The documents forming the Contract shall be interpreted in the following order of priority:

(1)	Agreement

(2)	Letter of Acceptance, notice to proceed with the works

(3)	Contractor’s Tender

(4)	Contract Data

(5)	Conditions of Contract

(6)	Specifications

(7)	Drawings

(8)	Bill of quantities and

(9)	any other document listed in the Contract Data as forming part of the Contract.

# 3.	 Law governing contract

3.1	The  law governing the Contract is the Laws of India supplanted by the Karnataka Local Acts.

4.	Employer's decisions

4.1	Except where otherwise specifically stated, the Employer will decide contractual matters between the Employer and the Contractor.

# 5.	Delegation

5.1		The Employer may delegate any of his duties and responsibilities to other people after notifying the Contractor and may cancel any delegation after notifying the Contractor.

# 6.		Communications

6.1		Communications between parties which are referred to in the conditions are effective only when in writing. A notice shall be effective only when it is delivered (in terms of Indian Contract Act).

7.		Deleted

# 8.	Other Contractors

8.1	The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the Employer.

9.	Personnel

  - The Contractor shall employ the technical personnel (of number and qualifications) as may be stipulated by GOK from time to time during the execution of the work. The technical staff so employed shall be available at site as may be stipulated by the Employer.

  - If the Employer asks the Contractor to remove a person who is a member of the Contractor’s staff or his work force stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract.

# 10. 		Employer’s and Contractor's risks

10.1		The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks.

11. 		Employer's risks

  - The Employer is responsible for the excepted risks which are:

- rebellion,  riot commotion or disorder unless solely restricted to employees of the Contractor or his Sub-Contractors arising from the conduct of the Works;  or

- a cause due solely to the design of the Works, other than the Contractor’s design; or

- any operation of the forces of nature (in so far as it occurs on the Site) which an experienced  contractor:

  - could not have reasonably foreseen; or

  - could reasonably have foreseen, but against which he could not reasonably have taken at least one of the following measures;

    - prevent loss or damage to physical property from occurring by taking appropriate measures or

    - insure against such loss or damage

12.		Contractor’s risks

12.1		All risks of loss of or damage to physical property and of personal injury and death which arise during and in consequence of the performance of the Contract other than the excepted risks are the responsibility of the Contractor.

13.	Insurance:

13.1		The Contractor shall prior to commencing the works, effect and thereafter maintain insurances , in the joint names of the Employer and the Contractor, (cover from the first working day after the Start Date to the end of Defects  Liability Period), in the amounts stated in the Contract Data :

- for loss of or damage to the Works, Plants and Materials and the Contractor’s equipment;

- for liability of both Parties for loss, damage, death and injury to third parties or their property arising out of the Contractor’s performance of the  Contract including the Contractor’s liability for damage to the Employer’s property other than the Works and

- for liability of both Parties and of any Employer’s representative for death and injury to the Contractor’s personnel except to the extent that liability arises from the negligence of the Employer, any Employer’s representative or their Employees.

  - Policies and certificates for insurance shall be delivered by the Contractor to the Employer for his approval before the Start Date. All such insurance shall provide for compensation to be payable to rectify the loss or damage incurred. All payments received from insurers relating to loss or damage shall be held jointly by the Parties and used for the repair of the loss or damage or as compensation for loss or damage that is not to be repaired.

13.3		If the Contractor fails to effect or keep in force any of the insurances referred to in the previous sub-clauses or fails to provide satisfactory evidence, policies or receipts, the Employer may without prejudice to any other right or remedy, effect insurance for the cover relevant to such default and pay the premiums due and recover the same as a deduction from any other monies due to the Contractor. If no payments is due, the payment of the premiums shall be a debt due.

13.4		Alterations to the terms of insurance shall not be made without the approval of the Employer.

13.5		Both Parties shall comply with any conditions of the insurance policies.

14.		Site Investigation Reports:

14.1		The Contractor, in preparing the tender, shall rely on any site investigation reports referred to in the Contract data, supplemented by any information available to the Tenderer.

15. 		Queries about the Contract Data

15.1		The Employer will clarify queries on the Contract Data.

# 16. 		Contractor to construct the Works

16.1		The Contractor shall construct the Works in accordance with the Specification and Drawings.

# 17. 		The Works to be completed by the Intended Completion Date

17.1		The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the program submitted by the Contractor, as updated with the approval of the Employer, and complete them by the Intended Completion Date.

# 18.		Approval by the Employer:

  - The Contractor shall submit Specification and drawings showing the proposed Temporary Works to the Employer, who is to approve them if they comply with the Specifications and Drawings.

# 18.2	The Contractor shall be responsible for the design of Temporary Works

# 18.3		The Employer’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works.

# 18.4		The Contractor shall obtain approval of third parties to the design of third parties to the design of the temporary Works where required.

# 18.5		All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Employer before their use.

# 19. 		Safety

19.1		The Contractor shall be responsible for the safety of all activities on the Site.

20. 		Discoveries

20.	1	Anything of historical or other interest or of significant value unexpectedly discovered on the Site is the property of the Employer. The Contractor is to notify the Employer of such discoveries and carry out the Employer's instructions for dealing with them.

# 21. 		Possession of the Site

21.1		The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the Contract Data the Employer is deemed to have delayed the start of the relevant activities and this will be Compensation Event.

22. 		Access to the Site

22.1		The Contractor shall allow the Employer and any person authorized by the Employer access to the Site, to any place where work in connection with the Contract is being carried out or is intended to be carried out and to any place where materials or plant are being manufactured / fabricated / assembled for the works.

# 23. 		Instructions

23.1		The Contractor shall carry out all instructions of the Employer which comply with the applicable laws where the Site is located.

# 24.	Procedure for resolution of Disputes:	Deleted

Arbitration Clause has been withdrawn as per the Government Circular Number LAW-LAC-198-2024 & Government Letter Number PWD/140/CRM/2025(e) Dated: 18/03/2025

B.  Time Control

# 25. 		Program

25.1		Within the time stated in the Contract Data the Contractor shall submit to the Employer for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works.

25.2		The Employer's approval of the Program shall not alter the Contractor's obligations. The Contractor may revise the Program and submit it to the Employer again at any time. A revised Program is to show the effect of Variations and Compensation Events.

# 26. 		Extension of the Intended Completion Date

26.1		The Employer shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date.

26.2		The Employer shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Employer for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information.

# 27. 		Delays ordered by the Employer

27.1		The Employer may instruct the Contractor to delay the start or progress of any activity within the Works.

28.		Management meetings

28.1		The Employer may require the Contractor to attend a management meeting. The business of a management meeting shall be to review the progress achieved and the plans for remaining work.

28.2		The responsibility of the parties for actions to be taken is to be decided by the Employer either at the management meeting or after the management meeting and stated in writing to be distributed to all who attended the meeting.

# C.  Quality Control

# 29. 		Identifying defects

29.1		The Employer shall check the Contractor's work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor's responsibilities. The Employer may instruct the Contractor to search for a Defect and to uncover and test any work that the Employer considers may have a Defect

30. 		Tests

30.1		If the Employer instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect the test shall be a Compensation Event.

# 31. 		Correction of defects

31.1		The Employer shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion and is defined in the Contract Data. The Defects Liability Period shall be extended for as long as Defects remain to be corrected.

31.2		Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Employer’s notice.

# 32.		Uncorrected defects

  - If the Contractor has not corrected a Defect within the time specified in the Employer’s notice, the Employer will assess the cost of having the Defect corrected, and the Contractor will pay this amount.

    - Cost Control

33. 		Bill of Quantities (BOQ)

33.1		The BOQ shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor.

33.2		The BOQ is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the BOQ for each item

# 34. 		Variations

  - The Employer shall have power to order the Contractor to do any or all of the following as considered necessary or advisable  during the progress of the work by him

- Increase or decrease of any item of work included in the Bill of Quantities (BOQ);

- Omit any item of work;

- Change the character or quality or kind of any item of work;

- Change the levels, lines, positions and dimensions of any part of the work;

- Execute additional items of work of any kind necessary for the completion of the works; and

- Change in any specified sequence, methods or timing of construction of any part of the work.

34.2		The Contractor shall be bound to carry out the work in accordance with any instructions in this connection, which may be given to him in writing by the Employer and such alteration shall not vitiate or invalidate the contract.

34.3		Variations shall not be made by the Contractor without an order in writing by the Employer, provided that no order in writing shall be required for increase or decrease in the quantity of an item appearing in the BOQ so long as the work executed conforms to the approved drawings.

34.4		The Contractor shall promptly request in writing the Employer to confirm verbal orders and if no such confirmation is received within 15 days of request, it shall be deemed to be an order in writing by the Employer.

35. 		Payments for Variations

  - Payment for increase in the quantities of an item in the BOQ up to 25% of that provided in the Bill of Quantities shall be made at the rates quoted by the Contractor.

  - For quantities in excess of 125% of the tendered quantity of an item as given in the BOQ, the Contractor shall be paid at the rate entered in or derived from in the Schedule of Rates (applicable for the area of the work and current at the time of award of contract) plus or minus the overall percentage of the original tendered rates over the current Schedule of Rates prevalent at the time of award of contract.

35.3		If there is no rate for the additional, substituted or altered item of the work in the BOQ, efforts would be made to derive the rates from those given in the BOQ or the Schedule of Rates (applicable for the area of the work and current at the time of award of contract) and if found feasible the payment would be made at the derived rate for the item plus or minus the overall percentage of the original tendered rates over the current Schedule of Rates prevalent at the time of award of contract

35.4		If the rates for additional, substituted or altered item of work cannot be determined either as at 35.1 or 35.2 or 35.3 above, the Contractor shall be requested to submit his quotation for the items supported by analysis of the rate or rates claimed, within 7 days.

  - If the Contractor's quotation is determined unreasonable, the Employer may order the Variation and make a change to the Contract Price which shall be based on Employer’s own forecast of the effects of the Variation on the Contractor's costs.

35.6		If the Employer decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event.

35.7		Under no circumstances the Contractor shall suspend the work on the plea of non-settlement of rates for items falling under this Clause.

36. 		Submission of bills for payment

36.1		The Contractor shall submit to the Employer monthly bills of the value of the work completed less the cumulative amount paid previously.

36.2		The Employer shall check the Contractor's bill and determine the value of the work executed which shall comprise of (i) value of the quantities of the items in the BOQ completed and (ii) valuation of Variations and Compensation Events.

36.3		The Employer may exclude any item paid in a previous bill or reduce the proportion of any item previously paid in the light of later information.

# 37. 		Payments

37.1		Payments shall be adjusted for deductions for retention, other recoveries in terms of the contract and taxes, at source, as applicable under the law.  The Employer shall, “as far as possible”, pay the Contractor the within 60 days of submission of bill.

37.2		Items of the Works for which no rate or price has been entered in will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract.

38. 		Compensation events

38.1		The following are Compensation events unless they are caused by the Contractor:

(a)	The Employer does not give access to a part of the Site by the Site Possession Date stated in the Contract Data.

(b)	The Employer orders a delay or does not issue drawings, specifications or instructions required for execution of works on time.

(c)	The Employer instructs the Contractor to uncover or to carry out additional tests upon work which is then found to have no Defects.

(d)	The Employer gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons.

(e)	The effect on the Contractor of any of the Employer’s Risks.

(f)	The Employer unreasonably delays issuing a Certificate of Completion.

(g)	Other Compensation Events listed in the Contract Data or mentioned in the Contract.

38.2		If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date is extended. The Employer shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended.

38.3		As soon as information demonstrating the effect of each Compensation event upon the Contractor's forecast cost has been provided by the Contractor, it is to be assessed by the Employer and the Contract Price shall be adjusted accordingly. If the Contractor's forecast is deemed unreasonable, the Employer shall adjust the Contract Price based on Employer’s own forecast. The Employer will assume that the Contractor will react competently and promptly to the event.

38.4		The Contractor shall not be entitled to compensation to the extent that the Employer's interests are adversely affected by the Contractor not having given early warning or not having cooperated with the Employer.

# 39. 	Tax

39.1		The rates quoted by the Contractor shall be deemed to be inclusive of the sales and other taxes that the Contractor will have to pay for the performance of this Contract.  The Employer will perform such duties in regard to the deduction of such taxes at source as per applicable law. GST shall be paid to the tendered amount separately, The Increase in GST shall not be paid in the extended period of contract for which the contractor alone is responsible for delay as determined by the authority while granting the exetension of time

40.		Price Adjustment:  Deleted.

Contract price shall be adjusted for increase or decrease in rates and prices of materials such as Cement, steel and bitumen in accordance with the following principles and procedures and as per formulae given in the Contract Data.29

41. 		Liquidated damages

41.1		The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the Contract Data for each day that the Completion Date is later than the Intended Completion Date (for the whole of the works or the milestone as stated in the Contract Data).  The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages does not affect the Contractor's liabilities.

41.2		If the Intended Completion Date is extended after liquidated damages have been paid, the Employer shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment of bill.

42. 		Deleted

43.		Securities:

  - The Security deposit (including additional security for unbalanced tenders) shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount and form and type of instrument acceptable to the Employer. The Security deposit shall be valid until a date 30 days from the date of expiry of Defects Liability Period and the additional security for unbalanced tenders shall be valid until a date 30 days from the date of issue of the certificate of completion.

44.	Cost of Repairs:

44.1	Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor's cost if the loss or damage arises from the Contractor's acts or omissions.

E.  Finishing the Contract

# 45.		Completion

45.1		The Contractor shall request the Employer to issue a Certificate of Completion of the Works and the Employer will do so upon deciding that the Work is completed.

# 46.		Taking over

46.1		The Employer shall take over the Site and the Works within seven days of issuing a certificate of Completion.

47. 		Final account

47.1		The Contractor shall supply to the Employer a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Employer shall issue a Defect Liability Certificate and certify any final payment that is due to the Contractor within 90 days of receiving the Contractor's account if it is correct and complete. If it is not, the Employer shall issue within 90 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Employer shall decide on the amount payable to the Contractor and  make payment within 60 days of receiving the Contractor’s revised account.

# 48.		As built drawings and /or Operating and Maintenance Manuals

48.1		If “as built” Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the Contract Data.

48.2		If the Contractor does not supply the Drawings by the dates stated in the Contract Data, or they do not receive the Employer’s approval, the Employer shall withhold the amount stated in the Contract Data from payments due to the Contractor.

# 49. 		Termination

49.1		The Employer may terminate the Contract if the other party causes a fundamental breach of the Contract.

49.2		Fundamental breaches of Contract include, but shall not be limited to the following:

(a)	The Contractor stops work for 45 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Employer;

(b)	Deleted

(c)	The Contractor becomes bankrupt or goes into liquidation other than for a reconstruction or amalgamation;

(d)	Deleted

(e)	the Employer gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Employer;

(f)	The Contractor does not maintain a security which is required;

(g)	the Contractor has delayed the completion of works by the number of days for which the maximum amount of liquidated damages can be paid as defined in the Contract data; and

(h)	If the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulent practices in competing for or in the executing the Contract.

For the purpose of this paragraph : “corrupt practice” means the offering, giving, receiving or soliciting of anything of value to influence the action of a public official in the procurement process or in contract execution.  “Fraudulent practice” means a misrepresentation of facts in order to influence a procurement process or the execution of a contract to the detriment of the Borrower, and includes collusive practice among Tenderers (prior to or after Tender submission) designed to establish Tender prices at artificial non-competitive levels and to deprive the Borrower of the benefits of free and open competition.”

49.3		When either party to the Contract gives notice of a breach of contract to the Employer for a cause other than those listed under Sub Clause 49.2 above, the Employer shall decide whether the breach is fundamental or not.

49.4		Notwithstanding the above, the Employer may terminate the Contract for convenience.

49.5		If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secure and leave the Site as soon as reasonably possible.

50. 		Payment upon Termination

50.1		If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Employer shall prepare bill for the value of the work done less advance payments received up to the date of the bill, less other recoveries due in terms of the contract, less taxes due to be deducted at source as per applicable law and less the percentage to apply to the work not completed as indicated in the Contract Data. Additional Liquidated Damages shall not apply.  If the total amount due to the Employer exceeds any payment due to the Contractor the difference shall be a debt payable to the Employer.

50.2		If the Contract is terminated at the Employer's convenience or because of a fundamental breach of Contract by the Employer, the Employer shall prepare bill for the value of the work done, the reasonable cost of removal of Equipment, repatriation of the Contractor's personnel employed solely on the Works, and the Contractor's costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the contract, and less taxes due to be deducted at source as per applicable law and make payment accordingly.

# 51. 		Property

51.1		All materials on the Site, Plant, Equipment, Temporary Works and Works are deemed to be the property of the Employer, if the Contract is terminated because of a Contractor’s default.

52. 		Release from performance

52.1		If the Contract is frustrated by any event entirely outside the control of either the Employer or the Contractor the Employer shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which commitment was made

# F.   Special Conditions of Contract

1.	Labour :

The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for the engagement of all staff and labour, local or other, and for their payment, housing, feeding and transport.

The Contractor shall, if required by the Employer, deliver to the Employer a return in detail, in such form and at such intervals as the Employer may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the Contractor on the Site and such other information as the Employer may require.

2.	Compliance with labour regulations:

During continuance of the contract, the Contractor and his sub contractors shall abide at all times by all existing labour enactments and rules made there under, regulations, notifications and bye laws of the State or Central Government or local authority and any other labour law (including rules), regulations, bye laws that may be passed or notification that may be issued under any labour law in future either by the State or the Central Government or the local authority. The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authority on account of contravention of any of the provisions of any Act or rules made there under, regulations or notifications including amendments. If the Employer is caused to pay or reimburse, such amounts as may be necessary to cause or observe, or for non-observance of the provisions stipulated in the notifications/bye laws/Acts/Rules/regulations including amendments, if any, on the part of the Contractor, Employer shall have the right to deduct any money due to the Contractor including his amount of security deposit.  The Employer shall also have right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by the Employer.

The employees of the Contractor and the Sub-Contractor in no case shall be treated as the employees of the Employer at any point of time.

3.		 Protection of Environment:

The contractor shall take all reasonable steps to protect the environment on and off the Site and to avoid damage or nuisance to persons or to property of the public or others resulting from pollution, noise or other causes arising as a consequence of his methods of operation. During continuance of the contract, the contractor and his sub-contractors shall abide at all times by all existing enactments on environmental protection and rules made there under, regulations, notifications and bye-laws of the State or Central Government, or local authorities and any other law, bye-law, regulations that may be passed or notification that may be issued in this respect in future by the State or Central Government or the local authority.

# 4.	Condition of Contract number 24-Deleted

Arbitration Clause has been withdrawn as per the Government Circular Number LAW-LAC-198-2024 & Government Letter Number PWD/140/CRM/2025(e) Dated: 18/03/2025

5. 		DEATH OF THE CONTRACTOR:

In case of death of a contractor after executing the agreement/ commencement of the work, his legal heir, if an eligible registered contractor and willing can execute and complete the work at the accepted tender rates irrespective of the cost of the work.

Price adjustment :Deleted

# SECTION 6: CONTRACT DATA

# Items marked "N/A" do not apply in this Contract.

# The following documents are also part of the Contract:			Clause Reference

- The Schedule of Operating and Maintenance Manuals - NA		[48]

- The Methodology and Program of Construction			[25]

- Site Investigation Reports - NA			[14]

- The Schedule of Key and Critical Equipment to be deployed

on the work as per agreed program of construction.			[25]

The Employer is :

Name: The Executive Engineer,			[1.1]

# Address: Public Works Department, Dharwad Division, Dharwad.

# Name of authorized Representative: __________________________

# The name and identification number of the Contract is

________________________________________________________________________________________

[insert name and number as indicated in the Invitation for Tenders ].		 [1.1]

The Intended Completion Date for the whole

of the Works is ----------------------- with the following milestones - 		[17, 26]

Milestone dates:

Physical works to be completed    Period from the date of issue of  Notice to proceed    with the work

Milestone 1 i.e 30% in 02 Months

Milestone 2 i.e 30% in 02 Months

Milestone 3 i.e 40% in 02 Months

Milestone 123 i.e Completion of 100% of work in all respect in 06 Months.

The Site Possession Date is:  			[21]

The Road site is near Improvements and Resurfacing of Tabbakaddahonalli to Bendalgatti via Beeeravalli Major District Road from km 0.00 to km 2.00 in Kalaghatagi taluk of Dharwad District CAT-1PWD/2025-26/RD/WORK_INDENT33455/CALL-3

[1.1]

and is defined in drawings nos. ______________________________

_______________________________________________________

The Defects Liability Period is 1 year  (365 days)			[31]

Insurance requirements are as under:			[13]

The liquidated damages for the whole of the works are 0.1% of the contract price per day  in Rupees rounded off to nearest hundred.

The maximum amount of liquidated damages for the whole of the works       [41]

is ten percent of final contract price.

The date by which “as-built” drawings (in scale …) in 2 sets are required is within 30 days of issue of certificate of completion of Whole or Section of the Work as the case may be.		   [48]

The amount to be withheld for failing to supply “as built” drawings or supply of Operation and Maintenance Manuals by the date required is Rs.25,000.00	[48]

# The following events shall also be fundamental breach of the contract:	                [49.2]

1.	The contractor has contravened Sub-clause 7.1 and Clause 9 of CC.

The percentage to apply to the value of the work not completed representing the Employer's additional cost for completing the Works shall be 30percent.

[50.1]

SECTION 7: SPECIFICATIONS

# Uploaded separately

# SECTION 8: DRAWINGS

Uploaded separately

# SECTION 9: BILL OF QUANTITIES

Uploaded separately

# Note:(1)	Item for which no rate or price has been entered in will not be paid for by the Employer when executed  and shall be deemed  covered by the other rates and prices in the Bill of Quantities

(2)	Unit rates shall be quoted by the Tenderer in Indian Rupees.

# SECTION 10: FORMAT OF BANK GUARANTEE FOR SECURITY DEPOSIT

# (to be furnished on stamp paper of value not less than Rs.100/- (One Hundred))

To:	The Executive Engineer, Public work Department, DharwadDivision,Dharwad.

WHEREAS _________________________ [name and address of Contractor] (hereinafter called "the Contractor") has undertaken, in pursuance of Contract No. _____ dated ________________ to execute Improvements and Resurfacing of Tabbakaddahonalli to Bendalgatti via Beeeravalli Major District Road from km 0.00 to km 2.00 in Kalaghatagi taluk of Dharwad District CAT-1PWD/2025-26/RD/WORK_INDENT33455/CALL-3

__________________________ [name of Contract and brief description of Works] (hereinafter called "the Contract");

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

# AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee;

NOW THEREFORE we hereby affirm that we are the Guarantor and responsible to you, on behalf of the Contractor, up to a total of Rs.____________________ [amount of guarantee] Rupees__________________________ __________________________[in words], and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ____________________ [amount of guarantee] as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said deo

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

# This guarantee shall be valid until 30 days from the date of expiry of the Defects Liability Period.

# Signature and seal of the guarantor _____________________________

Name of Bank ____________________________________________

Address ____________________________________________

Date ____________________________________________

28 days