### KW - 1

GOVERNMENT OF KARNATAKA

PUBLIC WORKS DEPARTMENT

TENDER DOCUMENTS

For

PROCUREMENT OF WORKS

(LESS THAN Rs.20.00 LAKHS)

(Amended as per GO No FD 4 PEL 2008 Bangalore, Dated: 14.10.2008)

EXECUTIVE ENGINEER

ChikmagalurDivision, Chikmagalur

K / W - 1

G O V E R N M E N T O F K A R N A T A K A

Karnataka Public Works Department.

Public Works Department,

Chikmagalur Division, Chikmagalur.

TelePhones:08262-234028Fax No.:

TENDERS FOR THE WORK OF :Repairs to GHPS School at Hirenalluru in KadurTaluk in Chikkamagaluru District.”(ST RESERVED)

TENDER NUMBER		 : PWD/2026-27/BD/WORK_INDENT37127

| TENDER REFERENCE | : | 08/2026-27 .DT:30.06.2026 |
| --- | --- | --- |
| PERIOD OF SALE OF TENDER DOCUMENT | : | Please refer KPPP |
| LAST DATE FOR SALE OF TENDER DOCUMENT | : | Please refer KPPP |
| LAST DATE AND TIME FOR RECEIPT OF TENDERS | : | Please refer KPPP |
| PLACE OF OPENING OF COVER ONE OF TENDERS | : | Office of the Executive Engineer, Public works, Department, Chikmagalur Division, Chikmagalur. |
| ADDRESS FOR COMMUNICATION | : | Office of the Executive Engineer, Public works, Department, Chikmagalur Division, Chikmagalur. |

Contents

| Section No. | Description | Page |
| --- | --- | --- |
| 1. | Invitation for Tenders (IFT) | 5 |
| 2. | Instructions to Tenderers (ITT) | 6 |
| 3. | FORM OF TENDER AND QUALIFICATION INFORMATION | 17 |
| 4. | Conditions of Contract (CC) | 24 |
| 5. | CONTRACT DATA | 37 |
| 6. | Specifications | 39 |
| 7. | Drawings | 40 |
| 8. | Bill of Quantities | 41 |

SECTION 1: INVITATION FOR TENDERS (IFT)

IFT:08/2026-27 .DT:30.06.2026

- The Executive Engineer,Karnataka Public Works Department, Chikmagalur Division, Chikmagalur invites tenders from eligible tenderers, registered in KarnatakaPublic Works  Department.2, for the construction of works detailed in the Table below. The tenderers may submit tenders for any or all of the works given in the Table.

- Tender documents may be downloaded from Government of Karnataka KPPPwebsitehttps://eproc.karnataka.gov.in/eportal/index.seam	under login for Contractors:

After login to Contractors, Please scroll down to the right side bottom to see List of Tenders, Please click there to find the details of NIT and download copy of the tender.   The tender can be downloaded in the portal as per prescribed date and time published in the portal. Only Interested   Contractors   who wish to participate should remit on line transaction fee for tender after registering in the portal. The transaction fee is non-refundable if you wish to participate.

- Tenders must be accompanied by earnest money deposit which will be paid online through KPPP as mentioned in KPPP itself.

- Tenders must be electronically submitted (on-line through internet) within the date and time published in KPPP. Tenders will be opened at prescribed time and date in the KPPP, in the presence of the Tenderers who wish to attend at the Office of the Executive Engineer, Public Works,  Department, Chikmagalur Division, Chikmagalur.

- Other details can be seen in the tender documents.

TABLE

| Package No. | Name of work | Contractor Elegibility | Approximate value of work (Rs.) | Earnest Money Deposit (Rs.) | Transaction fee, only in case Tenderers who wish to participate. | Period of completion |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1 | Repairs to GHPS School at Hirenalluru in KadurTaluk in Chikkamagaluru DistrictPWD/2025-26/RD/WORK_INDENT32913.” (ST RESERVED) | CLASS –IVAnd Above K-PWD | 437897.10 | 5475.00 | As per KPP PORTAL Ment. | 3 Months |

SECTION 2: INSTRUCTIONS TO TENDERERS (ITT)

Table of Clauses

| A. | General |  | Page No. |
| --- | --- | --- | --- |
|  | 1. | Scope of Tender | 7 |
|  | 2. | Eligible Tenderers | 7 |
|  | 3. | Tender capacity | 7 |
| B. | Tender Documents |  |  |
|  | 4. | Content of Tender documents | 8 |
|  | 5. | Amendment of Tender documents | 8 |
| C. | Preparation of Tenders |  |  |
|  | 6. | Documents comprising the Tender | 8 |
|  | 7. | Tender prices | 8 |
|  | 8. | Tender validity | 9 |
|  | 9. | Earnest money deposit | 9 |
|  | 10. | Format and signing of Tender | 10 |
| D. | Submission of Tenders |  |  |
|  | 11 | Sealing and marking of Tenders | 10 |
|  | 12 | Deadline for submission of Tenders | 11 |
|  | 13 | Late Tenders | 11 |
|  | 14 | Modification and Withdrawal of Tenders | 11 |
| E. | Tender opening and evaluation |  |  |
|  | 15. | Tender opening | 12 |
|  | 16. | Process to be confidential | 13 |
|  | 17. | Clarification of Tenders | 13 |
|  | 18. | Examination of Tenders and determination of responsiveness | 13 |
|  | 19. | Correction of errors | 14 |
|  | 20. | Evaluation and comparison of Tenders | 14 |
| F. | Award of contract |  |  |
|  | 21. | Award criteria | 15 |
|  | 22 | Employer’s right to accept any Tender and to reject any or all Tenders | 15 |
|  | 23. | Notification of award and signing of Agreement | 15 |
|  | 24. | Security deposit | 15 |
|  | 25. | Corrupt or Fraudulent practices | 16 |

A. General

1. 	Scope of Tender

1.1 	The Executive Engineer, KarnatakaPublic Works, Department, Chikmagalur Division, Chikmagalur3 (Referred to as Employer in these documents) invites tenders from Contractors registered in KarnatakaPublic Works Department4, for the construction of works (as defined in these documents and referred to as "the works") detailed in the Table given in the Invitation forTenders(IFT). The tenderers may submit tenders for any or all of the works detailed in the table givenin IFT.

2. 	Eligible Tenderers

2.1 	Tenderers shall not be under a declaration of ineligibility for corrupt and fraudulent practices issued bythe Government of Karnataka

2.2 	Tenders from Joint ventures are not acceptable.

3. 	Tender capacity:

  - Eligible Tenderers will be qualified only if their available tender capacity is more than the total tendervalue. The available tender capacity will be calculated as under:

Assessed available tender capacity = (A*N*5 – B)

where

A =Maximum value of civil engineering works executed in any one year during the last

Five years (updated to current financial year price level) (FY in which tenders are

Invited)  taking into account the completed as well as works in progress.

N =	Number of years prescribed for completion of the works for which tenders are invited.

B =	Value, at Current Financial year (FY in which tenders are invited) price level, of existing commitments and on-going works to be completed during the next3Months. (Period of completion of the works for which tenders are invited)

Note: 	The statements showing the value of existing commitments and on-going works as well as thestipulated period of completion remaining for each of the works listed should be countersigned bythe Employer in charge, not below the rank of an Executive Engineer or equivalent.

3.2 	Even though the tenderers meet the above criteria, they are subject to be disqualified if they have:

- made misleading or false representations in the forms, statements and attachments submitted inproof of the qualification requirements; and/or record of poor performance such as abandoning the works, not properly completing the contract,inordinate delays in completion, litigation history, or financial failures etc.; and/orparticipated in the previous Tender for the same work and had quoted unreasonably high tenderprices and could not furnish rational justification.

- The contractor belonging to Scheduled Tribe should upload Caste Certificate issued by Competent Authority.

- The contractor belonging to Scheduled Tribe shall be domicile of the State of Karnataka for more than 10 years(Should upload Certificate issued by Competent Authority).

B. Tender documents

4. 	Content of Tender documents

4.1 	The set of tender documents shall have all the Sections given in Page 2:

4.2 	Both the sets should be completed and returned with the tender.

5. 	Amendment of Tender documents

5.1 	Before the deadline for submission of tenders, the Employer may modify the tender documents byissuing addenda.

5.2 	Any addendum thus issued shall be part of the tender documents and shall be communicated in writingor by cable to all the purchasers of the tender documents.

5.3 	To give prospective tenderers reasonable time in which to take an addendum into account in preparing their tenders, the Employer shall extend as necessary the deadline for submission of tenders, in accordance with Sub-Clause 12.2 below.

C. Preparation of Tenders

6. 	Documents comprising the Tender

6.1	The tender submitted by the Tenderer shall comprise the following:

(a) The Tender (in the format indicated in Section 3).

(b) Earnest Money Deposit;

(c) Priced Bill of Quantities;

(d) Qualification Information Form and Documents;

And any other materials required be completing and submitting by tenderers in accordance with these instructions. The documents listed under Sections 3, 5 and 8 shall be filled in without exception.

7. 	Tender prices

7.1 	The contract shall be for the whole works as described in Sub-Clause 1.1, based on the priced Bill of Quantities submitted by the Tenderer.

7.2 	The Tenderer shall fill in rates and prices and line item total (both in figures and words) for all items of the Works described in the Bill of Quantities along with total tender price (both in figures and words).

Items for which no rate or price is entered by the Tenderer will not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities. Corrections, if any, shall be made by crossing out, initialing, dating and rewriting.

7.3 	All duties, taxes, and other levies payable by the contractor under the contract, or for any other cause, shall be included in the rates, prices and total Tender Price submitted by the Tenderer.

7.4	The rates and prices quoted by the Tenderer shall be fixed for the duration of the Contract and shall not be subject to adjustment on any account.

8. 	Tender validity

8.1 	Tenders shall remain valid for a period not less than ninety days after the deadline date for tender submission specified in Clause 12. A tender valid for a shorter period shall be rejected by the Employer as non-responsive.

8.2 	In exceptional circumstances, prior to expiry of the original time limit, the Employer may request that the tenderers may extend the period of validity for a specified additional period. The request and the tenderers' responses shall be made in writing or by cable. A tenderer may refuse the request without forfeiting his earnest money deposit. A tenderer agreeing to the request will not be required or permitted to modify his tender, but will be required to extend the validity of his earnest money deposit for a period of the extension, and in compliance with Clause 9 in all respects.

9. 	Earnest money deposit

The tenderer shall furnish, as part of his tender, earnest money deposit as shown in the column 5 of the table of the IFT for this particular work. The Earnest money Deposit shall be in single part.

9.1 The Tenderer shall furnish, as part of his tender, earnest money deposit (EMD) in the amount as shown as % of the estimated cost of the work put to tender.

| Sl.No | Estimated cost of the work put to tender | EMD Percentage |
| --- | --- | --- |
| a) | uptoRs . 20.00 lakhs | 1.25% |
| b) | Rs 20.00 lakhs and above uptoRs .50.00 lakhs | 1% subject to a minimum of Rs 25,000.00 |

Tender Transaction fee and Earnest Money Deposit.

The supplier/contractor can pay the Earnest Money Deposit (EMD) in the KPPP using any of the following payment modes:

- Credit Card

- Direct Debit

- National Electronic Fund Transfer (NEFT)

- Over the Counter (OTC)

OTC payment procedure
If a contractor/supplier chooses to make payment of EMD/tender processing fees Over The Counter (OTC) in any of the designated Axis Bank branches listed in the KPPPweb-site (www.eproc.karnataka.gov.in), the contractor/supplier will need to log into KPPPsystem, access the tender for which bid is being created and then select the OTC option under the payment section and print the Challan shown in that section. The printed challan will have the unique bid reference number and the amount to be remitted. Along with the challan, contractor can choose to make the payment either in the form of cash or in the form of Demand Draft. Cheque payments will not be accepted. The contractor is requested to specifically inform the bank officer to input the unique bid reference number printed in the challan in the banking software. Upon successful receipt of the payment, the bank will provide a 16-digit reference number acknowledging the receipt of payment. This 16-digit reference number has to be inputted by contractor in the payment section of its bid as payment confirmation before the bid is submitted (i.e.) as a pre-requisite for bid submission. 
NEFT payment procedure
If a contractor/supplier chooses to make payment of EMD/tender processing fees using Reserve Bank of India's (RBI) National Electronic Fund Transfer (NEFT) system, the contractor/supplier will need to log into KPPPsystem, access the tender for which bid is being created and then select the NEFT option under the payment section and print the Challan shown in that section. The printed challan will have the unique bid reference number, account details of Government of Karnataka and the amount to be remitted.

The contractor has to submit the printed challan to its bank-branch (NEFT-enabled) and request for an account-to-account transfer, wherein the money will get transferred from the contractors' bank account to GoK's bank account. The contractor should ensure that NEFT transfer instructions are executed and the funds are wired to the Government of Karnataka's principal account before the last date for bid submission and preferably 24 hours before the last date for bid submission. If the contractor's bank transfers/wires the money after the last date for bid submission, the contractor's bid will be liable for rejection. Upon executing the transfer, the contractor's bank will provide a reference number generated by NEFT software as confirmation of transfer, which has to be inputted by contractor in the payment section of its bid as payment confirmation before the bid is submitted (i.e.) as a pre-requisite for bid submission. Also, the account number from which the funds were transferred have to be inputted in the KPPPsystem as part of its bid.  
The supplier/contractor’s bid will be evaluated only on confirmation of receipt of the payment (EMD) in the Government of Karnataka central pooling a/c held at Axis Bank

EMD amount will have to be submitted by the supplier/contractor taking into account the following conditions:

a. EMD will be accepted only in the form of electronic cash (and not through Demand Draft or Bank Guarantee) and will be maintained in the Govt.’s central pooling account at Axis Bank until the contract is closed.

b. The entire EMD amount for a particular tender has to be paid in a single transaction

For details on e-Payment services refer to KPPP for more details on the process.

9.2 	Instruments having fixed validity issued as earnest money deposit for the tender shall be valid for 45days beyond the validity of the tender.

9.3 	Any tender not accompanied by an acceptable earnest money deposit and not secured as indicated inSub-Clauses 9.1 and 9.2 above shall be rejected by the Employer as non-responsive.

9.4 	The earnest money deposit of unsuccessful tenderers will be returned within 30 days of the end of thetender validity period specified in Sub-Clause 8.1.

9.5 	The earnest money deposit of the successful Tenderer will be discharged when the Tenderer has signed the Agreement and furnished the required Performance Security.

9.6 	The earnest money deposit may be forfeited:

(a) If the Tenderer withdraws the Tender after tender opening during the period of tender

validity;

(b) If the Tenderer does not accept the correction of the Tender Price, pursuant to

Clause 19; or

(c) In the case of a successful Tenderer, if the Tenderer fails within the specified

Time limit to

(i) 	Sign the Agreement; or

(ii) 	Furnish the required Security deposit

10.	Format and signing of Tender

Tenderer shall submit the Bid electronically before the submission date and time published in KPPP.

D.  Submission of Tenders

11.Sealing and marking of tenders

Tenderer shall submit the Bid electronically before the submission date and time published.

12.	Deadline for submission of the Tenders

12.1	Tenders must be submitted online in KPPP on or before the submission date and time published in KPPP.

12.2	The Employer may extend the deadline for submission of tenders by issuing an amendment in accordance with Clause 5, in which case all rights and obligations of the Employer and the Tenderers previously subject to the original deadline will then be subject to the new deadline.

13.	Late Tenders

13.1	  In online KPPPsystem, you shall not be able to submit the bid after the bid submission time and date as the icon or the task in the KPPP will not be available.

14.	Modification and Withdrawal of Tenders

14.1	Tender has all the time to modify and correct or upload any relevant document in   the portal till Bid submission date and time, as published in the KPPP. Note; inKPPP Contractor has the option of withdrawing the Bid by digitally signing to withdraw/can cell bid before the bid submission time /Date.

E- Tender opening and evaluation

15.	Opening of Bid of Tenderers and evaluation:

15.1	The Employer will inform all the Tenderers the time, date and venue fixed for the opening of the Bid containing the priced Tenders. The Employer will open online the Bids of Tenderers at the appointed time and date ( as indicated in the KPPP ) in the presence of the Tenders or their representatives who choose to attend. In the event of the specified date of Bid opening being declared a holiday for the Employer, the Bids will be opened at the appointed time and location on the next working day.

15.2	The Tenderer’s names, the Tender prices, the total amount of each Tender, any discounts, tender modifications and withdrawals, and such other details as the Employer may consider appropriate, will be announced by the Employer at the opening. No Tender shall be rejected at Tender opening.

15.3	The Employer shall prepare minutes of the Bid Tender opening, including the information disclosed to those present in accordance with Sub Clause 16.2

16. 	Process to be confidential

16.1 	Information relating to the examination, clarification, evaluation, and comparison of Tenders andrecommendations for the award of a contract shall not be disclosed to Tenderers or any other persons not officially concerned with such process until the award to the successful Tenderer has been announced. Any effort by a Tenderer to influence the Employer's processing of Tenders or awarddecisions may result in the rejection of his Tender.

17.	Clarification of Tenders

17.1	To assist in the examination, evaluation, and comparison of Tenders, the Employer may, at his discretion, ask any Tenderer for clarification of his Tender, including breakdowns of unit rates. The request for clarification and the response shall be in writing or by cable, but no change in the price or substance of the Tender shall be sought, offered, or permitted.

17.2	Subject to sub-clause 18.1, no Tenderer shall contact the Employer on any matter relating to its Tender from the time of the Tender opening to the time the contract is awarded.  If the Tenderer wishes to bring additional information to the notice of the Employer, it should do so in writing.

For Any clarifications related to eProcurement contact Help Desk from 9A.M. to 9 P.M.(Monday to Saturday) at Phone no. 080-22485867 or send query through KPPP through query option on or before specified time.

17.3	Any effort by the Tenderer to influence the Employer in the Employer’s Tender evaluation, Tender comparison or contract award decisions may result in the rejection of the Tenderers’ Tender.

18. 	Examination of Tenders and determination of responsiveness

18.1 	Prior to the detailed evaluation of Tenders, the Employer will determine whether each Tender (a)meets the eligibility criteria defined in Clause 2; (b) has been properly signed; (c) is accompanied by the required earnest money deposit and; (d) is substantially responsive to the requirements of theTender documents.

18.2 	A substantially responsive Tender is one which conforms to all the terms, conditions, andspecifications of the Tender documents, without material deviation or reservation. A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of theWorks; (b) which limits in any substantial way, inconsistent with the Tender documents, theEmployer's rights or the Tenderer's obligations under the Contract; or      (c) whose rectification wouldaffect unfairly the competitive position of other Tenderers presenting substantially responsive Tenders.

18.3 	If a Tender is not substantially responsive, it will be rejected by the Employer, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation orreservation.

19. 	Correction of errors

19.1 	Tenders determined to be substantially responsive will be checked by the Employer for any arithmeticerrors. Errors will be corrected by the Employer as follows:

(a) 	Where there is a discrepancy between the rates in figures and in words, the lower of the twowill govern; and

(b) 	Where there is a discrepancy between the unit rate and the line item total resulting frommultiplying the unit rate by the quantity, the unit rate as quoted will govern.

19.2 	The amount stated in the Tender will be adjusted by the Employer in accordance with the above procedure for the correction of errors and, with the concurrence of the Tenderer, shall be considered asbinding upon the Tenderer. If the Tenderer does not accept the corrected amount the Tender will berejected, and the earnest money deposit may be forfeited in accordance with Sub-Clause 9.6 (b).

20. 	Evaluation and comparison of Tenders

20.1 	The Employer will evaluate and compare only the Tenders determined to be substantially responsive inaccordance with Clause 18.

20.2 	In evaluating the Tenders, the Employer will determine for each Tender the evaluated Tender Price byadjusting the Tender Price as follows:

(a) 	Making any correction for errors pursuant to Clause 19; and

(b) 	Making appropriate adjustments to reflect discounts or other price modifications offered inaccordance with Sub Clause 14.5.

20.3 	The Employer reserves the right to accept or reject any variation, deviation, or alternative offer.Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the Tender documents or otherwise result in unsolicited benefits for the Employer shall not be takeninto account in Tender evaluation.

F. Award of Contract

21. 	Award criteria

21.1	 Subject to Clause 22, the Employer will award the Contract to the Tenderer whose Tender has beendetermined to be substantially responsive to the Tender documents and who has offered the lowestevaluated Tender Price, provided that such Tenderer has been determined to be (a) eligible inaccordance with the provisions of Clause 2, and (b) qualified in accordance with the provisions ofClause 3.

22. 	Employer's right to accept any Tender and to reject any or all Tenders

22.1 	Notwithstanding Clause 21, the Employer reserves the right to accept or reject any Tender, and tocancel the Tender process and reject all Tenders, at any time prior to the award of Contract, withoutthereby incurring any liability to the affected Tenderer or Tenderers or any obligation to inform theaffected Tenderer or Tenderers of the grounds for the Employer's action.

23. 	Notification of award and signing of Agreement

23.1 	The Tenderer whose Tender has been accepted will be notified of the award by the Employer prior toexpiration of the Tender validity period by cable, telex or facsimile confirmed by registered letter. This letter (hereinafter and in the Conditions of Contract called the "Letter of Acceptance") will state thesum that the Employer will pay the Contractor in consideration of the execution, completion, andmaintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in theContract called the "Contract Price").

23.2 	The notification of award will constitute the formation of the Contract, subject only to the furnishing ofa performance security in accordance with the provisions of Clause 24.

23.3 	The Agreement will incorporate all agreements between the Employer and the successful Tenderer. It will be kept ready for signature of the successful Tenderer in the office of Employer within 30 days following the notification of award along with the Letter of Acceptance. Within 20 days of receipt, thesuccessful Tenderer will sign the Agreement and deliver it to the Employer.

23.4 	Upon the furnishing by the successful Tenderer of the Security deposit, the Employer will promptlynotify the other Tenderers that their Tenders have been unsuccessful.

24. 	Security deposit

24.1 	Within 20 days of receipt of the Letter of Acceptance, the successful Tenderer make the contract agreementandSecurity deposit for an amount equivalent to 5% of the contract price shall be deducted in every running bill. However, in case of first and final bill the entire security deposit will be deducted from the final bill.

24.2 	deleted.

24.3 	Failure of the successful Tenderer to comply with the requirements of Sub-Clause 24.1 shall constitute sufficient grounds for cancellation of the award and forfeiture of the earnest money deposit.

25. 	Corrupt or Fraudulent practices

25.1 	The GOK requires that the Tenderers, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, GOK:

(a) 	will reject a proposal for award if it determines that the Tenderer recommended for award has engaged in corrupt or fraudulent practices in competing for the contract in question;

(b) 	will declare a firm ineligible, either indefinitely or for a stated period of time, to be awarded aGOK contract if it at any time determines that the firm has engaged in corrupt or fraudulentpractices in competing for, or in executing, a GOK contract.

25.2 	Furthermore, Tenderers shall be aware of the provision stated in sub-clause 43.2 of the Conditions ofContract.

26.0	Death of contractor

In case of death of contractor after executing the agreement / commencement of the work, is legal heir, if an eligible registered contractor and willing, can execute and complete the work at the accepted tender rates irrespective of the cause of the work.

SECTION 3:

FORMS OF TENDER,

AND QUALIFICATION INFORMATION

TABLE OF FORMS:

- 	FORM OF TENDER

- 	QUALIFICATION INFORMATION

- 	LETTER OF ACCEPTANCE\

- 	NOTICE TO PROCEED WITH THEWORK

-	AGREEMENT FORM

Form of Tender

Description of the WorksRepairs to GHPS School at Hirenalluru in KadurTaluk in Chikkamagaluru DistrictPWD/2026-27/BD/WORK_INDENT37127.” (ST RESERVED)

Tender

To:Executive Engineer, KarnatakaPublic Works,

Department,  Chikmagalur Division,  Chikmagalur

Address : Office Of Executive Engineer,

KarnatakaPublic Works, Department,

Chikmagalur Division, Chikmagalur11

GENTLEMEN,

We offer to execute the Works described above in accordance with the Conditions of Contract accompanyingthis Tender for the Contract Price of _________ [in figures]

(________________________________________________) [In letters].12

This Tender and your written acceptance of it shall constitute a binding contract between us. We understand thatyou are not bound to accept the lowest or any Tender you receive.

We undertake that, in competing for (and, if the award is made to us, in executing) the above contract, we will strictly observe the laws against fraud and corruption in force in India namely “Prevention of Corruption Act1988”.

We hereby confirm that this Tender complies with the Tender validity and Earnest money deposit required bythe Tender documents.

We attach herewith our current income-tax clearance certificate.

Yours faithfully,

Authorized Signature:

Name & Title of Signatory: _______________________________________________________________

Name of Tenderer ______________________________________________

Address: ___________________________________________________________________________

__________________________________________________________________________________

Class with registration No. _________________________________________________________

Qualification Information

The information to be filled in by the Tenderer hereunder will be used for purposes of computing Tendercapacity as provided for in Clause 3 of the Instructions to Tenderers. This information will not be incorporatedin the Contract.

1.1	 Constitution or legal status of Tenderer 				[Attach copy]

Agency in which Registered (with Registration No.)

________________________________________

(Attach Copy)

Principal place of business: _______________________________

|  |  |  |  | year | amount |
| --- | --- | --- | --- | --- | --- |
| 1.2 | Total value of civil engineering construction works. executed and payments received in the last five years (in Rs.4.38Lakhs) Attach Certificate from Chartered Accountant |  |  |  |  |
|  |  |  |  | ........2021-22..... | ...................... |
|  |  |  |  | ........2022-23.... | ...................... |
|  |  |  |  | ........2023-24.... | ...................... |
|  |  |  |  | ........2024-25.... | ...................... |
|  |  |  |  | ........2025-26.... | ...................... |

  - Information on works for which Tenders have been submitted and works which are yet to be completedas on the date of this Tender.

- Existing commitments and on-going works:

| Description of Work | Place & State | Contract No. & Date | Name and Address of Employer | Value of Contract (Rs. lakhs) | Stipulated period of completion | Value of works remaining to be completed (Rs. lakhs) | Anticipated date of completion |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |

1. Attach certificate from Engineer-in-charge

- Works for which Tenders already submitted:

| Description of Work | Place & State | Name and Address of Employer | Estimated value of works (Rs. lakhs) | Stipulated period of completion | Date when decision is expected | Remarks if any |
| --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) |

1.4.	 Name, address, and telephone, telex, and fax numbers of the Tenderers' bankers who may providereferences if contacted by the Employer.

Letter of Acceptance

(letterhead paper of the Employer)

date:_____________

To: Repairs to GHPS School at Hirenalluru in KadurTaluk in Chikkamagaluru DistrictPWD/2026-27/BD/WORK_INDENT37127.” (ST RESERVED)

Dear Sirs,

This is to notify you that your Tender dated ____________________ for execution of the _______________________________________________________________________________

[name of the contract and identification number, as given in the Instructions to Tenderers] for the Contract Price of Rupees _____________________________________________________________ (_____________) [amount in words and figures], as corrected and modified in accordance with the Instructions to Tenderers is hereby accepted .

You are hereby requested to furnish Security deposit, in the form detailed in Para 24.1 of ITT for an amount of Rs.————— within 20 days of the receipt of this letter of acceptance valid up to 30 days from the date of expiry of Defects Liability Period i.e. up to .................... and sign the contract, failing which action as stated in Para 24.3 of ITT will be taken.

Yours faithfully,

Executive Engineer

-----------------------------------------------------------------------------------------------------------------------

Issue of Notice to proceed with the work

(letterhead of the Employer)

————— (date)

To

——————————————

——————————————

——————————————

Dear Sirs:

Pursuant to your furnishing the requisite security deposit as stipulated in ITT Clause 24.1 and signing of  the contract agreement for the constructionRepairs road from SH 152 to join NH 69 Via Mallidevihalli, Chikatangali, Kanagondanahalli, Tangali, Kadurhalli, G.Thimmapura road at ch 9.00 to 10.20 km in kadurtaluk.

PWD/2026-27/BD/WORK_INDENT37127.” (ST RESERVED)

Tender Price of Rs.——————, you are hereby instructed to proceed with the execution of the said works in accordance with the contract documents.

Yours faithfully,

Executive Engineer

Agreement Form

This agreement, made the ___________________day of ______________20_______, between________________________________________________________________________

________________________________________[name and address of Employer]

(hereinafter called “the Employer”) of the one part and ______________________________________________________________________________

___________________________________________________________________________________________________________________________________________________[name and address of contractor] (hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor execute Repairs to GHPS School at Hirenalluru in KadurTaluk in Chikkamagaluru DistrictPWD/2026-27/BD/WORK_INDENT37127.” (ST RESERVED)

[name and identification number of Contract] (hereinafter called “the Works”) and the Employer has accepted the Tender by the Contractor for the execution and completion of such Works and the remedying of any defects therein at a contract price of Rupees...............................

NOW THIS AGREEMENT WITNESSETH as follows:

1.	In this Agreement, words and expression shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

2.	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all aspects with the provisions of the Contract.

3.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying the defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

4.	The following documents shall be deemed to form and be read and construed as part of this Agreement, viz:

i)	Letter of Acceptance;

ii)	Notice to proceed with the works;

iii)	Contractor’s Tender;

iv)	Contract Data;

v)	Conditions of contract (including Special Conditions of Contract);

vi)	Specifications;

vii)	Drawings;

viii)	Bill of Quantities; and

ix)	Any other document listed in the Contract Data as forming part of the contract.

In witness whereof the parties thereto have caused this Agreement to be executed the day and year first before written.

The Common Seal of___________________________________________________________

Was hereunto affixed in the presence of:

Signed, Sealed and Delivered by the said __________________________________________________

_________________________________________________________________________________

in the presence of:

Binding Signature of Employer_______________________________________________________

Binding Signature of Contractor_____________________________________________________

SECTION 4: CONDITIONS OF CONTRACT

Table of Contents

| A. General |  | Page |
| --- | --- | --- |
| 1. | Definitions | 26 |
| 2. | Interpretation | 27 |
| 3. | Law governing contract | 27 |
| 4. | Employers decisions | 28 |
| 5. | Delegation | 28 |
| 6. | Communications | 28 |
| 7. | Subcontracting | 28 |
| 8. | Other Contractors | 28 |
| 9. | Personnel | 28 |
| 10. | Employer’s and Contractor’s risks | 28 |
| 11. | Employer’s risks | 28 |
| 12. | Contractor’s risks | 28 |
| 13. | Query about Contract Data | 29 |
| 14. | Contractor to construct the Works | 29 |
| 15. | The Works to be completed by Intended Completion Date | 29 |
| 16. | Safety | 29 |
| 17. | Discoveries | 29 |
| 18. | Possession of the Site | 29 |
| 19. | Access to the Site | 29 |
| 20. | Instructions | 29 |
| B. Time Control |  |  |
| 21. | Program | 29 |
| 22. | Extension of the Intended Completion Date | 30 |
| 23. | Delays ordered by the Employer | 30 |
| 24. | Management meetings | 30 |

| C. Quality Control |  |  |
| --- | --- | --- |
| 25. | Identifying defects | 30 |
| 26. | Tests | 30 |
| 27. | Correction of defects | 30 |
| 28. | Uncorrected defects | 30 |
| D. Cost Control |  |  |
| 29. | Bill of Quantities (BOQ) | 31 |
| 30. | Variations | 31 |
| 31. | Payment for Variations | 31 |
| 32. | Submission of bills for payment | 32 |
| 33. | Payments | 32 |
| 34. | Compensation events | 32 |
| 35. | Tax | 33 |
| 36. | Liquidated damages | 33 |
| 37. | Cost of repairs | 33 |
| E. Finishing of Contract |  |  |
| 38. | Completion | 33 |
| 39. | Taking Over | 33 |
| 40. | Final account | 34 |
| 41. | As built drawings | 34 |
| 42. | Termination | 34 |
| 43. | Payment upon termination | 35 |
| 44. | Property | 35 |
| 45. | Release from performance | 35 |
| F. Special Conditions of Contract |  |  |

Conditions of Contract

A. General

1. 	Definitions

1.1 	Terms which are defined in the Contract Data are not also defined in the Conditions of Contract butkeep their defined meanings. Bold letters are used to identify defined terms.

Bill of Quantities means the priced and completed Bill of Quantities forming part of the

Tender.

Compensation events are those defined in Clause 34 hereunder.

The Completion Date is the date of completion of the Works as certified by the Employer inaccordance with Sub Clause 38.1.

The Contract is the contract between the Employer and the Contractor to execute, complete andmaintain the Works. It consists of the documents listed in Clause 2.3 below.

The Contract Data defines the documents and other information which comprise the

Contract.

The Contractor is a person or corporate body whose Tender to carry out the Works has been acceptedby the Employer.

The Contractor's Tender is the completed Tender document submitted by the Contractor

totheEmployer.

The Contract price is the price stated in the Letter of Acceptance and thereafter as adjusted inaccordance with the provisions of the Contract.

Days are calendar days; months are calendar months.

A Defect is any part of the Works not completed in accordance with the Contract.

The Defects liability period is the period named in the Contract Data and calculated from theCompletion Date.

The Employer is the party who will employ the Contractor to carry out the Works.

Equipment is the Contractor's machinery and vehicles brought temporarily to the Site to construct theWorks.

The Initial Contract price is the Contract Price listed in the Employer's Letter of

Acceptance.

The Intended Completion Date is the date on which it is intended that the Contractor shall completethe Works. The Intended Completion Date is specified in the Contract Data. The Intended CompletionDate may be revised only by the Employer by issuing an extension of time.

Materials are all supplies, including consumables, used by the contractor for incorporation

in theWorks.

Plant is any integral part of the Works which is to have a mechanical, electrical, electronic or chemicalor biological function.

The Site is the area defined as such in the Contract Data.

Specification means the Specification of the Works included in the Contract and any modification oraddition made or approved by the Employer.

The Start Date is given in the Contract Data. It is the date when the Contractor shall commenceexecution of the works. It does not necessarily coincide with any of the Site Possession Dates.

A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out apart of the work in the Contract which includes work on the Site.

A Variation is an instruction given by the Employer which varies the Works.

The Works are what the Contract requires the Contractor to construct, install, and turn over to theEmployer, as defined in the Contract Data.

2. 	Interpretation

2.1 	In interpreting these Conditions of Contract, singular also means plural, male also means female orneuter, and the other way around. Headings have no significance. Words have their normal meaningunder the language of the Contract unless specifically defined. The Employer will provide instructionsclarifying queries about the Conditions of Contract.

2.2 	The documents forming the Contract shall be interpreted in the following order of priority:

(1) 	Agreement

(2) 	Letter of Acceptance, notice to proceed with the works

(3)	 Contractor’s Tender

(4) 	Contract Data

(5) 	Conditions of Contract

(6) 	Specifications

(7) 	Drawings

(8) 	Bill of quantities and

(9) 	Any other document listed in the Contract Data as forming part of the Contract.

3. 	Law governing contract

3.1 The law governing the Contract is the Laws of India supplanted by the Karnataka

Local Acts.

4. 	Employer's decisions

4.1 	Except where otherwise specifically stated, the Employer will decide contractual matters between theEmployer and the Contractor .

5. 	Delegation

5.1 	The Employer may delegate any of his duties and responsibilities to other people after notifying theContractor and may cancel any delegation after notifying the Contractor.

6. 	Communications

6.1 	Communications between parties which are referred to in the conditions are effective only when inwriting. A notice shall be effective only when it is delivered (in terms of Indian Contract Act).

7. 	Subcontracting - Deleted

8. 	Other Contractors

8.1 	The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities,and the Employer.

9. 	Personnel

9.1 	The Contractor shall employ the technical personnel (of number and qualifications) as may bestipulated by GOK from time to time during the execution of the work. The technical staff soemployed shall be available at site as may be stipulated by the Employer.

9.2 	If the Employer asks the Contractor to remove a person who is a member of the Contractor’s staff orhis work force stating the reasons, the Contractor shall ensure that the person leaves the Site withinseven days and has no further connection with the work in the Contract.

10. 	Employer’s and Contractor's risks

10.1 	The Employer carries the risks which this Contract states are Employer’s risks, and the Contractorcarries the risks which this Contract states are Contractor’s risks.

11. 	Employer's risks

11.1 	The Employer is responsible for the excepted risks which are (a) in so far as rebellion, riotcommotion or disorder or (b) a cause due solely to the design of the Works, other than theContractor’s design.

12. 	Contractor’s risks

12.1 	All risks of loss of or damage to physical property and of personal injury and death which arise duringand in consequence of the performance of the Contract other than the excepted risks are theresponsibility of the Contractor.

13. 	Queries about the Contract Data

13.1 	The Employer will clarify queries on the Contract Data.

14. 	Contractor to construct the Works

14.1 	The Contractor shall construct the Works in accordance with the Specification and

Drawings.

15. 	The Works to be completed by the Intended Completion Date

15.1 	The Contractor may commence execution of the Works on the Start Date and complete them by theIntended Completion Date.

16. 	Safety

16.1 	The Contractor shall be responsible for the safety of all activities on the Site.

17. 	Discoveries

17.1 	Anything of historical or other interest or of significant value unexpectedly discovered on the Site isthe property of the Employer. The Contractor is to notify the Employer of such discoveries and carryout the Employer's instructions for dealing with them.

18. 	Possession of the Site

18.1 	The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part isnot given by the date stated in the Contract Data the Employer is deemed to have delayed the start ofthe relevant activities and this will be Compensation Event.

19. 	Access to the Site

19.1 	The Contractor shall allow the Employer and any person authorized by the Employer access to theSite, to any place where work in connection with the Contract is being carried out or is intended to becarried out and to any place where materials or plant are being manufactured / fabricated / assembledfor the works.

20.	 Instructions

20.1 	The Contractor shall carry out all instructions of the Employer which comply with the applicable lawswhere the Site is located.

B. Time Control

21. 	Program

21.1 	Within the time stated in the Contract Data the Contractor shall submit to the Employer for approval aProgram showing the general methods, arrangements, order, and timing for all the activities in theWorks.

21.2 	The Employer's approval of the Program shall not alter the Contractor's obligations. The Contractormay revise the Program and submit it to the Employer again at any time. A revised Program is to showthe effect of Variations and Compensation Events.

22. 	Extension of the Intended Completion Date

22.1 	The Employer shall extend the Intended Completion Date if a Compensation Event occurs or aVariation is issued which makes it impossible for Completion to be achieved by the IntendedCompletion Date.

22.2 	The Employer shall decide whether and by how much to extend the Intended Completion Date within21 days of the Contractor asking the Employer for a decision upon the effect of a Compensation Eventor Variation and submitting full supporting information.

23. 	Delays ordered by the Employer

23.1 	The Employer may instruct the Contractor to delay the start or progress of any activity

WithintheWorks.

24. 	Management meetings

24.1 	The Employer may require the Contractor to attend a management meeting. The business of amanagement meeting shall be to review the progress achieved and the plans for remaining work.

24.2 	The responsibility of the parties for actions to be taken is to be decided by the Employer either at themanagement meeting or after the management meeting and stated in writing to be distributed to allwho attended the meeting.

C. Quality Control

25. 	Identifying defects

25.1 	The Employer shall check the Contractor's work and notify the Contractor of any Defects that arefound. Such checking shall not affect the Contractor's responsibilities. The Employer may instruct theContractor to search for a Defect and to uncover and test any work that the Employer considers mayhave a Defect

26. 	Tests

26.1 	If the Employer instructs the Contractor to carry out a test not specified in the Specification to checkwhether any work has a Defect and the test shows that it does, the Contractor shall pay for the test andany samples. If there is no Defect the test shall be a Compensation Event.

27. 	Correction of defects

27.1	 The Employer shall give notice to the Contractor of any Defects before the end of the Defects LiabilityPeriod, which begins at Completion and is defined in the Contract Data. The Defects Liability Periodshall be extended for as long as Defects remain to be corrected.

27.2 	Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the lengthof time specified by the Employer’s notice.

28. 	Uncorrected defects

28.1 	If the Contractor has not corrected a Defect within the time specified in the Employer’s notice, theEmployer will assess the cost of having the Defect corrected, and the Contractor will pay this amount.

D. Cost Control

29. 	Bill of Quantities (BOQ)

29.1 	The BOQ shall contain items for the construction, installation, testing, and commissioning work to bedone by the Contractor.

29.2	 The BOQ is used to calculate the Contract Price. The Contractor is paid for the quantity of the workdone at the rate in the BOQ for each item

30. 	Variations

30.1 	The Employer shall have power to order the Contractor to do any or all of the following as considerednecessary or advisable during the progress of the work by him

(a) Increase or decrease of any item of work included in the Bill of Quantities (BOQ);

(b) Omit any item of work;

(c) Change the character or quality or kind of any item of work;

(d) Change the levels, lines, positions and dimensions of any part of the work;

(e) Execute additional items of work of any kind necessary for the completion of the

Works; and

(f) Change in any specified sequence, methods or timing of construction of any part of the

Work.

30.2 	The Contractor shall be bound to carry out the work in accordance with any instructions in thisconnection, which may be given to him in writing by the Employer and such alteration shall not vitiateor invalidate the contract.

30.3 	Variations shall not be made by the Contractor without an order in writing by the Employer, providedthat no order in writing shall be required for increase or decrease in the quantity of an item appearingin the BOQ so long as the work executed conforms to the approved drawings.

30.4 	The Contractor shall promptly request in writing to the Employer to confirm verbal orders and no such confirmation is received within 15 days of request, it shall be deemed to be an order in writing by the employer.

31. 	Payments for Variations

31.1 	Payment for increase in the quantities of an item in the BOQ up to 25% of that provided in the Bill of Quantities shall be made at the rates quoted by the Contractor.

31.2 	For quantities in excess of 125% of the tendered quantity of an item as given in the BOQ, the Contractor shall be paid at the rate entered in or derived from, in the Schedule of Rates (applicable forthearea of the work and current at the time of award of contract) plus or minus the overall percentageof the original tendered rates over the current Schedule of Rates prevalent at the time of award ofcontract.

31.3 	If there is no rate for the additional, substituted or altered item of the work in the BOQ, efforts wouldbe made to derive the rates from those given in the BOQ or the Schedule of Rates (applicable for thearea of the work and current at the time of award of contract) and if found feasible the payment wouldbe made at the derived rate for the item plus or minus the overall percentage of the original tenderedrates over the current Schedule of Rates prevalent at the time of award of contract

31.4 	If the rates for additional, substituted or altered item of work cannot be determined either as at 31.1,31.2 or 31.3 above, the Contractor shall be requested to submit his quotation for the items supportedby analysis of the rate or rates claimed, within 7 days.

31.5 	If the Contractor's quotation is determined unreasonable, the Employer may order the Variation andmake a change to the Contract Price which shall be based on Employer’s own forecast of the effects ofthe Variation on the Contractor's costs.

31.6 	if the Employer decides that the urgency of varying the work would prevent a quotation being givenand considered without delaying the work, no quotation shall be given and the Variation shall betreated as a Compensation Event.

31.7 	Under no circumstances the Contractor shall suspend the work on the plea of non-settlement of ratesfor items falling under this Clause.

32. 	Submission of bills for payment

32.1 	The Contractor shall submit to the Employer monthly bills of the value of the work completed less thecumulative amount paid previously.

32.2 	The Employer shall check the Contractor's bill and determine the value of the work executed whichshall comprise of (i) value of the quantities of the items in the BOQ completed and (ii) valuation ofVariations and Compensation Events.

32.3 	The Employer may exclude any item paid in a previous bill or reduce the proportion of any itempreviously paid in the light of later information.

33. 	Payments

33.1 	Payments shall be adjusted for deductions for advance payments, other than recoveries in terms of the contract and taxes, at source, as applicable under the law.  The Employer shall pay, “as far as possible”, the Contractor within 60 days of submission of bill. The contractor shall be liable to pay liquidated damages for shortfall in progress. For progress beyond the agreed programme payment is subject to availability of the grants.

33.2 	Items of the Works for which no rate or price has been entered in will not be paid for by the Employerand shall be deemed covered by other rates and prices in the Contract.

34. 	Compensation events

34.1 	The following are Compensation events unless they are caused by the Contractor:

(a) 	The Employer does not give access to a part of the Site by the Site Possession Date statedin the Contract Data.

(b) 	The Employer orders a delay or does not issue drawings, specifications or instructionsrequired for execution of works on time.

(c) 	The Employer instructs the Contractor to uncover or to carry out additional tests uponwork which is then found to have no Defects.

(d) 	The Employer gives an instruction for dealing with an unforeseen condition, caused by theTheEmployer, or additional work required for safety or other reasons.

(e) 	The effect on the Contractor of any of the Employer’s Risks.

(f)	 The Employer unreasonably delays issuing a Certificate of Completion.

(g) 	Other Compensation Events listed in the Contract Data or mentioned in the

Contract.

34.2 	If a Compensation Event would cause additional cost or would prevent the work being completedbefore the Intended Completion Date, the Contract Price shall be increased and/or the IntendedCompletion Date is extended. The Employer shall decide whether and by how much the Contract Priceshall be increased and whether and by how much the Intended Completion Date shall be extended.

34.3 	As soon as information demonstrating the effect of each Compensation event upon the Contractor'sforecast cost has been provided by the Contractor, it is to be assessed by the Employer and theContract Price shall be adjusted accordingly. If the Contractor's forecast is deemed unreasonable, theEmployer shall adjust the Contract Price based on Employer’s own forecast. The Employer willassume that the Contractor will react competently and promptly to the event.

34.4 	The Contractor shall not be entitled to compensation to the extent that the Employer's interests areadversely affected by the Contractor not having given early warning or not having cooperated with theEmployer.

35. 	Tax

35.1	 The rates quoted by the Contractor shall be deemed to be inclusive of the sales and other taxes that theContractor will have to pay for the performance of this Contract. The Employer will perform suchduties in regard to the deduction of such taxes at source as per applicable law.As per Govt. order  FD:417:Exependiture:12/2024 Bangalore dt. 09.08.2024  GST 18% will be added to the contract amount separately.

Increase in GST shall not be paid in the extended period of contract for which the contractor  alone is responsible for delay as determined by the authority while granting the extension of  time.

36. 	Liquidated damages

36.1 	The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the ContractData for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employermay deduct liquidated damages from payments due to the Contractor. Payment of liquidated damagesdoes not affect the Contractor's liabilities.

36.2 	If the Intended Completion Date is extended after liquidated damages have been paid, the Employershall correct any overpayment of liquidated damages by the Contractor by adjusting the next paymentof bill.

37. 	Cost of repairs

37.1 	Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date andthe end of the Defects Correction periods shall be remedied by the Contractor at the Contractor's cost ifthe loss or damage arises from the Contractor's acts or omissions.

E. Finishing the Contract

38. 	Completion

38.1 	The Contractor shall request the Employer to issue a Certificate of Completion of the Works and theEmployer will do so upon deciding that the Work is completed.

39. 	Taking over

39.1 	The Employer shall take over the Site and the Works within seven days of issuing a

CertificateofCompletion.

40. 	Final account

40.1 	The Contractor shall supply to the Employer a detailed account of the total amount that the Contractorconsiders payable under the Contract before the end of the Defects Liability Period. The Employershall issue a Defect Liability Certificate and certify any final payment that is due to the Contractorwithin 90 days of receiving the Contractor's account if it is correct and complete. If it is not, theEmployer shall issue within 90 days a schedule that states the scope of the corrections or additions thatare necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Employershall decide on the amount payable to the Contractor and make payment within 60 days of receivingthe Contractor’s revised account.

41. 	As built drawings

41.1 	If “as built” Drawings are required, the Contractor shall supply them by the dates stated in theContract Data.

41.2 	If the Contractor does not supply the Drawings by the dates stated in the Contract Data, or they do notreceive the Employer’s approval, the Employer shall withhold the amount stated in the Contract Datafrom payments due to the Contractor.

42. 	Termination

42.1 	The Employer may terminate the Contract if the other party causes a fundamentalbreach of the Contract.

42.2	 Fundamental breaches of Contract include, but shall not be limited to the following:

(a) 	the Contractor stops work for 45 days when no stoppage of work is shown on the currentProgram and the stoppage has not been authorized by the Employer;

(b) 	(deleted)

(c) 	The Contractor becomes bankrupt or goes into liquidation other than for a reconstructionor amalgamation;

(d) 	(deleted)

(e)	the Employer gives Notice that failure to correct a particular Defect is a fundamentalbreach of Contract and the Contractor fails to correct it within a reasonable period of timedetermined by the Employer;

(f)	 the Contractor does not maintain a security which is required;

(g) 	the Contractor has delayed the completion of works by the number of days for which themaximum amount of liquidated damages can be paid as defined in the Contract data; and

(h) 	if the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulentpractices in competing for or in the executing the Contract.

For the purpose of this paragraph : “corrupt practice” means the offering, giving, receivingor soliciting of anything of value to influence the action of a public official in theprocurement process or in contract execution.

“Fraudulent practice” means amisrepresentation of facts in order to influence a procurement process or the execution of acontract to the detriment of the Borrower, and includes collusive practice among Tenderers(prior to or after Tender submission) designed to establish Tender prices at artificial non-competitivelevels and to deprive the Borrower of the benefits of free and opencompetition.”

42.3 	When either party to the Contract gives notice of a breach of contract to the Employer for a cause otherthan those listed under Sub Clause 42.2 above, the Employer shall decide whether the breach isfundamental or not.

42.4	Notwithstanding the above, the Employer may terminate the Contract for convenience.

42.5 	If the Contract is terminated the Contractor shall stop work immediately, make the Site safe and secureand leave the Site as soon as reasonably possible.

43. 	Payment upon Termination

43.1 	If the Contract is terminated because of a fundamental breach of Contract by the Contractor, theEmployer shall prepare bill for the value of the work done less advance payments received up to thedate of the bill, less other recoveries due in terms of the contract, less taxes due to be deducted atsource as per applicable law and less the percentage to apply to the work not completed as indicated inthe Contract Data. Additional Liquidated Damages shall not apply. If the total amount due to theEmployer exceeds any payment due to the Contractor the difference shall be a debt payable to theEmployer.

43.2 	If the Contract is terminated at the Employer's convenience or because of a fundamental breach ofContract by the Employer, the Employer shall prepare bill for the value of the work done, thereasonable cost of removal of Equipment, repatriation of the Contractor's personnel employed solelyon the Works, and the Contractor's costs of protecting and securing the Works and less advancepayments received up to the date of the certificate, less other recoveries due in terms of the contract,and less taxes due to be deducted at source as per applicable law and make payment accordingly.

44. 	Property

44.1 	All materials on the Site, Plant, Equipment, Temporary Works and Works are deemed to be theproperty of the Employer, if the Contract is terminated because of a Contractor’s default.

45. 	Release from performance

  - If the Contract is frustrated by any event entirely outside the control of either the Employer or theContractor the Employer shall certify that the Contract has been frustrated. The Contractor shall makethe Site safe and stop work as quickly as possible after receiving this certificate and shall be paid forall work carried out before receiving it and for any work carried out afterwards to which commitmentwas made.

F. Special Conditions of Contract

1. 	Labour:

The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for theengagement of all staff and labour, local or other, and for their payment, housing, feeding andtransport.

The Contractor shall, if required by the Employer, deliver to the Employer a return in detail, in suchform and at such intervals as the Employer may prescribe, showing the staff and the numbers of theseveral classes of labour from time to time employed by the Contractor on the Site and such otherinformation as the Employer may require.

2. 	Compliance with labourregulations:

During continuance of the contract, the Contractor and his sub contractors shall abide at all times by allexistinglabour enactments and rules made there under, regulations, notifications and bye laws of theState or Central Government or local authority and any other labour law (including rules), regulations,bye laws that may be passed or notification that may be issued under any labour law in future either bythe State or the Central Government or the local authority. The Contractor shall keep the Employerindemnified in case any action is taken against the Employer by the competent authority on account ofcontravention of any of the provisions of any Act or rules made there under, regulations ornotifications including amendments. If the Employer is caused to pay or reimburse, such amounts asmay be necessary to cause or observe, or for non-observance of the provisions stipulated in the notifications/bye laws/Acts/Rules/regulations including amendments, if any, on the part of theContractor, Employer shall have the right to deduct any money due to the Contractor including hisamount of security deposit. The Employer shall also have right to recover from the Contractor anysum required or estimated to be required for making good the loss or damage suffered by theEmployer.

The employees of the Contractor and the Sub-Contractor in no case shall be treated as the employeesof the Employer at any point of time.

3. 	Protection of Environment:

The contractor shall take all reasonable steps to protect the environment on and off the Site and toavoid damage or nuisance to persons or to property of the public or others resulting from pollution,noise or other causes arising as a consequence of his methods of operation. During continuance of thecontract, the contractor and his sub-contractors shall abide at all times by all existing enactments onenvironmental protection and rules made there under, regulations, notifications and bye-laws of theState or Central Government, or local authorities and any other law, bye-law, regulations that may bepassed or notification that may be issued in this respect in future by the State or Central Government orthe local authority.

4          AdditionalCondition

  - Conditional  tenders will not be accepted.

  - Material like Steel, Cement, Bitumen etc., required for the work shall be procured by the contractors themselves & should be got tested by the quality control authority, before use on the work.

  - Department will not supply any material.

  - 1% of the bill amount would be deducted towards Labour welfare funds.

  - All royalties and taxes will be deducted as notified by the Government from time to time.

SECTION 5: CONTRACT DATA

Items marked "N/A" do not apply in this Contract.

The following documents are also part of the Contract: 		Clause Reference

The Employer is:

Name: Executive Engineer,					[1.1]

Address: Office of Executive Engineer,

Karnataka Public works, Department,

Chikmagalur Division, Chikmagalur.

Name of authorized Representative: Assistant Executive Engineer, Kadur.

The name and identification number of the ContractRepairs to GHPS School at Hirenalluru in KadurTaluk in Chikkamagaluru DistrictPWD/2026-27/BD/WORK_INDENT37127.” (ST RESERVED)

[brief summary, including relationship to other contracts under the Project].

The start date shall be the date of issue of notice to proceed with the work. [1.1]

The Intended Completion Date for the whole

of the Worksis 3 Months		[15, 22]

(At the time of preparation of the tender document give the period required for completion of work. When the

Agreement is drawn after award  of the contract, the dates can be put in)

The following documents also form part of the Contract: 		[2.2]

______________________________________________________

______________________________________________________

______________________________________________________

The Site Possession Date is:	[18]

(At the time of preparation of the tender document give the period after the issue of the work order, when the

site would be made available to the contractor fro example ‘one week after the issue of the work order’.

The Site is located atKadurTaluk.1.1]

and is defined in drawings nos. ______________________________

_______________________________________________________

The Defects Liability Period is1 YEAR.[27]

(The period should depend upon the period required for testing of the work. In case building it could be 12 months (passing of one rainy season); for pipe laying work, tanks, water retaining structure, the time required for testing; for canals, lining works, the passing of one monsoon or running of canal whichever is lower: roads and highways passing of one monsoon (12 months)

The liquidated damages for the whole of the works are

Rs.__0.10%___(amount) per day	[36]

(The amount is usually computed on the basis of 0.1% the contractor price per day.

The amount has to be specified as a round figure nearest to the hundred)

The maximum amount of liquidated damages for the whole of the works  [36]

is ten percent of final contract price.

The date by which “as-built”(Completion drawings ) drawings (in scale ……..) in 2 sets are required is within 30 days of issue of certificate of completion                   [41]

The amount to be withheld for failing to supply “as built” (The amount should be sufficient to get the completion drawing prepared by alternative agency in case the contractor fails to submit) drawings

by the date required is Rs.[41]

The following events shall also be fundamental breach of the contract :    [42.2]

1. 	The contractor has contravened Sub-clause 7.1 and Clause 9 of CC.

The percentage to apply to the value of the work not completed representing the Employer's additional cost for completing the Works shall be 30percent.(Change if need be. It should be sufficient to get the balance works completed by alternative agency)[43.1]

SECTION 6: SPECIFICATIONS

------------Separately uploaded in KPPP-------------------------

SECTION 7: DRAWINGS

Enclosed as per list below:

1.

2.

3.

4.

------------Separately uploaded in KPPP-------------------------

5.

6.

7.

8.

9.

10.

11.

12.

13.

14.

15.

16.

17.

18.

19.

20.

SECTION 8: BILL OF QUANTITIES

|  |  |  |  | Rate (Rs) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sl. No. | Description of item (with brief specification and reference to Book of specification) | Quantity | Unit | In figures | In words | Amount (Rs) |
|  | ENCLOSED SEPARATELY |  |  |  |  |  |
|  |  | Total Tender Price (in figures) |  |  |  |  |
|  |  |  | (in words) |  |  |  |

Note:

(1) 	Item for which no rate or price has been entered in will not be paid for by the Employer when executedand shall be deemed covered by the other rates and prices in the Bill of Quantities (refer: ITB Clause 7.2and CC Clause 33.2).

(2) 	Unit rates and prices shall be quoted by the Tenderer in Indian Rupees.

(3) 	Where there is a discrepancy between the rate in figures and words, the rates in words will

govern.[ITB Clause 19.1(a)]

(4) 	Where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by quantity, the unit rate quoted shall govern [ITB Clause 19.1 (b)]