## PHY + FIN
TENTATIVE PHYSICAL/FINANCIAL ACTIVITY CHART
Construction of Canal and Service Road From Tayappanadoddi village to Garepalya village ( chainage 7.00 km to 9.00km) of Erehalli Branch Canal-Byramangala Left Bank canal, Harohalli taluk Bengaluru South District.
SL NO | ITEM NAME | UNIT | QUANTITY | RATE (INR) | TOTAL (INR) | 1st MONTH |  | 2nd MONTH |  | 3rd MONTH |  | 4th MONTH |  | 5th MONTH |  | 6th MONTH |  | 7th MONTH |  | 8th MONTH |  | 9th MONTH |  | 10th MONTH |  | 11th MONTH
[6 empty] | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL | PHYSICAL | FINANCIAL
1 | Clearing and grubbing road land including uprooting rank vegetation, grass, bushes, shrubs, saplings and trees girth up to 300 mm, removal of stumps of trees cut earlier and disposal of unserviceable materials and stacking of serviceable material to be used or auctioned, including removal and disposal of top organic soil not exceeding 150 mm in thickness. By Mechanical Means using Dozer ( In area of thorny jungle) as per the directions of the engineer incharge of work. | 100 sqm | 357.66 | 503.36 | 180031.7376 | 357.66 | 180031.7376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180031.7376 | 0
2 | De-silting of tank bed/Feeder Channel/Canal in dry condition by excavating the deposited bed material and loading the same to transport vehicle ( excluding cost of transportation ) including cost of all machinery, labour & all necessary works as directed and complete as per specification. as per the directions of the engineer incharge of work. | cum | 1179.99 | 56.16 | 66268.2384 | 1179.99 | 66268.2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66268.2384 | 0
3 | Earth work excavation for Foundation by mechanical means for all works & depth upto 3 m, as per drawing and technical pecifications, including setting out, shoring, strutting, barricading, caution lights, including dressing of excavated surfaces, disposing off or levelling the excavated earth or sorting & stacking the selected earth for reuse in a radius of 50 m and lift upto 1.5 m including cost of labour, tools, usage of machinery & other appurtenaces required to omplete the work. In all kinds of soils Depth upto 3 m as per the directions of the engineer incharge of work. | cum | 2666.78 | 106.08 | 282892.0224 | 444.4633 | 47148.6704 | 444.4633 | 47148.6704 | 444.4633 | 47148.6704 | 444.4633 | 47148.6704 | 444.4633 | 47148.6704 | 444.4633 | 47148.6704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282892.0224 | 0
4 | Providing rubble and murum filling in layers of 250 to 300 mm including cost of all materials,machinery, labour, watering, ramming and all other ancillary operations complete. | cum | 420 | 1565.2 | 657384 | 0 | 0 | 52.5 | 82173 | 52.5 | 82173 | 52.5 | 82173 | 52.5 | 82173 | 52.5 | 82173 | 52.5 | 82173 | 52.5 | 82173 | 52.5 | 82173 | 0 | 0 | 0 | 0 | 657384 | 0
5 | Providing and laying in position Cement Concrete for levelling course for all works in foundation. The granite/trap/basalt crushed graded coarse aggregates and fine aggregates as per relevant IS Codes machine mixed, laid in layers not exceeding 150 mm thickness, well compacted using plate vibrators, including all lead & lifts, cost of all materials of quality, labour, Usage charges of machinery, curing, and all the other appurtenances required to complete the work as per technical specifications. Mix 1:2:4 Using 40 mm nominal size graded crushed coarse aggregates | cum | 639.896 | 6382.95 | 4084424.1732 | 0 | 0 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 63.9896 | 408442.4173 | 4084424.1732 | 0
6 | Providing and laying in position Cement Concrete for all Sub structures of building, Irrigation works, Sub structure works of bridges, Drain works & other parallel works from 0.50m to 3.50 m height. The granite/trap/basalt crushed graded coarse aggregates and fine aggregates as per relevant IS Codes machine mixed with super plasticisers, laid in layers, well compacted using needle vibrators, providing weep holes wherever necessary, including all lead & lifts, cost of all materials of quality, confirming to the requirements of relevant IS codes, labour, Usage charges of machinery, curing and all other appurtenances required to complete the work as per technical specifications. Mix 1:2:4 (M15) Using 20 mm nominal size graded crushed coarse aggregates as per the directions of the engineer incharge of work. (For side walls and Hanches) | cum | 1475.35 | 8883.11 | 13105696.3385 | 0 | 0 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 147.535 | 1310569.6339 | 13105696.3385 | 0
7 | Providing and laying in position Cement Concrete for all Sub structures of building, Irrigation works, Sub structure works of bridges, Drain works & other parallel works from 0.50m to 3.50 m height. The granite/trap/basalt crushed graded coarse aggregates and fine aggregates as per relevant IS Codes machine mixed with super plasticisers, laid in layers, well compacted using needle vibrators, providing weep holes wherever necessary, including all lead & lifts, cost of all materials of quality, confirming to the requirements of relevant IS codes, labour, Usage charges of machinery, curing and all other appurtenances required to complete the work as per technical specifications. Mix 1:2:4 (M15) Using 20 mm nominal size graded crushed coarse aggregates as per the directions of the engineer incharge of work. (For Base slab) | cum | 794.8 | 6580.08 | 5229847.584 | 0 | 0 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 79.48 | 522984.7584 | 5229847.584 | 0
8 | Providing and laying in position Cement Concrete for all Super structures of building, Irrigation works, Super structure works of bridges, Drain works & other parallel works from 0.50m to 3.50 m height. The granite/trap/basalt crushed graded coarse aggregates and fine aggregates as per relevant IS Codes machine mixed with super plasticisers, laid in layers, well compacted using needle vibrators, providing weep holes wherever necessary, including all lead & lifts, cost of all materials of quality, confirming to the requirements of relevant IS codes, labour, Usage charges of machinery, curing and all other appurtenances required to complete the work as per technical specifications.M25 Design Mix Using 20 mm nominal size graded crushed coarse aggregates as per the directions of the engineer incharge of work. | cum | 43.2 | 7353.53 | 317672.496 | 0 | 0 | 7.2 | 52945.416 | 7.2 | 52945.416 | 7.2 | 52945.416 | 7.2 | 52945.416 | 7.2 | 52945.416 | 7.2 | 52945.416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317672.496 | 0
9 | Providing and laying insitu vibrated M-20 ( 28 days cube compressive strength not less than 20 N / sq mm ) grade cement concrete using 20mm down size approved, clean, hard, graded aggregates as per relevant IS Codes machine mixed with super plasticisers, laid in layers, well compacted using needle vibrators, including cost of all materials of quality, confirming to the requirements of relevant IS codes, labour, Usage charges of machinery, curing, centering, formwork and scafolding and all other appurtenances required to complete the work as per technical specifications for check dam /pickups /irrigation tanks/waste weir/sluice, sluice canal and other allied works like abutments/wing walls/returns/cutoff walls works & all necessary works as directed and complete as per specification.as per the directions of the engineer incharge of work. | cum | 422.88 | 7116.72 | 3009518.5536 | 0 | 0 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 42.288 | 300951.8554 | 3009518.5536 | 0
10 | Supplying, fitting and placing TMT FE 550 / 550D Steel Reinforcement including cost of all aterials, machinery, labour, cleaning, straightening, cutting, bending, hooking, laping/welding joints, tying with binding wire / soft annealed steel wire and other ancilary operations f) ACanal & Allied Works complete as per drawing and technical specification as per the directions of the engineer incharge of work. | Tonne | 162.1486 | 94650.4 | 15347429.8494 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 16.2149 | 1534742.9849 | 0 | 0 | 15347429.8494
11 | Providing S&S RCC SPUN / VIBRATED CAST PIPES (REINFORCED) pipes NP-3 Class conforming to IS:458-1988 with latest amentments using ordinary portland cement, for sanitary works and conveying to work site, rolling and lowering into trenches, laying true to line and level including loading and unloading at both destinations and jointing of pipes and specials, perfect linking of joints with jack to correct position including cost of jointing materials, i.e, rubber rings conforming to IS: 5382 for S&S RCC pipes, with all leads and lifts as directed and giving necessary hydraulic test as per ISS to the required pressure and commissioning etc. complete. (Contractor will make his own arrangements for procuring water for testing) RCC NP3 Class pipe of 250 mm dia. as per the directions of the engineer incharge of work. | M | 35 | 1146.08 | 40112.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.5 | 20056.4 | 17.5 | 20056.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40112.8
12 | Design, fabrication, supply, erection and commissioning of vent liner using 20 mm thick plates with stiffeners and anchors for river sluice / canal sluice vents including cost of all materials, machinery, labour, cutting, aligning, anchoring, welding, finishing, cleaning, applying one coat zinc rich epoxy primer and four coats cold applied coal tar epoxy paint and all other ancillary operations complete as per specifications and approved drawings. | sqm | 7 | 26728 | 187096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 187096 | 187096
13 | Providing casing embankment using semi-pervious / pervious approved soil from borrow areas in layers of 250 to 300 mm ( before compaction ) including cost of all materials, machinery, labour, all other operations such as collection of soil, spreading soil in layer of specified thickness, sorting out, breaking clods, levelling, sectioning edges / sides, watering, compacting each layer to density control of not less than 95 percent or as stipulated using power roller and all other ancillary operations complete. | cum | 8750.958 | 654.16 | 5724526.6853 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1093.8698 | 715565.8357 | 1093.8698 | 715565.8357 | 1093.8698 | 715565.8357 | 1093.8698 | 715565.8357 | 1093.8698 | 715565.8357 | 1093.8698 | 715565.8357 | 2187.7395 | 1431131.6713 | 5724526.6853
14 | Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundations and other similar works etc. in layers not exceeding 20cm in depth, consolidating each deposited layer by ramming and watering, lead up to 50 m and lift upto 1.5 m.as per the directions of the engineer incharge of work. | cum | 17.64 | 276.64 | 4879.9296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.64 | 4879.9296 | 4879.9296
TOTAL |  |  |  |  | 48237780.408 | 1998.3282 | 1828191.6313 | 853.6708 | 4259958.7363 | 853.6708 | 4259958.7363 | 853.6708 | 4259958.7363 | 1965.0405 | 4995580.9719 | 1965.0405 | 4995580.9719 | 1503.0772 | 4928375.9015 | 1495.8772 | 4875430.4855 | 1495.8772 | 4875430.4855 | 1443.3772 | 4793257.4855 | 2545.6721 | 4166056.2659 | 48237780.408 | 48237780.408 | #REF! | 39923199.7404
|  |  |  | GST | 8682800.4734 |  | 329074.4936 |  | 766792.5725 |  | 766792.5725 |  | 766792.5725 |  | 899204.5749 |  | 899204.5749 |  | 887107.6623 |  | 877577.4874 |  | 877577.4874 |  | 862786.3474 |  | 749890.1279
| Tota including GST |  |  |  | 56920580.8815 |  | 2157266.125 |  | 5026751.3088 |  | 5026751.3088 |  | 5026751.3088 |  | 5894785.5469 |  | 5894785.5469 |  | 5815483.5638 |  | 5753007.9729 |  | 5753007.9729 |  | 5656043.8329 |  | 4915946.3937 |  | #REF!
LOC | [6 empty] | 10348109.1039 |  | 12779876.2088 |  | 13515498.4445 |  | 14251120.6801 |  | 14919537.8454 |  | 14799387.359 |  | 14679236.8726 |  | 14544118.4566 |  | 13834744.2369 |  | 8959313.7514 |  | 4166056.2659 | 48237780.408 | 14919537.8454
[6 empty] | 1st Milestone | [5 empty] | 2nd Milestone | [7 empty] | 3th Milestone | [8 empty] | 0
[6 empty] | 10348109.1039 | [5 empty] | 19179496.5817 | [7 empty] | 18710174.7225
[6 empty] | 10348109.1039 | [5 empty] | 29527605.6856 | [7 empty] | 48237780.408 | [7 empty] | 56920580.8815
|  |  |  | LOC | 14471334.1224 |  |  |  | Milestones and liquidity damages
[5 empty] | 21707001.1836 |  |  |  | MILESTONES | AMOUNT | Liquidity damage
[9 empty] | Mile Stone 1 | 10348109.1039 | 10348 | 10348.1091 | 103.4811
[9 empty] | Mile Stone 2 | 19179496.5817 | 19179 | 29527.6057 | 191.795
[9 empty] | Mile Stone 3 | 18710174.7225 | 18710 | 48237.7804 | 187.1017
[6 empty] | EMD |  |  |  | 48237780.408 |  | Per day
[6 empty] | 723566.7061 |  | Earth work |  | 12597.728 | Cum | 10078.1824
[6 empty] | 200000 |  | Concrete |  | 3376.126 | Cum | 2946.4372
[8 empty] | Steel |  | 162.1486 | T | 141.5115
[8 empty] | Annual turn over |  | 964.7556
[8 empty] | Line of credit |  | 149.1954
[8 empty] | Similar nature of work |  | 241.1889